## Summary All Towers
Lakecity Roof Gardens - Projected Cash Flow
(Structural & Finishes Works Nov 2024 to jan 2026) | [6 empty] | Combined | [16 empty] | 19.12.2025
S.No. | Area | Start Date Planned | Consultant Budget NADA/SEMS | Budget As per Initial Quotation Received | Awarded Value | Actual Spending | Balance Amount | Pending Approvals | Actual Value On Completion | Remarks | %age | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 |  | 2025-06-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-02 | 2026-03-03 | 2026-04-04
A | Structure ( I , L1 , L2,SOG ) Three Towers |  |  |  | 2495608676 | 2581111533 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | 10562111
A1 | Ground Floor - I-Tower |  |  | 60304169 | 51394568 | 22987058 | 13407510 | 8909601 | [10 empty] | 15640589.4 | 11066984.4 | 7566983.96
A3 | GYM+Business Center+Game room |  |  |  | 67266238 | 34816559.5 | 32449678.5 | [11 empty] | 7816559.5 | 30506495.2 | 10943183.3
A4 | External Development |  |  | 122433485 | 114717192 | 60913375 | 45588110 | 15932000 | [11 empty] | 20000000 | 5000000 | 11000000 |  | 11000000
B | Façade Works ( I, L1,L2 tower) |  | 86456205 |  | 141508845 | 128430940 | 13077905 |  | 0 | #VALUE! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13077905
C | Finishes For Tower I , L1 ,L2 |  |  | 5034678556.742 | 2202396913.45 | 1220754035.8 | 982324307.65 | 2557901236.5274 | 0 | 4382502 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 427572034.4941 | 466066761.119 | 370416206.4864 | 124731319.2596 | 1793266.3333 | 0
| Total |  |  |  | 5072892432.45 | 4049013501.3 | 1086847511.15 | 2582742837.5274 | 0 | #VALUE! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 474669199.3941 | 527640240.719 | 393926373.7464 | 135731319.2596 | 1793266.3333 | 0
Note : Exclusions are ( Roof top & MEP, Courtyard Finishes, Bridges Related Finishes, Basement)
-183282966

## Summary I Tower
Lakecity Roof Gardens - Projected Cash Flow | [9 empty] | 2024-07-10
(Structural & Finishes Works Jun 2025 to Jan 2026) | [5 empty] | I-Tower | [15 empty] | 19.12.2025
S.No. | Area | Start Date Planned | Consultant Budget NADA/SEMS | Budget As per Initial Quotation Received | Awarded Value | Actual Spending | Balance Amount | Pending Approval | Actual Value On Completion | Remarks | %age | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-06-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
A | Structure |  |  |  | 1095058864 | 1086522867 | 8535997 | [10 empty] | 3539864
B | Façade Works ( I tower) |  | 86456205 | 64000000 | 52883243 | 48820745 | 4062498 |  |  | In progress ( 86% completed) 3 sides | 38.83% | 0 | 0 | 0 |  |  |  | 4062498
C | Finishes For Tower 1 |  |  | 2295948450.142 | 1622153313 | 1016683319.7 | 606151423.3 | 458177504.9774 |  | 1460834 | 37.5179 | #REF! | #REF! |  |  |  |  | 337498041.8441 | 355266076.5844 | 299975038.8364 | 89399782.1929 | 0
| Total |  |  |  | 2770095420 | 2152026931.7 | 618749918.3 | 458177504.9774 | 0 | 1460834 | 37.9062 | #REF! | #REF! | 0 | 0 | 0 |  | 345100403.8441 | 355266076.5844 | 299975038.8364 | 89399782.1929 | 0

## Summary L1 Tower
Lakecity Roof Gardens - Projected Cash Flow | [9 empty] | 2024-07-10
(Structural & Finishes Works Jun 2025 to Jan 2026) | [6 empty] | L 1 Tower | [7 empty] | 19.12.2025
S.No. | Area | Start Date Planned | Consultant Budget NADA/SEMS | Budget As per Initial Quotation Received | Awarded Value | Actual Spending | Balance Amount | Pending Approvals | Actual Value On Completion | Remarks | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
A | Structure |  |  |  | 696162769 | 692680386 | 3482383 |  |  |  | 3482383
B | Façade Works (L1 tower) |  | 86456205 | 64000000 | 40291143 | 35449591 | 4841552 |  |  |  | 4841552
C | Finishes For Tower L1 |  |  | 1430180283.6 | 340973087 | 163909605.1 | 177063481.9 | 991071164 |  | 1460834 | 46930665.2833 | 59723357.1679 | 25946458.9167 | 6667630 | 1793266.3333
| Total |  |  |  | 1077426999 | 892039582.1 | 185387416.9 | 991071164 | 0 | 1460834 | 55254600.2833 | 59723357.1679 | 25946458.9167 | 6667630 | 1793266.3333

## Summary L2 Tower
Lakecity Roof Gardens - Projected Cash Flow
(Structural & Finishes Works Jun 2025 to Jan 2026) | [6 empty] | L-2 Tower | [7 empty] | 19.12.2025
S.No. | Area | Start Date Planned | Consultant Budget NADA/SEMS | Budget As per Initial Quotation Received | Awarded Value | Actual Spending | Balance Amount | Pending Approvals | Actual Value On Completion | Remarks | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
A | Structure |  |  |  | 704387043 | 697987678 | 6399365 |  |  |  | 3539864
B | Façade Works (L2 tower) |  | 86456205 | 64000000 | 48334459 | 44160604 | 4173855 |  |  |  | 5370108
C | Finishes For Tower L2 |  |  | 1308549823 | 239270513.45 | 40161111 | 199109402.45 | 1083810966.55 |  | 1460834 | 48806269.5 | 43143327.3667 | 51077327.3667 | 44494708.7333 | 28663907.0667
| Total |  |  |  | 991992015.45 | 782309393 | 209682622.45 | 1083810966.55 | 0 | 1460834 | 57716241.5 | 43143327.3667 | 51077327.3667 | 44494708.7333 | 28663907.0667

## I Finishes
Lakecity Roof Gardens - Projected Cash Flow | [15 empty] | 2026-01-04
(Structural & Finishes Works Jun 2025 to Jan 2026) | [5 empty] | I- Tower | [20 empty] | 19.12.2025
S.No. | Area | Start Date Planned | Time line | Consultant Budget NADA/SEMS | Budget As per Initial Quotation Received | Awarded Value | Actual Spending | Actual Balance Amount | Pending approval | Actual Value On Completion | Remarks | %age | 2024-12-01 | 2025-01-01 | 2025-02-03 | 2025-03-08 | 2025-05-10 | 2025-08-01 | 2025-09-02 | 2025-10-04 | 2025-11-05 | 2025-12-07 | 2026-01-08 | 2026-02-09 |  |  | Remarks
A | Façade Works ( I tower) |  |  | 86456205 | 64000000 | 52883243 | 48820745 | 4062498 |  |  |  | 38.83% | [6 empty] | 4062498 | [7 empty] | In progress
Finishes For Tower 1
1 | External Brick Works (M+L) | 2024-01-01 | 0 | 19400000 | 14809000 | 14500000 | 14500000 | 0 |  | 14609801.5 | Completed | 25.26% | [12 empty] | 0
2 | Internal Brick Works (M+L) | 2024-02-02 | 0 | 105250505 | 93557500 | 92385014 | 93066444 |  |  | -681430 |  | 12.22% | [12 empty] | 0 | 0
3 | Electrical Conduiting (M+L) | 2024-03-03 | 2 | 42123560 | 34734900 | 29485630 | 28688634.4 | 796995.6 |  | 0 |  | 30% | [5 empty] | 2440816 | 1132670 |  | 796995.6 |  |  |  | 796995.6 | 0 | In progress
4 | Plumbing Conduiting (M+L) | 2024-04-04 | 2 | 33256400 | 25013632 | 23645601 | 21009948 | 2635653 |  | 0 |  | 28.9% | [5 empty] | 1767701 | 867952 |  | 2635653 |  |  |  | 2635653 | 0 | In progress
5 | SOIL, WASTE VENT AND RAIN WATER DRAINAGE SYSTEM (M) | 2024-06-28 | 1 | 67805200 | 22173540 | 19367707 | 19362936 | 4771 |  | 0 |  | 71.44% | [5 empty] | 2763349 |  |  | 4771 |  |  |  | 4771 | 0 | In progress
6 | PCC (M+L) | 2024-04-04 | 2 | 43589100 | 32900000 | 27569921 | 26661230 | 908691 |  | 0 |  | 36.75% | [5 empty] | 2748201.7143 | 5107221.7143 |  | 908691 |  |  |  | 908691 | 0 | In progress
7 | External Plaster (M+L) | 2024-04-05 | 2 | 11073231 | 6841856 | 6841856 | 3712137 | 3129719 |  | 0 |  | 38.21% | [5 empty] | 1785429.75 | 1344289.25 |  | 3129719 |  |  |  | 3129719 | 0 | In progress
8 | Internal Plaster (M+L) | 2024-05-06 | 2 | 72699100 | 57158144 | 57158144 | 44216742 | 12941402 |  |  |  | 21.38% | [5 empty] | 4906620.25 | 8034781.75 |  | 6470701 | 6470701 |  |  | 12941402 | 0 | In progress
9 | Boundary Wall (M+L) | 2024-05-07 | 0 | 36982115 | 36982115 | 26604211 | 23545140 | 3059071 |  | 0 |  | 28.06% | [8 empty] | 2000000 |  |  |  | 3059071 | 1059071 | In progress
10 | Subcontract Electrical (L) | 2024-06-07 | 2 | 37629817 | 31686490 | 21095340 | 8037026 | 13058314 |  | 0 |  | 43.94% | [5 empty] | 1245757.1818 | 2475516.1818 |  | 3475516.1818 | 4475516.1818 | 5258330.1818 | 1985361.9545 | 13058314 | -2136410.5 | In progress
11 | Subcontract Plumbing (L) | 2024-06-26 | 2 | 35604250 | 27427180 | 25674500 | 12408721 | 13265779 |  | 0 |  | 27.89% | [5 empty] | 1635220.4545 | 3834045.4545 |  | 3219511.4545 | 5219511.4545 | 5219511.4545 | 1155591.1364 | 13265779 | -1548346.5 | In progress
12 | CABLE CONTAINMENT (M) | 2024-06-23 | 0 | 31018260 | 28656500 | 19470000 | 16502692 | 2967308 |  | 0 |  | 37.23% | [12 empty] | 2967308 | 2967308 | In progress
13 | Subcontract Firefighting (L) | 2024-07-29 | 2 | 8670000 | 6679244 | 5000000 | 4315435 | 684565 |  |  |  | 42.33% | [5 empty] | 339349 | 839349 |  |  | 1101432 |  |  | 684565 | -416867 | In progress
14 | FSS Works (Piping) (M) | 2024-07-29 | 1 | 33264800 | 25124723 | 18686350 | 15616841 | 3069509 |  | 0 |  | 43.83% | [5 empty] | 1549431 |  |  | 3451813 |  |  |  | 3069509 | -382304 | In progress
15 | Subcontract HVAC (M+L) | 2024-07-29 | 2 | 20290815 | 16644195.9 | 11000000 | 7206637 | 3793363 |  | 0 |  | 45.79% | [5 empty] | 1925000 | 1563638 |  | 1921400 | 1871963 |  |  | 3793363 | 0 | In progress
16 | Copper Pipe + Accessories (M+L) | 2024-07-24 | 2 | 39351450 | 32836457.1 | 20000000 | 17529297 | 2470703 |  | 0 |  | 49.18% | [5 empty] | 460449 | 3444884 |  | 2900000 | 1418948 |  |  | 2470703 | -1848245 | In progress
17 | LPG Works (M) | 2024-06-25 |  |  | 19090100 | 6500000 | 4047317 | 2452683 | 12590100 | 0 | Dropped | [6 empty] | 5196700 | 5196700 |  | 5196700 | 9909304 |  |  | 15042783 |  | Partial -
18 | WIRING / WIRING ACCESSORIES (M) | 2024-07-30 | 4 | 85098584.5 | 51089750 | 45147657 | 44465806.8 | 681850.2 |  | 0 |  | 46.95% | [6 empty] | 5508126 |  | 681850.2 |  |  |  | 681850.2 | 0 | In progress
19 | MAIN / SUB-MAIN CABLES (M) | 2024-07-01 | 4 | 21986420 | 18632283.155 | 17180375 | 16973827.2 | 206547.8 |  | 0 |  | 21.86% | [5 empty] | 3424065 |  |  | 206547.8 |  |  |  | 206547.8 | 0 | In progress
20 | VOICE & DATA COMMUNICATION (M+L) | 2024-10-27 | 2 | 21124350 | 16692700 | 5537660 | 4688280 | 849380 | 11155040 | 0 | 2024-10-27 | 73.79% | [5 empty] | 3782116.6667 | 3782116.6667 |  | 3658070 | 8437156 |  |  | 12004420 |  | In progress
21 | Pipes for Water Supply and fitting (M) | 2024-10-28 | 2 | 18218500 | 13469930 | 13000000 | 12212832.6 | 787167.4 |  | 0 |  | 28.64% | [5 empty] | 3177196 | 523921 |  |  | 787167.4 |  |  | 787167.4 | 0 | In progress
22 | Elevator (M+L) | 2024-10-27 | 1 | 121424000 | 55000000 | 49036000 | 17800000 | 31236000 |  | 0 | 2024-10-27 | 59.62% | [6 empty] | 28404500 |  | 26004500 | 5231500 |  |  | 31236000 | 0
23 | BORE WELL WATER SUPPLY SYSTEM (M+L) | 2024-10-27 | 1 | 15263600 | 12349580 |  |  | 0 | 12349580 | 0 | 2024-10-27 | 100% | [5 empty] | 6174790 |  |  | 6174790 | 6174790 |  |  | 12349580 | 0
24 | Aluminum Work (M+L) | 2024-10-27 | 1 | 117000000 | 50640851.59 | 68331343 | 31452514 | 36878829 |  | 0 | 2024-10-27 | 41.6% | [6 empty] | 10917164 |  | 17000000 | 17000000 | 9000000 | 8248507 | 36878829 | -14369678 | In progress
24 a | Glass Work (M+L) | 2024-10-28 |  |  | 60416539.02 | 31460182 | 7865045.5 | 23595136.5 |  | 0 | [7 empty] | 6609053.902 | 6609053.902 |  | 8609053.902 | 8609053.902 | 8609053.902 | 5609053.902 | 23595136.5
24 b | Baclony Glass Railing (M+L) | 2025-03-01 |  |  | 16617856 | 5269856 | 1317464 | 3952392 | 5674000 | [8 empty] | 2634500 | 2634500 |  | 5634500 | 5340356 |  |  | 9626392 |  | Partial -
25 | Ceiling Work (M+L) | 2024-10-27 | 1 | 72011500 | 42282623 | 38171630 | 10462396 | 27709234 |  | 0 | 2024-10-27 | 46.99% | [6 empty] | 6094326 |  | 7094326 | 7094326 | 6329532 | 3967126 | 27709234 | 3223924 | In progress
26 | DISTRIBUTION BOARDS (M) | 2024-10-27 | 2 | 34752905 | 34752905 | 46267080 | 37421590 | 8845490 |  | 0 | 2024-10-27 | -33.13% | [5 empty] | 5900000 | 8850000 |  | 8850000 | 8850000 | 2784682 |  | 8845490 | -11639192
27 | Paint (M+L) Internal | 2024-12-03 | 2 | 77163155 | 60269252 | 47509000 | 8100891 | 39408109 |  | 0 | 2024-12-03 | 38.43% | [5 empty] | 3611920 | 7350000 |  | 9850000 | 9850000 | 9850000 | 9850000 | 39408109 |  | In progress
27 a | Paint (M+L) External | 2024-12-04 | 2 | 18525600 | 16000000 | 9961998 | 2490500 | 7471498 |  | 0 | [7 empty] | 2490499.3333 | 2490499.3333 |  | 2490499.3333 | 4980998.6667 |  |  | 7471498 | 0
28 | Tile ( M+L) | 2024-09-04 | 2 | 277877655 | 154722922.8571 | 153071595 | 107326152 | 45745443 |  | 0 | 2024-09-04 | 44.91% | [5 empty] | 3459748 | 13782539 |  | 7782539 | 15782539 | 15782539 | 11173895 | 45745443 | -4776069
28 a | Marble Work (M+L) | 2025-11-01 | 1 | 34256200 | 29000000 | 28315671 | 15413467 | 12902204 |  | 0 | 2025-11-01 | [7 empty] | 5249640 |  | 7000000 | 7000000 | 4249640 |  | 12902204 | -5347436 | Partial -
29 | BUSWAYS (M) | 2024-11-04 | 6 | 60199030 | 55750703 | 46267080 | 9773346 | 36493734 |  | 0 | 2024-11-04 | 23.14% | [5 empty] | 9773346 | 6576654 |  |  | 16350000 | 20143734 |  | 36493734 | 0
30 | Wood Works (M+L) | 2024-11-04 | 1 | 358505101 | 280680000 | 210151423 | 98249211 | 111902212 | 15500000 | 0 | 2024-11-04 | 100% | [6 empty] | 38519653.6 |  | 38519653.6 | 38519653.6 | 38519653.6 | 38394550.2 | 127402212 | -26551299 | In progress
30a | Steel Works ( M+L) | 2025-02-01 | 2 | 27000000 | 20000000 |  |  | 0 | 20000000 | 0 | [7 empty] | 5000000 | 3500000 |  | 8500000 | 7000000 | 3500000 | 1000000 | 20000000 | 0
31 | MV+LT PANELS (M) | 2024-11-04 | 0 | 35830680 | 41230680 | 41052919 | 20615340 | 20437579 | 177761 | 0 | 2024-11-05 | 100% | [8 empty] | 10315340 |  | 20295340 |  | 20615340 | -9995340 | Partial -
32 | DIESEL GENERATOR & ALLIED WORKS (M+L) | 2024-11-05 | 0 | 187008071.94 | 20000000 |  |  | 0 | 20000000 | 0 | 2024-11-30 | 100% | [8 empty] | 15000000 |  | 5000000 |  | 20000000 | 0
33 | Chute (M+L) | 2024-11-30 | 0 | 8000000 | 8000000 |  |  | 0 | 8000000 | 0 | Dropped | [9 empty] | 5600000 |  | 2400000 |  | 8000000 | 0
34 | LPG System (M+L) | 2024-12-01 | 0 |  | 18438000 |  |  | 0 | 18438000 | 0 | [10 empty] | 9219000 |  | 9219000 |  | 18438000 | 0
35 | VERTICAL BACKBONE INFRASTRUCTURE (GPON) (M+L) | 2024-12-02 | 5 | 6989660 | 13804200 |  |  | 0 | 13804200 | 0 | 2024-12-06 | 100% | [6 empty] | 9662940 |  |  | 9662940 | 4141260 |  | 13804200 | 0
36 | SUPPLY OF PLUMBING FIXTURES (M) | 2024-12-06 | 2 | 139951151 | 126180487.9024 | 66000000 | 40000000 | 26000000 | 13200000 | 0 | 2024-12-07 | 100% | [5 empty] | 21030081.3833 | 21030081.3833 |  | 40000000 | 13200000 | 20000000 |  | 39200000 | -34000000 | Partial -
36a | Mirror | 2024-12-07 | 3 | 8443500 | 4500000 |  |  | 0 | 4500000 | 0 | [8 empty] | 1800000 |  | 1800000 | 1800000 | 900000 |  | 4500000 | 0
36b | Shower Cabin | 2024-12-08 | 3 | 14235600 | 12409756 | 5846400 | 1461600 | 4384800 | 6563356 | 0 | [7 empty] | 4963902.4 |  |  | 4963902.439 | 4963902.439 | 2481951.161 |  | 10948156 | -1461600.039 | Partial -
37 | MEDIUM VOLTAGE CABLES & TERMINATION KITS (M) | 2024-12-07 | 2 | 2145530 | 2145530 |  |  | 0 | 2145530 | 0 | 2025-01-01 | 100% | [6 empty] | 2145530 |  |  |  | 2145530 |  | 2145530 | 0
38 | SWITCHES & SOCKETS (M) | 2025-01-01 | 1 | 15914889 | 17889340 | 9905063 | 4952531 | 4952532 | 4200000 | 0 | 2025-01-02 | 100% | [5 empty] | 4952531 |  |  |  | 8192138 | 960394 |  | 9152532 | 0 | Partial -
39 | LIGHTING+ FIXTURES (M) | 2025-01-02 | 2 | 29324517 | 29324517 | 21052601 | 21052601 | 0 | 8271916 | 0 | 2025-01-03 | 100% | [9 empty] | 4170222.6667 | 4105222.6667 |  | 8271916 |  | Partial -
40 | UPS (UNINTERRUPTIBLE POWER SUPPLY) (M+L) | 2025-01-03 | 0 | 6147120 | 6147120 |  |  | 0 | 6147120 | 0 | 2025-01-04 | 100% | [8 empty] | 4302984 |  |  | 1844136 | 6147120 | 0
41 | CCTV SYSTEM (IP BASED) (M+L) | 2025-01-04 | 0 | 6264080 | 5715920 |  |  | 0 | 5715920 | 0 | 2025-01-05 | 100% | [8 empty] | 4001144 |  |  | 1714776 | 5715920 | 0
42 | Ventilation/Exhaust system (M+L) | 2025-01-05 | 4 | 7492650 | 7492650 | 7492650 | 6915439 | 577211 |  | 0 | 2025-01-05 | 100% | [6 empty] | 3206036 |  |  | 577211 |  |  | 577211 | 0 | In progress
43 | FSS Works (FFS equipment) (M) | 2025-01-05 | 4 | 48330248 | 41045103.1024 | 37610640 | 17373192 | 20237448 | 3434463.1024 | 0 | 2025-02-01 | 100% | [6 empty] | 22574806.7063 |  | 3022537 | 5313530.9307 | 13901615.1717 | 4456785 | 23671911.1024 | -3022557 | Partial
44 | DRY TYPE TRANSFORMERS (M+L) | 45689 | 5 | 34860000 | 19116375 | 17298800 | 8649400 | 8649400 |  | 0 | 45690 | 1 | [5 empty] | 13381462.5 |  |  |  | 5734912.5 | 2914487.5 |  | 8649400 | 0 | In progress
45 | FIRE ALARM SYSTEM (M+L) | 2025-02-02 | 1 | 11074630 | 8223361 |  |  | 0 | 8223361 | 0 | 2025-02-03 | 100% | [5 empty] | 5756352.7 |  |  |  | 2467008.3 | 5756352.7 |  | 8223361 | 0
46 | FACILITY LIGHTNING PROTECTION SYSTEM (OFM) | 2025-02-03 | 1 | 2463855 | 2463855 |  |  | 0 | 2463855 | 0 | 2025-02-04 | 100% | [5 empty] | 1724698.5 |  |  |  | 1724698 | 739156.5 |  | 2463855 | 0.5
47 | Water storage heater (M) | 2025-02-04 | 1 | 21696000 | 18650320 | 13500990 | 9964000 | 3536990 |  | 0 | 2025-03-05 | 100% | [6 empty] | 3536990 |  |  | 3536990 |  |  | 3536990 | 0 | In progress
48 | PUBLIC ADDRESS SYSTEM (M) | 2025-03-05 | 4 | 2860230 | 4858060 |  |  | 0 | 4858060 | 0 | 2025-03-06 | 100% | [6 empty] | 3400642 |  |  | 1457418 | 3400642 |  | 4858060 | 0
49 | ACCESS CONTROL SYSTEM (M) | 2025-03-06 | 4 | 4067570 | 4869034.875 |  |  | 0 | 4869034.875 | 0 | 2025-03-07 | 100% | [6 empty] | 3408324.4125 |  |  | 3408324.4125 | 1460710.4625 |  | 4869034.875 | 0
50 | Pump Sets (M) | 2025-03-07 | 4 | 5200000 | 4986000 |  |  | 0 | 4986000 | 0 | 2025-03-08 | 100% | [6 empty] | 4986000 |  |  |  | 4986000 |  | 4986000 | 0
51 | FSS Works (Fire Pumps) Basement (M+L) | 2025-03-08 | 4 | 46499716 | 39391701.64 | 28751340 | 8625402 | 20125938 | 3012500 | 0 | 2025-03-08 | 38.17% | [5 empty] | 27574191.148 |  |  |  | 11320927.508 | 11817510.492 |  | 23138438 | 0 | In progress
52 | ACMV Works (Ac units) (M+L) | 2025-03-08 | 4 | 107570000 | 99000000 |  |  | 0 | 99000000 | 0 | 2025-03-08 | 100% | [8 empty] | 33000000 | 33000000 | 33000000 |  | 99000000 | 0
53 | Water meter (M) | 2025-03-09 | 4 | 6160000 | 6160000 |  |  | 0 | 6160000 | 0 | 2025-03-09 | 100% | [8 empty] | 4312000 |  | 1848000 |  | 6160000 | 0
54 | Kitchen Hoods (M) | 2025-03-10 | 0 | 10000000 | 8800000 | 6160000 |  | 6160000 | 8800000 | 0 | 2025-03-10 | [9 empty] | 2933333.3333 | 2933333.3333 | 2933333.3333 |  | 14960000 | 6160000
55 | Travertiene | 2024-11-24 | 4 | 30513600 | 25640000 | 37835258 | 33782363 | 4052895 | 7020000 | 0 | 2024-11-24 | [10 empty] | 5075203.2892 | 2867256.7108 |  | 11072895 | 3130435 | In progress
| Total for Finishes |  |  | 2797458501.44 | 2097165484.142 | 1532169485 | 959832368.5 | 573018546.5 | 341259796.9774 |  | 1552507 | 32.1337 | 0 | 0 | 0 | 0 | 0 | 164184478.8839 | 260385091.3548 |  | 332638041.8441 | 316013676.5844 | 286520438.8364 | 89399782.1929 | 914278343.4774 | -110293595.9804
| Additional Items | [7 empty] | -681430 | [15 empty] | -681430 | -681430
56 | VRF In corridor ( M+L) |  |  |  | 50500000 | 50500000 | 36696520 | 13803480 | [9 empty] | 15150000 | 6200000 |  |  | 29150000 |  |  | 13803480 | -15346520
57 | Kitchen Hob (M) |  |  |  | 8800000 | 8800000 |  | 8800000 | 8800000 | [13 empty] | 8800000 |  | 17600000 | 8800000
58 | External lights |  |  |  | 4894000 | 4894000 | 4894000 | 0 | [14 empty] | 325000 |  | 0 | -325000
59 | Swimming Pool ( M+L) |  |  |  | 16200000 | 16200000 | 11340000 | 4860000 | [12 empty] | 4860000 |  |  |  | 4860000 | 0
60 | Pargola |  |  |  | 8744828 | 8744828 | 3497931.2 | 5246896.8 | [13 empty] | 0 | 0 |  | 5246896.8 | 5246896.8
61 | AC louvers. |  |  |  | 14432000 |  |  |  | 14432000 | [12 empty] | 10102400 | 4329600 |  |  | -14432000
62 | Roof Top |  |  |  | 29742999 | 845000 | 422500 | 422500 | 28897999 | [12 empty] | 20228599.3 | 8669399.7
63 | Additiona wood Work Item. |  |  |  | 13469139 |  |  |  | 13469139 | [12 empty] | 9428397.3 | 4040741.7
64 | Basement Civil Works ( I tower posting ) |  |  |  | 36000000 |  |  |  | 36000000
65 | Basement Civil MEP ( I tower posting ) |  |  |  | 16000000 |  |  |  | 16000000
C | Grand Total Finishes |  |  | 2797458501.44 | 2295948450.142 | 1622153313 | 1016683319.7 | 606151423.3 | 458177504.9774 | 0 | 1552507 | 32.1337 | 0 | 0 | 0 | 0 | 0 | 179334478.8839 | 266585091.3548 | 0 | 337498041.8441 | 355266076.5844 | 299975038.8364 | 89399782.1929
Note on L5: Babu: acyual Exoebses wull be updated wit on month end
Note on F69: Babu: Quanitity was 30,824
Note on G69: Babu: Quanities are Aroung 58000 sft

## L1 Finishes
Lakecity Roof Gardens - Projected Cash Flow (Structural & Finishes Works June 2025 to Jan 2026) |  |  |  | L1 Finishes | [16 empty] | 19.12.2025
S.No. | Area | Time line | Consultant Budget NADA/SEMS | Budget As per Initial Quotation Received | Awarded Value | Actual Spending | Actual Balance Amount | Pending approval | 2025-03-06 | 2025-06-02 | 2025-08-04 | 2025-09-05 | 2025-10-06 | 2025-11-06 | 2025-12-09 | 2026-01-01 | 2026-02-02 | 2026-03-01 | 2026-04-01 | 2026-05-01 | Remarks
C | Façade Works ( L 1 tower) | 2024-10-01 | 49636205 | 40291143 | 40291143 | 35449591 | 4841552 |  |  |  | 4841552 | [9 empty] | In progress
Finishes For Tower L 1
1 | External Brick Works (M+L) | 2024-09-01 | 12735095 | 9235361 | 9235361 | 6311073 | 2924288 | 0 |  |  | 2924288.5 |  |  | 2924288 | [6 empty] | In progress
2 | Internal Brick Works (M+L) | 2024-10-01 | 77560123 | 67811217 | 74421345 | 72814009.5 | 1607335.5 |  |  |  | 13318255.4167 | 7930808 |  | 1607335.5 | [6 empty] | In progress
3 | Electrical Conduiting (M+L) | M-03/ 6 Month | 26773680.21 | 18313647 | 13067330 | 4292391.8 | 8774938.2 | 5246317 |  |  | 6104549.0833 | 6104549.0833 | 6104549.0833 | 6987469.1 | 6987469.1 | [5 empty] | Partial
4 | Plumbing Conduiting (M+L) | M-03/ 6 Month | 21137725 | 15669062 | 12858616 | 8373422.8 | 4485193.2 | 2810446 |  |  | 5223020.8333 | 5223020.8333 | 5223020.8333 | 3642596.6 | 3642596.6 | [5 empty] | Partial
5 | SOIL, WASTE VENT AND RAIN WATER DRAINAGE SYSTEM (M) | M-03/ 8 Month | 55044200 | 11666143 | 11666143 | 1477354 | 10188789 | 0 |  |  | 1944357.1667 | 1944357.1667 | 1944357.1667 | 3944357.1667 | 3944357.1667 | 1944357.1667
6 | PCC (M+L) | M-04 | 28000000 | 21356000 | 21356000 | 14071168 | 7284832 | 0
7 | External Plaster (M+L) | M-05 | 5851000 | 5364800 | 5364800 | 1592000 | 3772800 |  |  |  | 2185920 | 1592600 |  | 3772800
8 | Internal Plaster (M+L) | M-05 | 45095450 | 34785601 | 34785601 | 14331336 | 20454265 |  |  |  | 6836400.25 | 8696400.25 | 8696400.25 | 8696400.25 | 8696400.25 | 8696400.25
10 | Subcontract Electrical (L) | M-06 | 21992008 | 14221499 | 12878310 | 1287831 | 11590479 |  |  |  | 643915.5 | 643915.5 | 1931746.5 | 2575662 | 2575662 | 3931746.5 | 3287831
11 | Subcontract Plumbing (L) | M-06 | 27128000 | 17542773 | 16256850 | 1978056 | 14278794 |  |  |  | 793266.3333 | 793266.3333 | 2379799 | 2379799 | 3379799 | 3379799 | 3379799 | 1793266.3333 |  |  | In progress
12 | CABLE CONTAINMENT (M) | M-06 | 11326915 | 12130712 | 12130712 |  | 12130712 | 0
13 | Subcontract Firefighting (L) | M-06 | 6947660 | 4500000 | 4293868 |  | 4293868 | 206132
14 | FSS Works (Piping) (M) | M-06 | 21654600 | 14003308 | 14003308 | 3624095 | 10379213 | 0
15 | Subcontract HVAC (M+L) | M-06 | 13159810 | 8510010 |  |  |  | 8510010
16 | Copper Pipe + Accessories (M+L) | M-06 | 21076800 | 13629664 | 14000000 | 7495229 | 6504771
17 | LPG Works (M) |  |  | 7500000 | 4952283 | 4491802 | 460481 | 2547717 |  |  | 1666666.6667 | 1666666.6667 | 1666666.6667 | 1250000 | 1250000 | [5 empty] | Partial
18 | WIRING / WIRING ACCESSORIES (M) | M-06 | 50927365.5 | 32933030 |  |  |  | 32933030
19 | MAIN / SUB-MAIN CABLES (M) | M-06 | 22324236.5 | 11436340 |  |  |  | 11436340
20 | VOICE & DATA COMMUNICATION (M+L) | M-06 | 11332805 | 22692700 |  |  |  | 22692700
21 | Pipes for Water Supply and fitting (M) | M-07 | 14218500 | 7469930 |  |  |  | 7469930
22 | Elevator (M+L) | M-07 | 60712000 | 44687500 | 33292000 | 4800000 | 28492000 |  |  |  |  | 19065384.6154 |  |  | 14226615.3846
24 a | Aluminum Work (M+L) | M-08 | 97040526 | 91826667 |  |  |  | 91826667
24 b | Glass Work (M+L)
24 b | Baclony Glass (M+L)
25 | Ceiling Work (M+L) | M-08 | 44903000 | 31464928 |  |  |  | 31464928
26 | DISTRIBUTION BOARDS (M) | M-08 | 30695163 | 26322872 |  |  |  | 26322872
27 a | Internal Paint (M+L) | M-08 | 58348355 | 28494951 |  |  |  | 28494951
27 b | External Paint |  |  | 9236985 | 8105205 | 2026300 | 6078905 | [5 empty] | 2026301.6667 | 2026301.6667 | 2026301.6667
28 | Tile (M+L) | M-08 | 201253640 | 140144021 |  |  |  | 140144021
28 b | Marble Works | [6 empty] | 0
29 | BUSWAYS (M) | M-08 | 38302485 | 28768940 |  |  |  | 28768940
30 a | Wood (M+L) | M-09 | 302206050 | 195426579 |  |  |  | 195426579
30 b | Steel Work (M+L) | [6 empty] | 0
31 | Dry Type Transformers (M) | M-09 | 19853260 | 12365108 | 11741000 | 5870500 | 5870500 | [7 empty] | 5870500 | 5870500
32 | DIESEL GENERATOR & ALLIED WORKS (M+L) | M-09 | 105066341.84 | 67942901 |  |  |  | 67942901
33 | Chute (M+L) | M-09 | 4000000 | 4000000 |  |  |  | 4000000
34 | LPG System (M+L) | [6 empty] | 0
35 | VERTICAL BACKBONE INFRASTRUCTURE (GPON) (M+L) | M-10 | 5087280 | 5087280 |  |  |  | 5087280
36a | SUPPLY OF PLUMBING FIXTURES (M) | M-10 | 98101000 | 95256396 |  |  |  | 95256396
36b | Mirror | [6 empty] | 0
36c | Shower Cabin | [6 empty] | 0
37 | MEDIUM VOLTAGE CABLES & TERMINATION KITS (M) | M-10 | 2145530 | 2145530 |  |  |  | 2145530
38 | SWITCHES & SOCKETS (M) | M-10 | 10380086.5 | 11568440 |  |  |  | 11568440
39 | LIGHTING FIXTURES (M) | M-10 | 12695189 | 18963188 |  |  |  | 18963188
40 | UPS (UNINTERRUPTIBLE POWER SUPPLY) (M+L) | M-10 | 6147120 | 6147120 |  |  |  | 6147120
41 | CCTV SYSTEM (IP BASED) (M+L) | M-10 | 4598000 | 5715920 |  |  |  | 5715920
42 | Ventilation/Exhaust system (M+L) | M-10 | 7492650 | 7492650 |  |  |  | 7492650
45 | FIRE ALARM SYSTEM (M+L) | M-11 | 8663440 | 6602358 |  |  |  | 6602358
46 | FACILITY LIGHTNING PROTECTION SYSTEM (OFM) | M-11 | 2463855 | 2463855 |  |  |  | 2463855
47 | Water storage heater (M) | M-11 | 12799500 | 14030080 |  |  |  | 14030080
48 | PUBLIC ADDRESS SYSTEM (M) | M-11 | 1537470 | 1537470 |  |  |  | 1537470
49 | ACCESS CONTROL SYSTEM (M) | M-11 | 2339725 | 2339725 |  |  |  | 2339725
50 | Pump Sets (M) | M-11 | 2050000 | 2050000 |  |  |  | 2050000
51 | FSS Works (Fire Pumps) Basement (M+L) | M-11 | 34320000 | 27391702 |  |  |  | 27391702
52 | ACMV Works (Ac units) (M+L) | M-12 | 68880000 | 54012569 |  |  |  | 54012569
53 | Water meter (M) | M-12 | 3920000 | 3920000 |  |  |  | 3920000
54 | Kitchen Hoods (M) |  | 6000000 | 6000000 |  |  |  | 6000000
55 | Travertiene |  |  |  | 21000000 | 4960775 | 16039225 | [6 empty] | 7123656 | 7123656 | 2123656
| Grand Total Finishes |  | 1746287639.55 | 1304177532 | 335408732 | 159797343.1 | 175611388.9 | 980968764 | 0 | 0 | 41640639.75 | 53660968.4487 | 29972841.1667 | 46930665.2833 | 59723357.1679 | 25946458.9167 | 6667630 | 1793266.3333 | 0 | 0
| Additional Items | [6 empty] | 0
56 | VRF In corridor ( M+L) |  |  | 35000000 |  |  |  | 35000000
57 | Kitchen Hob (M) |  |  | 6000000 |  |  |  | 6000000
58 | External lights |  |  | 3731700 | 3144200 | 3144200 | 0 | 587500
59 | Paddle Tenis Court ( M+L) | [6 empty] | 0 | [8 empty] | 0
60 | Pargola |  |  | 2420155 | 2420155 | 968062 | 1452093
61 | AC louvers. |  |  | 10102400 |  |  |  | 10102400
62 | Roof Top |  |  | 20820099.3 |  |  |  | 20820099.3 | 0
63 | Additiona wood Work Item. |  |  | 9428397.3 |  |  |  | 9428397.3 | 0
64 | Basement Civil Works ( L1 tower posting ) |  |  | 26500000 |  |  |  | 26500000
65 | Basement Civil MEP (L1 tower posting ) |  |  | 12000000 |  |  |  | 12000000
0
| Total Finishes |  | 1746287639.55 | 1430180283.6 | 340973087 | 163909605.1 | 177063481.9 | 991071164 | 0 | 0 | 41640639.75 | 53660968.4487 | 29972841.1667 | 46930665.2833 | 59723357.1679 | 25946458.9167 | 6667630 | 1793266.3333 | 0 | 0

## L2 Finishes
Lakecity Roof Gardens - Projected Cash Flow (Structural & Finishes Works June 2025 to Jan 2026) |  |  |  | L2 Finishes | [18 empty] | 19.12.2025
S.No | Area | Plan Start Month/Duration | NADA/SEMs Budget | First Quotation Recived | Awarded Valuue | Actual Spending | Actual Balance Amount | Pending approval | 2025-06-02 | 2025-08-04 | 2025-09-05 | 2025-10-07 | 2025-11-08 | 2025-12-10 | 2026-01-11 | 2026-02-12 | 2026-03-16 | 2026-04-17 | 2026-05-19 | 2026-06-20 | 2026-06-21 | 2026-07-23 | 2026-01-04
C | Façade Works ( L 2 tower) | 2025-04-01 | 49636205 | 49134722 | 48334459 | 44160604 | 4173855 | [5 empty] | 4550108
Finishes For Tower L 2
1 | External Brick Works (M+L) | 2024-09-01 | 12735095 | 9235361 | 9308278 | 8200000 | 1108278 | [5 empty] | 1108278
2 | Internal Brick Works (M+L) | 2024-10-01 | 77560123 | 67811217 | 74421345 | 14869592 | 59551753 | [5 empty] | 13550108 | 13550108 | 13550108 | 13550108 | 13550108
3 | Electrical Conduiting (M+L) | M-03/ 6 Month | 26773680.21 | 18313647 | 8241141.15 |  | 8241141.15 | 10072505.85 |  |  |  |  | 3102759.3333 | 3102759.3333 | 3102759.3333 |  | 0
4 | Plumbing Conduiting (M+L) | M-03/ 6 Month | 21137725 | 15669062 | 7051077.9 |  | 7051077.9 | 8617984.1 |  |  |  |  | 2350359.3 | 2350359.3 | 2350359.3 |  | 0
5 | SOIL, WASTE VENT AND RAIN WATER DRAINAGE SYSTEM (M) | M-03/ 8 Month | 55044200 | 11666143 | 11666143 |  | 11666143 | [5 empty] | 2333229 | 2333229 | 2333229 | 2333229 | 2333229
6 | PCC (M+L) | M-04 | 28000000 | 21356000 |  |  |  | 21356000
7 | External Plaster (M+L) | M-05 | 5851000 | 5364800 | 5364800 | 5050714 | 314086 | [5 empty] | 314086 |  |  |  | 0
8 | Internal Plaster (M+L) | M-05 | 45095450 | 34785601 | 34785601 |  | 34785601 | [6 empty] | 6957120.2 | 6957120.2 | 6957120.2 | 6957120.2 | 6957120.2
10 | Subcontract Electrical (L) | M-06 | 21992008 | 14221499 | 6399674.55 |  | 6399674.55 | 7821824.45 |  |  |  |  | 2607274.8167 | 2607274.8167 | 2607274.8167 | 2607274.8167 | 2607274.8167 | 1607274.8167
11 | Subcontract Plumbing (L) | M-06 | 27128000 | 17542773 | 7894247.85 |  | 7894247.85 | 9648525.15 |  |  |  |  | 3216175.05 | 3216175.05 | 3216175.05 | 3216175.05 | 3216175.05 | 3216175.05
12 | CABLE CONTAINMENT (M) | M-06 | 11326915 | 12130712 |  |  |  | 12130712 | [8 empty] | 0
13 | Subcontract Firefighting (L) | M-06 | 6947660 | 4500000 |  |  |  | 4500000 | [8 empty] | 0
14 | FSS Works (Piping) (M) | M-06 | 21654600 | 14003308 |  |  |  | 14003308 | [8 empty] | 0
15 | Subcontract HVAC (M+L) | M-06 | 13159810 | 8510010 |  |  |  | 8510010 | [8 empty] | 0
16 | Copper Pipe + Accessories (M+L) | M-06 | 21076800 | 13629664 |  |  |  | 13629664 | [8 empty] | 0
17 | LPG Works (M) |  |  | 7500000 |  |  |  | 7500000 | [8 empty] | 0
18 | WIRING / WIRING ACCESSORIES (M) | M-06 | 50927365.5 | 32933030 |  |  |  | 32933030 | [8 empty] | 0
19 | MAIN / SUB-MAIN CABLES (M) | M-06 | 22324236.5 | 11436340 |  |  |  | 11436340 | [8 empty] | 0
20 | VOICE & DATA COMMUNICATION (M+L) | M-06 | 11332805 | 22692700 |  |  |  | 22692700 | [8 empty] | 0
21 | Pipes for Water Supply and fitting (M) | M-07 | 14218500 | 7469930 |  |  |  | 7469930 | [8 empty] | 0
22 | Elevator (M+L) | M-07 | 60712000 | 44687500 | 33292000 |  | 33292000 | [5 empty] | 13224000 |  | 11934000 | 7934000
24 a | Aluminum Work (M+L) | M-08 | 97040526 | 91826667 |  |  |  | 91826667 | [8 empty] | 0
24 b | Glass Work (M+L) | [6 empty] | 0 | [8 empty] | 0
24 b | Baclony Glass (M+L) | [6 empty] | 0 | [8 empty] | 0
25 | Ceiling Work (M+L) | M-08 | 44903000 | 31464928 |  |  |  | 31464928 | [8 empty] | 0
26 | DISTRIBUTION BOARDS (M) | M-08 | 33695162.5 | 30695163 |  |  |  | 30695163 | [8 empty] | 0
27 a | Internal Paint (M+L) | M-08 | 58348355 | 28494951 |  |  |  | 28494951 | [8 empty] | 0
27 b | External Paint |  |  | 9236985 | 8105205 | 2026300 | 6078905 | [6 empty] | 2026301.6667 | 2026301.6667 | 2026301.6667
28 | Tile (M+L) | M-08 | 201253640 | 140144021 |  |  |  | 140144021 | [8 empty] | 0
28 b | Marble Works | [6 empty] | 0 | [8 empty] | 0
29 | BUSWAYS (M) | M-08 | 38302485 | 28768940 |  |  |  | 28768940 | [8 empty] | 0
30 a | Wood (M+L) | M-09 | 302206050 | 195426579 |  |  |  | 195426579 | [8 empty] | 0
30 b | Steel Work (M+L) | [6 empty] | 0 | [8 empty] | 0
31 | Dry Type Transformers (M) | M-09 | 19853260 | 12365108 | 11741000 | 5870500 | 5870500 | [8 empty] | 5870500
32 | DIESEL GENERATOR & ALLIED WORKS (M+L) | M-09 | 105066341.84 | 67942901 |  |  |  | 67942901 | [8 empty] | 0
33 | Chute (M+L) | M-09 | 4000000 | 4000000 |  |  |  | 4000000 | [8 empty] | 0
34 | LPG System (M+L) | [6 empty] | 0 | [8 empty] | 0
35 | VERTICAL BACKBONE INFRASTRUCTURE (GPON) (M+L) | M-10 | 5087280 | 5087280 |  |  |  | 5087280 | [8 empty] | 0
36a | SUPPLY OF PLUMBING FIXTURES (M) | M-10 | 98101000 | 95256396 |  |  |  | 95256396 | [8 empty] | 0
36b | Mirror | [6 empty] | 0 | [8 empty] | 0
36c | Shower Cabin | [6 empty] | 0 | [8 empty] | 0
37 | MEDIUM VOLTAGE CABLES & TERMINATION KITS (M) | M-10 | 2145530 | 2145530 |  |  |  | 2145530 | [8 empty] | 0
38 | SWITCHES & SOCKETS (M) | M-10 | 10380086.5 | 11568440 |  |  |  | 11568440 | [8 empty] | 0
39 | LIGHTING FIXTURES (M) | M-10 | 12695189 | 18963188 |  |  |  | 18963188 | [8 empty] | 0
40 | UPS (UNINTERRUPTIBLE POWER SUPPLY) (M+L) | M-10 | 6147120 | 6147120 |  |  |  | 6147120 | [8 empty] | 0
41 | CCTV SYSTEM (IP BASED) (M+L) | M-10 | 4598000 | 5715920 |  |  |  | 5715920 | [8 empty] | 0
42 | Ventilation/Exhaust system (M+L) | M-10 | 7492650 | 7492650 |  |  |  | 7492650 | [8 empty] | 0
45 | FIRE ALARM SYSTEM (M+L) | M-11 | 8663440 | 6602358 |  |  |  | 6602358 | [8 empty] | 0
46 | FACILITY LIGHTNING PROTECTION SYSTEM (OFM) | M-11 | 2463855 | 2463855 |  |  |  | 2463855 | [8 empty] | 0
47 | Water storage heater (M) | M-11 | 12799500 | 14030080 |  |  |  | 14030080 | [8 empty] | 0
48 | PUBLIC ADDRESS SYSTEM (M) | M-11 | 1537470 | 1537470 |  |  |  | 1537470
49 | ACCESS CONTROL SYSTEM (M) | M-11 | 2339725 | 2339725 |  |  |  | 2339725
50 | Pump Sets (M) | M-11 | 2050000 | 2050000 |  |  |  | 2050000
51 | FSS Works (Fire Pumps) Basement (M+L) | M-11 | 34320000 | 27391702 |  |  |  | 27391702
52 | ACMV Works (Ac units) (M+L) | M-12 | 68880000 | 54012569 |  |  |  | 54012569
53 | Water meter (M) | M-12 | 3920000 | 3920000 |  |  |  | 3920000
54 | Kitchen Hoods (M) |  | 6000000 | 6000000 |  |  |  | 6000000
55 | Travertiene |  |  |  | 21000000 | 4144005 | 16855995 | [5 empty] | 7000000 | 7000000 | 3000000
| Total Finishes |  | 1749287639.05 | 1308549823 | 239270513.45 | 40161111 | 199109402.45 | 1083810966.55 | 0 | 0 | 0 | 0 | 48806269.5 | 43143327.3667 | 51077327.3667 | 44494708.7333 | 28663907.0667 | 11780570.0667 | 0 | 0 | 0 | 0
Additional Items
56 | VRF In corridor ( M+L) |  |  | 35000000 |  |  |  | 35000000
57 | Kitchen Hob (M) |  |  | 6000000 |  |  |  | 6000000
58 | External lights |  |  | 3731700 | 3731700 | 3144200 | 0 | 0
59 | Paddle Tenis Court ( M+L) | [6 empty] | 0
60 | Pargola |  |  | 2420155 | 2420155 | 968062 | 1452093 | 0
61 | AC louvers. |  |  | 10102400 |  |  |  | 10102400
62 | Roof Top |  |  | 20820099.3 |  |  |  | 20820099.3
63 | Additiona wood Work Item. |  |  | 9428397.3 |  |  |  | 9428397.3
64 | Basement Civil Works (L2 tower posting ) |  |  | 26500000 |  |  |  | 26500000
65 | Basement Civil MEP (L2 tower posting ) |  |  | 12000000 |  |  |  | 12000000 | [9 empty] | 0
0
0
| Grand Total Finishes |  |  | 1434552574.6 | 245422368.45 | 44273373 | 200561495.45 | 1203661863.15 | 0 | 0 | 0 | 0 | 48806269.5 | 43143327.3667 | 51077327.3667 | 44494708.7333 | 28663907.0667 | 11780570.0667

## Ground Floor
19.12.2025
Ground floor I-Tower.
S.No | Area | Plan Start Month/Duration | NADA/SEMs Budget | First Quotation Recived | Awarded Valuue | Actual Spending | Actual Balance Amount | Pending approval
1 | Electrical Work | not finalize yet | Yet to finalize | 11820918.6 | 6220700 | 2762019 | 3458681
2 | Plumbing work | not finalize yet | Yet to finalize | 9924504.75 | 9428921 | 5928921 | 3500000
3 | Fire figthing works | not finalize yet | Yet to finalize | 5240700 | 2868500 | 1241083 | 1627417
4 | Copper piping | not finalize yet | Yet to finalize | 21498750 | 1900000 | 1900000 | 0
5 | Insulation of pipes | not finalize yet | Yet to finalize | 1755000 | 3141525 | 2054018 | 1087507
6 | Marble | not finalize yet | Yet to finalize | 6750000 | 12834922 | 9101017 | 3733905
7 | Aluminum Work (M+L) | not finalize yet | Yet to finalize | 17800000 | 15000000 |  |  | 15000000
8 | Total Lobby | not finalize yet | Yet to finalize | 74789873.35 | 51394568 | 22987058 | 13407510 | 15000000
10 | Gym Equipment | not finalize yet | Yet to finalize | 36000000 | 36000000 | 27000000 | 9000000
11 | Gym | not finalize yet | Yet to finalize | 18000000 | 16999424 | 4249856 | 12749568
12 | Business Center | not finalize yet | Yet to finalize | 6500000 | 5916720 | 1479180 | 4437540
13 | Game Room | not finalize yet | Yet to finalize | 8600000 | 8350094 | 2087523.5 | 6262570.5
15 | MEP Work | not finalize yet | Yet to finalize | 5600000 | 4000000 |  |  | 4000000
16 | Total Remianing | not finalize yet | Yet to finalize | 74700000 | 71266238 | 34816559.5 | 32449678.5 | 4000000
Additilan Items
17 | Acs |  |  | 13000000 |  |  |  | 13000000
18 | Furnitures |  |  | 15000000 | 5925924.2857 | 4148147 |  | 15000000
| Grand Total |  |  | 177489873.35 | 128586730.2857 | 61951764.5 | 45857188.5 | 47000000
External Development Plan
S.No | Area | Plan Start Month/Duration | NADA/SEMs Budget | First Quotation Recived | Awarded Valuue | Actual Spending | Actual Balance Amount | Pending approval
1 | Sewerage System ( Main holes system) | not finalize yet | Yet to finalize | 18000000 | 18000000 | 15500000 | 2500000
2 | Boundary Wall | not finalize yet | Yet to finalize | 7351485 | 7351485 | 4652300 | 2699185
3 | Boundary Wall Paint | not finalize yet | Yet to finalize | 1782000 |  |  |  | 1782000
4 | Boundary Wall Louvers | not finalize yet | Yet to finalize | 15925000 | 13386100 | 5354440 | 10570560
5 | Electrical Works ( Main hole System) | not finalize yet | Yet to finalize | 1300000 | 1300000 |  | 1300000
6 | Road Base Structure | not finalize yet | Yet to finalize | 5000000 | 5000000 | 5000000 | 0
7 | Fire Fighting System (Base Network) | not finalize yet | Yet to finalize | 8000000 | 8000000 | 5523642 | 2476358
8 | External Drain channel | not finalize yet | Yet to finalize | 3200000 |  |  |  | 3200000
10 | Re-charge pit | not finalize yet | Yet to finalize | 3500000 |  |  |  | 3500000
11 | PCC.+Drain | not finalize yet | Yet to finalize | 19925000 | 19925000 | 11200000 | 8725000
12 | Street Poles Lamp foundation | not finalize yet | Yet to finalize |  |  |  | 0
13 | Internal Drain Channels | not finalize yet | Yet to finalize | 2500000 | 2500000 | 1053972 |  | 2500000
15 | Paver system | not finalize yet | Yet to finalize | 31000000 | 37000000 | 13682993 | 17317007
16 | Plantations+Benches+Marble | not finalize yet | Yet to finalize
18 | Steps | not finalize yet | Yet to finalize | 3500000 |  |  |  | 3500000
19 | Fountain tile works | not finalize yet | Yet to finalize | 1450000 | 1450000 |  |  | 1450000
| Grand Total |  |  | 122433485 | 113912585 | 61967347 | 45588110 | 15932000

## Court Yard
Court Yard Related
S.No | Area | Plan Start Month/Duration | NADA/SEMs Budget | First Quotation Recived | Awarded Valuue | Actual Spending | Actual Balance Amount | Pending approval | If Contract finalize by 20.06.2025
1 | Sewerage System ( Main holes system) | not finalize yet | Yet to finalize | 18000000 | 18000000 | 15500000 | 2500000
2 | Boundary Wall | not finalize yet | Yet to finalize | 7351485 | 7351485 | 4652300 | 2699185
3 | Boundary Wall Paint | not finalize yet | Yet to finalize | 1782000 |  |  |  | 1782000
4 | Boundary Wall Louvers | not finalize yet | Yet to finalize | 15925000 | 13386100 | 5354440 | 10570560
5 | Electrical Works ( Main hole System) | not finalize yet | Yet to finalize | 1300000 | 1300000 |  | 1300000
6 | Road Base Structure | not finalize yet | Yet to finalize | 5000000 | 5000000 | 5000000 | 0
7 | Fire Fighting System (Base Network) | not finalize yet | Yet to finalize | 8000000 | 8000000 | 5523642 | 2476358
8 | External Drain channel | not finalize yet | Yet to finalize | 3200000 |  |  |  | 3200000
10 | Re-charge pit | not finalize yet | Yet to finalize | 3500000 |  |  |  | 3500000
11 | PCC.+Drain | not finalize yet | Yet to finalize | 19925000 | 20729607 | 11200000 | 8725000 |  | 38000 Sft.Wtaer proofing+Filling
12 | Street Poles Lamp foundation | not finalize yet | Yet to finalize |  |  |  | 0 |  | Removed
13 | Internal Drain Channels | not finalize yet | Yet to finalize | 2500000 | 2500000 |  |  | 2500000
15 | Paver system | not finalize yet | Yet to finalize | 31000000 | 37000000 | 13682993 | 17317007 |  | 108000 Sft Pavers
16 | Plantations+Benches+Marble | not finalize yet | Yet to finalize
18 | Steps | not finalize yet | Yet to finalize | 3500000 |  |  |  | 3500000
19 | Fountain tile works | not finalize yet | Yet to finalize | 1450000 | 1450000 |  |  | 1450000
| Grand Total |  |  | 122433485 | 114717192 | 60913375 | 45588110 | 15932000

## Approved Item-Actual
Lakecity Roof Gardens - Projected Cash Flow |  | Approved Item Only | [10 empty] | 2026-01-04 | 2026-01-04 | 2026-01-04
(Structural & Finishes Works Jun 2024 to Jan 2026)
S.No. | Cash Flow | Awarded Value | Actual Spending | Balance Amount | Jun-25 | Nov-25 | 2025-12-25 | 2026-01-25 | 2026-02-25 | 2026-03-25 | 2026-04-25 | 2026-05-25 | December
A1 | Structure for I Tower |  |  |  | 0 | 10000000
A2 | Structure for L1 Tower |  |  |  | #REF!
A3 | Structure Works for L2
A4 | Façade Works ( I tower) |  |  |  |  | 5350498
A5 | Façade Works ( L 1 tower) |  |  |  | 0 | 4841552 | 0 | 0
A6 | Façade Works ( L 2 tower) |  |  |  | 0 | 0 | 0 | 0
| Total |  |  |  | #REF! | 20192050 | 0 | 0
Finishes For Tower 1
1 | External Brick Works (M+L) | 14500000 | 14500000 | 0 |  | 0 | [5 empty] | 0
2 | Internal Brick Works (M+L) | 92385014 | 93066444 | 0 |  | 0 | [5 empty] | -681430
3 | Electrical Conduiting (M+L) | 29485630 | 28688634.4 | 796995.6 |  | 796995.6 | 0 | 0 | 0 |  |  | 0 | 0
4 | Plumbing Conduiting (M+L) | 23645601 | 21009948 | 2635653 |  | 2635653 | 0 | 0 | 0 |  |  | 0 | 0
5 | SOIL, WASTE VENT AND RAIN WATER DRAINAGE SYSTEM (M) | 19367707 | 19362936 | 4771 |  | 4771 | 0 | 0 | 0 |  |  | 0 | 0
6 | PCC (M+L) | 27569921 | 26661230 | 908691 |  | 908691 | 0 | 0 | 0 |  |  | 0 | 0
7 | External Plaster (M+L) | 6841856 | 3712137 | 3129719 |  | 3129719 | 0 | 0 | 0 |  |  | 0 | 0
8 | Internal Plaster (M+L) | 57158144 | 44216742 | 12941402 |  | 6470701 | 6470701 | 0 | 0 |  |  | 0
9 | Boundary Wall (M+L) | 26604211 | 23545140 | 3059071 |  | 2000000 | 0 | 0 | 0 |  |  | 0
10 | Subcontract Electrical (L) | 21095340 | 8037026 | 13058314 |  | 3475516.1818 | 4475516.1818 | 5258330.1818 | 1985361.9545 |  |  | 0
11 | Subcontract Plumbing (L) | 25674500 | 12408721 | 13265779 |  | 3219511.4545 | 5219511.4545 | 5219511.4545 | 1155591.1364 |  |  | 0
12 | CABLE CONTAINMENT (M) | 19470000 | 16502692 | 2967308 |  | 0 | 0 | 0 | 0 |  |  | 0
13 | Subcontract Firefighting (L) | 5000000 | 4315435 | 684565 |  | 0 | 1101432 | 0 | 0 |  |  | 0
14 | FSS Works (Piping) (M) | 18686350 | 15616841 | 3069509 |  | 3451813 | 0 | 0 | 0 |  |  | 0
15 | Subcontract HVAC (M+L) | 11000000 | 7206637 | 3793363 |  | 1921400 | 1871963 | 0 | 0 |  |  | 0
16 | Copper Pipe + Accessories (M+L) | 20000000 | 17529297 | 2470703 |  | 2900000 | 1418948 | 0 | 0 |  |  | 0
17 | LPG Works (M) | 6500000 | 4047317 | 2452683 |  |  | 2452683 | 0 | 0 |  |  | 0
18 | WIRING / WIRING ACCESSORIES (M) | 45147657 | 44465806.8 | 681850.2 |  | 681850.2 | 0 | 0 | 0 |  |  | 0
19 | MAIN / SUB-MAIN CABLES (M) | 17180375 | 16973827.2 | 206547.8 |  | 206547.8 | 0 | 0 | 0 |  |  | 0
20 | VOICE & DATA COMMUNICATION (M+L) | 5537660 | 4688280 | 849380 |  |  | 849380 | 0 | 0 |  |  | 0
21 | Pipes for Water Supply and fitting (M) | 13000000 | 12212832.6 | 787167.4 |  | 0 | 787167.4 | 0 | 0 |  |  | 0
22 | Elevator (M+L) | 49036000 | 17800000 | 31236000 |  | 26004500 | 5231500 | 0 | 0 |  |  | 0
23 | BORE WELL WATER SUPPLY SYSTEM (M+L) | 0 | 0 | 0 |  | 6174790 | 6174790 | 0 | 0 |  |  | 0
24 | Aluminum Work (M+L) | 68331343 | 31452514 | 36878829 |  |  | 17000000 | 12000000 | 8248507 |  |  | 0
24 a | Glass Work (M+L) | 31460182 | 7865045.5 | 23595136.5 |  | 8609053.902 | 8609053.902 | 8609053.902 | 5633019.902 |  |  | 0
24 b | Baclony Glass Railing (M+L) | 5269856 | 1317464 | 3952392 |  |  | 5269856 | 0 | 0 |  |  | 0
25 | Ceiling Work (M+L) | 38171630 | 10462396 | 27709234 |  | 7094326 | 7094326 | 6329532 | 3967126 |  |  | 0
26 | DISTRIBUTION BOARDS (M) | 46267080 | 37421590 | 8845490 |  | 8850000 | 8850000 | 2784682 | 0 |  |  | 0 | -11639192
27 | Paint (M+L) Internal | 47509000 | 8100891 | 39408109 |  | 9850000 | 9850000 | 9850000 | 10197559 |  |  | 0 | -339450
27 a | Paint (M+L) External | 9961998 | 2490500 | 7471498 |  | 2490499.3333 | 4980998.6667 | 0 | 0 |  |  | 0 | 0
28 | Tile ( M+L) | 153071595 | 107326152 | 45745443 |  | 7782539 | 15782539 | 15782539 | 11173895 |  |  | 0
28 a | Marble Work (M+L) | 28315671 | 15413467 | 12902204 |  | 7000000 | 7000000 | 4249640 | 0 |  |  | 0 | -5347436
29 | BUSWAYS (M) | 46267080 | 9773346 | 36493734 |  | 0 | 16350000 | 20143734 | 0 |  |  | 0 | 0
30 | Wood Works (M+L) | 210151423 | 98249211 | 111902212 |  | 38519653.6 | 38519653.6 | 38519653.6 | 22894550.2 |  |  | 0
30a | Steel Works ( M+L) | 0 | 0 | 0 |  | 8500000 | 7000000 | 3500000 | 1000000 |  |  | 0
31 | MV+LT PANELS (M) | 41052919 | 20615340 | 20437579 |  | 10315340 | 0 | 20117579 | 0 |  |  | 0
32 | DIESEL GENERATOR & ALLIED WORKS (M+L) | 0 | 0 | 0 |  | 15000000 | 0 | 5000000 | 0 |  |  | 0
33 | Chute (M+L) | 0 | 0 | 0 |  | 5600000 | 0 | 2400000 | 0 |  |  | 0
34 | LPG System (M+L) | 0 | 0 | 0 |  | 9219000 | 0 | 9219000 | 0 |  |  | 0
35 | VERTICAL BACKBONE INFRASTRUCTURE (GPON) (M+L) | 0 | 0 | 0 |  | 0 | 9662940 | 4141260 | 0 |  |  | 0
36 | SUPPLY OF PLUMBING FIXTURES (M) | 66000000 | 40000000 | 26000000 |  |  |  | 20000000 | 0 |  |  | 0
36a | Mirror | 0 | 0 | 0 |  | 1800000 | 1800000 | 900000 | 0 |  |  | 0
36b | Shower Cabin | 5846400 | 1461600 | 4384800 |  |  | 5846400 |  | 0 |  |  | 0
37 | MEDIUM VOLTAGE CABLES & TERMINATION KITS (M) | 0 | 0 | 0 |  | 0 | 0 | 2145530 | 0 |  |  | 0
38 | SWITCHES & SOCKETS (M) | 9905063 | 4952531 | 4952532 |  | 0 | 4000000 | 952532 | 0 |  |  | 0
39 | LIGHTING+ FIXTURES (M) | 21052601 | 21052601 | 0 |  | 0 |  |  | 0 |  |  | 0
40 | UPS (UNINTERRUPTIBLE POWER SUPPLY) (M+L) | 0 | 0 | 0 |  | 4302984 | 0 | 0 | 1844136 |  |  | 0
41 | CCTV SYSTEM (IP BASED) (M+L) | 0 | 0 | 0 |  | 4001144 | 0 | 0 | 1714776 |  |  | 0
42 | Ventilation/Exhaust system (M+L) | 7492650 | 6915439 | 577211 |  | 0 | 577211 | 0 | 0 |  |  | 0
43 | FSS Works (FFS equipment) (M) | 37610640 | 17373192 | 20237448 |  | 3022537 | 5313530.9307 | 13901615.1717 | 1022322 |  |  | 0
44 | DRY TYPE TRANSFORMERS (M+L) | 17298800 | 8649400 | 8649400 |  | 0 | 5734912.5 | 2914487.5 | 0 |  |  | 0
45 | FIRE ALARM SYSTEM (M+L) | 0 | 0 | 0 |  | 0 | 2467008.3 | 5756352.7 | 0 |  |  | 0
46 | FACILITY LIGHTNING PROTECTION SYSTEM (OFM) | 0 | 0 | 0 |  | 0 | 1724698 | 739156.5 | 0 |  |  | 0
47 | Water storage heater (M) | 13500990 | 9964000 | 3536990 |  | 0 | 3536990 | 0 | 0 |  |  | 0
48 | PUBLIC ADDRESS SYSTEM (M) | 0 | 0 | 0 |  | 0 | 1457418 | 3400642 | 0 |  |  | 0
49 | ACCESS CONTROL SYSTEM (M) | 0 | 0 | 0 |  | 0 | 3408324.4125 | 1460710.4625 | 0 |  |  | 0
50 | Pump Sets (M) | 0 | 0 | 0 |  | 0 | 0 | 4986000 | 0 |  |  | 0
51 | FSS Works (Fire Pumps) Basement (M+L) | 28751340 | 8625402 | 20125938 |  | 0 | 11320927.508 | 8805010.492 | 0 |  |  | 0
52 | ACMV Works (Ac units) (M+L) | 0 | 0 | 0 |  | 33000000 | 33000000 | 33000000 | 0 |  |  | 0
53 | Water meter (M) | 0 | 0 | 0 |  | 4312000 | 0 | 1848000 | 0 |  |  | 0
54 | Kitchen Hoods (M) | 6160000 | 0 | 6160000 |  | 2933333.3333 | 2933333.3333 | 2933333.3333 | 0 |  |  | 0
55 | Travertiene | 37835258 | 33782363 | 4052895 |  | 0 | 922460 |  | 0 |  |  | 0
56 | VRF In corridor ( M+L) | 50500000 | 36696520 | 13803480 |  | 6125000 | 8282088 | 4325399 |  |  |  | 0
| Kitchen Hob (M) | 8800000 | 0 | [8 empty] | 8800000
58 | External lights | 4894000 | 4894000 |  | 4894000 | [6 empty] | 0
59 | Swimming Pool ( M+L) | 16200000 | 11340000 | 4860000 |  |  | 4860000 |  |  |  |  | 0
60 | Pargola | 8744828 | 3497931.2 | 5246896.8 | 8744828 |  | 3497931.2 |  | 1748965.6 | 0 | 0 | 0
61 | AC louvers. | 0 | 0 | 0 | [7 empty] | 0
62 | Roof Top | 845000 | 422500 | 422500
63 | Additiona wood Work Item. | 0 | 0 | 0 | [7 empty] | 0
64 | Basement Civil Works ( I tower posting ) | 0 | 0 | 0
65 | Basement Civil MEP ( I tower posting ) | 0 | 0 | 0
| Total | 1606348313 | 1016260819.7 | 590768923.3 | 13638828 | 167466618.0717 | 223077680.3438 | 199763299.302 | 68026897.7929 | 0 | 0 | -681430
Finishes For L1
1 | External Brick Works (M+L) | 9235361 | 6311073 | 2924288 |  | 2924288 | 0 | 0 | 0 | 0 | 0 | 0
2 | Internal Brick Works (M+L) | 74421345 | 72814009.5 | 1607335.5 |  | 1607335.5 | 0 | 0 | 0 | 0 | 0 | 0
3 | Electrical Conduiting (M+L) | 13067330 | 4292391.8 | 8774938.2 |  | 4387469.1 | 4387469.1 | 0 | 0 | 0 | 0 | 0
4 | Plumbing Conduiting (M+L) | 12858616 | 8373422.8 | 4485193.2 |  | 2242596.6 | 2242596.6 | 0 | 0 | 0 | 0 | 0
5 | SOIL, WASTE VENT AND RAIN WATER DRAINAGE SYSTEM (M) | 11666143 | 1477354 | 10188789 |  | 3944357.1667 | 3944357.1667 | 2300074.1667 | 0 | 0 | 0 | 0
6 | PCC (M+L) | 21356000 | 14071168 | 7284832 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | External Plaster (M+L) | 5364800 | 1592000 | 3772800 |  | 3772800 | 0 | 0 | 0 | 0 | 0 | 0
8 | Internal Plaster (M+L) | 34785601 | 14331336 | 20454265 |  | 8696400.25 | 8696400.25 | 8696400.25 | 4332396 | 0 | 0 | 0
10 | Subcontract Electrical (L) | 12878310 | 1287831 | 11590479 |  | 2575662 | 2575662 | 3541746.5 | 2897409 | 0 | 0 | 0
11 | Subcontract Plumbing (L) | 16256850 | 1978056 | 14278794 |  | 2379799 | 3379799 | 3379799 | 3379799 | 1759598.3333 | 0 | 0
12 | CABLE CONTAINMENT (M) | 12130712 | 0 | 12130712 |  | 0 | 12130712 | 0 | 0 | 0 | 0 | 0
13 | Subcontract Firefighting (L) | 4293868 | 0 | 4293868 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | FSS Works (Piping) (M) | 14003308 | 3624095 | 10379213 |  | 7000000 | 0 | 7003308 | 0 | 0 | 0 | 0
15 | Subcontract HVAC (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Copper Pipe + Accessories (M+L) | 14000000 | 7495229 | 6504771 |  | 3266666.6667 | 3266666.6667 | 3266666.6667 | 0 | 0 | 0 | 0
17 | LPG Works (M) | 4952283 | 4491802 | 460481 |  |  | 460481 | 0 | 0 | 0 | 0 | 0
18 | WIRING / WIRING ACCESSORIES (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | MAIN / SUB-MAIN CABLES (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | VOICE & DATA COMMUNICATION (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Pipes for Water Supply and fitting (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Elevator (M+L) | 33292000 | 4800000 | 28492000 |  | 0 | 14226615.3846 | 0 | 14265384.3846 | 0 | 0 | 0
24 a | Aluminum Work (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 b | Glass Work (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 b | Baclony Glass (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Ceiling Work (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | DISTRIBUTION BOARDS (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 a | Internal Paint (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 b | External Paint | 8105205 | 2026300 | 6078905 |  | 2026301.6667 | 2026301.6667 | 2026301 | 0 | 0 | 0 | 0
28 | Tile (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 b | Marble Works | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | BUSWAYS (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 a | Wood (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 b | Steel Work (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Dry Type Transformers (M) | 11741000 | 5870500 | 5870500 |  | 0 |  | 5870500 | 0 | 0 | 0 | 0
32 | DIESEL GENERATOR & ALLIED WORKS (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Chute (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | LPG System (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | VERTICAL BACKBONE INFRASTRUCTURE (GPON) (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
36a | SUPPLY OF PLUMBING FIXTURES (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
36b | Mirror | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
36c | Shower Cabin | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | MEDIUM VOLTAGE CABLES & TERMINATION KITS (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | SWITCHES & SOCKETS (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | LIGHTING FIXTURES (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | UPS (UNINTERRUPTIBLE POWER SUPPLY) (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | CCTV SYSTEM (IP BASED) (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | Ventilation/Exhaust system (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | FIRE ALARM SYSTEM (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | FACILITY LIGHTNING PROTECTION SYSTEM (OFM) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Water storage heater (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | PUBLIC ADDRESS SYSTEM (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | ACCESS CONTROL SYSTEM (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | Pump Sets (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | FSS Works (Fire Pumps) Basement (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | ACMV Works (Ac units) (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | Water meter (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Kitchen Hoods (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Travertiene | 21000000 | 4960775 | 16039225 |  | 7123656 | 6791914 | 2123656 | 0 | 0 | 0 | 0
56 | VRF In corridor ( M+L) | 0 | 0 | 0 |  | 46930665.2833 | 1592600 | 0 | 3772800 | 0 |  | 0
57 | Kitchen Hob (M) | 0 | 0 | 0 |  | 0 | 8696400.25 | 8696400.25 | 8696400.25 | 8696400.25 |  | 0
58 | External lights | 3144200 | 3144200 | 0 |  | 0 |  |  | 0
59 | Paddle Tenis Court ( M+L) | 0 | 0 | 0 |  |  | 0 | 2026301.6667 | 2026301.6667
60 | Pargola | 2420155 | 968062 | 1452093
61 | AC louvers. | 0 | 0 | 0
62 | Roof Top | 0 | 0 | 0
63 | Additiona wood Work Item. | 0 | 0 | 0
64 | Basement Civil Works ( L1 tower posting ) | 0 | 0 | 0
65 | Basement Civil MEP (L1 tower posting ) | 0 | 0 | 0
| Total | 340973087 | 163909605.1 | 177063481.9 | 0 | 51947331.95 | 64128974.8346 | 38208451.5833 | 24874988.3846 | 1759598.3333
Finishes For L2
1 | External Brick Works (M+L) | 9308278 | 8200000 | 1108278 |  | 1108278 | 0 | 0 | 0 | 0 | 0 | 0
2 | Internal Brick Works (M+L) | 74421345 | 14869592 | 59551753 |  | 13550108 | 13550108 | 13550108 | 13550108 | 13550108 | 0 | 0
3 | Electrical Conduiting (M+L) | 8241141.15 | 0 | 8241141.15 |  | 3102759.3333 | 3102759.3333 | 2035623.3333 | 0 | 0 | 0 | 0
4 | Plumbing Conduiting (M+L) | 7051077.9 | 0 | 7051077.9 |  | 2350359.3 | 2350359.3 | 2350359.3 | 0 | 0 | 0 | 0
5 | SOIL, WASTE VENT AND RAIN WATER DRAINAGE SYSTEM (M) | 11666143 | 0 | 11666143 |  | 2333229 | 2333229 | 2333229 | 2333229 | 2333229 | 0 | 0
6 | PCC (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | External Plaster (M+L) | 5364800 | 5050714 | 314086 |  | 314086 | 0 | 0 | 0 | 0 | 0 | 0
8 | Internal Plaster (M+L) | 34785601 | 0 | 34785601 |  | 0 | 6957120.2 | 6957120.2 | 6957120.2 | 6957120.2 | 6957120.2 | 0
10 | Subcontract Electrical (L) | 6399674.55 | 0 | 6399674.55 |  | 2607274.8167 | 2607274.8167 | 1185125.8167 |  |  |  | 0
11 | Subcontract Plumbing (L) | 7894247.85 | 0 | 7894247.85 |  | 3216175.05 | 3216175.05 | 1461898.05 |  |  |  | 0
12 | CABLE CONTAINMENT (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Subcontract Firefighting (L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | FSS Works (Piping) (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Subcontract HVAC (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Copper Pipe + Accessories (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | LPG Works (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | WIRING / WIRING ACCESSORIES (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | MAIN / SUB-MAIN CABLES (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | VOICE & DATA COMMUNICATION (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Pipes for Water Supply and fitting (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Elevator (M+L) | 33292000 | 0 | 33292000 |  | 13224000 | 0 | 11934000 | 7934000 | 0 | 0 | 0
24 a | Aluminum Work (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 b | Glass Work (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 b | Baclony Glass (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Ceiling Work (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | DISTRIBUTION BOARDS (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 a | Internal Paint (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 b | External Paint | 8105205 | 2026300 | 6078905 | 0 | 0 | 2026301.6667 | 2026301.6667 | 2026301.6667 | 0 | 0 | 0
28 | Tile (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 b | Marble Works | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | BUSWAYS (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 a | Wood (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 b | Steel Work (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Dry Type Transformers (M) | 11741000 | 5870500 | 5870500 | 0 | 0 | 0 | 0 | 5870500 | 0 | 0 | 0
32 | DIESEL GENERATOR & ALLIED WORKS (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Chute (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | LPG System (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | VERTICAL BACKBONE INFRASTRUCTURE (GPON) (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
36a | SUPPLY OF PLUMBING FIXTURES (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
36b | Mirror | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
36c | Shower Cabin | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | MEDIUM VOLTAGE CABLES & TERMINATION KITS (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | SWITCHES & SOCKETS (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | LIGHTING FIXTURES (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | UPS (UNINTERRUPTIBLE POWER SUPPLY) (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | CCTV SYSTEM (IP BASED) (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | Ventilation/Exhaust system (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | FIRE ALARM SYSTEM (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | FACILITY LIGHTNING PROTECTION SYSTEM (OFM) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Water storage heater (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | PUBLIC ADDRESS SYSTEM (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | ACCESS CONTROL SYSTEM (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | Pump Sets (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | FSS Works (Fire Pumps) Basement (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | ACMV Works (Ac units) (M+L) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | Water meter (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Kitchen Hoods (M) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Travertiene | 21000000 | 4144005 | 16855995 |  | 7000000 | 7000000 | 3000000 | 0 | 0 | 0 | 0
56 | VRF In corridor ( M+L) | 35000000 | 0 | 0 |  |  |  |  | 0 | 0
57 | Kitchen Hob (M) | 6000000 | 0 | 0
58 | External lights | 3731700 | 3731700 | 3144200
59 | Paddle Tenis Court ( M+L) | 0 | 0 | 0
60 | Pargola | 2420155 | 2420155 | 968062
61 | AC louvers. | 10102400 | 0 | 0 | [6 empty] | 11934000
62 | Roof Top | 20820099.3 | 0 | 0 |  |  |  |  | 0 | 2026301.6667
63 | Additiona wood Work Item. | 9428397.3 | 0 | 0
64 | Basement Civil Works (L2 tower posting ) | 26500000 | 0 | 0
65 | Basement Civil MEP (L2 tower posting ) | 12000000 | 0 | 0
| Total | 245422368.45 | 46312966 | 203221664.45 | 0 | 48806269.5 | 43143327.3667 | 46833765.3667 | 38671258.8667 | 22840457.2 | 6957120.2 | 0
Finishes For Ground Floor I tower
1 | Electrical Work | 6220700 | 2762019 | 3458681 | 0 | 3458681 | [5 empty] | 0
2 | Plumbing work | 9428921 | 5928921 | 3500000 |  |  | 3500000 |  |  |  |  | 0
3 | Fire figthing works | 2868500 | 1241083 | 1627417 |  | 1627417 | [5 empty] | 0
4 | Copper piping | 1900000 | 1900000 | 0 |  | 1900000 | [5 empty] | 0
5 | Insulation of pipes | 3141525 | 2054018 | 1087507 |  | 1087507 | [5 empty] | 0
6 | Marble | 12834922 | 9101017 | 3733905 |  | 2566984.4 | 2566984.4 | 2566983.96 |  |  |  | 0
7 | Aluminum Work (M+L) | 15000000 |  |  |  | 5000000 | 5000000 | 5000000 |  |  |  | 15000000
8 | Paint Works | 51394568 | 22987058 | 13407510
9 | Ceiling Work (M+L) | 36000000 | 27000000 | 9000000
10 | AC | 16999424 | 4249856 | 12749568
11 | Final Touch Ups | 5916720 | 1479180 | 4437540
| Total Lobby | 51394568 | 22987058 | 13407510 | 0 | 15640589.4 | 11066984.4 | 7566983.96
1 | Gym Equipment | 36000000 | 27000000 | 9000000 |  |  | 18000000 |  |  |  |  | 0 | 9000000
2 | Gym | 16999424 | 4249856 | 12749568 |  | 4249856 | 6799769.6 | 5949798.4 |  |  |  | 0
3 | Business Center | 5916720 | 1479180 | 4437540 |  | 1479180 | 2366688 | 2070852 |  |  |  | 0
4 | Game Room | 8350094 | 2087523.5 | 6262570.5 |  | 2087523.5 | 3340037.6 | 2922532.9 |  |  |  | 0
5 | MEP Work | 4000000 |  |  |  | 2000000 | 2000000 |  |  |  |  | 4000000
6 | AC | 71266238 | 34816559.5 | 32449678.5 | [7 empty] | 4000000
| Total | 67266238 | 34816559.5 | 32449678.5 | 0 | 7816559.5 | 30506495.2 | 10943183.3 |  |  |  | 0
1 | External Development | 114717192 | 60913375 | 45588110 | [8 empty] | 10500000
2
| Grand Total | 2426121766.45 | 1345200383.3 | 1062499368.15 | 13638828 | 291677368.4217 | 371923462.145 | 303315683.512 | 131573145.0442 | 24600055.5333 | 6957120.2

## Table 1
Lake City Roof Gardens Project Tracking Sheet ( On going ) | [12 empty] | 2026-01-04
Sr. No. | Activity | Resposible Contractor | Approved Budget | Consumed Budget | Consumed Busget % | Duration Months | Planned Start Date | Planned Finish Date | Effective Finish Date | Actual Finish Date | Planned % | Current Status % | Remarks |  | 2026-01-04 | 2026-01-04
Structure Work
2 | Mumty, Generator Pad, Swimming Pool | ICPL/GE |  |  |  |  | 2025-02-15 | 2025-05-15 | 2025-05-15 |  | 100% | 96%
Finishes of I-Tower
0 | External Brick Works (M+L) | GE | 14500000 | 14500000 | 100% | 4 | 2024-01-20 | 2024-04-19 | 2024-07-18 |  | 100% | 100%
0 | Internal Brick Works (M+L) | GE | 92385014 | 93066444 | 100.7% | 8 | 2024-03-20 | 2024-11-17 | 2024-11-17 |  | 100% | 100%
0 | Boundary wall | GE | 26604211 | 23545140 | [6 empty] | 100% | 100%
1 | Electrical Conduiting | Qatalytic Eng. | 29485630 | 28688634.4 | 97.3% | 6 | 2024-04-20 | 2024-10-20 | 2025-09-15 |  | 100% | 100%
2 | Plumbing Conduiting | Qatalytic Eng. | 23645601 | 21009948 | 88.85% | 6 | 2024-04-20 | 2024-10-20 | 2025-09-16 |  | 100% | 100%
3 | P.C.C | GE | 27569921 | 26661230 | 96.7% | 4 | 2024-07-01 | 2024-10-31 | 2025-08-26 |  | 100% | 100%
4 | External Plaster | Ezymix | 6841856 | 3712137 | 54.26% | 8 | 2024-04-20 | 2024-12-15 | 2025-09-16 |  | 100% | 57%
5 | Internal Plaster | Ezymix | 57158144 | 44216742 | 77.36% | 8 | 2024-04-20 | 2024-12-15 | 2025-09-16 |  | 98% | 91%
6 | Electrical work | Qatalytic Eng. | 298237905 | 207057560 | 69.43% | 12 | 2024-07-15 | 2025-07-14 | 2025-09-30 |  | 82% | 70%
7 | Plumbing Work | Qatalytic Eng. | 131534857 | 92361528.6 | 70.22% | 12 | 2024-07-25 | 2025-07-24 | 2025-09-30 |  | 82% | 70%
8 | Fire fighting | Captive Aire | 90048330 | 45930870 | 51.01% | 4 | 2024-08-15 | 2024-12-16 | 2025-09-15 |  | 90% | 95%
9 | HVAC Ductng | Al Ahamd | 11000000 | 7206637 | 65.51% | 4 | 2024-08-19 | 2024-12-19 | 2025-09-15 |  | 100% | 90%
10 | Copper Piping | Al Ahamd | 20000000 | 17529297 | 87.65% | 6 | 2024-08-19 | 2024-12-19 | 2025-09-23 |  | 100% | 100%
11 | Travertine Marble | Rock stone | 37835258 | 33782363 | 89.29% | 4 | 2024-12-01 | 2025-03-31 | 2025-09-24 |  | 95% | 93%
12 | False ceiling | Star/Elegance/BuildKo | 38171630 | 10462396 | 27.41% | 4 | 2024-11-20 | 2025-03-20 | 2025-10-15 |  | 85% | 70%
13 | Paint Work(internal) | Juton | 47509000 | 8100891 | 17.05% | 6 | 2024-12-06 | 2025-05-06 | 2025-10-25 |  | 55% | 36%
14 | Paint Work(External) | Rock shield | 9961998 | 2490500 | 25% | [5 empty] | 20% | 20%
15 | Aluminium Work | Chawala | 68331343 | 31452514 | 46.03% | 5 | 2024-09-07 |  | 2025-09-20 |  | 66% | 60%
16 | Tile Work | Orient/GE/AE | 153071595 | 107326152 | 70.12% | 3 | 2024-09-08 |  | 2025-07-30 |  | 88% | 75%
17 | Glass Works | Ghanii | 48260308 | 12065077 | 25% |  | 2024-09-07 |  |  |  | 50% | 45%
18 | Wood Work | Riz Wood | 210151423 | 98249211 | 46.75% | 6 | 2024-10-09 |  | 2025-09-28 |  | 60% | 48%
19 | LPG | Qatalytic Eng. | 6500000 | 4047317 | 62.27% | 2 | 2024-11-01 |  | 2025-07-25 |  | 80% | 80%
20 | DATA and Voice | EPN | 5537660 | 4688280 | 84.66% | 3 | 2025-01-30 |  | 2025-07-24 |  | 80% | 80%
21 | Tie Cols | GE | 2000000 | 2000000 | 100% | 2 | 2025-04-16 | 2025-06-16 | 2025-07-20 |  | 100% | 100%
22 | Foam Concrete | GE | 1419000 | 1419000 | 100% |  | 2025-04-21 |  | 2025-05-05 |  | 100% | 100%
23 | Elevator | EEE | 49036000 | 17800000 | 36.3% |  |  |  | 2025-09-14 |  | 20% | 15%
24 | Marble Works/Sill | Rock Stone | 28315671 | 15413467 | 54.43% |  |  |  | 2025-09-14 |  | 70% | 65%
25 | VRF In corridor ( M+L) | Meca Tech | 50500000 | 18750000 | 37.13% |  |  |  | 2025-12-15 |  | 60% | 60%
26 | External lights | Cybersol | 4894000 | 4894000 | 100% |  |  |  | 2025-09-14 |  | 100% | 100%
27 | Swimming Pool ( M+L) | Aqua Pool | 16200000 | 11340000 | 70% | [5 empty] | 45% | 45%
|  |  | 1606706355 | 1009767336 | 62.85% | 117 |  |  |  |  | 81% | 76%
Finishes of Ground Floor-Tower
1 | Electrical Work | Qatalytic Eng. | 6220700 | 2762019 | 44.4% |  |  |  | 2025-06-30 |  |  | 85%
2 | Plumbing work | Qatalytic Eng. | 9428921 | 5928921 | 62.88% |  |  |  | 2025-07-01 |  |  | 85%
3 | Fire figthing works | Captive Aire | 2868500 | 1241083 | 43.27% |  |  |  | 2025-07-02 |  |  | 85%
4 | Copper piping | Alhamd | 1900000 | 1900000 | 100% |  |  |  | 2025-07-03 |  |  | 100%
5 | Insulation of pipes | Cybersol | 3141525 | 2054018 | 65.38% |  |  |  | 2025-09-14 |  |  | 75%
6 | Marble | Rock Stone | 12834922 | 9101017 | 70.91% |  |  |  | 2025-09-14 |  |  | 90%
8 | Gym Equipment | SK | 36000000 | 18000000 | 50%
|  |  | 72394568 | 40987058 | 56.62%
L-1 Tower
Façade
3 | Façade Work Front side | GE | 40291143 | 35449591 | 87.98% | 4 | 2024-09-10 | 2025-01-10 | 2025-05-15 |  | 100% | 98%
4 | Façade Work Empty Plot side | GE |  |  |  | 4 | 2025-02-20 | 2025-06-20 | 2025-07-20 |  | 90% | 98%
5 | Façade Work Internal Side | GE |  |  |  | 3 | 2025-02-28 | 2025-06-20 | 2025-07-15 |  | 95% | 98%
Finishes Of L 1
1 | External Brick Work | GE | 0 | 0 | #DIV/0! | 4 | 2024-08-25 | 2024-12-25 | 2025-02-28 |  | 100% | 100%
2 | Internal Brickwork | GE | 0 | 0 | #DIV/0! | 8 | 2024-10-01 | 2025-05-31 | 2025-05-31 |  | 90% | 98%
3 | Electrical Conduiting | Cybersol | 0 | 0 | #DIV/0! | 4 | 2025-04-16 | 2025-09-14 |  |  | 70% | 65% | Material Delievery Issues
4 | Plumbing Conduiting | Cybersol | 0 | 0 | #DIV/0! | 4 | 2025-04-16 | 2025-09-14 |  |  | 70% | 45% | Material Delievery Issues
5 | Kitchen Hoods (M) | Cybersol | 0 | 0 | #DIV/0! |  | 2025-04-16 | 2025-12-15 |  |  | 5% | 5%
6 | Travertiene | Cybersol | #REF! | #REF! | #REF! |  | 2025-04-16 | 2025-12-15 |  |  | 10% | 30%
7 | #REF! | Cybersol | #REF! | #REF! | #REF! |  | 2025-04-16 | 2025-12-15 |  |  | 35% | 45%
8 | VRF In corridor ( M+L) | GE | 0 | 0 | #DIV/0! |  |  | 2025-08-31 |  |  | 80% | 90% | Cement Cost to be added
9 | Kitchen Hob (M) | GE | 0 | 0 | #DIV/0! |  |  | 2025-12-15 |  |  | 30% | 33% | Cement Cost to be added
10 | External lights | EEE | 3144200 | 3144200 | 100% |  |  | 2025-12-16
11 | Paddle Tenis Court ( M+L) | Rock shield | 0 | 0 | #DIV/0! | [6 empty] | 10%
26 | External lights |  |  | 2731700 |  |  |  | 2025-09-14
| Total |  | #REF! | #REF! | #REF! | [6 empty] | 58%
Finishes of L-2Tower
Façade | [13 empty] | 0
1 | Façade Work Internal Side | GE | 48334459 | 44160604 | 91.36% | 2 | 2025-04-16 | 2025-05-25 | 2025-07-29 |  |  | 100%
2 | Façade Work Front side | GE |  |  |  | 3 | 2025-04-16 | 2025-07-20 | 2025-07-30 |  |  | 100%
3 | Façade Work UMT side | GE |  |  |  | 3 | 2025-04-16 | 2025-07-20 | 2025-07-30 |  |  | 85%
Finishes Of L 2
1 | External Brick Works | GE | 0 | 0 | #DIV/0! | 2 | 2025-04-16 | 2025-06-15 |  |  | 99% | 98%
2 | Subcontract Plumbing (L) | CyberSol/TBA | 2420155 | 2420155 | 100% | [5 empty] | 0% | 0%
3 | AC louvers. | EEE | 10102400 | 0 | 0% |  |  | 2025-12-16 |  |  | 0% | 0%
4 | Roof Top | Rock Sheild | 20820099.3 | 0 | 0% |  |  | 2025-12-16 |  |  | 0% | 0%
26 | External lights |  |  | 2731700 |  |  |  | 2025-09-14
|  |  | 33342654.3 | 5151855 | 15.45% | [5 empty] | 10% | 15%
| Grand Total |  | #REF! | #REF! | #REF! | [6 empty] | 43%