## Overall IR Status
Overall IR Status
Sr. No | Contractor Name | IR Status | I Tower | L1 Tower | L2 Tower | External Development
1 | ICPL | 1. Fully Approved | 956 | 689 | 799
|  | 2. Approved with comments (B) | 2 | 3 | 5
|  | 3. Rejected (R) | 2 | 1 | 0
|  | 4. Open/Pending (OP) | 0 | 0 | 3
|  | 5. Total | 960 | 693 | 807
2 | IIL | 1. Fully Approved | 689 | 119
|  | 2. Approved with comments (B) | 3 | 54
|  | 3. Rejected (R) | 1 | 1
|  | 4. Open/Pending (OP) | 0 | 2
|  | 5. Total | 693 | 176
3 | GE | 1. Fully Approved | 0 | 636 | 663 | 13
|  | 2. Approved with comments (B) | 333 | 43 | 73 | 0
|  | 3. Rejected (R) | 82 | 55 | 19 | 0
|  | 4. Open/Pending (OP) | 32 | 32 | 19 | 0
|  | 5. Total | 1401 | 766 | 774 | 13
4 | Ezy Mix | 1. Fully Approved | 163 |  |  | 163
|  | 2. Approved with comments (B) | 37 |  |  | 37
|  | 3. Rejected (R) | 20 |  |  | 20
|  | 4. Open/Pending (OP) | 16 |  |  | 16
|  | 5. Total | 236 |  |  | 236
5 | QE | 1. Fully Approved | 222 |  |  | 222
|  | 2. Approved with comments (B) | 164 |  |  | 164
|  | 3. Rejected (R) | 4 |  |  | 4
|  | 4. Open/Pending (OP) | 14 |  |  | 14
|  | 5. Total | 404 |  |  | 404
6 | Captive Aire | 1. Fully Approved | 25
|  | 2. Approved with comments (B) | 7
|  | 3. Rejected (R) | 3
|  | 4. Open/Pending (OP) | 0
|  | 5. Total | 35
7 | Al Hamd | 1. Fully Approved | 48
|  | 2. Approved with comments (B) | 0
|  | 3. Rejected (R) | 2
|  | 4. Open/Pending (OP) | 1
|  | 5. Total | 51
8 | Rayyan Associates | 1. Fully Approved | 121
|  | 2. Approved with comments (B) | 1
|  | 3. Rejected (R) | 1
|  | 4. Open/Pending (OP) | 9
|  | 5. Total | 132
9 | EPN | 1. Fully Approved | 0
|  | 2. Approved with comments (B) | 1
|  | 3. Rejected (R) | 0
|  | 4. Open/Pending (OP) | 1
|  | 5. Total | 2
10 | Group star | 1. Fully Approved | 28
|  | 2. Approved with comments (B) | 7
|  | 3. Rejected (R) | 4
|  | 4. Open/Pending (OP) | 1
|  | 5. Total | 40
11 | Buildko | 1. Fully Approved | 8
|  | 2. Approved with comments (B) | 0
|  | 3. Rejected (R) | 0
|  | 4. Open/Pending (OP) | 0
|  | 5. Total | 8
12 | Rock Stone | 1. Fully Approved | 214
|  | 2. Approved with comments (B) | 155
|  | 3. Rejected (R) | 96
|  | 4. Open/Pending (OP) | 19
|  | 5. Total | 484
13 | Elegant Engineering | 1. Fully Approved | 17
|  | 2. Approved with comments (B) | 0
|  | 3. Rejected (R) | 9
|  | 4. Open/Pending (OP) | 6
|  | 5. Total | 32
14 | Aizdi | 1. Fully Approved | 1
|  | 2. Approved with comments (B) | 0
|  | 3. Rejected (R) | 0
|  | 4. Open/Pending (OP) | 0
|  | 5. Total | 1
15 | Archtive | 1. Fully Approved | 57
|  | 2. Approved with comments (B) | 41
|  | 3. Rejected (R) | 4
|  | 4. Open/Pending (OP) | 4
|  | 5. Total | 106
16 | Cybersol | 1. Fully Approved |  | 26
|  | 2. Approved with comments (B) |  | 1
|  | 3. Rejected (R) |  | 10
|  | 4. Open/Pending (OP) |  | 33
|  | 5. Total |  | 70
17 | Rex Engineering | 1. Fully Approved | 4
|  | 2. Approved with comments (B) | 0
|  | 3. Rejected (R) | 2
|  | 4. Open/Pending (OP) | 0
|  | 5. Total | 6

## GE L1 Tower
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (L1 Tower) | [5 empty] | Fully Approved (A) |  | 636
[9 empty] | Approved with comments (B) |  | 43
[9 empty] | Rejected ( R) |  | 55
[9 empty] | Open/Pending (OP) |  | 32
[9 empty] | Total |  | 766
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | basement | LT-1-001 | 2024-07-13 | 2024-07-13 | formwork | Check internal walls formwork of rain water tank Zone 4 | (-11.75) | Grid L-S/26-26 | B | 2024-07-18
2 | Sub Structure | basement | LT-1-002 | 2024-07-20 | 2024-07-20 | formwork | Check internal walls of septic tank formwork Zone 3 & 4 | (-11.75) | Grid F-L/26-26 | B | 2024-07-23
3 | Sub Structure | basement | LT-1-003 | 2024-07-22 | 2024-07-22 | formwork | Check internal walls of rain water harvesting tank formwork Zone 4 | (-11.75) | Grid A-T/26-26 | B | 2024-07-23
4 | Sub Structure | Basement | LT-1-004 | 2024-08-05 | 2024-08-05 | formwork | Check SOG & slab formwork of rain water harvesting tank Zone 4 | (+0.0) | Grid L-T/26-26 | B | 2024-08-07
5 | Sub Structure | Basement | LT-1-005 | 2024-08-19 | 2024-08-19 | formwork | Check formwork for SOG & slab of septic tank Zone 4 | (+0.0) | Grid G-L/26-26 | A | 2024-08-21
6 | Sub Structure | 1st floor | LT-1-006 | 2024-08-22 | 2024-08-22 | layout | Check layout & allow to start brick work on external sides Zone 5 | (+19.0) | Grid N-U/14-20 | A | 2024-08-24
7 | Sub Structure | 1st floor | LT-1-007 | 2024-08-24 | 2024-08-24 | layout | Check layout & allow to start brick work on external sides of building Zone 4 | (+19.0) | Grid G-U/20-26 | OP
8 | Sub Structure | 2nd floor | LT-1-008 | 2024-09-03 | 2024-09-03 | layout | Check layout & allow to start brick work on external sides Zone 4 & 5 | (+30.0) | Grid N-U/14-26 | A | 2024-09-09
9 | Sub Structure | 2nd floor | LT-1-009 | 2024-09-04 | 2024-09-04 | layout | Check layout & allow to start brick work on external sides Zone 4 & 5 | (+30.0) | Grid G-U/20-26 | A | 2024-09-09
10 | Sub Structure | 3rd floor | LT-1-010 | 2024-09-08 | 2024-09-08 | layout | Check layout and allow to start brick work Zone 5 | (+41.0) | Grid N-U/14-20 | B | 2024-09-10
11 | Sub Structure | 3rd floor | LT-1-011 | 2024-09-11 | 2024-09-12 | layout | Check layout & allow to start brick work | (+41.0) | Grid G-U/20-26 | A | 2024-09-16
12 | Sub Structure | 4th floor | LT-1-012 | 2024-09-11 | 2024-09-12 | layout | Check layout and allow to start brick work Zone 4 & 5 | (+52.0) | Grid G-U/14-26 | A | 2024-09-16
13 | Sub Structure | 1st floor | LT-1-013 | 2024-09-12 | 2024-09-12 | brick work | Check brick work on external sides of building in Zone 4 & 5 | (+19.0) | Grid G-U/14-26 | B | 2024-09-24
14 | Sub Structure | 3rd Floor | LT-1-014 | 2024-09-14 | 2024-09-14 | formwork | Check formwork for slab & beam of balcony zone 5 | (+18.75) | Grid U/16-17, U/18-19 | A | 2024-09-18
15 | Sub Structure | 1st floor | LT-1-015 | 2024-09-14 | 2024-09-14 | reinforcement | Check slab & beam reinforcement & allow to start concrete | (+18.75) | Grid U/16-17, U/18-19 | A | 2024-09-18
16 | Sub Structure | 5th floor | LT-1-016 | 2024-09-16 | 2024-09-16 | layout | Check layout & allow to start brick work on external sides of building Zone 5 | (+63.0) | Grid N-U/14-20 | A | 2024-09-20
17 | Sub Structure | 5th floor | LT-1-017 | 2024-09-16 | 2024-09-16 | layout | Check layout & allow to start brick work zone 4 | (+63.0) | Grid G-U/20-26 | A | 2024-09-24
18 | Sub Structure | 7th floor | LT-1-018 | 2024-09-23 | 2024-09-23 | layout | Check layout and allow to start brick work zone 4 & 5 | (+85.0) | Grid G-U/15-26 | A | 2024-09-26
19 | Sub Structure | 8th floor | LT-1-019 | 2024-09-23 | 2024-09-23 | layout | Check layout & allow to start brick work zone 5 | (+96.0) | Grid M-U/15-19 | A | 2024-09-26
20 | Sub Structure | 8th floor | LT-1-020 | 2024-09-23 | 2024-09-24 | layout | Check layout & allow to start brick work on external sides of building zone 4 | (+96.0) | Grid G-U/19-26 | A | 2024-09-30
21 | Sub Structure | 6th floor | LT-1-021 | 2024-09-24 | 2024-09-24 | layout | Check layout & allow to start brick work zone 4 & 5 | (+74.75) | Grid G-U/15-26 | A | 2024-09-30
22 | Sub Structure | 1st floor | LT-1-022 | 2024-09-24 | 2024-09-24 | reinforcement | Check vertical band reinforcement & allow to start formwork | (+18.75) | Grid U/16-17, U/18-19 | A | 2024-10-04
23 | Sub Structure | 2nd floor | LT-1-023 | 2024-09-25 | 2024-09-25 | brick work | Check brick work on external sides of building zone 4 & 5 | (+30.0) | Grid G-U/14-26 | B | 2024-09-30
24 | Sub Structure | 3rd floor | LT-1-024 | 2024-09-25 | 2024-09-25 | brick work | Check brick work on external sides of building zone 4 & 5 | (+41.0) | Grid G-U/14-26 | B | 2024-09-30
25 | Sub Structure | 4th floor | LT-1-025 | 2024-09-25 | 2024-09-25 | brick work | Check brick work on external sides of building zone 4 & 5 | (+52.0) | Grid G-U/14-26 | B | 2024-09-30
26 | Sub Structure | 1st floor | LT-1-026 | 2024-09-25 | 2024-09-25 | formwork | Check vertical band formwork and allow to start concrete work | (+18.75 to +29.75) | Grid U/18-19 | A | 2024-10-02
27 | Sub Structure | 9th floor | LT-1-027 | 2024-09-26 | 2024-09-26 | layout | Check layout & allow to start brick work zone 4 & 5 | (+107.00'') | Grid G-U/14-26 | A | 2024-09-30
28 | Sub Structure | 5th floor | LT-1-028 | 2024-09-26 | 2024-09-26 | brick work | Check brick work on external sides of building zone 4 & 5 | (+63.0) | Grid G-U/14-26 | B | 2024-09-30
29 | Sub Structure | 1st floor | LT-1-029 | 2024-09-27 | 2024-09-27 | formwork | check vertical band formwork and allow to start cncrete work | (+18.75 to +29.75) | Grid U/16-17 | A | 2024-10-02
30 | Sub Structure | 2nd floor | LT-1-030 | 2024-09-27 | 2024-09-27 | formwork | Check slab/beam formwork and allow to start concrete work | (+29.75) | Grid U/18-19 | A | 2024-10-02
31 | Sub Structure | 2nd floor | LT-1-031 | 2024-09-30 | 2024-09-30 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+29.75) | Grid U/18-19 | A | 2024-10-04
32 | Sub Structure | 2nd floor | LT-1-032 | 2024-10-01 | 2024-10-01 | formwork | Check slab/beam formwork & allow to start concrete work zone 5 | (+29.75) | Grid U/16-17 | A | 2024-10-09
33 | Sub Structure | 2nd floor | LT-1-033 | 2024-10-02 | 2024-10-02 | formwork | Check vertical band formwork and allow to start concrete work | (+29.75 to +40.75) | Grid U/18-19 | A | 2024-10-09
34 | Sub Structure | 2nd floor | LT-1-034 | 2024-10-04 | 2024-10-04 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+29.75) | Grid U/16-17 | A | 2024-10-09
35 | Sub Structure | 10th floor | LT-1-035 | 2024-10-05 | 2024-10-05 | layout | Check layout & allow to start brick work on external sides zone 4 & 5 | (+118.0) | Grid G-U/14-26 | A | 2024-10-09
36 | Sub Structure | 6th floor | LT-1-036 | 2024-10-05 | 2024-10-05 | brick work | Check brick work on external sides of building zone 4 & 5 | (+74.0) | Grid G-U/14-26 | B | 2024-10-11
37 | Sub Structure | 8th floor | LT-1-037 | 2024-10-05 | 2024-10-05 | brick work | Check brick work on external sides of building zone 4 & 5 | (+96.0) | Grid G-U/14-26 | B | 2024-10-11
38 | Sub Structure | 2nd floor | LT-1-038 | 2024-10-09 | 2024-10-09 | formwork | Check vertical band formwork and allow to start concrete work | (+29.75 to +40.75) | Grid U/16-17 | A | 2024-10-11
39 | Sub Structure | 7th floor | LT-1-039 | 2024-10-15 | 2024-10-15 | brick work | Check brick work on external sides of building zone 4 & 5 | (+85.0) | Grid G-U/14-26 | B | 2024-10-28
40 | Sub Structure | 9th floor | LT-1-040 | 2024-10-15 | 2024-10-15 | brick work | Check brick work on external sides of building in Zone 4 & 5 | (+107.00) | Grid G-U/14-26 | B | 2024-10-28
41 | Sub Structure | 1st floor | LT-1-041 | 2024-10-15 | 2024-10-15 | layout | check layout & allow to start brick work on external sides of building zone 5 | (+19.0) | Grid M-U/14-20 | A | 2024-10-24
42 | Sub Structure | 2nd floor | LT-1-042 | 2024-10-19 | 2024-10-19 | layout | Check layout & allow to start brick work on internal sides zone 4 & 5 | (+30.0) | Grid N-U/14-26, G-L/20-26 | A | 2024-10-24
43 | Sub Structure | 10th floor | LT-1-043 | 2024-10-16 | 2024-10-17 | brick work | Check brick work on external sides of building zone 4 & 5 | (+118.0) | Grid G-U/14-26 | A | 2024-10-28
44 | Sub Structure | 2nd floor | LT-1-044 | 2024-10-19 | 2024-10-19 | brick work | Check layout & allow to start brick work of building zone 4 | (+30.0) | Grid K-R/20-26 | A | 2024-10-24
| Sub Structure | 2nd floor | LT-1-044 A | 2024-10-22 | 2024-10-22 | layout | Check layout and allow to start brick work Zone 4 | (+30.0) | Grid R-U/14-20, G-R/23-26 | A | 2024-10-24
45 | Sub Structure | 1st floor | LT-1-045 | 2024-10-21 | 2024-10-21 | formwork | Check slab/beam formwork in balcony zone 4 | (+18.75) | Grid U/21-23 | A | 2024-10-31
46 | Sub Structure | 1st floor | LT-1-046 | 2024-10-21 | 2024-10-21 | reinforcement | Check slab/beam reinforcement of balcony & allow to start concrete work zone 4 | (+18.75) | Grid U/21-23 | A | 2024-10-31
47 | Sub Structure | 1st floor | LT-1-047 | 22-Oct*-24 | 22-Oct*-24 | reinforcement | Check slab & beam reinforcement and allow to start concrete work | (+18.75) | Grid U/24-26 | A | 2024-10-24
48 | Sub Structure | 1st floor | LT-1-048 | 22-Oct*-24 | 22-Oct*-24 | formwork | Check slab & beam formwork zone 4 | (+18.75) | Grid U/24-26 | A | 2024-10-24
49 | Sub Structure | 3rd floor | LT-1-049 | 2024-10-23 | 2024-10-24 | formwork | Check leftover formwork of balcony zone 5 | (+40.75) | Grid U/18-19, U/16-17 | A | 2024-10-31
50 | Sub Structure | 3rd floor | LT-1-050 | 2024-10-23 | 2024-10-24 | reinforcement | Check slab and beam reinforcement and allow to start concrete zone 5 | (+40.75) | Grid U/18-19, U/16-17 | A | 2024-10-31
51 | Sub Structure | 2nd floor | LT-1-051 | 2024-10-23 | 2024-10-23 | reinforcement | Check RCC Lintel reinforcement and allow to start concrete work | (+30.0) |  | A | 2024-10-24
52 | Sub Structure | GF | LT-1-052 | 2024-10-24 | 2024-10-24 | layout | Check layout and allow to start brick work zone 5 | (+2.0) | Grid N-S/15-20 | A | 2024-10-31
53 | Sub Structure | 1st floor | LT-1-053 | 2024-10-25 | 2024-10-25 | reinforcement | Check vertical band reinforcement & allow to start formwork | (+18.75) | Grid U/21-23, U/24-26 | A | 2024-10-28
54 | Sub Structure | 1st floor | LT-1-054 | 2024-10-26 | 2024-10-26 | formwork | Check vertical band formwork & allow to start concrete work | (+18.75 to +29.75) | Grid U/21-23 | A | 2024-11-06
55 | Sub Structure | 1st floor | LT-1-055 | 2024-10-28 | 2024-10-28 | formwork | Check vertical band formwork and allow to start concrete work | (+18.75 to +29.75) | Grid U/24-26 | A | 2024-11-06
56 | Sub Structure | 2nd floor | LT-1-056 | 2024-10-28 | 2024-10-28 | formwork | Check leftover slab/beam formwork and allow to start concrete work zone 4 | (+29.75) | Grid U/21-23 | A | 2024-10-31
57 | Sub Structure | 2nd floor | LT-1-057 | 2024-10-29 | 2024-10-29 | formwork | Check vertical band formwork and allow to start concrete work | (+29.75 to +40.75) | Grid U/21-23, | A | 2024-11-06
58 | Sub Structure | 2nd floor | LT-1-058 | 2024-10-29 | 2024-10-29 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+29.75) | Grid U/21-23 | A | 2024-10-31
59 | Sub Structure | 2nd floor | LT-1-059 | 2024-10-31 | 2024-10-31 | formwork | Check leftover slab/beam formwork and allow to start concrete zone 4 | (+29.75) | Grid U/24-26 | A | 2024-11-06
60 | Sub Structure | 3rd Floor | LT-1-060 | 2024-11-01 | 2024-11-01 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+40.75) | Grid U/18-19 | A | 2024-11-06
61 | Sub Structure | 3rd floor | LT-1-061 | 2024-11-01 | 2024-11-01 | formwork | Check vertical band formwork and allow to start concrete work | (+40.75 to +51.75) | Grid U/18-19 | A | 2024-11-06
62 | Sub Structure | 3rd floor | LT-1-062 | 2024-11-02 | 2024-11-02 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+40.75) | Grid U/16-17 | A | 2024-11-06
63 | Sub Structure | 2nd floor | LT-1-063 | 2024-11-02 | 2024-11-02 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+29.75) | Grid U/24-26 | A | 2024-11-06
64 | Sub Structure | 3rd Floor | LT-1-064 | 2024-11-02 | 2024-11-02 | reinforcement | Check rienforcement and formwork for leftover slab/beam zone 4 | (+40.75) | Grid U/21-23 | A | 2024-11-06
65 | Sub Structure | 1st floor | LT-1-065 | 2024-11-02 | 2024-11-02 | reinforcement | Check reinforcement and formwork for leftover slab/beam of balcony zone 5 | (+18.75) | Grid U/14-16 | A | 2024-11-06
66 | Sub Structure | 5th Floor | LT-1-066
67 | Sub Structure | 3rd floor | LT-1-067 | 2024-11-04 | 2024-11-04 | formwork | Check vertical band formwork an and allow to start concrete work | (+40.75 to +51.75) | Grid U/16-17 | A | 2024-11-06
68 | Sub Structure | 3rd floor | LT-1-068 | 2024-11-06 | 2024-11-06 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+40.75) | Grid U/21-23 | A | 2024-11-14
69 | Sub Structure | 3rd floor | LT-1-069 | 2024-11-06 | 2024-11-06 | formwork | Check vertical band formwork and allow to start concrete work | (+40.75 to +51.75) | Grid U/21-23 | A | 2024-11-14
70 | Sub Structure | 4th floor | LT-1-070 | 2024-11-06 | 2024-11-06 | reinforcement | Check reinforcement and formwork for leftover slab/beam of balcony an | (+51.75) | Grid U/18-19 | A | 2024-11-14
71 | Sub Structure | 3rd floor | LT-1-071 | 2024-11-11 | 2024-11-11 | reinforcement | Check reinforcement & formwork for leftover and allow to start concrete work | (+40.75) | Grid u/24-26 | A | 2024-11-13
72 | Sub Structure | 1st floor | LT-1-072 | 2024-11-08 | 2024-11-09 | layout | Check layout & allow to start brick work zone 4 & 5 | (+19.0) | Grid R-U/17-24 | A | 2024-11-11
73 | Sub Structure | 4th floor | LT-1-073 | 2024-11-11 | 2024-11-11 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+51.75) | Grid U/16-17, U/18-19, U/21-23 | A | 2024-11-13
74 | Sub Structure | 1st floor | LT-1-074 | 2024-11-11 | 2024-11-11 | layout | Check layout and allow to start brick work on internal sides zone 4 | (+19.0) | Grid G-N/19-23 | A | 2024-11-18
75 | Sub Structure | 3rd floor | LT-1-075 | 2024-11-13 | 2024-11-13 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+40.75) | Grid U/24-26 | A | 2024-11-18
76 | Sub Structure | 3rd floor | LT-1-076 | 2024-11-13 | 2024-11-14 | formwork | Check vertical band formwork and allow to start concrete work | (+40.75 to +51.75) | Grid U/24-26 | A | 2024-12-02
77 | Sub Structure | 4th floor | LT-1-077 | 2024-11-16 | 2024-11-16 | formwork | Check vertical band formwork and allow to start concrete work | (+51.75 to +62.75) | Grid U/18-19 | A | 2024-11-22
78 | Sub Structure | 1st floor | LT-1-078 | 2024-11-30 | 2024-11-30 | layout | Check layout & allow to start brick masonry on internal sides zone 4 | (+19.0) | Grid Q-J/23-26 | A | 2024-12-02
79 | Sub Structure | 4th floor | LT-1-079 | 2024-11-30 | 2024-11-30 | formwork | Check vertical band formwork and allow to start concrete work | (+51.75 to +62.75) | Grid U/21-230 | A | 2024-12-10
80 | Sub Structure | 4th floor | LT-1-080 | 2024-11-30 | 2024-11-30 | reinforcement | Check rienforcement and formwork for leftover and allow to start concrete work | (+51.75) | Grid U/24-26 | A | 2024-12-10
81 | Sub Structure | 4th floor | LT-1-081 | 2024-11-30 | 2024-12-02 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+51.75) | Grid U/24-26 | A | 2024-12-02
82 | Sub Structure | 4th floor | LT-1-082 | 2024-12-02 | 2024-11-30 | formwork | Check vertical band formwork and allow to start concrete work zone 4 | (+51.75) | Grid U/24-26 | A | 2024-12-10
83 | Sub Structure | 4th floor | LT-1-083 | 2024-12-02 | 2024-12-03 | reinforcement | Check vertical band reinforcement and allow to start formwork zone 5 | (+51.75) | Grid U/16-17 | OP
84 | Sub Structure | 5th Floor | LT-1-084 | 2024-12-04 | 2024-12-04 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete z-5 | (+63.75) | Grid U/18-19 | A | 2024-12-10
85 | Sub Structure | 4th floor | LT-1-085 | 2024-12-04 | 2024-12-05 | formwork | Check vertical band formwork and allow to start concrete zone 5 | (+51.75) | Grid U/16-17 | A | 2024-12-10
86 | Sub Structure | 5th floor | LT-1-086 | 2024-12-06 | 2024-12-07 | reinforcement | Check formwork and reinforcement slab/beam and allow to start concrete work z-5 | (+63.75) | Grid U/21-23 | A | 2024-12-10
87 | Sub Structure | 5th floor | LT-1-087 | 2024-12-09 | 2024-12-09 | reinforcement | Check reinforcement and formwrok of slab and allow to start concrete work | (+63.75) | Grid U/24-26 | A | 2024-12-16
88 | Sub Structure | 5th floor | LT-1-088 | 2024-12-09 | 2024-12-09 | formwork | Check vertical band formwork and allow to start concrete work | (+52.75) | Grid U/18-19 | A | 2024-12-16
89 | Sub Structure | 5th floor | LT-1-089 | 2024-12-10 | 2024-12-10 | reinforcement | check vertical bend reinforcement and allow to start formwork | (+62.75) | Grid U/21-23 | A | 2024-12-10
90 | Sub Structure | 5th floor | LT-1-090 | 2024-12-11 | 2024-12-11 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete z-5 | (+63.75) | grid U/16-17 | A | 2024-12-11
91 | Sub Structure | 1st floor | LT-1-091 | 2024-12-11 | 2024-12-11 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+18.75) | Grid U/21-23 | B | 2024-12-11
92 | Sub Structure | 5th floor | LT-1-092 | 2024-12-12 | 2024-12-12 | formwork | Check vertical bend formwork and allow to start concrete | (+62.75) | Grid U/21-23 | A | 2024-12-19
93 | Sub Structure | 5th floor | LT-1-093 | 2024-12-12 | 2024-12-12 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+62.75) | Grid U/24-26 | B | 2024-12-12
94 | Sub Structure | 5th floor | LT-1-094 | 2024-12-14 | 2024-12-14 | formwork | Check vertical bend formwork and allow to start concrete | (+62.75) | Grid U/24-26 | A | 2024-12-19
95 | Sub Structure | 6th floor | LT-1-095 | 2024-12-15 | 2024-12-15 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+73.75) | Grid U/21-23 | A | 2024-12-16
96 | Sub Structure | 5th floor | LT-1-096 | 2024-12-16 | 2024-12-16 | formwork | Check vertical bend formwork and allow to start concrete work | (+62.75) | Grid U/16-17 | A | 2024-12-19
97 | Sub Structure | 6th floor | LT-1-097 | 2024-12-16 | 2024-12-16 | formwork | Check rienforcement and formwork of leftover slab and allow to start concrete | (+73.75) | Grid U/18-19 | A | 2024-12-19
98 | Sub Structure | 6th floor | LT-1-098 | 2024-12-17 | 2024-12-17 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+73.75) | Grid U/24-26 | A | 2024-12-19
99 | Sub Structure | 3rd floor | LT-1-099 | 2024-12-17 | 2024-12-17 | layout | Check layout and allow to start brick work on internal sides | (+41.0) | Grid G-U/23-26 | A | 2024-12-23
100 | Sub Structure | 6th floor | LT-1-100 | 2024-12-18 | 2024-12-18 | reinforcement | Check vertical bend formwork and allow to start formowrk | (+73.75) | Grid U/21-23 | B | 2024-12-19
101 | Sub Structure | 6th floor | LT-1-101 | 2024-12-18 | 2024-12-18 | formwork | Check vertical bend formwork and allow to start concrete work | (+73.75) | Grid U/21-23 | A | 2024-12-23
102 | Sub Structure | 6th floor | LT-1-102 | 2024-12-19 | 2024-12-19 | reinforcement | check vertical bend reinforcement and allow to start formwork | (+73.75) | Grid U/18-19 | A | 2024-12-23
103 | Sub Structure | 6th floor | LT-1-103 | 2024-12-20 | 2024-12-20 | formwork | Check vertical bend formwork and allow to start concrete work | (+73.75) | Grid U/18-19 | A | 2024-12-23
104 | Sub Structure | 3rd floor | LT-1-104 | 2024-12-20 | 2024-12-20 | layout | Check layout and allow to start brick work on internal sides | (+41.00) | Grid R-U/17-24, G-N/19-23 | A | 2024-12-31
105 | Sub Structure | 6th floor | LT-1-105 | 2024-12-20 | 2024-12-20 | reinforcement | Check formwork and reinforcement of leftover slab and allow to start concrete | (+73.75) | Grid U/16-17 | A | 2024-12-31
106 | Sub Structure | 6th floor | LT-1-106 | 2024-12-21 | 2024-12-21 | reinforcement | check vertical bend reinforcement and allow to start formwork | (+73.75) | Grid U/24-26 | B | 2024-12-23
107 | Sub Structure | 6th floor | LT-1-107 | 2024-12-22 | 2024-12-22 | formwork | Check vertical bend formwork and allow to start concrete work | (+73.75) | Grid U/24-26 | A | 2024-12-31
108 | Sub Structure | 3rd floor | LT-1-108 | 2024-12-23 | 2024-12-23 | layout | Check layout and allow to start brick work on internal sides | (+41.0) | Grid M-U/15-20 | A | 2024-12-31
109 | Sub Structure | 4th floor | LT-1-109 | 2024-12-23 | 2024-12-23 | layout | Check layout and allow to start brick work on internal sides of building | (+41.0) | Grid J-Q/23-26 | A | 2024-12-31
110 | Sub Structure | 7th Floor | LT-1-110 | 2024-12-23 | 2024-12-23 | reinforcement | Check reinforcement and formwrok of leftover slab and allow to start concrete | (+84.75) | Grid U/21-23 | A | 2024-12-31
111 | Sub Structure | 6th floor | LT-1-111 | 2024-12-23 | 2024-12-24 | reinforcement | chck vertical bend reinforcement and allow to start formwork | (+73.75) | Grid U/16-17 | A | 2024-12-24
112 | Sub Structure | 6th floor | LT-1-112 | 2024-12-24 | 2024-12-24 | formwork | Check vertical bend formwork and allow to start concrete work | (+73.75) | Grid U/16-17 | B | 2024-12-31
113 | Sub Structure | 7th floor | LT-1-113 | 2024-12-25 | 2024-12-25 | reinforcement | check rienforcement and formwork of leftover slab and allow to start concrete | (+84.75) | Grid U/18-19 | A | 2025-01-02
114 | Sub Structure | 7th floor | LT-1-114 | 2024-12-26 | 2024-12-26 | reinforcement | Check vertical bend rienforcement and allow to start formwork | (+84.75) | Grid U/21-23 | A | 2024-12-31
115 | Sub Structure | 7th floor | LT-1-115 | 2024-12-27 | 2024-12-27 | formwork | Check vertical bend formwork and allow to start concrete | (+84.75) | Grid U/21-23 | A | 2025-01-02
116 | Sub Structure | 4th floor | LT-1-116 | 2025-01-01 | 2025-01-02 | layout | Check layout and allow to start brick work on internal sides of building | (+52.0) | Grid G-N/19-23 | A | 2025-01-05
117 | Sub Structure | GF | LT-1-117 | 2024-12-30 | 2024-12-28 | brick wrok | Check brick work on internal sides of building |  | Grid M-S/15-26 | A | 2025-01-07
118 | Sub Structure | 7th floor | LT-1-118 | 2024-12-28 | 2024-12-28 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+84.75) | Grid U/18-19 | A | 2024-12-31
119 | Sub Structure | 7th floor | LT-1-119 | 2024-12-29 | 2024-12-29 | reinforcement | Check rienforcement and formwork of leftover slab and allow to start concrete | (+84.75) | Grid U/16-17 | A | 2025-01-02
120 | Sub Structure | 3rd floor | LT-1-120 | 2024-12-28 | 2024-12-28 | layout | Check layout and allow to start brick work on internal sides of building | (+41.0) | Grid R-U/15-18, G-L/20-23 | A | 2025-01-02
121 | Sub Structure | 7th floor | LT-1-121 | 2024-12-30 | 2024-12-30 | reinforcement | Check vertical bend rienforcement and allow to start formwork | (+84.75) | Grid U/16-17 | A | 2024-12-31
122 | Sub Structure | 7th floor | LT-1-122 | 2024-12-30 | 2024-12-30 | formwork | Check vertical bend formwork and allow to start concrete work | (+84.75) | Grid U/18-19 | A | 2025-01-02
123 | Sub Structure | 7th floor | LT-1-123 | 2024-12-30 | 2024-12-30 | formwork | Check reinforcement and formwork of leftover slab and allow to start concrete | (+84.75) | Grid U/24-26 | A | 2025-01-02
124 | Sub Structure | 8th floor | LT-1-124 | 2025-01-01 | 2025-01-01 | reinforcement | Check reinforcement and formwork of beam/nib and allow to start concrete | (+95.75) | Grid U/21-23 | B | 2025-01-11
125 | Sub Structure | 7th floor | LT-1-125 | 2025-01-01 | 2025-01-01 | formwork | Check formwork of vertical bend and allow to start concrete work | (+84.75) | Grid U/16-17 | A | 2025-01-07
126 | Sub Structure | 1st floor | LT-1-126 | 2025-01-13 | 2025-01-13 | brick work | Check brick work on internal sides of building | (+19.0) | Grid G-U/15-26 | A | 2025-01-17
|  |  | LT-1-126 R01 | 2025-09-12 | 2025-09-12 | brick work | Check brick work on internal sides of building |  | Grid G-U/15-26 | A | 2025-09-12
127 | Sub Structure | 2nd floor | LT-1-127 | 2025-01-13 | 2025-01-13 | brick work | Check brick work on internal sides of building | (+30.0) | Grid G-U/15-26 | A | 2025-01-17
128 | Sub Structure | GF | LT-1-128 | 2025-01-02 | 2025-01-02 | formwork | Check front platform wall formwork and allow to start concrete work |  | Grid N/15-20 | B | 2025-01-05
129 | Sub Structure | 7th floor | LT-1-129 | 2025-01-03 | 2025-01-03 | reinforcement | check vertical band reinforcement and allow to start formwork | (+84.75) | Grid U/24-26 | A | 2025-01-03
130 | Sub Structure | 8th floor | LT-1-130 | 2025-01-03 | 2025-01-03 | reinforcement | Check reinforcement and formwork of nib beam and allow to start concrete work | (+95.75) | Grid U/18-19 | A | 2025-01-11
131 | Sub Structure | 7th floor | LT-1-131 | 2025-01-04 | 2025-01-04 | formwork | Check vertical band formwrok and allow to start concreteq | (+84.75) | Grid U/24-26 | A | 2025-01-11
132 | Sub Structure | 8th floor | LT-1-132 | 2025-01-04 | 2025-01-04 | reinforcement | Check reinforcement and formwork of beam/nib and allow to start concrete | (+95.75) | grid U/16-17 | B | 2025-01-06
133 | Sub Structure | 8th floor | LT-1-133 | 2025-01-05 | 2025-01-05 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+95.75) | Grid U/21-23 | A | 2025-01-11
| Sub Structure | 8th floor | LT-1-134 | 2025-01-06 | 2025-01-06 | reinforcement | check leftover slab reinforcement and allow to start formwork | (+95.75) | Grid U/18-19 | A | 2025-01-06
| Sub Structure | 8th floor | LT-1-135 | 2025-01-07 | 2025-01-07 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+95.75) | Grid U/16-17 | B | 2025-01-11
| Sub Structure | 8th floor | LT-1-136 | 2025-01-07 | 2025-01-07 | formwork | Check leftover slab formwork and allow to start concrete | (+95.75) | Grid U/18-19 | A | 2025-01-11
| Sub Structure | 8th floor | LT-1-137 | 2025-01-07 | 2025-01-08 | reinforcement | check vertical band reinforcement and allow to start formwork | (+95.75) | Grid U/21-23 | A | 2025-01-09
| Sub Structure | 4th floor | LT-1-138 | 2025-01-08 | 2025-01-08 | layout | Check layout and allow to start brick work on internal sides of building | (+52.0) | Grid M-U/15-26 | A | 2025-01-10
| Sub Structure | 1st floor | LT-1-139 | 2025-01-09 | 2025-01-09 | formwork | Check beam formwork and allow to start concrete zone 5 | (+18.75) | Grid S/14-15 | A | 2025-01-10
| Sub Structure | GF | LT-1-140 | 2025-01-09 | 2025-01-09 | formwork | Check plaftform formwork and allow to start concrete work |  | Grid N-G/18-20 | A | 2025-01-10
| Sub Structure | 1st floor | LT-1-141 | 2025-01-09 | 2025-01-09 | formwork | Check beam formwork and allow to start concrete work zone 5 | (+18.75) | Grid Q/14-15 | B | 2025-01-11
| Sub Structure | 8th floor | LT-1-142 | 2025-01-10 | 2025-01-10 | formwork | Check vertical formwork and allow to start concrete | (+95.75) | Grid U/21-23 | A | 2025-01-17
| Sub Structure | 8th floor | LT-1-143 | 2025-01-10 | 2025-01-10 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+95.75) | Grid U/16-17 | A | 2025-01-10
| Sub Structure | 8th floor | LT-1-144 | 2025-01-14 | 2025-01-14 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+95.75) | Grid U/18-19 | A | 2025-01-15
| Sub Structure | 8th floor | LT-1-145 | 2025-01-11 | 2025-01-11 | formwork | Check vertical band formwork and allow to start concrete work | (+95.75) | Grid U/16-17 | A | 2025-01-17
| Sub Structure | 7th floor | LT-1-146 | 2025-01-14 | 2025-01-14 | reinforcement | Check reinforcement and formwork of lftover slab and allow to start concrete | (+84.75) | Grid U/24-26 | B | 2025-01-22
| Sub Structure | 9th floor | LT-1-147 | 2025-01-14 | 2025-01-14 | formwork | Check leftover slab formwork and allow to start concrete | (+106.75) | Grid U/21-23 | A | 2025-01-22
| Sub Structure | 5th floor | LT-1-148 | 2025-01-13 | 2025-01-13 | layout | Check layout and allow to start brick work on internal sides of building | (+63.0) | Grid R-U/17-23, J-U/23-26 | A | 2025-01-20
| Sub Structure | 5th floor | LT-1-149 | 2025-01-24 | 2025-01-24 | layout | Check layout and allow to start brick work on internal sides of building | (+63.0) | Grid G-N/20-23 | A | 2025-02-05
| Sub Structure | 8th floor | LT-1-150 | 2025-01-15 | 2025-01-15 | formwork | Check vertical band formwork and allow to start concrete work | (+95.75) | Grid U/18-19 | A | 2025-01-17
| Sub Structure | 10th floor | LT-1-151 | 2025-01-15 | 2025-01-15 | formwork | Check leftover slab formwrok and allow to start concrete work | (+117.75) | Grid U/16-17 | A | 2025-01-22
| Sub Structure | 5th floor | LT-1-152 | 2025-01-16 | 2025-01-16 | layout | Check layout and allow to start brick work on internal sides | (+63.0) | Grid M-U/14-20 | A | 2025-01-22
| Sub Structure | 9th floor | LT-1-153 | 2025-01-17 | 2025-01-17 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+106.75) | Grid U/21-23 | OP
| Sub Structure | 6th floor | LT-1-154 | 2025-01-18 | 2025-01-18 | layout | Check layout and allow to start brick work on internal sides of building | (+74.0) | Grid H-U/23-26 | A | 2025-01-22
| Sub Structure | 9th floor | LT-1-155 | 2025-01-18 | 2025-01-18 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+107.0) | Grid U/21-23 | A | 2025-01-19
| Sub Structure | 9th floor | LT-1-156 | 2025-01-19 | 2025-01-19 | formwork | Check leftover slab formwork and allow to start concrete | (+107.0) | Grid U/18-19 | A | 2025-01-27
| Sub Structure | 8th floor | LT-1-157 | 2025-01-19 | 2025-01-19 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+95.75) | Grid U/24 | A | 2025-01-22
| Sub Structure | 9th floor | LT-1-158 | 2025-01-20 | 2025-01-21 | formwork | Check vertical band formwork and allow to start concrete work | (+106.75) | Grid U/21-23 | A | 2025-01-27
| Sub Structure | 9th floor | LT-1-159 | 2025-01-22 | 2025-01-22 | reinforcement | check vertical band rienforcement and allow to start formwork | (+107.0) | Grid U/16-17 | A | 2025-01-23
| Sub Structure | 9th floor | LT-1-160 | 2025-01-23 | 2025-01-23 | formwork | Check vertical band formwork and allow for concrete pouring | (+107.0) | Grid U/16-17 | A | 2025-01-29
| Sub Structure | 6th floor | LT-1-161 | 2025-01-24 | 2025-01-24 | layout | Check layout and allow to start brick work on internal sides of building | (+74.0) | Grid R-U/15-24 | A | 2025-01-31
| Sub Structure | 9th floor | LT-1-162 | 2025-01-27 | 2025-01-27 | reinforcement | Check vertical band reinforcement and allow for formwork | (+107.0) | Grid U/18-19 | A | 2025-01-28
| Sub Structure | 9th floor | LT-1-163 | 2025-01-28 | 2025-01-28 | formwork | Check vertical band formwork and allow to start concrete work | (+107.0) | Grid U/18-19 | A | 2025-02-05
| Sub Structure | 8th floor | LT-1-164 | 2025-01-28 | 2025-01-28 | formwork | Check vertical band formwork and allow to start concrete work | (+96.0) | Grid U/24 | A | 2025-02-05
| Sub Structure | 10th floor | LT-1-165 | 2025-01-28 | 2025-01-28 | formwork | Check leftover slab and allow to start concrete work | (+118.0) | Grid U/16-17 | A | 2025-02-05
| Sub Structure | 10th floor | LT-1-166 | 2025-01-29 | 2025-01-29 | reinforcement | check vertical band rienforcemetn and allow to start formwork | (+118.0) | Grid U/21-23 | A | 2025-01-31
| Sub Structure | 3rd floor | LT-1-167 | 2025-01-29 | 2025-01-30 | brick work | Check brick work on internal sides of building | (+41.0) | Grid G-U/15-26 | A | 2025-02-05
|  |  | LT-1-167 R01 | 2025-09-12 | 2025-09-12 | brick work | Check brick work on internal sides of building | (+41.0) | Grid G-U/15-26 | A | 2025-09-13
| Sub Structure | 3rd floor | LT-1-168 | 2025-01-30 | 2025-01-30 | formwork | Check beam formwork and allow to start concrete Zone 5 | (+40.75) | Grid Q/14-15 | A | 2025-02-08
| Sub Structure | 10th floor | LT-1-169 | 2025-01-31 | 2025-02-01 | formwork | check vertical band formwork and allow to start concrete work | (+118.0) | Grid U/21-23 | A | 2025-02-08
| Sub Structure | 7th floor | LT-1-170 | 2025-02-03 | 2025-02-03 | layout | Check layout & allow for brick work on internal sides | (+85.0) | Grid G-Q/23-26 | A | 2025-02-05
| Sub Structure | 10th floor | LT-1-171 | 2025-02-03 | 2025-02-03 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+118.0) | Grid U/16-17 | A | 2025-02-04
| Sub Structure | 10th floor | LT-1-172 | 2025-02-04 | 2025-02-04 | formwork | check vertical band formwork and allow to start concrete work | (+118.0) | Grid U/16-17 | A | 2025-02-08
| Sub Structure | 4th floor | LT-1-173 | 2025-02-04 | 2025-02-04 | brick work | Check brick work on internal sides of building | (+52.0) | Grid G-U/15-26 | A | 2025-02-08
|  |  | LT-1-173 R01 | 2025-09-12 | 2025-09-12 | brick work | Check brick work on internal sides of building |  | Grid G-U/15-26 | R | 2025-09-13
| Sub Structure | 10th floor | LT-1-174 | 2025-02-05 | 2025-02-05 | formwork | Check leftover slab formwork and allow to start concrete work | (+118.0) | Grid U/18-19 | A | 2025-02-19
| Sub Structure | 9th floor | LT-1-175 | 2025-02-05 | 2025-02-05 | reinforcement | Check reinforcement and leftover slab formwork and allow to start concrete work | (+107.0) | Grid U/24 | A | 2025-02-19
| Sub Structure | 3rd floor | LT-1-176 | 2025-02-05 | 2025-02-05 | formwork | Check beam formwrok and allow to start concrete work | (+41.0) | Grid S/15 | A | 2025-02-19
| Sub Structure | 7th floor | LT-1-177 | 2025-02-06 | 2025-02-06 | layout | Check layout and allow to start brick work on internal sides of building | (+85.0) | Grid M-U/15-26 | A | 2025-02-08
| Sub Structure | 11th floor | LT-1-178 | 2025-02-06 | 2025-02-06 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid U/21-23 | A | 2025-02-19
| Sub Structure | 4th Floor | LT-1-179
| Sub Structure | 10th floor | LT-1-180 | 2025-02-06 | 2025-02-06 | reinforcement | check vertical band reinforcement and allow to start formwork | (+131.0) | Grid U/18-19 | A | 2025-02-08
| Sub Structure | GF to 11th floor | LT-1-181 | 2025-02-07 | 2025-02-07 | DB installation | Check DBS installation (12 Nos) 25mm sq cable (355 ft) |  |  | A | 2025-02-21
| Sub Structure | 10th floor | LT-1-182 | 2025-02-07 | 2025-02-07 | formwork | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid U/18-19 | A | 2025-02-19
| Sub Structure | 7th floor | LT-1-183 | 2025-02-07 | 2025-02-07 | layout | Check layout and allow to start brick work on internal sides of building | (+85.0) | Grid N-G/20-26 | A | 2025-02-08
| Sub Structure | 11th floor | LT-1-184 | 2025-02-08 | 2025-02-08 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid U/16-17 | A | 2025-02-19
| Sub Structure | 11th floor | LT-1-185 | 2025-02-10 | 2025-02-10 | reinforcement | check vertical band reinforcement and allow to start formwork | (+131.0) | Grid U/21-23 | B | 2025-02-13
| Sub Structure | 11th floor | LT-1-186 | 2025-02-11 | 2025-02-12 | formwork | Check vertical band formwork and allow to start concrete work | (+131.0) | Grid U/21-23 | A | 2025-02-19
| Sub Structure | 9th floor | LT-1-187 | 2025-02-13 | 2025-02-13 | reinforcement | check vertical band reinforcement and allow to start formwork | (+107.0) | Grid U/24 | A | 2025-02-13
| Sub Structure | 11th floor | LT-1-188 | 2025-02-11 | 2025-02-12 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid U/18-19 | A | 2025-02-19
| Sub Structure | 5th floor | LT-1-189 | 2025-02-12 | 2025-02-12 | formwork | Check beam formwork and allow to start concrete work | (+63.0) | Grid Q/14-15, S/14-15 | A | 2025-02-19
| Sub Structure | 9th floor | LT-1-190 | 2025-02-13 | 2025-02-13 | formwork | Check leftover slab formwork and allow to start concrete work | (+107.0) | Grid U/24 | OP
| Sub Structure | 11th floor | LT-1-191 | 2025-02-15 | 2025-02-15 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+131.0) | Grid U/18-19 | A | 2025-02-19
| Sub Structure | 6th floor | LT-1-192 | 2025-02-16 | 2025-02-17 | layout | check layout and allow to start brick work on internal sides | (+74.0) | Grid N-G/20-23 | A | 2025-02-19
| Sub Structure | 11th floor | LT-1-193 | 2025-02-16 | 2025-02-17 | formwork | Check vertical band formwork and allow to start concrete work | (+131.0) | Grid U/18-19 | A | 2025-02-19
| Sub Structure | 10th floor | LT-1-194 | 2025-02-16 | 2025-02-16 | formwork | Check leftover slab formwork and allow to start concrete work | (+118.0) | Grid U/24 | A | 2025-02-27
| Sub Structure | 1st floor | LT-1-195 | 2025-02-17 | 2025-02-17 | reinforcement | Check reinforcement and leftover slab formwork and allow to start concrete work | (+19.0) | Grid M/16-17 | A | 2025-02-19
| Sub Structure | 11th floor | LT-1-196 | 2025-02-18 | 2025-02-18 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+131.0) | Grid U/15-16 | A | 2025-02-18
| Sub Structure | 11th floor | LT-1-197 | 2025-02-18 | 2025-02-18 | formwork | Check vertical band formwork and allow to start concrete work | (+131.0) | Grid U/16-17 | A | 2025-02-27
| Sub Structure | 1st floor | LT-1-198 | 2025-02-18 | 2025-02-18 | pipe line | Check PPRC Water supply pipe lines |  |  | A | 2025-02-19
| Sub Structure | 6th floor | LT-1-199 | 2025-02-20 | 2025-02-20 | layout | Check layout and allow to start brick work on internal sides of building | (+74.0) | Grid N-U/15-23 | A | 2025-02-27
| Sub Structure | 1st floor | LT-1-200 | 2025-02-21 | 2025-02-21 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+19.0) | Grid U/16-17 | A | 2025-03-04
| Sub Structure | 10th floor | LT-1-201 | 2025-02-21 | 2025-02-21 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+118.0) | Grid U/24 | A | 2025-03-03
| Sub Structure | 11th floor | LT-1-202 | 2025-02-21 | 2025-02-21 | formwork | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid U/24 | A | 2025-02-27
| Sub Structure | 1st floor | LT-1-203 | 2025-02-21 | 2025-02-21 | formwork | Check vertical band formwork and allow to start concrete wrok | (+19.0) | Grid U/15 | A | 2025-02-27
| Sub Structure | Top floor | LT-1-204 | 2025-02-24 | 2025-02-23 | formwork | Check parapet wall formwork |  | Grid T-U/14-18 | A | 2025-02-27
| Sub Structure | 11th floor | LT-1-205 | 2025-02-24 | 2025-02-24 | reinforcement | check reinforcement and formwork of leftover slab and allow to start concrete | (+131.0) | Grid U/24 | A | 2025-02-27
| Sub Structure | 4th Floor | LT-1-206
| Sub Structure | 8th floor | LT-1-207 | 2025-02-25 | 2025-02-25 | layout | check layout & alow to start brick work on internal sides of building | (+96.0) | Grid G-U/20-23, G-N/23-26 | A | 2025-03-04
| Sub Structure | Top floor | LT-1-208 | 2025-02-26 | 2025-02-26 | formwork | Check parapet wall formwork |  | Grid U/19-26, R-U/26 | A | 2025-03-04
| Sub Structure | 1st floor | LT-1-209 | 2025-02-26 | 2025-02-26 | reinforcement | Check leftover slab reinforcement formwork and allow to start concrete work | (+19.0) | Grid K-L/26 | A | 2025-02-27
| Sub Structure | 1st floor | LT-1-210 | 2025-02-26 | 2025-02-26 | reinforcement | Check leftover slab rienforcement formwork | (+19.0) | Grid M-P/26 | A | 2025-02-27
| Sub Structure | Top floor | LT-1-211 | 2025-02-26 | 2025-01-27 | formwork | Check parapet wall formwrok |  | Grid N/15-18 | A | 2025-03-04
| Sub Structure | 1st floor | LT-1-212 | 2025-02-26 | 2025-01-27 | reinforcement | Check leftover slab reinforcement and allow to start concrete work | (+19.0) | Grid R-T/26 | A | 2025-03-04
| Sub Structure | Top floor | LT-1-213 | 2025-02-26 | 2025-01-27 | reinforcement | check beam & leftover slab reinforcement and formwork and allow to start concrete | (+145.75) | Grid U/19-23 | A | 2025-03-04
| Sub Structure | 11th floor | LT-1-214 | 2025-02-26 | 2025-01-27 | reinforcement | check vertical band reinforcement and allow to start formwrok | (+131.0) | Grid U/24 | A | 2025-03-04
| Sub Structure | 1st floor | LT-1-215 | 2025-02-27 | 2025-02-27 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+19.0) | Grid U/15 | A | 2025-03-04
| Sub Structure | 1st floor | LT-1-216 | 2025-02-27 | 2025-02-27 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+19.0) | Grid K-L, M-P/26 | A | 2025-03-04
| Sub Structure | 5th floor | LT-1-217 | 2025-02-27 | 2025-02-27 | formwork | Check bean formwork and allow to start concrete work | (+63.0) | Grid U/24-26 | A | 2025-03-04
| Sub Structure | 2nd floor | LT-1-218 | 2025-02-27 | 2025-02-27 | formwork | Check vertical band formwork and allow to start concrete work | (+30.0) | Grid U/15 | A | 2025-03-04
| Sub Structure | 8th floor | LT-1-219 | 2025-02-28 | 2025-02-28 | reinforcement | Check reinforcement and formwork and allow to start concrete work | (+96.0) | Grid U/24-26 | A | 2025-03-04
| Sub Structure | Ground floor | LT-1-220 | 2025-02-28 | 2025-02-28 | formwork | Check fron platform wall formwork and allow to start concrete work |  | Grid G-K/20 | A | 2025-03-04
| Sub Structure | 8th floor | LT-1-221 | 2025-02-28 | 2025-02-28 | layout | Check layout and allow to start brick work on internal sides of building | (+96.0) | Grid R-U/17-24 | A | 2025-03-04
| Sub Structure | Top floor | LT-1-222 | 1-Ma-25 | 1-Ma-25 | formwork | Check parapet wall formwork |  | Grid G-N/20-21 | A | 2025-03-04
| Sub Structure | 1st floor | LT-1-223 | 1-Ma-25 | 1-Ma-25 | formwork | Check vertical band formwork and allow to start concrete work | (+19.0) | Grid K-L, M-P/26 | A | 2025-03-04
| Sub Structure | 11th floor | LT-1-224 | 1-Ma-25 | 1-Ma-25 | formwork | Check vertical band formwork and allow to start concrete work | (+131.0) | Grid U/24 | A | 2025-03-04
| Sub Structure | Top floor | LT-1-225 | 2025-03-03 | 2025-03-03 | reinforcement | Check reinforcement and formwork of beam & leftover slab and allow for concrete | (+146.0) | Grid U/16-18 | OP
| Sub Structure | 3rd floor | LT-1-226 | 2025-03-03 | 2025-03-03 | reinforcement | check vertical band reinforcement and allow to start formwork | (+41.0) | Grid U/15 | A | 2025-03-04
| Sub Structure | 6th floor | LT-1-227
| Sub Structure | Top floor | LT-1-228 | 2025-03-03 | 2025-03-03 | formwrok | Check parapet wall formwork |  | Grid J-R/26 | A | 2025-03-04
| Sub Structure | 6th Floor | LT-1-229
| Sub Structure | 5th floor | LT-1-230 | 2025-03-03 | 2025-03-03 | brick work | Check brick work on internal sides of building | (+63.0) | Grid G-U/15-26 | OP
| Sub Structure | 8th floor | LT-1-231 | 2025-03-05 | 2025-03-06 | reinforcement | check reinforcement and formwrok of nib and allow to start concrete | (+96.0) | Grid U/17-18, 19-21, 23-24 | OP
| Sub Structure | Top floor | LT-1-232 | 2025-03-03 | 2025-03-03 | formwork | Check column (2 Nos) formwork and allwo to start concrete work | (+146.0) | Grid G/26, H/26 | OP
| Sub Structure | 3rd floor | LT-1-233 | 2025-03-04 | 2025-03-04 | formwork | Check vertical band formwork and allow to start concrete work | (+41.0) | Grid U/15 | OP
| Sub Structure | Top floor | LT-1-234 | 2025-03-04 | 2025-03-04 | formwork | Check parapet wall formwork |  | grid U/18-23 | OP
| Sub Structure | 2nd floor | LT-1-235 | 2025-03-04 | 2025-03-05 | formwork | Check leftover slab formwork and allow to start concrete work | (+30.0) | Grid R-T/26 | OP
| Sub Structure | 2nd floor | LT-1-236 | 2025-03-04 | 2025-03-05 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+30.0) | Grid K-L, M-P/26 | OP
| Sub Structure | 2nd floor | LT-1-237 | 2025-03-05 | 2025-03-06 | formwork | Check vertical band formwork and allow to start concret work | (+30.0) | Grid K-L, M-P/26 | OP
| Sub Structure | Top floor | LT-1-238 | 2025-03-05 | 2025-03-05 | fomrwork | check columns (2 Nos) formwork | (+146.0) | Grid G/24, J/26 | OP
| Sub Structure | 2nd floor | LT-1-239 | 2025-03-05 | 2025-03-05 | reinforcement | Check vertical band rienforcement and allow to start formwrok | (+30.0) | Grid R-T/26 | OP
| Sub Structure | 2nd floor | LT-1-240
| Sub Structure | 2nd floor | LT-1-241
| Sub Structure | 2nd floor | LT-1-242
| Sub Structure | 2nd floor | LT-1-243
| Sub Structure | 2nd floor | LT-1-244
| Sub Structure | 2nd floor | LT-1-245
| Sub Structure | 2nd floor | LT-1-246
| Sub Structure | 2nd floor | LT-1-247
| Sub Structure | 2nd floor | LT-1-248
| Sub Structure | 2nd floor | LT-1-249
| Sub Structure | 2nd floor | LT-1-250
| Sub Structure | 2nd floor | LT-1-251
| Sub Structure | 2nd floor | LT-1-252
| Sub Structure | 2nd floor | LT-1-253
| Sub Structure | 2nd floor | LT-1-254 R01 | 2025-09-11 | 2025-09-11 | Brick masnory | Check Complete brick masonary work on internal sides of building | 7th floor |  | R | 2025-09-13 | Waseem
| Sub Structure | 8th floor | LT-1-255 | 1st-May-25 | 1st-May-25 | brick work | Check brick work on internal sides of building | (+96.0) | Grid G-U/15-26 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-1-256
| Sub Structure | 2nd floor | LT-1-257
| Sub Structure | 2nd floor | LT-1-258
| Sub Structure | 5th floor | LT-1-259 | 2025-03-21 | 2025-03-22 | reinforcement | Check reinforcement and formwork of leftover slab and allow for concrete pouring | (+63.0) | Grid U/15-16 | A | 2025-03-24
| Sub Structure | 2nd floor | LT-1-260
| Sub Structure | 2nd floor | LT-1-261
| Sub Structure | 2nd floor | LT-1-262
| Sub Structure | 2nd floor | LT-1-263
| Sub Structure | 2nd floor | LT-1-264
| Sub Structure | 2nd floor | LT-1-265
| Sub Structure | 2nd floor | LT-1-266
| Sub Structure | 2nd floor | LT-1-267
| Sub Structure | 2nd floor | LT-1-268
| Sub Structure | 2nd floor | LT-1-269
| Sub Structure | 2nd floor | LT-1-270
| Sub Structure | 2nd floor | LT-1-271
| Sub Structure | 2nd floor | LT-1-272
| Sub Structure | 2nd floor | LT-1-273
| Sub Structure | 2nd floor | LT-1-274
| Sub Structure | 2nd floor | LT-1-275
| Sub Structure | 2nd floor | LT-1-276
| Sub Structure | 2nd floor | LT-1-277
| Sub Structure | 2nd floor | LT-1-278
| Sub Structure | 2nd floor | LT-1-279
| Sub Structure | 2nd floor | LT-1-280
| Sub Structure | 2nd floor | LT-1-281
| Sub Structure | 2nd floor | LT-1-282
| Sub Structure | 2nd floor | LT-1-283
| Sub Structure | 2nd floor | LT-1-284
| Sub Structure | 2nd floor | LT-1-285
| Sub Structure | 2nd floor | LT-1-286
| Sub Structure | 2nd floor | LT-1-287
| Sub Structure | 2nd floor | LT-1-288
| Sub Structure | 2nd floor | LT-1-289
| Sub Structure | 2nd floor | LT-1-290
| Sub Structure | 2nd floor | LT-1-291
| Sub Structure | 3rd floor | LT-1-292 | 2025-03-20 | 2025-03-21 | formwork | Check leftover slab formwork and allow to start concrete work | (+41.0) | Grid N/16-17 | A | 2025-03-24
| Sub Structure | 2nd floor | LT-1-293
| Sub Structure | 2nd floor | LT-1-294
| Sub Structure | 2nd floor | LT-1-295
| Sub Structure | 2nd floor | LT-1-296
| Sub Structure | 2nd floor | LT-1-297
| Sub Structure | 2nd floor | LT-1-298 | 2025-03-21 | 2025-03-21 | formwork | Check leftovers slab formwork and allow to start concrete work | (+30.0) | Grid N/15 | A | 2025-03-24
| Sub Structure | 4th floor | LT-1-299 | 2025-03-21 | 2025-03-21 | formwork | Check vertical band formwrok and allow to start concrete work | (+52.0) | Grid R-T/26 | A | 2025-03-24
| Sub Structure | 2nd floor | LT-1-300
| Sub Structure | 2nd floor | LT-1-301 | 2025-03-21 | 2025-03-22 | formwrok | Check vertical band formwork and allow to start concrete work | (+30.0) | Grid H-K, L-M/19 | A | 2025-03-24
| Sub Structure | Top floor | LT-1-302 | 2025-03-22 | 2025-03-22 | formwork | Check over head water tank and FSS formwork |  | Grid N-R/18-20 | A | 2025-04-24
| Sub Structure | 3rd floor | LT-1-303 | 2025-03-22 | 2025-03-24 | formwork | Check leftovers slab formwork and allow to start concrete work | (+41.0) | Grid N/18-19 | A | 2025-03-24
| Sub Structure | 3rd floor | LT-1-304 | 2025-03-22 | 2025-03-24 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+41.0) | Grid N/16-17 | A | 2025-03-24
| Sub Structure | 3rd floor | LT-1-305 | 2025-03-22 | 2025-03-24 | formwork | Check vertical band formwrok and allow to start concrete work | (+41.0) | Grid N/16-17 | A | 2025-03-24
| Sub Structure | 2nd floor | LT-1-306 | 2025-03-22 | 2025-03-24 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+30.0) | Grid N/15 | A | 2025-03-27
| Sub Structure | 2nd floor | LT-1-307 | 2025-03-22 | 2025-03-24 | formwrok | Check formwork of vertical band and allow to start concrete work | (+30.0) | Grid N/15 | A | 2025-03-27
| Sub Structure | 3rd floor | LT-1-308 | 2025-03-24 | 2025-03-24 | formwrok | Check leftover slab formwork and allow to start concrete work | (+41.0) | Grid H-K, L-M/19 | A | 2025-04-08
| Sub Structure | 5th floor | LT-1-309 | 2025-03-24 | 2025-03-24 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+63.0) | Grid U/19-21 | A | 2025-03-27
| Sub Structure | 3rd floor | LT-1-310 | 2025-03-24 | 2025-03-25 | reinforcement | Check concrete of vertical band and allow to start formwork | (+41.0) | Grid N/17-18 | A | 2025-03-27
| Sub Structure | 3rd floor | LT-1-311 | 2025-03-25 | 2025-03-26 | formwork | Check vertical band formwork and allow to start concrete work | (+41.0) | Grid N/18-19 | A | 2025-04-14
| Sub Structure | 4th floor | LT-1-312 | 2025-03-25 | 2025-03-25 | formwork | Check leftover slab formwork and allow to start concrete work | (+52.0) | Grid N/16-17 | A | 2025-04-14
| Sub Structure | 3rd floor | LT-1-313 | 2025-03-25 | 2025-03-26 | reinforcement | Check vertical band rienforcement and allow to start formwrok | (+41.0) | Grid H-K/19 | A | 2025-04-08
| Sub Structure | 3rd floor | LT-1-314 | 2025-03-25 | 2025-03-26 | formwork | Check vertical band formwrok and allow to start concrete work | (+41.0) | Grid H-K/19 | A | 2025-04-14
| Sub Structure | Ground floor | LT-1-315 | 2025-03-26 | 2025-03-26 | formwork | Check fuel tank beam formwrok |  | Grid U/26 | A | 2025-04-08
| Sub Structure | Mummty roof | LT-1-316 | 2025-03-26 | 2025-03-26 | formwork | Check Mummty slab formwork |  | Grid G-J/24-26 | A | 2025-04-16
| Sub Structure | 3rd floor | LT-1-317 | 2025-03-26 | 2025-03-26 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+41.0) | Grid L-M/19 | A | 2025-04-08
| Sub Structure | 3rd floor | LT-1-318 | 2025-03-26 | 2025-03-26 | formwork | Check vertical band formwork and allow to start concrete work | (+41.0) | Grid L-M/19 | A | 2025-04-19
| Sub Structure | 4th floor | LT-1-319 | 2025-03-26 | 2025-03-27 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+52.0) | Grid M-N/16-17 | A | 2025-04-08
| Sub Structure | 4th floor | LT-1-320 | 2025-03-26 | 2025-03-27 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid M-N/16-17 | A | 2025-04-14
| Sub Structure | 5th floor | LT-1-321 | 2025-03-26 | 2025-03-27 | formwork | Check leftover slab formwork and allow to start concrete work | (+63.0) | Grid K-L/M-P/26 | A | 2025-04-14
| Sub Structure | 5th floor | LT-1-322 | 2025-03-26 | 2025-03-27 | formwork | Check leftover slab formwrok and allow to start concrete work | (+63.0) | Grid R-T/26 | A | 2025-04-14
| Sub Structure | 5th floor | LT-1-323 | 2025-03-26 | 2025-03-27 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+63.0) | Grid L-M/26 | A | 2025-04-08
| Sub Structure | 5th floor | LT-1-324 | 2025-03-27 | 2025-03-28 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+63.0) | Grid P-R/26 | A | 2025-04-08
| Sub Structure | 3rd floor | LT-1-325 | 2025-04-08 | 2025-04-08 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete work | (+41.0) | Grid M-N/15 | A | 2025-04-14
| Sub Structure | 4th floor | LT-1-326 | 2025-04-08 | 2025-04-08 | formwork | Check leftover slab formwork and allow to start concrete work | (+52.0) | Grid N/18-19 | A | 2025-04-14
| Sub Structure | 4th floor | LT-1-327 | 2025-04-09 | 2025-04-09 | formwork | Check leftovers slab formwork and allow to start concrete work | (+52.0) | Grid L-M/19-20 | A | 2025-04-14
| Sub Structure | 4th floor | LT-1-328 | 2025-04-09 | 2025-04-09 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+52.0) | Grid H-K/19 | A | 2025-04-14
| Sub Structure | 4th floor | LT-1-329 | 2025-04-10 | 2025-04-10 | reinforcement | Check reinforcement of vertical band and allow to start formwork |  | Grid L-M/19 | A | 2025-04-14
| Sub Structure | 4th floor | LT-1-330 | 2025-04-10 | 2025-04-10 | formwork | Check vertical band formwork and allow to start concrete work |  | Grid H-K/19 | A | 2025-04-14
| Sub Structure | 5th floor | LT-1-331 | 2025-04-10 | 2025-04-10 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+63.0) | Grid U/17-18 | A | 2025-04-14
| Sub Structure | 4th floor | LT-1-332 | 2025-04-10 | 2025-04-11 | formwork | Check vertical band formwork and allow to start concrete | (+52.0) | Grid L-M/19 | A | 2025-04-19
| Sub Structure | 4th floor | LT-1-333 | 2025-04-10 | 2025-04-11 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+52.0) | Grid N/18-19 | A | 2025-04-14
| Sub Structure | 3rd floor | LT-1-334 | 2025-04-10 | 2025-04-11 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+41.0) | Grid N/15 | A | 2025-04-14
| Sub Structure | 5th floor | LT-1-335 | 2025-04-10 | 2025-04-11 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+63.00) | Grid U/15-16 | A | 2025-04-16
| Sub Structure | Mummty roof | LT-1-336 | 2025-04-11 | 2025-04-11 | formwork | Check slab formwork |  | Grid N-R/20-22 | A | 2025-04-19
| Sub Structure | 4th floor | LT-1-337 | 2025-04-11 | 2025-04-11 | formwrok | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid N/18-19 | A | 2025-04-19
| Sub Structure | 3rd floor | LT-1-338 | 2025-04-11 | 2025-04-11 | formwork | Check vertical band formwork and allow to start concrete work | (+41.0) | Grid N/15 | A | 2025-04-19
| Sub Structure | 4th floor | LT-1-339 | 2025-04-12 | 2025-04-12 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+52.0) | Grid N/15 | A | 2025-04-16
| Sub Structure | 5th floor | LT-1-340 | 2025-04-12 | 2025-04-12 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+63.0) | Grid K-L, M-P, R-T/26 | A | 2025-04-14
| Sub Structure | 5th floor | LT-1-341 | 2025-04-12 | 2025-04-12 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid K-L, M-P, R-T/26 | A | 2025-04-19
| Sub Structure | 8th floor | LT-1-342 | 2025-04-12 | 2025-04-12 | reinforcement | Check reinforcement and fomrwork of horizontal band and allow to start concrete work | (+96.0) | Grid U/23-26 | A | 2025-04-16
| Sub Structure | 4th floor | LT-1-343 | 2025-04-14 | 2025-04-14 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid N/15 | A | 2025-04-19
| Sub Structure | 6th floor | LT-1-344 | 2025-04-14 | 2025-04-14 | formwork | Check leftover slab formwork and allow to start concrete work | (+74.0) | Grid K-L, M-P/26 | A | 2025-04-19
| Sub Structure | Top floor | LT-1-345 | 2025-04-14 | 2025-04-14 | plaster work | Check external façade plaster work | (+19.0 to +146.0) | Grid U/16-17, 26 | A | 2025-04-19
| Sub Structure | 10th floor | LT-1-346 | 2025-04-14 | 2025-04-14 | layout | Check layout and allow to start brick work | (+118.0) | Grid G-U/23-26 | A | 2025-04-19
| Sub Structure | 6th floor | LT-1-347 | 2025-04-14 | 2025-04-14 | formwork | Check leftover slab formwork and allow to start concrete work | (+74.0) | Grid R-T/26 | A | 2025-04-19
| Sub Structure | 6th floor | LT-1-348 | 2025-04-15 | 2025-04-15 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+74.0) | Grid K-L, M-P/26 | A | 2025-04-16
| Sub Structure | 5th floor | LT-1-349 | 2025-04-16 | 2025-04-16 | formwork | Check leftover slab formwork and allow to start concrete work | (+63.0) | Grid N/18-19, 16-17 | A | 2025-04-19
| Sub Structure | 6th floor | LT-1-350 | 2025-04-15 | 2025-04-15 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid K-L, M-P/26 | A | 2025-04-19
| Sub Structure | 5th floor | LT-1-351 | 2025-04-15 | 2025-04-16 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+63.0) | Grid N/17-18 | OP
| Sub Structure | 6th floor | LT-1-352 | 2025-04-16 | 2025-04-16 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+74.0) | Grid R-Y/26 | A | 2025-04-19
| Sub Structure | 6th floor | LT-1-353 | 2025-04-16 | 2025-04-16 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid R-T/26 | A | 2025-04-19
| Sub Structure | 5th floor | LT-1-354 | 2025-04-16 | 2025-04-17 | reinforcement | Check reinforcement and formwork of horizontal band & leftover slab and allow concrete | (+63.0) | Grid H-M/19 | A | 2025-04-19
| Sub Structure | 7th floor | LT-1-355 | 2025-04-17 | 2025-04-17 | formwork | Check leftover slab formwrok and allow to start concrete work | (+85..0) | Grid M-P/26 | A | 2025-04-22
| Sub Structure | 5th floor | LT-1-356 | 2025-04-17 | 2025-04-17 | reinforcement | Check vertical band reinforcement and allow to start formwrok | (+63.0) | Grid N/18-19 | A | 2025-04-19
| Sub Structure | 5th floor | LT-1-357 | 2025-04-17 | 2025-04-18 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid N/18-19 | A | 2025-04-22
| Sub Structure | 5th floor | LT-1-358 | 2025-04-17 | 2025-04-18 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+63.0) | Grid N/16-17 | A | 2025-04-19
| Sub Structure | 7th floor | LT-1-359 | 2025-04-17 | 2025-04-18 | formwork | Check leftover slab formwrok and allow to start concrete work | (+85.0) | Grid K-L, R-T/26 | A | 2025-04-22
| Sub Structure | 7th floor | LT-1-360 | 2025-04-17 | 2025-04-18 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+85.0) | Grid M-P/26 | A | 2025-04-19
| Sub Structure | 5th floor | LT-1-361 | 2025-04-18 | 2025-04-18 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid N/16-17 | A | 2025-04-22
| Sub Structure | 7th floor | LT-1-362 | 2025-04-18 | 2025-04-18 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+85.0) | Grid K-L, M-P/26 | A | 2025-04-19
| Sub Structure | 5th floor | LT-1-363 | 2025-04-18 | 2025-04-18 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+63.0) | Grid L-M/19 | A | 2025-04-19
| Sub Structure | 7th floor | LT-1-364 | 2025-04-18 | 2025-04-18 | formwork | Check vertical band formwork and allow to start concrete work | (+85.0) | Grid K-L, M-P/26 | A | 2025-04-22
| Sub Structure | 5th floor | LT-1-365 | 2025-04-18 | 2025-04-18 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+63.0) | Grid H-K/19 | A | 2025-04-19
| Sub Structure | 5th floor | LT-1-366 | 2025-03-19 | 2025-03-19 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+63.0) | Grid G-H/19 | A | 2025-04-22
| Sub Structure | 6th floor | LT-1-367 | 2025-03-19 | 2025-03-19 | formwork | Check leftover slab formwork and allow to start concrete work | (+74.0) | Grid N/18-19 | A | 2025-04-22
| Sub Structure | 7th floor | LT-1-368 | 2025-03-19 | 2025-03-19 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+85.0) | Grid R-T/26 | A | 2025-04-22
| Sub Structure | 6th floor | LT-1-369 | 2025-03-19 | 2025-03-19 | formwork | Check leftover slab formwrok and allow to start concrete work | (+74.0) | Grid N/16-17 | A | 2025-04-24
| Sub Structure | 7th floor | LT-1-370 | 2025-03-19 | 2025-03-19 | formwork | Check vertical band formwork and allow to start concrete work | (+85.0) | Grid R-T/26 | A | 2025-04-24
| Sub Structure | 5th floor | LT-1-371 | 2025-03-19 | 2025-03-19 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid L-M/19 | A | 2025-04-24
| Sub Structure | 5th floor | LT-1-372 | 2025-03-19 | 2025-03-19 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid N/15 | A | 2025-04-24
| Sub Structure | 6th floor | LT-1-373 | 2025-03-19 | 2025-03-19 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid L-M/19 | A | 2025-04-24
| Sub Structure | 5th floor | LT-1-374 | 2025-03-19 | 2025-03-19 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid H-K/19 | A | 2025-04-24
| Sub Structure | 6th floor | LT-1-375 | 2025-03-19 | 2025-03-21 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+74.0) | Grid N/16-19 | A | 2025-04-24
| Sub Structure | 6th floor | LT-1-376 | 2025-03-19 | 2025-03-21 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid N/18-19 | A | 2025-04-24
| Sub Structure | Top floor | LT-1-377 | 2025-04-21 | 2025-04-21 | plaster work | Check plaster work on external side of façade | (+19.0 to +146.0) | Grid U/21-23, 15 | A | 2025-04-24
| Sub Structure | 6th floor | LT-1-378 | 2025-04-21 | 2025-04-21 | formwork | Check leftover slab formwork and allow to start concrete work | (+74.0) | Grid H-K/19 | A | 2025-05-08
| Sub Structure | 6th floor | LT-1-379 | 2025-04-21 | 2025-04-22 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid N/16-17 | A | 2025-05-08
| Sub Structure | 6th floor | LT-1-380 | 2025-04-22 | 2025-04-22 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid L-M/19 | A | 2025-05-08
| Sub Structure | 6th floor | LT-1-381 | 2025-04-22 | 2025-04-22 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+74.0) | Grid L-M/19 | A | 2025-04-24
| Sub Structure | 10th floor | LT-1-382 | 2025-04-22 | 2025-04-23 | layout | Check layout and allow to start brick work on internal sides | (+118.0) | Grid R-U/17-24 | A | 2025-05-08
| Sub Structure | 6th floor | LT-1-383 | 2025-04-22 | 2025-04-22 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+74.0) | Grid H-K/19 | A | 2025-05-08
| Sub Structure | 6th floor | LT-1-384 | 2025-04-22 | 2025-04-22 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid H-K/19 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-385 | 2025-04-22 | 2025-04-23 | reinforcement | Check reinforcement and formwork of horizontal band & lefto over slab and allow to start concrete work | (+96.0) | Grid K-P/26 | A | 2025-04-24
| Sub Structure | 5th floor | LT-1-386 | 2025-04-23 | 2025-04-23 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+63.0) | Grid N/15 | A | 2025-05-08
| Sub Structure | 5th floor | LT-1-387 | 2025-04-23 | 2025-04-23 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid N/15 | A | 2025-05-08
| Sub Structure | 7th floor | LT-1-388 | 2025-04-23 | 2025-04-23 | formwork | Check leftover slab formwrok and allow to start concrete work | (+85.0) | Grid N/16-17, 18-19 | A | 2025-05-08
| Sub Structure | 6th floor | LT-1-389 | 2025-04-24 | 2025-04-24 | formwork | Check leftover slab formwork and allow to start concrete work | (+74.0) | Grid N/15 | A | 2025-05-08
| Sub Structure | 7th floor | LT-1-390 | 2025-04-24 | 2025-04-24 | reinforcement | Check vertical band reinforcement and allow to start formwrok | (+85.0) | Grid N/16-17, 18-19 | A | 2025-05-08
| Sub Structure | 10th floor | LT-1-391 | 2025-04-24 | 2025-04-24 | layout | Check layout and allow to start brick work on internal side | (+118.0) | Grid R-U/15-17 | OP
| Sub Structure | 7th floor | LT-1-392 | 2025-04-24 | 2025-04-24 | formwork | Check vertical band formwork and allow to start concrete work | (+85.0) | Grid N/16-17, 18-19 | A | 2025-05-08
| Sub Structure | Mummty roof | LT-1-393 | 2025-04-25 | 2025-04-25 | formwork | Check machinery room wall formwork |  | Grid H-J/21-22 | A | 2025-05-08
| Sub Structure | 7th floor | LT-1-394 | 2025-04-25 | 2025-04-25 | formwork | Check leftover slab formwrok and allow to start concrete work | (+85.0) | Grid H-K, L-M/19 | A | 2025-05-08
| Sub Structure | 6th floor | LT-1-395 | 2025-04-25 | 2025-04-25 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+74.0) | Grid N/15 | A | 2025-05-08
| Sub Structure | 7th floor | LT-1-396 | 2025-04-25 | 2025-04-25 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+85.0) | Grid H-K, L-M/19 | A | 2025-05-08
| Sub Structure | 7th floor | LT-1-397 | 2025-04-26 | 2025-04-26 | formwork | Check vertical band formwork and allow to start concrete work | (+85.0) | Grid H-K/19 | A | 2025-05-08
| Sub Structure | 7th floor | LT-1-398 | 2025-04-26 | 2025-04-26 | formwork | Check vertical band formwork and allow to start concrete work | (+85.0) | Grid L-M/19 | A | 2025-05-08
| Sub Structure | 6th floor | LT-1-399 | 2025-04-26 | 2025-04-26 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid N/15 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-400 | 2025-04-26 | 2025-04-26 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+96.0) | Grid K-L, M-P/26 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-401 | 2025-04-26 | 2025-04-26 | reinforcement | Check reinforcement and formwork and allow to start concrete work | (+96.0) | Grid P-T/26 | A | 2025-05-08
| Sub Structure | Top floor | LT-1-402 | 2025-04-26 | 2025-04-26 | formwork | Check machinery room formwork |  | Grid N-Q/21-22 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-403 | 2025-04-26 | 2025-04-26 | formwork | Check vertical band formwork and allow to start concrete work | (+96.0) | Grid K-L, M-P/26 | A | 2025-05-08
| Sub Structure | Ground floor | LT-1-404 | 2025-04-28 | 2025-04-28 | formwork | Check slab formwork and allow to start light weight concrete |  | Grid N/15-18 | A | 2025-05-08
| Sub Structure | 10th floor | LT-1-405 | 2025-04-28 | 2025-04-28 | layout | Check layout and allow to start brick work on internal sides | (+118.0) | Grid N-R/15-20 | A | 2025-05-08
| Sub Structure | 10th floor | LT-1-406 | 2025-04-28 | 2025-04-28 | reinforcement | Check tie column reinforcement and allow to start concrete work |  | Grid G-Q/23-26 | A | 2025-05-08
| Sub Structure | 7th floor | LT-1-407 | 2025-04-28 | 2025-04-28 | formwork | Check leftover slab formwork and allow to start concrete work |  | Grid N/15 | A | 2025-05-08
| Sub Structure | Top floor | LT-1-408 | 2025-04-29 | 2025-04-29 | formwork | Check machine room slab formwork |  | Grid H-J/23-24 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-409 | 2025-04-29 | 2025-04-29 | reinforcement | Check vertical band rienforcement and allow to start formwrok | (+96.0) | Grid R-T/26 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-410 | 2025-04-30 | 2025-05-01 | formwrok | Check vertical band formwork and allow to start concrete work | (+96.0) | Grid R-T/26 | A | 2025-05-08
| Sub Structure | 1st floor to top | LT-1-411 | 2025-04-29 | 2025-04-30 | plaster work | Check plaster work on external side of façade | (+19.0) | Grid U/18-19,24 | A | 2025-05-08
| Sub Structure | 9th floor | LT-1-412 | 2025-04-29 | 2025-04-29 | formwork | Check leftover slab formwork and allow to start concrete work | (+107.0) | Grid K-L/26, R_T | A | 2025-05-08
| Sub Structure | Ground floor | LT-1-413 | 2025-04-30 | 2025-05-01 | formwork | Check deck slab formwork and allow to start light weight concrete work |  | Grid J-N/18-20 | A | 2025-05-08
| Sub Structure | 7th floor | LT-1-414 | 2025-04-29 | 2025-04-29 | formwork | check vertical band formwork and allow to start concrete work | (+85.0) | Grid N/15 | A | 2025-05-08
| Sub Structure | 10th floor | LT-1-415 | 2025-04-30 | 2025-04-30 | reinforcement | Check tie column reinforcement and allow to start concrete work |  | Grid S-T/18-22 | A | 2025-05-08
| Sub Structure | Mummty roof | LT-1-416 | 2025-04-29 | 2025-04-29 | formwork | Check mummty formwork parapet wall |  | Grid G-J/24-26 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-417 | 2025-04-30 | 2025-05-01 | reinforcement | check reinforcement and formwork of leftover slab and allow to start concrete |  | Grid H-K/19, L-M | A | 2025-05-08
| Sub Structure | Mummty roof | LT-1-418 | 2025-04-30 | 2025-04-30 | formwrok | Check machinery room formwork |  | Grid N-Q/21-22 | A | 2025-05-08
| Sub Structure | 9th floor | LT-1-419 | 2025-05-01 | 2025-05-01 | reinforcement | Check vertical band reinforcement and allow to start formwrok | (+107.0) | Grid K-L, M-P/26 | A | 2025-05-08
| Sub Structure | 9th floor | LT-1-420 | 2025-05-01 | 2025-05-01 | brick work | Check brick work on internal sides of building | (+107.0) | Grid G-U/15-26 | A | 2025-05-08
| Sub Structure | 11th floor | LT-1-421 | 2025-05-01 | 2025-05-01 | brick work | Check brick work on external sides of building | (+131.0) | Grid G-U/15-26 | A | 2025-05-05
| Sub Structure | 9th floor | LT-1-422 | 2025-05-01 | 2025-05-01 | formwork | Check vertical band formwork and allow to start concrete work | (+107.0) | Grid K-L/26 | A | 2025-05-08
| Sub Structure | wall | LT-1-423 | 2025-05-01 | 2025-05-01 | formwrok | Check machinery room parapet wall formwork |  | Grid H-J/23-24 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-424 | 2025-05-01 | 2025-05-01 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+96.0) | Grid H-K, L-M/19 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-425 | 2025-05-01 | 2025-05-01 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete |  | Grid N/16-19 | A | 2025-05-08
| Sub Structure | Mummty roof | LT-1-426 | 2025-05-02 | 2025-05-02 | formwork | Check machinery room and parapet wall formwork |  | Grid N-Q/20-22 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-427 | 2025-05-02 | 2025-05-02 | formwork | Check vertical band formwork and allow to start concrete work | (+96.0) | Grid H-K, L-M/19 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-428 | 2025-05-02 | 2025-05-02 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete work | (+96.0) | Grid N/15-19 | OP
| Sub Structure | 8th floor | LT-1-429 | 2025-05-03 | 2025-05-03 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+96.0) | Grid N/18-19 | A | 2025-05-08
| Sub Structure | 9th floor | LT-1-430 | 2025-05-03 | 2025-05-03 | formwork | Check leftover slab formwrok and allow to start concrete work | (+107.0) | Grid R-T/26 | A | 2025-05-08
| Sub Structure | Top floor | LT-1-431 | 2025-05-15 | 2025-05-15 | level | Check level points and allow to start plaster work on external side |  | Grid U/15-26 | R | 2025-05-14
| Sub Structure | 8th floor | LT-1-432 | 2025-05-03 | 2025-05-03 | formwork | Check vertical band formwrok and allow to start concrete work | (+96.0) | Grid N/18-19 | A | 2025-05-08
| Sub Structure | 8th floor | LT-1-433 | 2025-05-03 | 2025-05-03 | formwork | Check vertical band formwork and allow to start concrete work | (+96.0) | Grid N/16-17 | A | 2025-05-05
| Sub Structure | 9th floor | LT-1-434 | 2025-05-03 | 2025-05-03 | formwork | check leftover slab formwork and allow to start concrete work | (+107.0) | Grid H-K, L-M/19 | A | 2025-05-05
| Sub Structure | 9th floor | LT-1-435 | 2025-05-03 | 2025-05-03 | formwork | check leftover slab formwork and allow to start concrete work | (+107.0) | Grid N/18-19 | A | 2025-05-05
| Sub Structure | basement to top | LT-1-436 | 2025-05-26 | 2025-05-26 | level | Check level points and allow to start plaster work |  | Grid N-Q/20-21 | A | 2025-05-30
| Sub Structure | 9th floor | LT-1-437 | 2025-05-05 | 2025-05-05 | formwork | Check vertical band formworkand allow to start concrete work | (+107.0) | Grid H-K/19, L-M | A | 2025-05-05
| Sub Structure | 10th floor | LT-1-438 | 2025-05-09 | 2025-05-09 | layout | Check layout and allow to start brick work on internal sides | (+118.0) | Grid G-N/20-23 | A | 2025-05-10
| Sub Structure | 9th floor | LT-1-439 | 2025-05-07 | 2025-05-08 | formwork | Check vertical band formwork and allow to start concrete work | (+107.0) | Grid M-P/26 | A | 2025-05-10
| Sub Structure | 9th floor | LT-1-440 | 2025-05-05 | 2025-05-05 | formwork | Check leftover slab formwrok and allow to start concrete work | (+107.0) | Grid N/16-17 | A | 2025-05-05
| Sub Structure | 9th floor | LT-1-441 | 2025-05-05 | 2025-05-05 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+107.0) | Grid N/18-19 | A | 2025-05-08
| Sub Structure | 9th floor | LT-1-442 | 2025-05-05 | 2025-05-05 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+107.0) | Grid N/16-17 | A | 2025-05-06
| Sub Structure | 9th floor | LT-1-443 | 2025-05-06 | 2025-05-06 | formwork | Check vertical band formwork and allow to start concrete work | (+107.0) | Grid N/18-19 | A | 2025-05-06
| Sub Structure | 9th floor | LT-1-444 | 2025-05-06 | 2025-05-06 | formwork | Check vertical band formwork and allow to start concrete work | (+107.0) | Grid N/16-17 | A | 2025-05-06
| Sub Structure | 2nd floor | LT-1-445
| Sub Structure | 10th floor | LT-1-446 | 2025-05-06 | 2025-05-06 | formwork | Check leftover slab formwork and allow to start concrete work | (+118.0) | Grid H-K, L-M/19 | A | 2025-05-06
| Sub Structure | 10th floor | LT-1-447 | 2025-05-07 | 2025-05-07 | formwrok | Check leftover slab formwork and allow to start concrete work | (+118.0) | Grid K-L/26 | A | 2025-05-06
| Sub Structure | Top floor | LT-1-448 | 2025-05-07 | 2025-05-07 | formwork | Check water tank formwork and FSS tank wall |  | Grid N-R/18-20 | A | 2025-05-09
| Sub Structure | 8th floor | LT-1-449 | 2025-05-07 | 2025-05-07 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+96.0) | Grid G-H, K-L/19 | A | 2025-05-09
| Sub Structure | 10th floor | LT-1-450 | 2025-05-07 | 2025-05-07 | formwork | Check leftover slab formwork and allow to start concrete work | (+118.0) | Grid N/16-19 | A | 2025-05-09
| Sub Structure | 10th floor | LT-1-451 | 2025-05-07 | 2025-05-07 | formwrok | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid H-K, L-M/19 | A | 2025-05-09
| Sub Structure | 10th floor | LT-1-452 | 2025-05-07 | 2025-05-07 | reinforcement | check vertical band rienforcement and allow to start formwork | (+118.0) | Grid H-K, L-M/19 | A | 2025-05-07
| Sub Structure | 10th floor | LT-1-453 | 2025-05-08 | 2025-05-08 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+118.0) | Grid N/16-19 | A | 2025-05-08
| Sub Structure | 10th floor | LT-1-454 | 2025-05-08 | 2025-05-09 | formwrok | Check vertical band formwrok and allow to start concrete work | (+118.0) | Grid N16-19 | A | 2025-05-09
| Sub Structure | 9th floor | LT-1-455 | 2025-05-08 | 2025-05-08 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+107.0) | Grid R-T/26 | A | 2025-05-09
| Sub Structure | 9th floor | LT-1-456 | 2025-05-08 | 2025-05-09 | formwork | Check vertical band formwrok and allow to start concrete work | (+107.0) | Grid R-T/26 | A | 2025-05-09
| Sub Structure | 11th floor | LT-1-457 | 2025-05-09 | 2025-05-09 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid H-K, L-M/19 | A | 2025-05-09
| Sub Structure | 10th floor | LT-1-458 | 2025-05-09 | 2025-05-09 | formwork | Check leftover slab formwork and allow to start concrete work | (+118.0) | Grid M-P/26 | A | 2025-05-09
| Sub Structure | 11th floor | LT-1-459 | 2025-05-09 | 2025-05-09 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+131.0) | Grid H-K, L-M/19 | A | 2025-05-10
| Sub Structure | 11th floor | LT-1-460 | 2025-05-10 | 2025-05-10 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid N/16-19 | A | 2025-05-12
| Sub Structure | 11th floor | LT-1-461 | 2025-05-10 | 2025-05-10 | formwork | check vertical band formwork and allow to start concrete work | (+131.0) | Grid H-K, L-M/19 | A | 2025-05-10
| Sub Structure | Top floor | LT-1-462 | 2025-05-10 | 2025-05-10 | formwork | Check over head water tank and fss tank slab formwork |  | Grid N-R/18-20 | A | 2025-05-14
| Sub Structure | 11th floor | LT-1-463 | 2025-05-10 | 2025-05-10 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+131.0) | Grid N/16-19 | A | 2025-05-12
| Sub Structure | 11th floor | LT-1-464 | 2025-05-10 | 2025-05-10 | formwork | Check vertical band formwork and allow to start concrete work | (+131.0) | Grid N/16-19 | A | 2025-05-12
| Sub Structure | 10th floor | LT-1-465 | 2025-05-11 | 2025-05-11 | formwork | check leftover slab formwork and allow to start concrete work | (+118.0) | Grid R-T/26 | A | 2025-05-12
| Sub Structure | 10th floor | LT-1-466 | 2025-05-11 | 2025-05-11 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+118.0) | Grid K-L, M-P/26 | A | 2025-05-12
| Sub Structure | 10th floor | LT-1-467 | 2025-05-11 | 2025-05-11 | formwork | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid K-L/26 | A | 2025-05-12
| Sub Structure | 1st floor | LT-1-468 | 2025-05-15 | 2025-05-15 | level | Check level points and allow to start plaster work |  | Grid M-U/15-24 | R
| Sub Structure | Ground floor | LT-1-469 | 2025-05-13 | 2025-05-13 | formwork | Check stair step formwork |  | Grid M/15-19 | A | 2025-05-13
| Sub Structure | 1st floor | LT-1-470 | 2025-05-15 | 2025-05-15 | level | Check level points and allow to start plaster work on internal side |  | Grid G-U/19-26 | R
| Sub Structure | 11th floor | LT-1-471 | 2025-05-13 | 2025-05-13 | formwork | Check leftover slab formwork and allow to start concrete work |  | Grid K-L/26 | A | 2025-05-13
| Sub Structure | 8th floor | LT-1-472 | 2025-05-13 | 2025-05-13 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+96.0) | Grid N/15-18 | A | 2025-05-13
| Sub Structure | Ground floor | LT-1-473 | 2025-05-13 | 2025-05-13 | formwork | Check stair step formwork |  | Grid L-M/19 | A | 2025-05-13
| Sub Structure | Top floor | LT-1-474 | 2025-05-13 | 2025-05-14 | formwork | Check genset beam formwork | (+146.0) | Grid J-L/24-26 | A | 2025-05-14
| Sub Structure | 10th floor | LT-1-475 | 2025-05-13 | 2025-05-13 | formwork | Check vertical band formwrok and allow to start concrete work | (+118.0) | Grid M-P/26 | A | 2025-05-14
| Sub Structure | 10th floor | LT-1-476 | 2025-05-14 | 2025-05-14 | reinforcement | Check vertical band reinforcement and allow to start formwrok | (+118.0) | Grid R-T/26 | A | 2025-05-14
| Sub Structure | 10th floor | LT-1-477 | 2025-05-14 | 2025-05-14 | formwork | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid R-T/26 | A | 2025-05-14
| Sub Structure | 11th floor | LT-1-478 | 2025-05-14 | 2025-05-14 | reinforcement | check vertical band reinforcement and allow to start formwork | (+131.0) | Grid K-L/26 | A | 2025-05-14
| Sub Structure | 11th floor | LT-1-479 | 2025-05-14 | 2025-05-14 | formwork | Check vertical band formwrk and allow to start concrete work | (+131.0) | Grid K-L/26 | A | 2025-05-15
| Sub Structure | 11th floor | LT-1-480 | 2025-05-14 | 2025-05-14 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid M-P/26 | A | 2025-05-15
| Sub Structure | 11th floor | LT-1-481 | 2025-05-15 | 2025-05-15 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid R-T/26 | A | 2025-05-15
| Sub Structure | 11th floor | LT-1-482 | 2025-05-16 | 2025-05-16 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+131.0) | Grid M-P/26 | A | 2025-05-16
| Sub Structure | 11th floor | LT-1-483 | 2025-05-16 | 2025-05-16 | formwork | Check vertical band formwork and allow to start concrete work | (+131.0) | Grid M-P/26, R-T | A | 2025-05-19
| Sub Structure | 11th floor | LT-1-484 | 2025-05-16 | 2025-05-16 | reinforcement | check vertical band rienforcement and allow to start formwork | (+131.0) | Grid R-T/26 | A | 2025-05-17
| Sub Structure | Top floor | LT-1-485 | 2025-05-17 | 2025-05-17 | reinforcement | Check reinforcement and formwork of leftover slab and horizontal band allow concrete |  | Grid H-M/19 | A | 2025-05-19
| Sub Structure | 11th floor | LT-1-486 | 2025-05-17 | 2025-05-17 | layout | check layout and allow to start brick work on internal side of building | (+131.0) | Grid G-Q/20-26 | A | 2025-05-21
| Sub Structure | Top floor | LT-1-487 | 2025-05-19 | 2025-05-19 | formwork | check head water tank formwork and FSS tank parapet |  | Grid N-R/18-20 | A | 2025-05-19
| Sub Structure | Ground floor | LT-1-488 | 2025-05-19 | 2025-05-19 | formwork | check stair step formwrok |  | Grid K-L/19 | A | 2025-05-19
| Sub Structure | 1st floor | LT-1-489 | 2025-05-19 | 2025-05-19 | level | Check level points chicken mesh and corner beads, and allow to start plaster work |  | Grid R-U/20-24, K-N/20-23, R-U/15-16 | A | 2025-05-21
| Sub Structure | Top floor | LT-1-490 | 2025-05-21 | 2025-05-21 | reinforcement | check reinforcement and formwork of leftover slab and allow to start concrete |  | Grid N/16-19 | A | 2025-05-22
| Sub Structure | Top floor | LT-1-491 | 2025-05-21 | 2025-05-21 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete |  | Grid H-M/7 | A | 2025-05-22
| Sub Structure | 1st floor | LT-1-492 | 2025-05-22 | 2025-05-22 | level | check level points and chicken mesh, allow to start plaster on internal side zne 4 | (+19.0) | Grid G-R/23 | A | 2025-05-23
| Sub Structure | 10th floor | LT-1-493 | 2025-05-22 | 2025-05-22 | brick work | Check brick work on internal sides of building | (+118.0) | Grid G-U/15-26 | A | 2025-05-13
| Sub Structure | 2nd floor | LT-1-494
| Sub Structure | 1st floor | LT-1-495 | 2025-05-26 | 2025-05-26 | level | check level points, corner beads and chicken mesh and allow to start plaster work | (+19.0) | Grid Q-U/23-26 | A | 2025-05-26
| Sub Structure | Top floor | LT-1-496 | 2025-05-28 | 2025-05-28 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete work |  | Grid K-T/26 | A | 2025-05-29
| Sub Structure | 4th floor | LT-1-497 | 2025-05-28 | 2025-05-28 | level | check level points and chicken mesh and allow to start plaster work |  | Grid N-Q/20-21 | OP
| Sub Structure | 1st floor to top | LT-1-498 | 2025-05-29 | 2025-05-29 | plaster work | check plaster work on external side of façade | (+19.0 to +146.0) | Grid N/15-17 | OP
| Sub Structure | Top floor | LT-1-499 | 2025-05-30 | 2025-05-30 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+146.0) | Grid K-T/26 | A | 2025-06-01
| Sub Structure | 8th floor | LT-1-500 | 2025-06-02 | 2025-06-02 | reinforcement | check reinforcement and formwork of leftover slab band and allow to start concrete | (+96.0) | Grid U/15 | A | 2025-06-02
| Sub Structure | 9th floor | LT-1-501 | 2025-06-03 | 2025-06-03 | formwork | Check leftover slab band formwork and allow to start concrete work | (+107.0) | Grid N/15 | A | 2025-06-03
| Sub Structure |  | LT-1-502 | 2025-06-03 | 2025-06-03 | plaster work | check plaster work on front side external side |  | Grid U/15-26 | OP
| Sub Structure | 1st floor | LT-1-503 | 2025-06-03 | 2025-06-03 | plaster work | check plaster work zone 4 |  | Grid K-U/20-26, N-R/15-17 | A | 2025-06-18
| Sub Structure | 1st floor | LT-1-504 | 2025-06-04 | 2025-06-04 | plaster work | check plaster work zone 5 |  | Grid N-U/20-25 | A | 2025-06-18
| Sub Structure | 1st floor to top | LT-1-505 | 2025-06-04 | 2025-06-04 | plaster work | Check plaster work on external side façade | (+19.0 to +146.0) | Grid H-K/19 | A | 2025-06-19
| Sub Structure | 2nd floor | LT-1-506 | 2025-06-12 | 2025-06-13 | plaster work | check plaster work zone 4 &5 |  | Grid G-U/15-23 | A | 2025-06-19
| Sub Structure | 1st floor | LT-1-507 | 2025-06-16 | 2025-06-16 | level | check level points & chicken mesh and allow to start plaster work |  | Grid Q-S/15 | A | 2025-06-18
| Sub Structure | Top floor | LT-1-508 | 2025-06-17 | 2025-06-18 | plaster work | check plaster work on external side of façade | (+19.0 to +146.0) | Grid N/18-19 | A | 2025-06-18
| Sub Structure | 1st floor to top | LT-1-509 | 2025-06-17 | 2025-06-18 | plaster work | check plaster work on external side of façade | (+19.0 to +146.0) | Grid L-M/19 | A | 2025-06-18
| Sub Structure | 4th floor | LT-1-510 | 2025-06-19 | 2025-06-19 | cleaning work | check cleaning work | (+52.0) | Grid G-U/15-26 | A | 2025-06-27
| Sub Structure | 2nd floor | LT-1-511 | 2025-06-23 | 2025-06-23 | level points | check level points, conrner beads & chicken mesh and allow to start plaster work |  | Grid G-U/15-26 | A | 2025-06-27
| Sub Structure | 2nd floor | LT-1-512 | 2025-06-24 | 2025-06-24 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid J-L/23-26 | A | 2025-06-27
| Sub Structure | 2nd floor | LT-1-513 | 2025-06-25 | 2025-06-25 | level | check level points, corner beads & chickem mesh and allow to start plaster work |  | Grid K-U/17-23 | A | 2025-06-27
| Sub Structure | 2nd floor | LT-1-514
| Sub Structure | 2nd floor | LT-1-515 | 2025-06-26 | 2025-06-26 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | -203 | Grid N-R/17-20 | A | 2025-06-27
| Sub Structure | 2nd floor | LT-1-516 | 2025-06-27 | 2025-06-27 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  |  | A | 2025-06-27
| Sub Structure | 2nd floor | LT-1-517
| Sub Structure | 11th floor | LT-1-518 | 2025-07-02 | 2025-07-02 | layout | Check layout and allow to start brick work on internal sides | (+131.0) | Grid N-U/15-26 | A | 2025-07-08
| Sub Structure | 2nd floor | LT-1-519
| Sub Structure | 2nd floor | LT-1-520
| Sub Structure | 10th floor | LT-1-521 | 2025-08-16 | 2025-08-16 | Tie columns | Check the Complete Additional tie columns work |  |  | A | 2025-08-24
| Sub Structure | 2nd floor | LT-1-522 | 2025-07-07 | 2025-07-07 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | Zone 4,5 | Grid G-U/23, R/15-23 | A | 2025-07-08
| Sub Structure | 1st floor | LT-1-523 | 2025-07-12 | 2025-07-12 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | -301308309 | Grid L-U/22-26,15-17 | OP
| Sub Structure | 3rd floor | LT-1-524 | 2025-07-12 | 2025-07-12 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | (101-104,106) | Grid N-U/15-23 | A | 2025-07-12
| Sub Structure | 3rd floor | LT-1-525 | 2025-07-17 | 2025-07-17 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | (302-307) | Grid N-R/15-17 & G-K/20-23 | A | 2025-07-19
| Sub Structure | Top floor | LT-1-526 | 2025-07-19 | 2025-07-19 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid K-L/26 | R | 2025-07-22
| Sub Structure | 3rd floor | LT-1-527 | 2025-07-19 | 2025-07-19 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid N-R/15-17 & G-K/20-23 | R | 2025-07-22
| Sub Structure | 2nd floor | LT-1-528 | 2025-07-25 | 2025-07-25 | level points | Check level points and allow to start plaster work on façade(vertical band) |  | Grid M-P/26 | A | 2025-07-30
| Sub Structure | 1st floor | LT-1-529 | 2025-07-26 | 2025-07-26 | brick work | Check the complete external block work plaster work at 1st floor |  | Grid G-M/20 | B | 2025-08-12
| Sub Structure | 1st floor | LT-1-529 R1 | 2025-11-24 | 2025-11-24 | brick work | Check the complete external block work plaster work at 1st floor |  | Grid G-M/20 | A | 2025-11-24
| Sub Structure | 2nd floor | LT-1-530 | 2025-07-26 | 2025-07-26 | brick work | Check the complete external block work plaster work at 1st floor to 11th floor |  | Grid N/15-20 | B | 2025-08-12
| Sub Structure | 2nd floor | LT-1-530 R01 | 2025-11-20 | 2025-11-20 | brick work | Check the complete external block work plaster work at 1st floor to 11th floor |  | Grid N/15-20 | A | 2025-11-22
| Sub Structure | 2nd floor | LT-1-531 | 2025-07-26 | 2025-07-26 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid J-M/20-26 | A | 2025-07-30
| Sub Structure | 2nd floor | LT-1-532 | 2025-07-28 | 2025-07-28 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid L-M/26 | A | 2025-07-30
| Sub Structure | 11th floor | LT-1-533 | 2025-07-30 | 2025-07-30 | brick work | Check 75% brick masonary work on internal sides of building |  | Grid G-U/15-26 | A | 2025-07-31
|  | 11th floor | LT-1-533 R01 | 2025-09-11 | 2025-09-11 | brick work | Check Complete brick masonary work on internal sides of building |  | Grid G-U/15-26 | R | 2025-09-13
| Sub Structure | 1st floor | LT-1-534 | 2025-07-30 | 2025-07-30 | plaster work | Check complete Plaster work at first floor PWD/LND & Bath rooms |  | Grid G-U/15-26 | A | 2025-08-12
| Sub Structure | 2nd floor | LT-1-535 | 2025-07-30 | 2025-07-30 | plaster work | Check complete Plaster work at 2nd floor (bed rooms & Living room) |  | Grid G-U/18-26 | A | 2025-08-12
| Sub Structure | 3rd floor | LT-1-536 | 2025-07-30 | 2025-07-30 | plaster work | Check complete Plaster work at 2nd floor (bed rooms & Living room) |  | Grid G-U/19-26 | A | 2025-08-12
| Sub Structure | 3rd floor | LT-1-537 | 2025-07-30 | 2025-07-30 | plaster work | Check complete Plaster work at 2nd floor (bed rooms & Living room) |  | Grid Q-U/15-24 | A | 2025-08-12
| Sub Structure | 3rd floor | LT-1-538 | 2025-07-30 | 2025-07-30 | plaster work | Check complete Plaster work of Corridor |  | Grid R/15 , G-R/23 | A | 2025-08-12
| Sub Structure | 1st to 11 floor | LT-1-539 | 2025-08-02 | 2025-08-02 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-K/26 | R
|  |  | LT-1-539 R01 | 2025-08-05 | 2025-08-05 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-K/26 | A | 2025-09-01
| Sub Structure | 2nd floor | LT-1-540 | 2025-08-04 | 2025-08-04 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-U/20-26 | R
| Sub Structure | 1st to 11 floor | LT-1-541 | 2025-08-04 | 2025-08-04 | plaster work | Check the complete façade Vertical band Plaster work |  | Grid K-L/26 | R
|  | 1st to 11 floor | LT-1-541 R01 | 2025-08-07 | 2025-08-07 | plaster work | Check the complete façade Vertical band Plaster work |  | Grid K-L/26 | A | 2025-09-01
| Sub Structure | 1st to 11 floor | LT-1-542 | 2025-08-06 | 2025-08-06 | plaster work | Check the complete façade Vertical band Plaster work |  | Grid M-P/26 | A | 2025-08-08
| Sub Structure | Top floor | LT-1-543 | 2025-08-08 | 2025-08-08 | brick work | Check the complete brickwork internal side of horizental band |  | Grid K-R/26 | A | 2025-08-12
| Sub Structure | Top floor | LT-1-544 | 2025-08-08 | 2025-08-08 | brick work | Check the complete brickwork internal side of horizental band |  | Grid H-M/19 | A | 2025-08-12
| Sub Structure | Top floor | LT-1-545 | 2025-08-08 | 2025-08-08 | plaster work | Check the complete plasterwork at internal side of horizental band |  | Grid K-T/26 | R | 2025-08-12
| Sub Structure | Top floor | LT-1-546 | 2025-08-08 | 2025-08-08 | plaster work | Check the complete plasterwork at internal side of horizental band |  | Grid H-M/19 | A | 2025-08-12
| Sub Structure | 1st to top floor | LT-1-547 | 2025-08-11 | 2025-08-11 | Level | Check level Points and allow to start plaster work on façade (vertical band ) |  | Grid R-T/26 | A | 2025-08-12
| Sub Structure | 2nd floor | LT-1-548 | 2025-08-12 | 2025-08-12 | Level | Check level Points and allow to start screed flooring |  | Grid M-U/17-24 | A | 2025-08-15
| Sub Structure | 2nd floor | LT-1-549 | 2025-08-13 | 2025-08-13 | Level | Check level pointsand allow to start plaster work on façade vertical band at FF |  | Grid P-R/26 | R | 2025-08-15
|  |  | LT-1-549 R01 | 2025-08-16 | 2025-08-16 | Level | Check level pointsand allow to start plaster work on façade vertical band at FF |  | Grid P-R/26 | A | 2025-08-16
| Sub Structure | 2nd floor | LT-1-550 | 2025-08-16 | 2025-08-16 | layout | Check layout and allow to start brick masonry |  | Grid G-J/22-26 | A | 2025-09-01
| Sub Structure | 2nd floor | LT-1-551 | 2025-08-18 | 2025-08-18 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid M-U/23-26 | A | 2025-08-23
| Sub Structure | 2nd floor | LT-1-552 | 2025-08-21 | 2025-08-21 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid M-Q/23-26 | R | 2025-08-23
|  |  | LT-1-552 R01 | 2025-09-04 | 2025-09-04 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid M-Q/23-26 | A | 2025-09-05
| Sub Structure | Top floor | LT-1-553 | 2025-08-22 | 2025-08-22 | layout | Check Layout and allow to start brick masnory |  | Grid G-J/23-26 & P-Q/20-22 | A | 2025-08-23
| Sub Structure | 2nd floor | LT-1-554 | 2025-08-23 | 2025-08-23 | plaster work | check the final inspection of bath room & PWR/LND rooms plaster work |  | Grid G-Q/20-26 | B | 2025-08-25
|  | 2nd floor | LT-1-554 R01 | 2025-09-05 | 2025-09-05 | plaster work | check the final inspection of bath room & PWR/LND rooms plaster work |  | Grid G-Q/20-26 | R | 2025-09-05
|  | 2nd floor | LT-1-554 R02 | 2025-09-10 | 2025-09-10 | plaster work | check the final inspection of bath room & PWR/LND rooms plaster work |  | Grid G-Q/20-26 | A | 2025-09-13
| Sub Structure | 2nd floor | LT-1-555 | 2025-08-23 | 2025-08-23 | plaster work | check the final inspection of bath room & PWR/LND rooms plaster work |  | Grid T-U/18-26 | R | 2025-09-05
|  | 2nd floor | LT-1-555 R01 | 2025-09-05 | 2025-09-05 | plaster work | check the final inspection of bath room & PWR/LND rooms plaster work |  | Grid T-U/18-26 | R | 2025-09-05
|  | 2nd floor | LT-1-555 R02 | 2025-09-10 | 2025-09-10 | plaster work | check the final inspection of bath room & PWR/LND rooms plaster work |  | Grid T-U/18-26 | A | 2025-09-13
| Sub Structure | 2nd floor | LT-1-556 | 2025-08-25 | 2025-08-25 | level | Check the level and allow to start screed flooring |  | Grid M-U/15-18,23-26 | A | 2025-08-26
| Sub Structure | 2nd floor | LT-1-557 | 2025-08-26 | 2025-08-26 | level | Check the level and allow to start screed flooring |  | Grid J-Q/23-26 | A | 2025-08-26
| Sub Structure | 2nd floor | LT-1-558 | 2025-08-27 | 2025-08-27 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G/23-26 | R | 2025-08-28
|  | 3rd floor | LT-1-559 | 2025-08-27 | 2025-08-27 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-U/15-26 | R | 2025-09-01
|  | 3rd floor | LT-1-559 R01 | 2025-09-27 | 2025-09-27 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-U/15-26 | A | 2025-09-29
|  | 4th floor | LT-1-560 | 2025-08-27 | 2025-08-27 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid N-R/15-2=18 | A | 2025-09-01
|  |  | LT-1-561 | 2025-08-28 | 2025-08-28 | level | Check the level and allow to start screed flooring |  | Grid N-U/17-20 | A | 2025-09-01
|  |  | LT-1-562 | 2025-08-29 | 2025-08-29 | level | Check the level and allow to start screed flooring |  | Grid N-U/15-18 | A | 2025-09-01
|  | 4th floor | LT-1-563 | 2025-08-29 | 2025-08-29 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid R-U/15-18 | A | 2025-09-01
|  |  | LT-1-564 | 2025-09-02 | 2025-09-02 | level | Check the level and allow to start screed flooring |  | Grid M-U/20-26 | R | 2025-09-02
|  |  | LT-1-564 R01 | 2025-09-03 | 2025-09-03 | level | Check the level and allow to start screed flooring |  | Grid M-U/20-26 | A | 2025-09-04
|  |  | LT-1-565 | 2025-09-01 | 2025-09-01 | level | Check the level and allow to start screed flooring |  | Grid G-N/20-26 | A | 2025-09-02
|  |  | LT-1-566 | 2025-09-02 | 2025-09-02 | level | Check the level and allow to start screed flooring |  | Grid N-U/15-23 | A | 2025-09-04
|  |  | LT-1-567 | 2025-09-03 | 2025-09-03 | level | Check the level and allow to start screed flooring |  | Grid N-U/15-21 | A | 2025-09-04
|  |  | LT-1-568 | 2025-09-03 | 2025-09-03 | level | Check the level of screed flooring |  | Grid G-U/20-26 | A | 2025-09-05
|  | 4th floor | LT-1-569 | 2025-09-03 | 2025-09-03 | level | Check level points, corner beads & chicken mesh |  | Grid R/16-23, K-l/24-26 | R | 2025-09-03
|  | 4th floor | LT-1-569 R01 | 2025-09-04 | 2025-09-04 | level | Check level points, corner beads & chicken mesh |  | Grid R/16-23, K-l/24-26 | A | 2025-09-12
|  | 11th floor | LT-1-570 | 2025-09-04 | 2025-09-04 | plaster work | Check external façade plaster work |  | Grid P-S/15 | R | 2025-09-15
|  | 11th floor | LT-1-570 R01 | 2025-09-17 | 2025-09-17 | plaster work | Check external façade plaster work |  | Grid P-S/15 | A | 2025-09-20 | Asad Butt
|  |  | LT-1-571 | 2025-09-04 | 2025-09-04 | level | Check level points, chicken mesh |  | Grid G/24-26 | A | 2025-09-08 | Pm Sab
|  | 1st floor to top | LT-1-572 | 2025-09-05 | 2025-09-05 | plaster work | Chech complete façade (vertical band) plaster work |  | Grid R-T/26 | B | 2025-09-07 |  |  |  | 2025-09-05
|  | 1st floor to top | LT-1-572 R01 | 2025-09-17 | 2025-09-17 | plaster work | Chech complete façade (vertical band) plaster work |  | Grid R-T/26 | A | 2025-09-18 | Asad BUtt |  |  | 2025-09-05
|  | 2nd floor | LT-1-573 | 2025-09-05 | 2025-09-05 | plaster work | Check the Final inspection of plaster work |  | Grid Q-U/23-26 | B | 2025-09-05
|  | 2nd floor | LT-1-573 R01 | 2025-09-10 | 2025-09-10 | plaster work | Check the Final inspection of plaster work |  | Grid Q-U/23-26 | R | 2025-09-13
|  | 2nd floor | LT-1-573 R02 | 2025-09-17 | 2025-09-17 | plaster work | Check the Final inspection of plaster work |  | Grid Q-U/23-26 | A | 2025-09-18
|  | 2nd floor | LT-1-574 | 2025-09-05 | 2025-09-05 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room |  | Grid N-U/15-18 | R | 2025-09-05
|  | 2nd floor | LT-1-574 R01 | 2025-09-10 | 2025-09-10 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room |  | Grid N-U/15-18 | R | 2025-09-13
|  | 2nd floor | LT-1-574 R02 | 2025-09-17 | 2025-09-17 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room |  | Grid N-U/15-18 | A | 2025-09-17
|  | 2nd floor | LT-1-575 | 2025-09-05 | 2025-09-05 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room |  | Grid N-U/17-20 | R | 2025-09-05
|  | 2nd floor | LT-1-575 R01 | 2025-09-10 | 2025-09-10 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room |  | Grid N-U/17-20 | B | 2025-09-13
|  | 2nd floor | LT-1-575 R02 | 2025-09-17 | 2025-09-17 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room |  | Grid N-U/17-20 | A | 2025-09-20 | Asad Butt
|  | 2nd floor | LT-1-576 | 2025-09-05 | 2025-09-05 | plaster work | Check the Final inspection of plaster work |  | Grid G-K/20-23 | B | 2025-09-05
|  | 2nd floor | LT-1-576 R01 | 2025-09-10 | 2025-09-10 | plaster work | Check the Final inspection of plaster work |  | Grid G-K/20-23 | R | 2025-09-16
|  | 2nd floor | LT-1-576 R02 | 2025-09-17 | 2025-09-17 | plaster work | Check the Final inspection of plaster work |  | Grid G-K/20-23 | A | 2025-09-18
|  |  | LT-1-577 | 2025-09-05 | 2025-09-05 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room |  | Grid N-U/17-20 | A | 2025-09-10
|  | 3rd floor | LT-1-578 | 2025-09-05 | 2025-09-05 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room |  | Grid L-N/20-26 | A | 2025-09-15
|  |  | LT-1-579 | 2025-09-05 | 2025-09-05 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room |  | Grid J-P/23-26 | A | 2025-09-15
|  |  | LT-1-580 | 2025-09-08 | 2025-09-08 | plaster work | Check complete plaster work on External side |  | Grid G-M/26 | B | 2025-09-12 | Bilal sab
|  |  | LT-1-580 R01 | 2025-09-17 | 2025-09-17 | plaster work | Check complete plaster work on External side |  | Grid G-M/26 | A | 2025-09-18 | Bilal sab
|  |  | LT-1-581 | 2025-09-08 | 2025-09-08 | plaster work | Check complete plaster work on External side |  | Grid M-T/26 | A | 2025-09-11 | Bilal sab
|  |  | LT-1-582 | 2025-09-09 | 2025-09-09 | level | Check the level of screed flooring |  | Grid G-R/20-26 | A | 2025-09-11 | Hassan
|  | 9th floor | LT-1-583 | 2025-09-09 | 2025-09-09 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G/24-26 | A | 2025-09-15
|  | 4th floor | LT-1-584 | 2025-09-09 | 2025-09-09 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid M-Q/23-26 | A | 2025-09-11
|  | 4th floor | LT-1-585 | 2025-09-09 | 2025-09-09 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid R-U/17-24 | OP
|  |  | LT-1-586 | 2025-09-10 | 2025-09-10 | level | Check the level of screed flooring |  | Grid M-U/20-26, R/15-23 | A | 2025-09-10
|  |  | LT-1-587 | 2025-09-10 | 2025-09-10 | level | Check the level of screed flooring |  | Grid R-U/12-24 | R | 2025-09-13
|  |  | LT-1-587 R01 | 2025-09-15 | 2025-09-15 | level | Check the level of screed flooring |  | Grid R-U/12-24 | A | 2025-09-17
|  |  | LT-1-588 | 2025-09-10 | 2025-09-10 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid N-R/12-17 | R | 2025-09-13
|  |  | LT-1-588 R01 | 2025-09-15 | 2025-09-15 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid N-R/12-17 | B | 2025-09-17
|  |  | LT-1-588 R02 | 2025-09-18 | 2025-09-18 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid N-R/12-17 | A | 2025-09-20
|  |  | LT-1-589 | 2025-09-11 | 2025-09-11 | Tie columns | Check Tie Columns work 11th floor |  |  | B | 2025-09-11
|  | 5th floor | LT-1-590 | 2025-09-11 | 2025-09-11 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid R-U/12-17 | R | 2025-09-13 | Asad Jawed
|  | 5th floor | LT-1-590 R01 | 2025-09-15 | 2025-09-15 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid R-U/12-17 | A | 2025-09-17
|  | 6th floor | LT-1-591 | 2025-09-12 | 2025-09-12 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid M-U/13-24 | R | 2025-09-13 | Waseem
|  | 6th floor | LT-1-591 R01 | 2025-09-15 | 2025-09-15 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid M-U/13-24 | B | 2025-09-17 | Waseem
|  | 6th floor | LT-1-591 R02 | 2025-09-18 | 2025-09-18 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid M-U/13-24 | A | 2025-09-20 | Waseem
|  |  | LT-1-592 | 2025-09-13 | 2025-09-13 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid R/15-23 | R | 2025-09-15 | Waseem
|  |  | LT-1-592 R01 | 2025-09-17 | 2025-09-17 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid R/15-23 | A | 2025-09-20 | Waseem
|  |  | LT-1-593 | 2025-09-15 | 2025-09-15 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid N-U/15 | A | 2025-09-17
|  |  | LT-1-594 | 2025-09-16 | 2025-09-16 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid Q-U/26-26 | A | 2025-09-17 | Waseem
|  |  | LT-1-595 | 2025-09-16 | 2025-09-16 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G/24-26 | A | 2025-09-17 | Waseem
|  |  | LT-1-596 | 2025-09-16 | 2025-09-16 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-Q/19-26 | A | 2025-09-18
|  |  | LT-1-597 | 2025-09-17 | 2025-09-17 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid M-U/17-20 | R | 2025-09-19 | Waseem
|  |  | LT-1-598 | 2025-09-17 | 2025-09-17 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid R-U/20-26 | A | 2025-09-20 | Waseem
|  |  | LT-1-599 | 2025-09-17 | 2025-09-17 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid K-Q/20-26 | A | 2025-09-20 | Waseem
|  |  | LT-1-600 | 2025-09-17 | 2025-09-17 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-R/22-24 | A | 2025-09-20 | Waseem
|  |  | LT-1-601 | 2025-09-17 | 2025-09-17 | plaster work | Check Complete Plaster work on external side |  | Grid T-U/26 | R | 2025-09-18
|  |  | LT-1-601 R1 | 2025-09-26 | 2025-09-26 | plaster work | Check Complete Plaster work on external side |  | Grid T-U/26 | A | 2025-09-29
|  |  | LT-1-602 | 2025-09-17 | 2025-09-17 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G/24-26 | A | 2025-09-20
|  |  | LT-1-603 | 2025-09-18 | 2025-09-18 | level | Check the level of screed flooring |  | Grid M-R/15-24 | A | 2025-09-25
|  |  | LT-1-604 | 2025-09-18 | 2025-09-18 | level | Check the level of screed flooring |  | Grid L-U/24-26 | A | 2025-09-25
|  |  | LT-1-605 | 2025-09-19 | 2025-09-19 | level | Check the level of screed flooring |  | Grid G-N/19-26 | A | 2025-09-20
|  |  | LT-1-606 | 2025-09-19 | 2025-09-19 | level | Check the level of screed flooring |  | Grid J-M/23-26 | A | 2025-09-24
|  |  | LT-1-607 | 2025-09-22 | 2025-09-22 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 403 | A | 2025-09-24
|  |  | LT-1-608 | 2025-09-22 | 2025-09-22 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 407, 408 | A | 2025-09-24
|  |  | LT-1-609 | 2025-09-22 | 2025-09-22 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G/24-26 | A | 2025-09-23
|  |  | LT-1-610 | 2025-09-23 | 2025-09-23 | plaster work | Check Complete Plaster work on external side |  | Grid G/24-26 | A | 2025-09-23
|  |  | LT-1-611 | 2025-09-23 | 2025-09-23 | Level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 507510 | A | 2025-09-24
|  |  | LT-1-612 | 2025-09-24 | 2025-09-24 | level | Kindly check the level points & chicken mesh and allow to start plaster work at Electrical & Store room at 5th Floor (level +63.00) of L1-Tower |  | 5th Floor
|  |  | LT-1-613 | 2025-09-24 | 2025-09-24 | level | Kindly check the level points & chicken mesh and allow to start plaster work at Electrical & Store room at 4th Floor (level +52.00) of L1-Tower |  | 4th floor
|  |  | LT-1-614 | 2025-09-26 | 2025-09-26 | plaster work | Kindly check the plaster work at Apartment No.401 ( Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | R | 2025-10-02
|  |  | LT-1-614 R01 | 2025-10-22 | 2025-10-22 | plaster work | Kindly check the plaster work at Apartment No.401 ( Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-23
|  |  | LT-1-615 | 2025-09-26 | 2025-09-26 | plaster work | Kindly check the plaster work at Apartment No.402( Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | R | 2025-10-02
|  |  | LT-1-615 R01 | 2025-10-07 | 2025-10-07 | plaster work | Kindly check the plaster work at Apartment No.402( Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-09
|  |  | LT-1-615 R02 | 2025-10-22 | 2025-10-22 | plaster work | Kindly check the plaster work at Apartment No.402( Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-23
|  |  | LT-1-616 | 2025-09-26 | 2025-09-26 | plaster work | Kindly check the plaster work at Apartment No.404( Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | R | 2025-10-02
|  |  | LT-1-616 R01 | 2025-10-07 | 2025-10-07 | plaster work | Kindly check the plaster work at Apartment No.404( Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | OP
|  |  | LT-1-616 R02 | 2025-10-22 | 2025-10-22 | plaster work | Kindly check the plaster work at Apartment No.404( Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-23
|  |  | LT-1-617 | 2025-09-26 | 2025-09-26 | plaster work | Kindly check the plaster work at Apartment No.406(Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | R | 2025-10-02
|  |  | LT-1-617 R01 | 2025-10-07 | 2025-10-07 | plaster work | Kindly check the plaster work at Apartment No.406(Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-09
|  |  | LT-1-617 R02 | 2025-10-22 | 2025-10-22 | plaster work | Kindly check the plaster work at Apartment No.406(Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-23
|  |  | LT-1-618 | 2025-09-26 | 2025-09-26 | plaster work | Kindly check the plaster work at Apartment No.409 (Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | R | 2025-10-02
|  |  | LT-1-618 R01 | 2025-10-07 | 2025-10-07 | plaster work | Kindly check the plaster work at Apartment No.409 (Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-09
|  |  | LT-1-618 R02 | 2025-10-22 | 2025-10-22 | plaster work | Kindly check the plaster work at Apartment No.409 (Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-23
|  |  | LT-1-619 | 2025-09-26 | 2025-09-26 | plaster work | Kindly check the plaster work at Apartment No.410 (Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | B | 2025-10-02
|  |  | LT-1-619 R01 | 2025-10-07 | 2025-10-07 | plaster work | Kindly check the plaster work at Apartment No.410 (Except Bath & PWR/LND Rooms) on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-10
|  |  | LT-1-620 | 2025-09-26 | 2025-09-26 | plaster work | Kindly check the plaster work at zone#4 corridor on 4th floor of L1-Tower |  | 4th floor | R | 2025-10-02
|  |  | LT-1-620 R01 | 2025-10-07 | 2025-10-07 | plaster work | Kindly check the plaster work at zone#4 corridor on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-10
|  |  | LT-1-621 | 2025-09-26 | 2025-09-26 | plaster work | Kindly check the plaster work at zone#5 corridor on 4th floor of L1-Tower |  | 4th floor | R | 2025-10-02
|  |  | LT-1-621 R01 | 2025-10-07 | 2025-10-07 | plaster work | Kindly check the plaster work at zone#5 corridor on 4th floor of L1-Tower |  | 4th floor | A | 2025-10-10
|  |  | LT-1-622 | 2025-09-26 | 2025-09-26 | plaster work | Kindly check the complete plaster work on external side Top Floor to Ground Floor (Face to I-Tower) of L1-Tower |  | top roof to gf
|  |  | LT-1-623 | 2025-09-29 | 2025-09-29 | level | Kindly check the levels points, Chicken mesh & corner beads and allow to start plaster work at Apartment No. 601,602 on the 6th floor of L1-Tower |  | 6th Floor | A | 2025-10-02
|  |  | LT-1-624 | 2025-09-30 | 2025-09-30 | level | Kindly check the levels of screed flooring in Apartment No. #602,#604 & #606 at 6th floor of L1-Tower |  | 6th Floor | A | 2025-10-02
|  |  | LT-1-625 | 2025-09-29 | 2025-09-29 | level | Kindly check the levels of screed flooring in Apartment No. #601,#603,#608 & #609 and corridor Zone 5 at 6th floor of L1-Tower |  | 6th Floor | A | 2025-10-02
|  |  | LT-1-626 | 2025-09-29 | 2025-09-29 | level | Check the level of screed flooring |  | 605, 607 , 610 | A | 2025-09-30
|  |  | LT-1-627 | 2025-09-30 | 2025-09-30 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 604 | R | 2025-10-02
|  |  | LT-1-627 R01 | 2025-10-08 | 2025-10-08 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 604 | A | 2025-10-10
|  |  | LT-1-628 | 2025-09-30 | 2025-09-30 | level | Check the level of screed flooring |  | 701-704, 706 | A | 2025-10-02
|  |  | LT-1-629 | 2025-10-01 | 2025-10-01 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 603 | A | 2025-10-10
|  |  | LT-1-630 | 2025-10-02 | 2025-10-02 | level | Check the level of screed flooring |  | 605, 607, 610 | A | 2025-10-07
|  |  | LT-1-631 | 2025-10-02 | 2025-10-02 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 606, 608 | A | 2025-10-02
|  |  | LT-1-632 | 2025-10-02 | 2025-10-02 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 601-604 | A | 2025-10-02
|  |  | LT-1-633 | 2025-10-02 | 2025-10-02 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 501 | B | 2025-10-07
|  |  | LT-1-633 R01 | 2025-10-08 | 2025-10-08 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 501 | A | 2025-10-09
|  |  | LT-1-633 R02 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 501 | A | 2025-10-23
|  |  | LT-1-634 | 2025-10-02 | 2025-10-02 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 502 | R | 2025-10-07
|  |  | LT-1-634 R1 | 2025-10-08 | 2025-10-08 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 502 | A | 2025-10-09
|  |  | LT-1-634 R2 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 502 | A | 2025-10-23
|  |  | LT-1-635 | 2025-10-02 | 2025-10-02 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 504 | B | 2025-10-07
|  |  | LT-1-635 R01 | 2025-10-08 | 2025-10-08 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 504 | A | 2025-10-09
|  |  | LT-1-635 R02 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 504 | A | 2025-10-23
|  |  | LT-1-636 | 2025-10-02 | 2025-10-02 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 503 | R | 2025-10-07
|  |  | LT-1-636 R01 | 2025-10-08 | 2025-10-08 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 503 | A | 2025-10-09
|  |  | LT-1-636 R02 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 503 | A | 2025-10-23
|  |  | LT-1-637 | 2025-10-02 | 2025-10-02 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 506 | B | 2025-10-07
|  |  | LT-1-637 R01 | 2025-10-08 | 2025-10-08 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 506 | A | 2025-10-09
|  |  | LT-1-637 R02 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 506 | A | 2025-10-23
|  |  | LT-1-638 | 2025-10-03 | 2025-10-03 | level | Check the level of screed flooring |  | 701-704, 706 | A | 2025-10-07
|  | 4th floor | LT-1-639 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 405 | A | 2025-10-09
|  | 4th floor | LT-1-639 R01 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 405 | A | 2025-10-23
|  |  | LT-1-640 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 407 | A | 2025-10-09
|  |  | LT-1-640 R01 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 407 | A | 2025-10-23
|  |  | LT-1-641 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work |  | 508 | A | 2025-10-09
|  |  | LT-1-641 R01 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work |  | 508 | A | 2025-10-23
|  |  | LT-1-642 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work |  | 509 | A | 2025-10-09
|  |  | LT-1-642 R01 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work |  | 509 | A | 2025-10-23
|  |  | LT-1-643 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work |  | 510 | A | 2025-10-09
|  |  | LT-1-643 R01 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work |  | 510 | A | 2025-10-23
|  |  | LT-1-644 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work |  | 507 | A | 2025-10-09
|  |  | LT-1-644 R01 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work |  | 507 | A | 2025-10-23
|  |  | LT-1-645 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work |  | 505 | A | 2025-10-09
|  |  | LT-1-645 R01 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work |  | 505 | A | 2025-10-23
|  | 5th floor | LT-1-646 | 2025-10-07 | 2025-10-07 | plaster work | Check the corridor plaster work |  | Zone 5 | A | 2025-10-10
|  | 5th floor | LT-1-647 | 2025-10-07 | 2025-10-07 | plaster work | Check the corridor plaster work |  | Zone 4 | A | 2025-10-09
|  | 5th floor | LT-1-647 R01 | 2025-10-22 | 2025-10-22 | plaster work | Check the corridor plaster work |  | Zone 4 | A | 2025-10-23
|  | 6th floor | LT-1-648 | 2025-10-07 | 2025-10-07 | plaster work | Check the corridor plaster work |  | Zone 5 | A | 2025-10-09
|  | 6th floor | LT-1-648 R01 | 2025-10-22 | 2025-10-22 | plaster work | Check the corridor plaster work |  | Zone 5 | A | 2025-10-23
|  | 6th floor | LT-1-649 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 601 | A | 2025-10-10
|  | 6th floor | LT-1-650 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 602 | A | 2025-10-10
|  | 6th floor | LT-1-651 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 603 | A | 2025-10-10
|  | 6th floor | LT-1-652 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 604 | A | 2025-10-10
|  | 6th floor | LT-1-653 | 2025-10-07 | 2025-10-07 | plaster work | Check the plaster work Except Bath & PWR/LND |  | 606 | A | 2025-10-10
|  |  | LT-1-654 | 2025-10-07 | 2025-10-07 | plaster work | Check the bath & PWR/LND plaster work |  | 501 | A | 2025-10-10
|  |  | LT-1-655 | 2025-10-07 | 2025-10-07 | plaster work | Check the bath & PWR/LND plaster work |  | 503 | A | 2025-10-10
|  |  | LT-1-656 | 2025-10-07 | 2025-10-07 | plaster work | Check the bath & PWR/LND plaster work |  | 504 | A | 2025-10-10
|  |  | LT-1-657 | 2025-10-07 | 2025-10-07 | plaster work | Check the bath & PWR/LND And electrical room plaster work |  | 506 | A | 2025-10-10
|  |  | LT-1-658 | 2025-10-07 | 2025-10-07 | plaster work | Check the bath & PWR/LND plaster work |  | 304 | A | 2025-10-09
|  |  | LT-1-659 | 2025-10-07 | 2025-10-07 | plaster work | Check the bath & PWR/LND plaster work |  | 306 | A | 2025-10-09
|  |  | LT-1-660 | 2025-10-07 | 2025-10-07 | plaster work | Check the bath & PWR/LND plaster work |  | 303 | A | 2025-10-09
|  |  | LT-1-660 R01 | 2025-10-22 | 2025-10-22 | plaster work | Check the bath & PWR/LND plaster work |  | 303 | A | 2025-10-23
|  |  | LT-1-661 | 2025-10-09 | 2025-10-09 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 6th Floor | A | 2025-10-10
|  |  | LT-1-662 | 2025-10-09 | 2025-10-09 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 2nd Floor | A | 2025-10-09
|  |  | LT-1-663 | 2025-10-09 | 2025-10-09 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 3rd floor | A | 2025-10-09
|  |  | LT-1-664 | 2025-10-09 | 2025-10-09 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 1st floor | A | 2025-10-11 | Asad Butt
|  |  | LT-1-665 | 2025-10-10 | 2025-10-10 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 4th floor Zone 4 | R | 2025-10-11 | M.Waseem
|  |  | LT-1-665 R01 | 2025-10-14 | 2025-10-14 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 4th floor Zone 4 | A | 2025-10-15
|  |  | LT-1-666 | 2025-10-10 | 2025-10-10 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 6th Floor | R | 2025-10-11 | M.Waseem
|  |  | LT-1-667 | 2025-10-11 | 2025-10-11 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 6th Floor | A | 2025-10-11 | M.Waseem
|  |  | LT-1-668 | 2025-10-15 | 2025-10-15 | level | Check the level of screed flooring |  | 705, 707-710 | A | 2025-10-16
|  |  | LT-1-669 | 2025-10-18 | 2025-10-18 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 110 | A | 2025-10-21
|  |  | LT-1-670 | 2025-10-19 | 2025-10-19 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 401-406 | R | 2025-10-20
|  |  | LT-1-671 | 2025-10-21 | 2025-10-21 | brick work | Check the complete brick masonry on internal side of façade |  | 10th floor | B | 2025-10-23
|  |  | LT-1-671 R01 | 2025-11-03 | 2025-11-03 | brick work | Check the complete brick masonry on internal side of façade |  | 10th floor | A | 2025-11-04
|  |  | LT-1-672 | 2025-10-21 | 2025-10-21 | brick work | Check the complete brick masonry on internal side of façade |  | 9th floor | B | 2025-10-23
|  |  | LT-1-672 R01 | 2025-11-03 | 2025-11-03 | brick work | Check the complete brick masonry on internal side of façade |  | 9th floor | A | 2025-11-04
|  |  | LT-1-673 | 2025-10-23 | 2025-10-23 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 701-702 | R | 2025-10-24
|  |  | LT-1-674 | 2025-10-25 | 2025-10-25 | level | Check the level of screed flooring |  | 301-304 | A | 2025-10-29
|  |  | LT-1-675 | 2025-10-27 | 2025-10-27 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 710 | A | 2025-10-29
|  |  | LT-1-676 | 2025-10-29 | 2025-10-29 | plaster work | Check the plaster work |  | 403 | R | 2025-11-01
|  |  | LT-1-676 R01 | 2025-11-26 | 2025-11-26 | plaster work | Check the plaster work |  | 403 | OP
|  |  | LT-1-677 | 2025-10-29 | 2025-10-29 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 702-, 704 | R | 2025-11-01
|  |  | LT-1-677 R01 | 2025-11-03 | 2025-11-03 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 702-, 704 | A | 2025-11-04
|  |  | LT-1-678 | 2025-10-29 | 2025-10-29 | plaster work | Check the bath & PWR/LND plaster work |  | 401 | R | 2025-11-01
|  |  | LT-1-678 R01 | 2025-11-26 | 2025-11-26 | plaster work | Check the bath & PWR/LND plaster work |  | 401 | OP
|  |  | LT-1-679 | 2025-10-29 | 2025-10-29 | plaster work | Check the bath & PWR/LND plaster work |  | 402 | A | 2025-11-01
|  |  | LT-1-680 | 2025-10-29 | 2025-10-29 | plaster work | Check the bath & PWR/LND plaster work |  | 404 | A | 2025-11-01
|  |  | LT-1-681 | 2025-10-29 | 2025-10-29 | plaster work | Check the bath & PWR/LND plaster work |  | 406 | A | 2025-11-01
|  |  | LT-1-682 | 2025-10-30 | 2025-10-30 | plaster work | Check the plaster work |  | 110 | A | 2025-11-01 |  |  |  | 2025-10-30
|  |  | LT-1-683 | 2025-10-30 | 2025-10-30 | Corner Beads | Check the corner beads on all apartments except 106 |  | 1st floor | A | 2025-12-18
|  |  | LT-1-684 | 2025-10-30 | 2025-10-30 | Corner Beads | Check the corner beads on all apartments |  | 3rd floor | A | 2025-12-18
|  |  | LT-1-685 | 2025-10-30 | 2025-10-30 | plaster work | Check the bath & PWR/LND plaster work |  | 308 | A | 2025-11-01
|  |  | LT-1-686 | 2025-10-30 | 2025-10-30 | plaster work | Check the bath & PWR/LND plaster work |  | 301 | R | 2025-11-01
|  |  | LT-1-686 R01 | 2025-11-18 | 2025-11-18 | plaster work | Check the bath & PWR/LND plaster work |  | 301 | A | 2025-11-19
|  |  | LT-1-687 | 2025-10-30 | 2025-10-30 | plaster work | Check the bath & PWR/LND plaster work |  | 302 | R | 2025-11-01
|  |  | LT-1-687 R01 | 2025-11-18 | 2025-11-18 | plaster work | Check the bath & PWR/LND plaster work |  | 302 | A | 2025-11-19
|  |  | LT-1-688 | 2025-10-30 | 2025-10-30 | plaster work | Check the plasater work |  | 408 | A | 2025-11-01
|  |  | LT-1-689 | 2025-10-30 | 2025-10-30 | plaster work | Check the bath & PWR/LND plaster work |  | 405 | A | 2025-11-01
|  |  | LT-1-690 | 2025-10-30 | 2025-10-30 | plaster work | Check the bath & PWR/LND plaster work |  | 407 | A | 2025-11-01
|  |  | LT-1-691 | 2025-10-30 | 2025-10-30 | plaster work | Check the bath & PWR/LND plaster work |  | 409 | A | 2025-11-01
|  |  | LT-1-692 | 2025-10-30 | 2025-10-30 | plaster work | Check the bath & PWR/LND plaster work |  | 410 | A | 2025-11-01
|  |  | LT-1-693 | 2025-10-30 | 2025-10-30 | plaster work | Check the bath & PWR/LND plaster work |  | 502 | R | 2025-11-01
|  |  | LT-1-694 | 2025-10-30 | 2025-10-30 | level | Check the level of screed flooring |  | 305,307-310, Corridor | A | 2025-11-01
|  |  | LT-1-695 | 2025-10-31 | 2025-10-31 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  |  | R | 2025-11-01
|  |  | LT-1-695 R01 | 2025-11-03 | 2025-11-03 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  |  | A | 2025-11-04
|  |  | LT-1-696 | 2025-11-01 | 2025-11-01 | plaster work | Check the plaster work |  | 605 | A | 2025-11-04
|  |  | LT-1-697 | 2025-11-01 | 2025-11-01 | plaster work | Check the plaster work |  | 607 | A | 2025-11-04
|  |  | LT-1-697 R01 | 2025-11-10 | 2025-11-10 | plaster work | Check the plaster work |  | 607 | A | 2025-11-11
|  |  | LT-1-698 | 2025-11-01 | 2025-11-01 | plaster work | Check the plaster work |  | 608 | A | 2025-11-04
|  |  | LT-1-699 | 2025-11-03 | 2025-11-03 | level | Check the level of screed flooring |  | 705-710 | A | 2025-11-04
|  |  | LT-1-700 | 2025-11-04 | 2025-11-04 |  |  |  |  | A | 2025-11-06
|  |  | LT-1-701 | 2025-11-04 | 2025-11-04 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 706708709 | A | 2025-11-05
|  |  | LT-1-702 | 2025-11-05 | 2025-11-05 | plaster work | Check the plaster work |  | 609 | A | 2025-11-07
|  |  | LT-1-703 | 2025-11-05 | 2025-11-05 | plaster work | Check the plaster work |  | 610 | A | 2025-11-07
|  |  | LT-1-704 | 2025-11-05 | 2025-11-05 | level | Check the level of screed flooring |  | 801-804,8006 | A | 2025-11-06
|  |  | LT-1-705 | 2025-11-06 | 2025-11-06 | plaster work | Check the plaster work (bath, PWd/LND) |  | 601 | A | 2025-11-07 |  |  |  | 2025-11-06
|  |  | LT-1-706 | 2025-11-06 | 2025-11-06 | plaster work | Check the plaster work (bath, PWd/LND) |  | 602 | A | 2025-11-07
|  |  | LT-1-707 | 2025-11-06 | 2025-11-06 | plaster work | Check the plaster work (bath, PWd/LND) |  | 603 | A | 2025-11-07
|  |  | LT-1-708 | 2025-11-06 | 2025-11-06 | plaster work | Check the plaster work at stair area |  | basement to 1st floor | A | 2025-12-18
|  |  | LT-1-709 | 2025-11-06 | 2025-11-06 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 7th floor | A | 2025-11-07
|  |  | LT-1-710 | 2025-11-06 | 2025-11-06 | plaster work | Check the plaster work (bath, PWd/LND) |  | 604 | A | 2025-11-07
|  |  | LT-1-711 | 2025-11-06 | 2025-11-06 | plaster work | Check the plaster work (bath, PWd/LND) |  | 606 | A | 2025-11-07
|  |  | LT-1-712 | 2025-11-07 | 2025-11-07 | plaster work | Check the plaster work at corridor zone 4 |  | 6th floor | A | 2025-11-10
|  |  | LT-1-713 | 2025-11-07 | 2025-11-07 | level | Check the level of screed flooring |  | 305-310 | A | 2025-11-11
|  |  | LT-1-714 | 2025-11-08 | 2025-11-08 | level | Check the level of screed flooring |  | 805,807-810 | A | 2025-11-11
|  |  | LT-1-715 | 2025-11-10 | 2025-11-10 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 807, 810 | A | 2025-11-11
|  |  | LT-1-716 | 2025-11-10 | 2025-11-10 | level | Check the level points and allow to start plaster work |  | 5th floor to 4th | A | 2025-11-11
|  |  | LT-1-717 | 2025-11-10 | 2025-11-10 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 701, 702 | A | 2025-11-11
|  |  | LT-1-718 | 2025-11-12 | 2025-11-12 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 805 & 809 | A | 2025-11-14
|  |  | LT-1-719 | 2025-11-12 | 2025-11-12 | level | Check level points and allow to start plaster work at stair case area |  | 6th to 5th | A | 2025-11-14
|  |  | LT-1-720 | 2025-11-13 | 2025-11-13 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 801-806 | A | 2025-11-14
|  |  | LT-1-721 | 2025-11-14 | 2025-11-14 | level | Check level points and allow to start plaster work at stair case area |  | 11th floor to 9th floor | A | 2025-11-19
|  |  | LT-1-722 | 2025-11-15 | 2025-11-15 | level | Check the level points for screed flooring |  | corridor zone 5 | A | 2025-11-18
|  |  | LT-1-723 | 2025-11-20 | 2025-11-20 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 801-806 | A | 2025-11-24
|  |  | LT-1-724 | 2025-11-20 | 2025-11-20 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 205207208209210 | A | 2025-11-21
|  |  | LT-1-725 | 2025-11-23 | 2025-11-23 | Level | Check the level points & Chicken mesh and allow to start plaster work |  | 8th floor Corridor | A | 2025-11-25
|  |  | LT-1-726 | 2025-11-24 | 2025-11-24 | plaster work | Check the plaster work |  | 701 | A | 2025-11-25
|  |  | LT-1-727 | 2025-11-24 | 2025-11-24 | plaster work | Check the plaster work |  | 702 | A | 2025-11-25
LT-1-728
|  |  | LT-1-729 | 2025-11-25 | 2025-11-25 | plaster work | Check the plaster work |  | 704 | OP
|  |  | LT-1-730 | 2025-11-25 | 2025-11-25 | plaster work | Check the plaster work |  | 706 | OP
|  |  | LT-1-731 | 2025-11-26 | 2025-11-26 | level | Check the level points for screed flooring |  | 901-906 | OP
|  |  | LT-1-732 | 2025-11-26 | 2025-11-26 | plaster work | Check the plaster work |  | 707
|  |  | LT-1-733 | 2025-11-26 | 2025-11-26 | plaster work | Check the plaster work |  | 710
|  |  | LT-1-734 | 2025-11-27 | 2025-11-27 | level | Check the level points ,chicken mesh and allow to start façade plaster work |  | zone 5 9th floor | OP
|  |  | LT-1-735 | 2025-11-27 | 2025-11-27 | level | Check the level points ,chicken mesh and allow to start façade plaster work |  | 9th floor Zone 4 | OP
|  |  | LT-1-736 | 2025-11-27 | 2025-11-27 | level | Check the level points ,chicken mesh and allow to start façade plaster work |  | 904,906, 908 | OP
|  |  | LT-1-737 | 2025-12-02 | 2025-12-02 | level | Check level points, & chicken mesh and allow to start plaster work |  | zone 04 & 05 8th floor | A | 2025-12-03
|  |  | LT-1-738 | 2025-12-02 | 2025-12-02 | level | Check level points, & chicken mesh and allow to start plaster work |  | ZONE 5 901,902,903 9TH FLOOR | A | 2025-12-03
|  |  | LT-1-739 | 2025-12-02 | 2025-12-02 | level | Check level points for screed flooring and corridor zone |  | zone 4 905,907,908,909,910 9th floor | A | 2025-12-03
|  |  | LT-1-740 | 2025-12-02 | 2025-12-02 | level | Check level points, & chicken mesh and allow to start plaster work |  | 901,902,903,904,906 CORRIDOR AREA 5 on 9th floor | A | 2025-12-03
|  |  | LT-1-741 | 2025-12-02 | 2025-12-02 | level | Check level points, & chicken mesh and allow to start plaster work |  | 805 8TH FLOOR | A | 2025-12-03
|  |  | LT-1-742 | 2025-12-07 | 2025-12-09 | level | Check level points, & chicken mesh and allow to start plaster work |  | PTH FLOOR 909-910 | A | 2025-12-09
|  |  | LT-1-743 | 2025-12-15 | 2025-12-15 | plaster work | Check the plaster work | 7TH FLOOR | 705 | A | 2025-12-18
|  |  | LT-1-744 | 2025-12-15 | 2025-12-15 | plaster work | Check the plaster work | 7TH FLOOR | 708 | A | 2025-12-18
|  |  | LT-1-745 | 2025-12-15 | 2025-12-15 | plaster work | Check the plaster work | 7TH FLOOR | 709 | A | 2025-12-18
LT-1-746
|  |  | LT-1-747 | 2025-12-09 | 2025-12-10 | plaster work | Check the plaster work |  | 2TH FLOOR TO 5 TH FLOOR
|  |  | LT-1-748 | 2025-12-15 | 2025-12-15 | plaster work | Check the plaster work | 8TH FLOOR | N~Q/20-22 | A | 2025-12-18
|  |  | LT-1-749 | 2025-12-15 | 2025-12-15 | plaster work | Check the plaster work | 9TH TO 11TH FLOOR | N~Q/20-22 | A | 2025-12-18
|  |  | LT-1-750 | 2025-12-15 | 2025-12-15 | level | Check level points, & chicken mesh and allow to start plaster work | 8TH FLOOR | 807-810 | A | 2025-12-18
|  |  | LT-1-751 | 2025-12-09 | 2025-12-10 | level | Check the level points for screed flooring |  | 8TH FLOOR 801-805 | A | 2025-12-10
|  |  | LT-1-752 | 2025-12-09 | 2025-12-10 | level | Check the level points for screed flooring |  | 8TH FLOOR 805-810 | A | 2025-12-10
|  |  | LT-1-753 | 2025-12-11 | 2025-12-11 | level | Check the level points for screed flooring |  | 2ND FLOOR 201-206 | A | 2025-12-12
|  |  | LT-1-754 | 2025-12-11 | 2025-12-11 | level | Check the level points for screed flooring |  | 2ND FLOOR 205-210 | A | 2025-12-12
|  |  | LT-1-755 | 2025-12-15 | 2025-12-15 | level | Check level points, corner bead | 2ND FLOOR | A-112 | A | 2025-12-18
|  |  | LT-1-756 | 2025-12-13 | 2025-12-13 | level | Check the level points for screed flooring |  | 9TH FLOOR 901-906 | A | 2025-12-18
|  |  | LT-1-757 | 2025-12-13 | 2025-12-13 | level | Check level points, & chicken mesh and allow to start plaster work |  | 9th floor 905-908 | A | 2025-12-18
|  |  | LT-1-758 | 2025-12-13 | 2025-12-13 | level | Check the level points for screed flooring |  | 1ST FLOOR 105-106-107-109-110 | A | 2025-12-15
|  |  | LT-1-759 | 2025-12-15 | 2025-12-15 | plaster work | Check the plaster work |  | 7TH FLOOR ZONE 4 | A | 2025-12-18
|  |  | LT-1-760 | 2025-12-15 | 2025-12-15 | plaster work | Check the plaster work |  | 7TH FLOOR ZONE 5 | A | 2025-12-18
|  |  | LT-1-761 | 2025-12-18 | 2025-12-18 | level | Check the level points for screed flooring | 9th floor | 905-907-908-909-910
LT-1-762
LT-1-763
LT-1-764
LT-1-765
LT-1-766
LT-1-767
LT-1-768
LT-1-769
LT-1-770
LT-1-771
LT-1-772
LT-1-773
LT-1-774
LT-1-775
LT-1-776
LT-1-777
LT-1-778
LT-1-779
LT-1-780
LT-1-781
LT-1-782
LT-1-783
LT-1-784
LT-1-785
LT-1-786
LT-1-787
LT-1-788
LT-1-789
LT-1-790
LT-1-791
LT-1-792
LT-1-793
LT-1-794
LT-1-795
LT-1-796
LT-1-797
LT-1-798
LT-1-799
LT-1-800
LT-1-801
LT-1-802
LT-1-803
LT-1-804
LT-1-805
LT-1-806
LT-1-807
LT-1-808
LT-1-809
LT-1-810
LT-1-811
LT-1-812
LT-1-813
LT-1-814
LT-1-815
LT-1-816
LT-1-817
LT-1-818
LT-1-819
LT-1-820
LT-1-821
LT-1-822
LT-1-823
LT-1-824
LT-1-825
LT-1-826
LT-1-827
LT-1-828
LT-1-829
LT-1-830
LT-1-831
LT-1-832
LT-1-833
LT-1-834
LT-1-835
LT-1-836
LT-1-837
LT-1-838
LT-1-839
LT-1-840
LT-1-841
LT-1-842
LT-1-843
LT-1-844
LT-1-845
LT-1-846
LT-1-847
LT-1-848
LT-1-849
LT-1-850
LT-1-851
LT-1-852
LT-1-853
LT-1-854
LT-1-855
LT-1-856
LT-1-857
LT-1-858
LT-1-859
LT-1-860
LT-1-861
LT-1-862
LT-1-863
LT-1-864
LT-1-865
LT-1-866
LT-1-867
LT-1-868
LT-1-869
LT-1-870
LT-1-871
LT-1-872
LT-1-873
LT-1-874
LT-1-875
LT-1-876
LT-1-877
LT-1-878
LT-1-879
LT-1-880
LT-1-881
LT-1-882
LT-1-883
LT-1-884
LT-1-885
LT-1-886
LT-1-887
LT-1-888
LT-1-889
LT-1-890
LT-1-891
LT-1-892
LT-1-893
LT-1-894
LT-1-895
LT-1-896
LT-1-897
LT-1-898
LT-1-899
LT-1-900
LT-1-901
LT-1-902
LT-1-903
LT-1-904
LT-1-905
LT-1-906
LT-1-907
LT-1-908
LT-1-909
LT-1-910
LT-1-911
LT-1-912
LT-1-913
LT-1-914
LT-1-915
LT-1-916
LT-1-917
LT-1-918
LT-1-919
LT-1-920
LT-1-921
LT-1-922
LT-1-923
LT-1-924
LT-1-925
LT-1-926
LT-1-927
LT-1-928
LT-1-929
LT-1-930
LT-1-931
LT-1-932
LT-1-933
LT-1-934
LT-1-935
LT-1-936
LT-1-937
LT-1-938
LT-1-939
LT-1-940
LT-1-941
LT-1-942
LT-1-943
LT-1-944
LT-1-945
LT-1-946
LT-1-947
LT-1-948
LT-1-949
LT-1-950
LT-1-951
LT-1-952
LT-1-953
LT-1-954
LT-1-955
LT-1-956
LT-1-957
LT-1-958
LT-1-959
LT-1-960
LT-1-961
LT-1-962
LT-1-963
LT-1-964
LT-1-965
LT-1-966
LT-1-967
LT-1-968
LT-1-969
LT-1-970
LT-1-971
LT-1-972
LT-1-973
LT-1-974
LT-1-975
LT-1-976
LT-1-977
LT-1-978
LT-1-979
LT-1-980
LT-1-981
LT-1-982
LT-1-983
LT-1-984
LT-1-985
LT-1-986
LT-1-987
LT-1-988
LT-1-989
LT-1-990
LT-1-991
LT-1-992
LT-1-993
LT-1-994
LT-1-995
LT-1-996
LT-1-997
LT-1-998
LT-1-999
LT-1-1000
LT-1-1001
LT-1-1002
LT-1-1003
LT-1-1004
LT-1-1005
LT-1-1006
LT-1-1007
LT-1-1008
LT-1-1009
LT-1-1010
LT-1-1011
LT-1-1012
LT-1-1013
LT-1-1014
LT-1-1015
LT-1-1016
LT-1-1017
LT-1-1018
LT-1-1019
LT-1-1020
LT-1-1021
LT-1-1022
LT-1-1023
LT-1-1024
LT-1-1025
LT-1-1026
LT-1-1027
LT-1-1028
LT-1-1029
LT-1-1030
LT-1-1031
LT-1-1032
LT-1-1033
LT-1-1034
LT-1-1035
LT-1-1036
LT-1-1037
LT-1-1038
LT-1-1039
LT-1-1040
LT-1-1041
LT-1-1042
LT-1-1043
LT-1-1044
LT-1-1045
LT-1-1046
LT-1-1047
LT-1-1048
LT-1-1049
LT-1-1050
LT-1-1051
LT-1-1052
LT-1-1053
LT-1-1054
LT-1-1055
LT-1-1056
LT-1-1057
LT-1-1058
LT-1-1059
LT-1-1060
LT-1-1061
LT-1-1062
LT-1-1063
LT-1-1064
LT-1-1065
LT-1-1066
LT-1-1067
LT-1-1068
LT-1-1069
LT-1-1070
LT-1-1071
LT-1-1072
LT-1-1073
LT-1-1074
LT-1-1075
LT-1-1076
LT-1-1077
LT-1-1078
LT-1-1079
LT-1-1080
LT-1-1081
LT-1-1082
LT-1-1083
LT-1-1084
LT-1-1085
LT-1-1086
LT-1-1087
LT-1-1088
LT-1-1089
LT-1-1090
LT-1-1091
LT-1-1092
LT-1-1093
LT-1-1094
LT-1-1095
LT-1-1096
LT-1-1097
LT-1-1098
LT-1-1099
LT-1-1100
LT-1-1101
LT-1-1102
LT-1-1103
LT-1-1104
LT-1-1105
LT-1-1106
LT-1-1107
LT-1-1108
LT-1-1109
LT-1-1110
LT-1-1111
LT-1-1112
LT-1-1113
LT-1-1114
LT-1-1115
LT-1-1116
LT-1-1117
LT-1-1118
LT-1-1119
LT-1-1120
LT-1-1121
LT-1-1122
LT-1-1123
LT-1-1124
LT-1-1125
LT-1-1126
LT-1-1127
LT-1-1128

## I Tower ICPL IR log
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 956
[9 empty] | Approved with comments (B) |  | 2
[9 empty] | Rejected ( R) |  | 2
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 960
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | Basement | IT/1 | 2022-06-09 |  | Survey | Checking of control points and shifting of BM |  | I & L Tower | A | 2022-06-09
2 | Sub Structure | Basement | IT/2 | 2022-06-10 |  | Survey | Layout & level before excavation |  | I & L Tower | A | 2022-06-10
3 | Sub Structure | Basement | IT/3 | 2022-06-26 |  | Excavation | Excavation level, surface preparation & final bed level before PCC | (-17'-3'') | A~F/1~10 | A | 2022-06-28
4 | Sub Structure | Basement | IT/4 | 2022-06-28 |  | Termite Proofing | Termite proofing of Zone-1 |  | A~F/1~10 | A | 2023-05-17
5 | Sub Structure | Basement | IT/5 | 2022-06-28 |  | PCC | Laying of PCC 3" thick (1st layer) Zone-1 |  | A~F/1~10 | A | 2022-06-29 | PC-1 | 38
6 | Sub Structure | Basement | IT/6 | 2022-06-29 |  | Excavation | Excavation level, surface preparation & final bed level before PCC Zone-3 |  | A~F/17~26 | A | 2022-06-30
7 | Sub Structure | Basement | IT/7 | 2022-06-30 |  | Termite Proofing | Termite proofing oF Zone-3 |  | A~F/17~26 | A | 2023-05-17
8 | Sub Structure | Basement | IT/8 | 2022-06-30 |  | PCC | Laying of PCC 3" thick (1st layer) Zone-3 |  | A~F/17~26 | A | 2022-06-30 | PC-2 | 54
9 | Sub Structure | Basement | IT/9 | 2022-07-02 |  | Excavation | Excavation level, surface preparation & final bed level before PCC Zone-2 |  | A~F/11~16 | A | 2022-07-02
10 | Sub Structure | Basement | IT/10 | 2022-06-30 |  | Termite Proofing | Termite proofing of Zone-2 |  | A~F/11~16 | A | 2023-05-17
11 | Sub Structure | Basement | IT/11 | 2022-06-30 |  | PCC | Laying of PCC 3" thick (1st layer) Zone-2 |  | A~F/11~16 | A | 2023-03-28 | PC-3 | 50
| Sub Structure | Basement | IT/11a | 2022-07-02 |  | PCC | 1st layer PCC of I Tower (Zone 2) |  | Grid D-F/11-14 | A | 29--Aug-22 | PC-5 | 62
12 | Sub Structure | Basement | IT/12 | 2022-06-26 |  | Excavation | Excavation level, surface preparation & final bed level of lift well Zone1 & 3 |  | A~B/9~10, A~B/17~18 | A | 2022-06-27
13 | Sub Structure | Basement | IT/13 | 2022-06-26 |  | Termite Proofing | Termite proofing at lifet wells Zone-1 & 3 |  | A~B/9~10, A~B/17~18 | A | 2023-05-17
14 | Sub Structure | Basement | IT/14 | 2022-06-26 |  | PCC | Laying of PCC 3" thick (1st layer) Zone-1 & 3 |  | A~B/9~10, A~B/17~18 | A | 2022-07-01 | PC-4 | 60
15 | Sub Structure | Basement | IT/15 | 2022-07-06 |  | Brick Work | Brick work of Lift Wells IT Tower (Zone 1 & 3) |  | Grid-A-B/9-10, A-B/17-18 | A | 2022-08-04
16 | Sub Structure | Basement | IT/16 | 2022-08-03 |  | Brick Work | Brick work (th 9" and ht 4') for Raft external face protection I Tower (Zone 1 & 3) |  | Grid A-F/1, Grid A-F/26 | A | 2022-08-04
17 | Sub Structure | Basement | IT/17 | 2022-08-03 |  | Brick Work | Brick work (Th 13" and ht 4') for Raft external face protection I Tower (Zone 1 & 3) |  | Grid A-/01-10, Grid A/12-24 | A | 2022-08-04
18 | Sub Structure | Basement | IT/18 | 2022-08-03 |  | Brick Work | Brick work (Th 18" and ht 10') for Raft external face protection I Tower (Zone 2) |  | Grid A-/10-12, | A | 2022-08-04
19 | Sub Structure | Basement | IT/19 | 2022-08-03 |  | Brick Work | Brick work (Th 18" and ht 4') for Raft external face protection I Tower (Zone 3) |  | Grid A/24-26 | A | 2022-08-04
20 | Sub Structure | Basement | IT/20 | 2022-08-03 |  | Excavation | Layout excavation surface preparation and final bed level before laying of PCC I Tower (Zone 1, 2 & 3) |  | Grid F/1-26 | A | 2022-08-04
21 | Sub Structure | Basement | IT/21 | 2022-08-03 |  | Termitte | Termitte proofing (Fiprokill) before laying of PCC |  | Grid F/1-26 | A | 2022-08-04
22 | Sub Structure | Basement | IT/22 | 2022-08-05 |  | PCC | First layer of PCC I Tower Zone 1, 2 and 3 as per revised drawing |  | Grid F/1-26 | A | 2022-08-05 | PC-6 | 15
23 | Sub Structure | Basement | IT/23 | 2022-08-05 |  | Brick work | Layout, surface preparation, brick work, backfilling and PCC |  | Backside of ICPL office | A | 2022-08-06 | PC-7 | 5
24 | Sub Structure | Basement | IT/24 | 2022-08-05 |  | Brick work | Work of Brickwall (Th 9" and ht 4') raft external face protection I Towr (Zone 1 and 3) |  | Grid A-F/1, A-F/26 | A | 2022-08-06
25 | Sub Structure | Basement | IT/25 | 2022-08-05 |  | Plaster work | Plaster work of Brick wall (Th 13" and ht 4') raft external face protection I Tower Zone (1 and 3) |  | Grid A/1-10, Grid A/12-24 | A | 2022-08-16
26 | Sub Structure | Basement | IT/26 | 2022-08-05 |  | Plaster work | Plaster work of Brick wall (Th 18" and ht 10') raft external face protection I Tower Zone (2) |  | Grid A/10-12 | A | 2022-08-16
27 | Sub Structure | Basement | IT/27 | 2022-08-05 |  | Plaster work | Plaster work of Brick wall (Th 18" and ht 4') raft external face protection I Tower Zone (3) |  | Grid A/24-26 | A | 2022-08-06
28 | Sub Structure | Basement | IT/28 | 2022-08-05 |  | Dismental | Dismental of 1sty layer PCC for pits excavation (14' 6" x 14' -6") as per revised drawing I Tower Zone (1 & 3) |  | Grid AB/8-9, AB/18-19 | A | 2022-08-05
29 | Sub Structure | Basement | IT/29 | 2022-08-06 |  | Dismental | Dismental additional 1sty layer PCC and excavation b/w pits and lift well (14' -6 x 2' -9") as per revised drawing I Tower Zone (1 & 3) |  | Grid AB/8-9, AB/18-19 | A | 2022-08-06
30 | Sub Structure | Basement | IT/30 | 2022-08-06 |  | Gen foundation | Layout, surface preparation, brick work, backfilling and PCC of Generator foundation as per approved drawing |  | Steel yard area | A | 2022-08-22
31 | Sub Structure | Basement | IT/31 | 2022-08-06 |  | PCC | 1st layer of PCC I tower Zone 1 as per revised drawing |  | F/1-4 | A | 2022-08-06 | PC-7 | 5
32 | Sub Structure | Basement | IT/32 | 2022-08-06 |  | Backfilling | Backfilling, spreading and levelling site office area |  | Site Office Area | A | 2022-08-06
33 | Sub Structure | Basement | IT/33 | 2022-08-06 |  | Backfilling | Backfilling, spreading, levellingand Compaction site office area |  | Site Office Area | A | 2022-08-22
34 | Sub Structure | Basement | IT/34 | 2022-08-06 |  | Backfilling | Backfilling, spreading and levelling outside of plot along main road |  | Outside of plot | A | 2022-08-06
35 | Sub Structure | Basement | IT/35 | 2022-08-15 |  | Brick work | Brick wall (Th 9" and h2'-9") raft external face protection I tower (Zone 1 and 3) |  | Grid F/1-26 | A | 2022-08-16
36 | Sub Structure | Basement | IT/36 | 2022-08-15 |  | Plaster work | Plaster workof Brickwall (Th 9", ht: 2'-9") for raft external face protection I Tower Zone (1&3) |  | Grid F/1-26 | A | 2022-08-16
37 | Sub Structure | Basement | IT/37 | 2022-08-15 |  | Sand filling | Sand filling around lift wells Qty 2760 Cft I Tower (Zone 1 & 3) |  | Grid A-B/9-10 & A-B/17-18 | A | 2022-08-16
38 | Sub Structure | Basement | IT/38 | 2022-08-16 |  | Redo work/PCC | Redo work of 1st layer of PCC Total area 3640 ft I tower (Zone 1-3) |  | Grid A-C/8-11, Grid B-D/12-14, & A-D/16-21 | A | 2022-09-30
39 | Sub Structure | Basement | IT/39 | 2022-08-16 |  | Brick Wall | Rework of Brick wall of lift well I Tower (Zone 1 & 3) |  | Grid A-B/9-10, A-B/17-18 | A | 2022-08-20
40 | Sub Structure | Basement | IT/40 | 2022-08-17 |  | Surface cleaning | Surface cleaning and allow for water proofing I Tower (Zone 1) |  | Grid A-F/1-7 | A | 2022-08-20
41 | Sub Structure | Basement | IT/41 | 2022-08-18 |  | Water Proofing | Water Proofing before 2nd layer of PCC I Tower (Zone 1) |  | Grid A-F/1-7 | A | 2022-08-20
42 | Sub Structure | Basement | IT/42 | 2022-08-18 |  | Surface cleaning | Surface cleaning of vertical brick walls and allow for water proofing I tower (Zone-1) |  | Grid A/1-7, Grid F/1-7, A-F/1 | A | 2022-08-20
43 | Sub Structure | Basement | IT/43 | 2022-08-18 |  | Water Proofing | Water Proofing of vertical brick walls before 2nd layer of PCC I Tower (Zone 1) |  | Grid A/1-7, F/1-7, A-F/1 | A | 2022-08-20
44 | Sub Structure | Basement | IT/44 | 2022-08-18 |  | Sand filling | Sand filling (ht: 2'-7") I Tower (Zone 2) |  | Grid B-D/12-14 | A | 2022-08-20
45 | Sub Structure | Basement | IT/45 | 2022-08-18 |  | Sand filling | Sand filling (ht: 6") O Tpwer (Zone 1) |  | Grid A-D/8-11 | A | 2022-08-20
46 | Sub Structure | Basement | IT/46 | 2022-08-18 |  | Sand filling | Sand filling (ht 1"-6") I Tower (Zone 3) |  | Grid A-D/16-21 | A | 2022-08-22
47 | Sub Structure | Basement | IT/47 | 2022-08-18 |  | Sand filling | Sand filling (ht: 01') I Tower (Zone 1 & 3) |  | Grid A-B/8-9, A-B/18-19 | A | 2022-08-20
48 | Sub Structure | Basement | IT/48 | 2022-08-18 |  | Termitte Proofing | Termite Proofingof sum pits I Tower (Zone 1-3) |  | Grid A-B/8-9, A-B/18-19 | A | 2022-08-20
49 | Sub Structure | Basement | IT/49 | 2022-08-18 |  | PCC | 1st layer of PCC of sum pits I Tower (Zone 1-3) |  | Grid A-B/8-9, A-B/18-19 | A | 2022-08-20 | 8 | 11
50 | Sub Structure | Basement | IT/50 | 2022-08-18 |  | Termite Proofing | Termite proofing around sum pits and lift wells I Tower (Zone 1-3) |  | Grid A-D/8-11, A-D/16-21 | A | 2023-05-17
51 | Sub Structure | Basement | IT/51 | 2022-08-18 |  | PCC | 1st layer of PCC around sum pits and lift wells I Tower (Zone 1-3) |  | Grid A-D/8-11, A-D/16-2) | A | 2022-08-20 | 8 | 11
52 | Sub Structure | Basement | IT/52 | 2022-08-18 |  | Plaster work | Internal Plaster work of brick wall of lift well I Tower (Zone 1) |  | Grid A-B/9-10 | A | 2022-08-20
53 | Sub Structure | Basement | IT/53 | 2022-08-20 |  | Surface preparation | Surface preparation after water proofing and llow for 2nd layer of PCC I Tower (Z-1) |  | Grid A-F/1-7 | A | 2022-08-20
54 | Sub Structure | Basement | IT/54 | 2022-08-22 |  | Plaster work | Plaster work of lift well and sum pits I Tower (Zone 1-3) |  | Grid A-B/8-9, A-B/18-19 | A | 2022-08-22
55 | Sub Structure | Basement | IT/55 | 2022-08-21 |  | Termite proofing | Termite proofing around sum pits and lift well I Tower (Zone 3) |  | Grid A-D/16-21 | A | 2022-08-22
56 | Sub Structure | Basement | IT/56 | 2022-08-21 |  | PCC | 1st layer of PCC around sum pits and lift well I Tower (Zone 3) |  | Grid A-D/16-21 | A | 2022-08-22 | 10 | 15
57 | Sub Structure | Basement | IT/57 | 2022-08-21 |  | PCC | 2nd layer of PCC (Th 3") I Tower (Zone 1) |  | Grid A-F/1-6 | A | 2022-08-22 | 10 | 41
58 | Sub Structure | Basement | IT/58 | 2022-08-20 |  | Sand filling | Sand filling around sum pits before laying of 1st layer of PCC I Tower (Zone 1-3) |  | Grid A-B/8-9, A-B/18-19 | A | 2022-08-22
59 | Sub Structure | Basement | IT/59 | 2022-08-23 |  | Surface cleaning | Surface cleaning and llow for water proofing I Tower excluding Lift well |  | Grid A-F/7-14 | A | 2022-08-24
60 | Sub Structure | Basement | IT/60 | 2022-08-24 |  | Surface cleaning | Surface cleaning and allow for water proofing over 1st layer of PCC and vertical brick |  | Grid A-B/8-9, A-B/9-10 | A | 2022-08-26
61 | Sub Structure | Basement | IT/61 | 2022-08-27 |  | Surface cleaning | Surface cleaning and allow for water proofing over 1st layer of PCC and vertical brick |  | Grid A/7-14 & F/7-14 | A | 2022-08-25
62 | Sub Structure | Basement | IT/62 | 2022-08-25 |  | Surface preparation | Surface preparation , compaction and excavation level before termite proofing |  | Grid F/17-18 | A | 2022-08-26
63 | Sub Structure | Basement | IT/63 | 2022-08-26 |  | Water Proofing | Water Proofing over 1st layer of PCC and vertical brick wall |  | Grid A-F/7-14 | A | 2023-03-28
64 | Sub Structure | Basement | IT/64 | 2022-08-27 |  | Water Proofing | Water Proofing over 1st layer of PCC and vertical brick wall I Tower Zone 1 |  | Grid A-B/8-10 | A | 2022-08-27
65 | Sub Structure | Basement | IT/65 | 2022-08-27 |  | Core cutting | Core cutting in 1st layer of PCC for earthing Rod conduit Zone 2 |  | Grid A-B/11-10 | A | 2022-08-27
66 | Sub Structure | Basement | IT/66 | 2022-08-27 |  | Brick work | Brick work for raft external face protection I Tower (Zone 2-3) |  | Grid F/16-17 | A | 2022-08-28
67 | Sub Structure | Basement | IT/67 | 2022-08-27 |  | Plaster work | Plaster work of brick wall for raft external face protection I Tower (Zone 2-3) |  | Grid F/16-17 | A | 2022-08-28
68 | Sub Structure | Basement | IT/68 | 2022-08-27 |  | Termite Proofing | Termite proofing of remaining area I Tower (Zone 3) |  | Grid F/17-18 | A | 2022-08-28
69 | Sub Structure | Basement | IT/69 | 2022-08-27 |  | PCC | 1st layer of PCC of remaining area I Tower (Zone 3) |  | Grid F/17-18 | A | 2022-08-29 | 11 | 23
70 | Sub Structure | Basement | IT/70 | 2022-08-27 |  | PCC | 2nd layer of PCC I Tower Zone 1-2 excluding sum pit |  | Grid A-F/7-14 | A | 2022-08-29 | 12 | 52
71 | Sub Structure | Basement | IT/71 | 2022-08-27 |  | PCC | 2nd layer PCC of sum pit and lift well I Tower Zone 1 |  | Grid A-B/8-10 | A | 2022-08-29 | 13 | 15
72 | Sub Structure | Basement | IT/72 | 2022-08-29 |  | Surface cleaning | Surface cleaning and allow for water proofing over 1st layer of PCC I Tower Zone-3 |  | Grid A-F/19-26 | A | 2022-09-02
73 | Sub Structure | Basement | IT/73 | 2022-08-29 |  | Raft and RCC Wall | Layout of Raft and RCC wall of sump pit & Lift well as per IFC drawings I Tower Z-1 |  | Grid A-B/8-9 & A-B/9-10 | A | 2022-08-29
| Sub Structure | Basement | IT/74 | 2022-10-13 |  | Steel Fixing | Steel fixing of column I Tower Zone 2 |  | Grid A-F/11-15 | A | 2022-10-18
1 | Sub Structure | Basement | IT/75 | 2022-09-02 |  | Brick wall rework | Redowork brick wall of I Tower Zone -1 |  | Grid F/1-5 | A | 2022-09-02
2 | Sub Structure | Basement | IT/76 | 2022-09-02 |  | Plaster work | Redo work internal side plaster of brick wall I Tower Zone 1 |  | Grid F/1-5 | A | 2022-09-03
3 | Sub Structure | Basement | IT/77 | 2022-09-03 |  | Brick work | Redo work Brick wall I Tower Zone 2 |  | Grid F/10-14 | A | 2022-09-03
4 | Sub Structure | Basement | IT/78 | 2022-09-03 |  | Brick work | Redo Plaster of brick wall I Tower Zone-2 |  | Grid F/10-14 | A | 2022-09-05
5 | Sub Structure | Basement | IT/79 | 2022-09-03 |  | Surface cleaning | Surface cleaning and allow for water proofing over 1st layer of PCC I Tower |  | Grid F/14-19 | A | 2022-09-05
6 | Sub Structure | Basement | IT/80 | 2022-09-03 |  | Water Proofing | Water proofing over vertical brick wall up to 4 ft height |  | Grid A/10-12 | A | 2022-09-03
7 | Sub Structure | Basement | IT/81 | 2022-09-03 |  | Brick work | Redo work of brick masonry for raft external face protection I Tower |  | Grid F/17-19 | A | 2022-09-03
8 | Sub Structure | Basement | IT/82 | 2022-09-03 |  | Plaster work | Redo work plaster of brick wall for raft external face protection I Tower |  | Grid F/17-19 | A | 2022-09-05
9 | Sub Structure | Basement | IT/83 | 2022-09-03 |  | PCC | 2nd layer of PCC over water proofing before steel fixing and concrete pouring I Tower |  | Grid F/1-14 | A | 2022-09-03
10 | Sub Structure | Basement | IT/84 | 2022-09-04 |  | Water Proofing | Water proofing over 1st layer of PCC and vertical brick wall and allow for 2nd layer |  | Grid A-F/19-26 | A | 2022-09-05
11 | Sub Structure | Basement | IT/85 | 2022-09-04 |  | Concrete pouring | Concrete pouring of Raft of Sump pit and lift well I Tower Zone 1 |  | Grid A-B/8-10 | A | 2022-09-05 | PC-15 | 63
12 | Sub Structure | Basement | IT/86 | 2022-09-04 |  | Surface preparation | Surface preparation/cleaning of 1st layer of PCC and vertical brick wall I Tower |  | Grid A-B/17-19 | A | 2022-09-14
| Sub Structure | Basement | IT/87 | 2022-09-04 |  | PCC | 2nd layer of PCC after water proofing layer of Raft I Tower |  | Grid A-F/19-26 | A | 2022-09-09 | PC-14 | 39
| Sub Structure | Basement | IT/88 | 2022-09-05 |  | Water Proofing | Water Proofing over 1st layer of PCC and vertical brick walls |  | Grid A-F/14-19 | A | 2022-09-05
| Sub Structure | Basement | IT/89 | 2022-09-05 |  | Surface preparation | Surface preparation/cleaning (Redowork) of vertical brick wall and allow for water proofing I Tower |  | Grid F/1-13 | A | 2023-05-17
| Sub Structure | Basement | IT/90 | 2022-09-04 |  | RCC wall | Layout of RCC wall and columns of I Tower |  | Grid A-F/1-5 | A | 2022-09-05
| Sub Structure | Basement | IT/91 | 2022-09-09 |  | Vertical brick | Redo work of vertical brick wall I Tower Zone 1 |  | Grid F/1-10 | A | 2022-09-09
| Sub Structure | Basement | IT/92 | 2022-09-09 |  | Plaster work | Redo work Plaster of vertical brick wall I Tower Zone - 1 |  | Grid F/1-10 | A | 2022-09-09
13 | Sub Structure | Basement | IT/93 | 2022-09-11 |  | RCC Wall | Layout of RCC wall, columns, Stairs, sump pit RCC wall and lift well I Tower Zone |  | Grid A-F/5-10 | A | 2022-09-12
| Sub Structure | Basement | IT/94 | 2022-09-11 |  | Brick work | Redo work brick wall I Tower Zone 2 |  | Grid F/13-17 | R | 2022-09-12
| Sub Structure | Basement | IT/95 | 2022-09-12 |  | Plaster work | Redo work Plaster work of brick wall I Tower Zone 2 |  | Grid F/13-17 | R | 2022-09-12
| Sub Structure | Basement | IT/96 | 2022-09-12 |  | Water Proofign | Water Proofing and levels of 2nd PCC I Tower Zone 2-3 |  | Grid A-F/14-19 | A | 2022-09-15
| Sub Structure | Basement | IT/97 | 2022-09-12 |  | Redo work/Proofing | Redo work of Water Proofing of vertical brick wall I Tower |  | Grid F/1-14 | A | 2022-09-13
| Sub Structure | Basement | IT/98 | 2022-09-14 |  | Surface preparation | Layout, excavation, surface Preparation, compaction Zone 1-3 |  | Grid F/1-26 | A | 2022-09-14
| Sub Structure | Basement | IT/99 | 2022-09-14 |  | Termite Proofing | Termite proofing and allow for 1st layer of PCC |  | Grid F/1-26 | A | 2022-09-14
| Sub Structure | Basement | IT/100 | 2022-09-14 |  | PCC | 1st layer of PCC of Raft foundation |  | Grid F/1-26 | A | 2022-09-16 | PC-17 | 15
| Sub Structure | Basement | IT/101 | 2022-09-14 |  | Surface preparation | Surface preparation of vertical brick wall |  | Grid F/13-17 | A | 2022-09-14
| Sub Structure | Basement | IT/102 | 2022-09-14 |  | Water Proofing | Water Proofing and over 1st layer of PCC and vertical brick walls of Sump pit |  | Grid A-B/17-19 | A | 2022-09-15
| Sub Structure | Basement | IT/103 | 2022-09-15 |  | Surface preparation | Surface preparation and llow for water proofing over 1st layer PCC Zone 1 |  | Grid F/1-9 | A | 2022-09-15
| Sub Structure | Basement | IT/104 | 2022-09-15 |  | PCC | 2nd layer PCC over water proofing I Tower |  | Grid A-F/14-19 | A | 2022-09-21 | PC-17 | 40
| Sub Structure | Basement | IT/105 | 2022-09-16 |  | Raft and RCC wall | Steel fixing of Raft and RCC wall, columns dowels as per IFC drawings I Tower Z-1 |  | Grid A-F/1-7 | A | 2022-09-21
| Sub Structure | Basement | IT/106 | 2022-09-16 |  | Water Proofing | Water Proofing over 1st layer PCC and allow for 2nd layer PCC Z-1 |  | Grid F/1-9 | A | 2022-09-17
| Sub Structure | Basement | IT/107 | 2022-09-16 |  | Surface preparation | Surface preparation and allow for water proofing Z-1 |  | Grid F/9-26 | A | 2022-09-17
| Sub Structure | Basement | IT/108 | 2022-09-16 |  | PCC | 2nd layer PCC Zone 1 |  | Grid F/1-9 | A | 2022-09-20 | PC-18 | 8
| Sub Structure | Basement | IT/109 | 2022-09-16 |  | PCC | 2nd layer PCC of sump pit and lift well Zone 3 |  | Grid A-B/17-19 | A | 2022-09-21 | PC-18 | 16
| Sub Structure | Basement | IT/110 | 2022-09-17 |  | Water Stopper | PVC Water stopper placing and fixing in RCC wall as per IFC drawings Z-1 |  | Grid A-F/1-7 | A | 2022-09-20
| Sub Structure | Basement | IT/111 | 2022-09-19 |  | Earth Bores | layout of earth bores and allow for boring 06 nos Zone 2 |  | Grid A-B/11-13 | A | 2022-09-20
| Sub Structure | Basement | IT/112 | 2022-09-18 |  | RCC | Raft concrete pouring 4000 psi as per IFC drawings Zone 1 (First Pour) |  | Grid A-F/1-7 | A | 2022-09-21 | PC-19 | 694
| Sub Structure | Basement | IT/113 | 2022-09-18 |  | Raft Concrete | Curing of Raft Concrete Pouring Zone 1 I Tower |  | Grid A-F/1-7 | A | 2022-10-05
| Sub Structure | Basement | IT/114 | 2022-09-20 |  | RCC wall | Layout of raft, footing beams, columns and RCC wall Zone 2 |  | Grid A-F/10-13 | A | 2022-10-06
| Sub Structure | Basement | IT/115 | 2022-09-20 |  | Columns and RCC | Layout of columns and RCC wall Zone 1 I Tower |  | Grid A-F/1-6 | A | 2022-09-21
| Sub Structure | Basement | IT/116 | 2022-09-20 |  | Boring for earth | Boring for earth Rod placing Zone 2 |  | Grid A-B/11-10 | A | 2022-10-06
| Sub Structure | Basement | IT/117 | 2022-10-01 |  | Steel Fixing | Steel fixing of Columns and RT wall I Tower Zone 2 |  | Grid A-F/6-11 | A | 2022-10-05
| Sub Structure | Basement | IT/118 | 2022-09-21 |  | Steel Fixing | Steel fixing of columns up to basement slab and dowels for steel lap as per IFC Z-1 |  | Grid A-F/1-6 | A | 2022-09-28
| Sub Structure | Basement | IT/119 | 2022-09-22 |  | RCC wall | Layout of RCC wall and raft of Sump pit and lift well I Tower Zone 3 |  | Grid A-B/17-19 | A | 2022-10-06
| Sub Structure | Basement | IT/120 | 2022-09-23 |  | Earth Rod | Placing of Earth Rod in bore holes as per shop drawing |  | Grid A-B/11-13 | A | 2022-09-23
| Sub Structure | Basement | IT/121 | 2022-09-23 |  | PCC | 2nd layer of PCC of Raft foundation |  | Grid F/9-26 | A | 2022-10-06 |  | 16
| Sub Structure | Basement | IT/122 | 2022-09-24 |  | Surface preparation | Surface preparation and allow for waterproofing of vertical brick wall |  | Grid A/10-12 | A | 2022-09-26
| Sub Structure | Basement | IT/123 | 2022-09-25 |  | Waterproofing | Water Proofing of vertical brick walls |  | Grid A/10-12 | A | 2022-09-29
| Sub Structure | Basement | IT/124 | 2022-09-26 |  | bare copper | Laying of bare copper conductor |  | Grid A-B/11-13 | A | 2022-10-05
| Sub Structure | Basement | IT/125 | 2022-09-26 |  | bare copper | Laying of bare copper conductor |  | Grid A-B/11-13 | A | 2022-10-05
| Sub Structure | Basement | IT/126 | 2022-09-26 |  | Weld connection | Thermo weld connection as per drawings |  | Grid A-B/11-13 | A | 2022-10-05
1 | Sub Structure | Basement | IT/127 | 2022-09-26 |  | Steel Fixing | Steel fixing of raft and Shear wall, RW, RCC Wall stairs, columns dowels as per IFC Zone 1-2 |  | Grid A-F/6-12 | A | 2023-05-17
| Sub Structure | Basement | IT/128 | 2022-09-26 |  | Water stopper | PVC water stopper placing and fixing in RCC wall as per IFC Zone 1 |  | Grid A-F/6-12 | A | 2022-09-28
| Sub Structure | Basement | IT/129 | 2022-09-27 |  | Raft footing | Layout of Raft footings, columns and RCC wall |  | Grid A-F/13-16 | A | 2022-10-06
| Sub Structure | Basement | IT/130 | 2022-09-27 |  | RCC | Concrete pouring of columns 5000 psi upto bottom Zone 1 |  | Grid A-F/1-6 | A | 2023-05-17 | PC-21 | 30.5
| Sub Structure | Basement | IT/131 | 2022-09-28 |  | Layout of Columns | Layout of columns shear wall, sump pit lift walls and stair walls I Tower Zone 1-2 |  | Grid A-F/8-11 | A | 2022-10-06
| Sub Structure | Basement | IT/132 | 2022-10-03 |  | Curing | Curing of basement columns of I Tower Zone 1 |  | Grid A-F/1-6 | A | 2022-10-12
| Sub Structure | Basement | IT/133 | 2022-09-28 |  | RCC | Concrete pouring of raft 4000 psi of I Tower Zone 1 & 2 (2nd Pour) |  | Grid A-F/7-12 | A | 2022-09-30 | PC-22 | 690
| Sub Structure | Basement | IT/134 | 2022-09-28 |  | Curing | Curing of raft of I Tower |  | Grid A-F/7-12 | A | 2022-10-06
| Sub Structure | Basement | IT/135 | 2022-09-28 |  | bare copper | laying of bare copper conductor |  | Grid A-B/11-13 | A | 2022-09-29
| Sub Structure | Basement | IT/136 | 2022-09-28 |  | Weld connection | Thermo weld connection as per drawings |  | Grid A-B/11-13 | A | 2022-09-29
| Sub Structure | Basement | IT/137 | 2022-09-29 |  | Steel Fixing | Steel fixing of Raft of sump pit & Lift well and RCC wall dowels and allow for raft concrete Zone 3 |  | Grid A-B/17-19 | A | 2022-10-06
| Sub Structure | Basement | IT/138 | 2022-10-01 |  | RCC wall | layout of RCC wall lift shear wall sump pit columns raft footing |  | Grid A-F/16-26 | A | 2022-10-06
| Sub Structure | Basement | IT/139 | 2022-09-30 |  | Concrete pouring | Concrete pouring of raft of sum pit and lift well I Tower Zone 3 |  | Grid A-B/17-19 | A | 2022-10-05 | pc-23 | 63
| Sub Structure | Basement | IT/140 | 2022-10-01 |  | Steel Fixing | Steel fixing of raft foundation (3rd Pour) Zone 2 |  | Grid A-F/11-16 | A | 2022-10-06 |  | 761
| Sub Structure | Basement | IT/141 | 2022-10-17 |  | Steel Fixing | Steel fixing of raft I Tower Zone 3 |  | Grid A-F/20-26 | A | 2022-10-18
| Sub Structure | Basement | IT/142 | 2022-09-25 |  | Water Stopper | PVC Water Stopper placing and fixing in raft foundation |  | Grid A-F/6-12 | A | 2022-10-05
| Sub Structure | Basement | IT/143 | 2022-09-22 |  | Water Stopper | Horizontal PVC Water stopper placing and fixing |  | Grid A-F/1-10 | A | 2022-10-05
| Sub Structure | Basement | IT/144 | 2022-10-17 |  | Excavation | Excavation, surface preparation, final bed level |  | Grid F-G/1-11 | A | 2022-10-20
| Sub Structure | Basement | IT/145 | 2022-10-05 |  | Level of columns | Layout and level of columns and RCC wall starter I Tower |  | Grid A-F/11-15 | A | 2022-10-06
| Sub Structure | Basement | IT/146 | 2022-10-04 |  | Condute UPVC | Condute U-PVC D class as per approved by consultant |  | Grid 9/F | A | 2022-10-06
| Sub Structure | Basement | IT/147 | 2022-10-10 |  | Curing | Curing of retaining wall of I Tower Zone 1 |  | Grid A-F/ | A | 2022-10-15
| Sub Structure | Basement | IT/148 | 2022-10-12 |  | Curing | Curing of raft I Tower Zone 2 |  | Grid A-F/11-17 | A | 2022-10-13
| Sub Structure | Basement | IT/149 | 2022-10-11 |  | Curing | Curing of Raft of Tower Crane Zone 8 |  | Grid K-M/17-20 | A | 2022-10-12
| Sub Structure | Basement | IT/150 | 2022-10-08 |  | Steel Fixing | Steel fixing of raft of I Tower |  | Grid A-F/16-20 | A | 2022-10-12
| Sub Structure | Basement | IT/151 | 2022-10-17 |  | Curing | Curing of column of I Tower Zone 1 |  | Grid A-F/8-11 | A | 2022-10-18
| Sub Structure | Basement | IT/152 | 2022-10-17 |  | Curing | Curing of retaining wall of I Tower Zone 1 |  | Grid 1-10 | A | 2022-10-18
| Sub Structure | Basement | IT/153 | 2022-09-16 |  | Joint and chicken | Construction Joint and Chicken Mesh of Pour I I Tower Tower |  | Grid A-F/7 | A | 2022-10-05
| Sub Structure | Basement | IT/154 | 2022-09-26 |  | Joint and chicken | Construction Joint and Chicken Mesh of Pour 2 I Tower |  | Grid A-F/7-11 | A | 2022-10-08
| Sub Structure | Basement | IT/155 | 2022-10-01 |  | Joint and chicken | Construction Joint and Chicken Mesh of Pour 3 I Tower |  | Grid A-F/11-16 | A | 2022-10-12
| Sub Structure | Basement | IT/156 | 2022-10-08 |  | Joint and chicken | Construction Joint and Chicken Mesh of Pour 4 I Tower |  | Grid A-F/16-20 | A | 2022-10-12
| Sub Structure | Basement | IT/157 | 2022-10-10 |  | PVC Water stopper | PVC water stopper placing and fixing in raft foundation Zone 3 |  | Grid A-F/16-20 | A | 2022-10-12
| Sub Structure | Basement | IT/158 | 2022-10-02 |  | PVC Water stopper | PVC Water stopper placing and fixing vertical in RTW I Tower Zone 1 |  | Grid F Zone 1 | A | 2022-10-12
| Sub Structure | Basement | IT/159 | 2022-10-08 |  | PVC Water stopper | PVC Water stopper placing and fixing vertical in RTW I Tower Zone 1 |  | Grid 11 Zone 1 | A | 2022-10-12
| Sub Structure | Basement | IT/160 | 2022-09-29 |  | Steel Fixing | Steel fixing of raft of sump pit & Lift well and RCC wall I Tower Zone 3 |  | Grid A-B/17-19 | A | 2022-10-06
| Sub Structure | Basement | IT/161 | 2022-09-22 |  | Steel Fixing | Steel fixing of RCC wall upto basement slab as per IFC Zone 1 |  | Grid A-F/1 & A/1-7 | A | 2022-09-28
| Sub Structure | Basement | IT/162 | 2022-10-10 |  | Steel Fixing | Steel fixing of RTW-1 for concrete pouring I Tower Zone 2 |  | Grid 11-15 | A | 2022-10-13
| Sub Structure | Basement | IT/163 | 2022-10-13 |  | Raft level | Raft level and layout column, Lift, wall, Shear walls, Sumpit wall Zone 2-3, (4th Pour) |  | A-F/15-20 | A | 2022-10-17 | PC-9 | 680
| Sub Structure | Basement | IT/164 | 2022-10-21 |  | Curing | Curing of Raft of I Tower Zone 2 & 3 |  | Grid A-F/16-20 | A | 2022-10-24
| Sub Structure | Basement | IT/165 | 2022-10-14 |  | Level & Dismension | Level and Dismension of slush area |  | F-G | A | 2022-10-17
| Sub Structure | Basement | IT/166 | 2022-10-11 |  | Steel Fixing | Steel fixing of shear wall 1 & 2 for concrete pouring I Tower Zone 1 |  | Grid B-D/8 | A | 2022-10-13
| Sub Structure | Basement | IT/167 | 2022-10-17 |  | Steel Fixing | Steel fixing of shear wall SW3, SW4, SW5, SW6, SW7, SW8 and WC1, WC2, WC3 |  | Grid A-B/9-10 | A | 2022-11-01
| Sub Structure | Basement | IT/168 | 2022-10-18 |  | PVC Water stopper | PVC water stopper placing and fixing in raft foundation Zone 3 |  | Grid A-F/20-26 | A | 2022-10-24
| Sub Structure | Basement | IT/169 | 2022-10-19 |  | UPVC | condute UPVC D class 32 mm dia in wall |  | Grid 9/A | A | 2022-10-24
| Sub Structure | Basement | IT/170 | 2022-10-19 |  | Steel Fixing | Steel fixing of columns and retaining wall and allow for concrete pouring Zone 2, 3 |  | Grid A-F/16-19, A/15-20 | A | 2022-11-01
| Sub Structure | Basement | IT/171 | 2022-10-20 |  | Lift doors | Layout of lift doors and allow for previous rebar remove I Tower |  | Grid A-B/9-10 | A | 2022-10-24
| Sub Structure | Basement | IT/172 | 2022-10-25 |  | Rebaring epoxy | Rebaring epoxy as per new drawing I Tower Zone 1 |  | Grid A-B/9-10 | A | 2022-11-01
| Sub Structure | Basement | IT/173 | 2022-10-26 |  | Dowels | Dowels of Stair Zone 1 |  | Grid A-B/9-10 | A | 2022-11-01
| Sub Structure | Basement | IT/174 | 2022-10-26 |  | Curing of columns | The couring of columns Zone 1 & 2 |  | Grid A-F/9-11 | A | 2022-11-01
| Sub Structure | Basement | IT/175 | 2022-10-26 |  | Curing | Curing of SW1 & SW2 Zone 1 |  | Grid B-D/8 | A | 2022-11-01
| Sub Structure | Basement | IT/176 | 2022-10-27 |  | Curing | Curing of 5th Pour of Raft Foundation |  | Grid A-F/21-26 | A | 2022-11-01
| Sub Structure | Basement | IT/177 | 2022-10-28 |  | Rebaring epoxy | Rebaring epoxy as per new drawing I Tower Zone 3 |  | Grid A-B/17-18 | A | 2022-11-01
| Sub Structure | Basement | IT/178 | 2022-10-28 |  | Steel Fixing | Steel fixing of beam and allow for steel fixing of slab Zone 1 |  | Grid A-F/1-8 | A | 2022-11-08
| Sub Structure | Basement | IT/179 | 2022-10-20 |  | RCC Raft | RCC raft top level and layout of columns and RTW Zone 3 I Tower (5th Pour) |  | Grid A-F/20-26 | A | 2022-11-01 |  | 750
| Sub Structure | Basement | IT/180 | 2022-10-29 |  | Steel Fixing | Allow for steel fixing |  | Grid F-G/1 | A | 2022-11-01
| Sub Structure | Basement | IT/181 | 2022-10-31 |  | Steel Fixing | Steel fixing of columns and shear wall SW3 & SW4 and RTW1 and allow for pouring |  | Grid A-F/20-26, Grid A/20-26, A-F/26 | A | 2022-11-01
| Sub Structure | Basement | IT/182 | 2022-11-01 |  | Steel Fixing | Steel fixing of Shear wall SW3, SW4, SW5, SW6, SW7, SW8 and WC1, WC2, WC3 and allow for concrete pouring |  | Grid A-B/17-18 | A | 2022-11-14
| Sub Structure | Basement | IT/183 | 2022-11-02 |  | Excavation | Excavation as per Estimate and allow for concrete bolts etc |  |  | A | 2022-11-08
| Sub Structure | Basement | IT/184 | 2022-11-08 |  | Steel Fixing | Steel fixing of RTW and allow for concrete pouring I Tower |  | Grid F-G/1 | A | 2022-11-17
| Sub Structure | Basement | IT/185 | 2022-11-08 |  | Water Stopper | PVC horizontal water stopper in RTW I Tower |  | Grid A/10-16 | A | 2022-11-14
| Sub Structure | Basement | IT/186 | 2022-11-08 |  | Steel Fixing | Steel fixing of beam and allow for steel fixing of slab Zone 1 |  | Grid A-F/8-11 | A | 2022-11-14
| Sub Structure | Basement | IT/187 | 2022-11-09 |  | Steel Fixing | Steel fixing of beam and allow for steel fixing of slab Zone 1 |  | Grid F-G/1-11 | A | 2023-05-11
| Sub Structure | Basement | IT/188 | 2022-11-10 |  | Steel Fixing | Steel fixing slab and allow for concrete pouring Zone 1 |  | Grid A-G/1-11 | A | 2023-05-17
| Sub Structure | Basement | IT/189 | 2022-11-10 |  | Epoxy | Check the epoxy for stair Dowel Zone 1 |  | Grid A-A/9-10 | A | 2022-11-14
| Sub Structure | Basement | IT/190 | 2022-11-10 |  | Epoxy | Check the epoxy for stair Dowel, Zone 3 |  | Grid A-A/17-18 | A | 2022-11-14
| Sub Structure | Basement | IT/191 | 2022-11-10 |  | Curing | Check the curing of columns I Tower |  | Grid 12D, 12F, 13D, 13F, 15F | A | 2022-11-14
| Sub Structure | Basement | IT/192 | 2022-11-10 |  | Curing | Check the curing of columns I Tower |  | Grid G/1-11 | A | 2022-11-14
14 | Sub Structure | Basement | IT/193 | 2022-11-10 |  | Curing | Curing of SW3, SW4, SW5, SW6, SW7, SW8, WC1, WC2, WC3 I Tower |  | Grid A-B/9-10 | A | 2022-11-14
| Sub Structure | Basement | IT/194 | 2022-11-11 |  | Formwork | Check formwork of stairs and allow for steel fixing |  | Grid A-A/9-10 | A | 2022-11-14
| Sub Structure | Basement | IT/195 | 2022-11-14 |  | Steel Fixing | Steel fixing of stairs and allow for concrete pouring Zone 1 |  | Grid A-A/9-10 | A | 2022-11-17
| Sub Structure | Basement | IT/196 | 2022-11-15 |  | Concrete pouring | Allow for concrete pouring of columns Zone 2 |  | Grid A-F/12-16 | A | 2022-11-30
| Sub Structure | Basement | IT/197 | 2022-11-17 |  | Concrete pouring | Allow for concrete pouring |  | Grid A-B/1-8 | A | 2022-11-30
| Sub Structure | Basement | IT/198 | 2022-11-19 |  | Brickwork | Brickwork of wall both sides of Main Gate |  | Main gate site entrance | A | 2022-11-22
| Sub Structure | Basement | IT/199 | 2022-11-19 |  | Slab level, layout | Top slab level and layout of columns RCC Toe wall & ramp wall allow for steel |  | A/1-8, B-F/1,A/9-10,F/3-5,7-8 | A | 2022-11-22
| Sub Structure | Basement | IT/200 | 2022-11-19 |  | Concrete pouring | allow for concrete pouring of slab Zone 1 |  | Grid B-F/3-10,A-B/8-9,A-B/10-10 | A | 2022-11-22
| Sub Structure | Basement | IT/201 | 2022-11-23 |  | Concrete pouring | Allow pouring of columns Zone 2 |  | Grid 12A, 15A, 16A, 14F | A | 2022-11-30
| Sub Structure | Basement | IT/202 | 2022-11-22 |  | Level, layout | Check level and layout of slab upper portion, columns Zone 1 |  | Grid B-F/3-10 b/w 11, A-B/8 | A | 2023-03-28
| Sub Structure | Basement | IT/203 | 2022-11-24 |  | Steel Fixing | Steel fixing of columns on expansion Joint |  | Grid G/12-18 | A | 2022-11-30
| Sub Structure | Basement | IT/204 | 2022-11-25 |  | Water Stopper | PVC horizontal water stopper in RTW I Tower |  | Grid A/16-21 | A | 2022-11-30
| Sub Structure | Basement | IT/205 | 2022-11-25 |  | Concrete pouring | Allow for pouring in RTW I Tower |  | Grid A/16-21 | A | 2022-11-30
| Sub Structure | Basement | IT/206 | 2022-11-26 |  | Concrete pouring | Allow for concrete pouring in columns on EJ |  | Grid G/12-16 | A | 2022-11-30
| Sub Structure | Basement | IT/207 | 2022-11-29 |  | Steel Fixing | Check steel fixing of columns I Tower |  | Grid A-F/1, 2A, A-F/4, 8A | A | 2022-11-02
| Sub Structure | Basement | IT/208 | 2022-11-29 |  | Curing | Check curing of RTW I Tower |  | Grid A/10-16 | A | 2022-11-02
| Sub Structure | Basement | IT/209 | 2022-11-29 |  | Curing | Check Curing of Stais I Tower |  | Grid A-A/9-10 | A | 2022-11-02
| Sub Structure | Basement | IT/210 | 2022-11-29 |  | Curing | Check curing of columns I Tower |  | Grid A-F/13-16 | A | 2022-11-02
| Sub Structure | Basement | IT/211 | 2022-11-29 |  | Curing | Check Curing of Slab I Tower |  | Grid A-B/1-8, A/8-10, B-F/1-3, F-G/1-10 | A | 2022-11-02
| Sub Structure | Basement | IT/212 | 2022-11-29 |  | Curing | Check curing of slab I Tower |  | Grid B-F/3-11 | A | 2022-11-02
| Sub Structure | Basement | IT/213 | 2022-11-30 |  | Excavation | Check excavation and allow for concrete |  | Light poles | A | 2022-11-02
| Sub Structure | Basement | IT/214 | 2022-11-15 |  | Concrete pouring | Allow for concrete pouring of RTW1 |  | Grid A-F/10-16 Zone 2 | A | 2022-11-30
| Sub Structure | Basement | IT/215 | 2022-12-01 |  | Curing | Check the curing of columns I TOwer |  | Grid 12A, 15A, 16A, 14F Zone 2 | A | 2022-11-02
| Sub Structure | Basement | IT/216 | 2022-12-01 |  | Pouring | Allow for pouring of columns 7 NO. SW |  | Grid F-F/17, D-F/18, 19-23/A B-D/18 | A | 2022-12-07
| Sub Structure | Basement | IT/217 | 2022-12-02 |  | Electric pole | Check electric pole foundation & Pole fixing, DB foundation, Laying of cable |  | Attached drawing | A | 2022-12-13
| Sub Structure | Basement | IT/218 | 2022-12-02 |  | Steel Fixing | Check the steel fixing |  | Grid A-G/10-16 | A | 2022-12-07
| Sub Structure | Basement | IT/219 | 2022-12-03 |  | Concrete pouring | Allow for concrete of RTW and columns NO. 03 |  | Grid A/21-26, | A | 2022-12-13
| Sub Structure | Basement | IT/220 | 2022-12-03 |  | Water stopper | Check for horizontal and vertical water stopper |  | Grid A/21-26, A/26 | A | 2022-12-07
| Sub Structure | Basement | IT/221 | 2022-12-03 |  | Steel fixing | Check steel fixing of slab Zone 2 |  | Grid A-A/10-16, A-B/11-16, F-G/10-16 | A | 2022-12-13
| Sub Structure | Basement | IT/222 | 2022-12-05 |  | Primer, membrane | allow for vertical primer and membrane Zone 1 |  | Grid A-G/1-10 | A | 2022-12-28
| Sub Structure | Basement | IT/223 | 2022-12-05 |  | Steel Fixing | Check steel fixing of columns on EJ Zone 1 |  | Grid G/18-26 | A | 2022-12-07
| Sub Structure | Basement | IT/224 | 2022-12-05 |  | Concrete pouring | Allow for concrete pouring of slab and columns Zone 2 |  | Grid A-A/10-16, A-B/11-16, F-G/10-16 | A | 2022-12-13
| Sub Structure | Basement | IT/225 | 2022-12-06 |  | Curing | Check the curing of RTW Zone 3 |  | Grid A/16-21 | A | 2022-12-13
| Sub Structure | Basement | IT/226 | 2022-12-06 |  | Curing | Check the curing of columns on EJ I Tower |  | Grid G/12-16 | A | 2022-12-13
| Sub Structure | Basement | IT/227 | 2022-12-06 |  | Concrete pouring | Allow for concrete pouring of columns Zone 3 |  | Grid B-F/19-26 | A | 2022-12-13
| Sub Structure | Basement | IT/228 | 2022-12-06 |  | Steel Fixing | Check steel fixing of slab Zone 2 | (+1'-9'') | Grid B-F/10-16, A/10-11, 16-16 | A | 2022-12-13
| Sub Structure | Basement | IT/229 | 2022-12-06 |  | Concrete pouring | Concrete pouring of slab Zone 2 | (+1'-9'') | Grid B-F/10-16, A/10-11, 16-16 | A | 2022-12-13
| Sub Structure | Basement | IT/230 | 2022-12-06 |  | Level, layout | Check level & Layout of columns & Ramp wall of GF slab Zone 2 | (0'-0'') | Grid A/11-16, F/12-13, 14-14, A-B/11-15 | A | 2022-12-13
| Sub Structure | Basement | IT/231 | 2022-12-08 |  | Concrete pouring | Allow for concrete pouring of columns |  | Grid G/18-26 | A | 2022-12-13
| Sub Structure | Basement | IT/232 | 2022-12-08 |  | Water Stopper | Check horizontal & Vertical water stopper Zone 3 |  | Grid A-G/26 | A | 2022-12-13
| Sub Structure | Basement | IT/233 | 2022-12-08 |  | Concrete pouring | Allow for concrete pouring of RTW Zone 3 |  | Grid A-G/26 | A | 2022-12-13
| Sub Structure | Basement | IT/234 | 2022-12-08 |  | Water bores | Check the water bores & Motor placing |  | Nil | A | 2022-12-13
| Sub Structure | Basement | IT/235 | 2022-12-08 |  | Level, layout | Check level & Layout of columns Zone 2 |  | Grid B-D/11-16 | A | 2022-12-13
| Sub Structure | Basement | IT/236 | 2022-12-09 |  | Steel Fixing | Check steel fixing of columns & Shear wall on GF Zone 2 |  | Grid A-F/1-10 | A | 2022-12-13
| Sub Structure | Basement | IT/237 | 11-Dec--22 |  | Concrete pouring | allow for concrete pouring of columns GF Zone 1 |  | Grid A-F/1-2, B-F/4 | A | 2022-12-13
| Sub Structure | Basement | IT/238 | 2022-12-12 |  | Concrete pouring | Allow for concrete pouring of SW3, SW4, SW5, SW6, SW7 Sw8, WC1 to WC3 Zone 3 |  | Grid A-F/1-2, B-F/4 | A | 2022-12-13
| Sub Structure | Basement | IT/239 | 2022-12-13 |  | Curing | Check curing of columns Zone 3 |  | Grid D-G/17, D-F/18, A/19-26 | A | 2022-12-13
| Sub Structure | Basement | IT/240 | 2022-12-13 |  | Curing | Check curing of RTW Zone 3 |  | Grid A/21-26 | A | 2022-12-13
| Sub Structure | Basement | IT/241 | 2022-12-13 |  | Curing | Check curing of shear walls SW1, SW2, Zone 3 |  | Grid B-E/18-19 | A | 2022-12-13
| Sub Structure | Basement | IT/242 | 2022-12-12 |  | UPVC | Condute UPVC D class 32 mm dia as approved by consultant for earthing wire |  | Zone 1 Ground Floor | A | 2022-12-21
| Sub Structure | Basement | IT/243 | 2022-12-14 |  | Concrete pouring | Allow for concrete pouring of columns GF |  | Grid B-F/3, A/4-8, B-D/6 | A | 2022-12-21
| Sub Structure | Ground | IT/244 | 2022-12-14 |  | Steel Fixing | Check steell fixing of lift wall GF I Tower |  | Grid A-B/9-10 | A | 2022-12-29
| Sub Structure | Ground | IT/245 | 2022-12-15 |  | Concrete pouring | Allow for concrete pouring of columns GF Zone 1 I Tower |  | Grid A-F/1, 2B | A | 2022-12-21
| Sub Structure | Ground | IT/246 | 2022-12-16 |  | Concrete pouring | Allow for concrete pouring of columns GF Zone 1 |  | Grid A/4-8, B-F/6 | A | 2022-12-18
| Sub Structure | Ground | IT/247 | 2022-12-16 |  | Concrete pouring | Allow for concrete pouring columns GF Zone 1 |  | Grid D-F/8 | A | 2022-12-18
| Sub Structure | Ground | IT/248 | 2022-12-16 |  | Curing | Check curing of columns Zone 3 I Tower |  | Grid B-F/19-26 | A | 2022-12-21
| Sub Structure | Ground | IT/249 | 2022-12-16 |  | Curing | Check curing of slab GF Zone 2 I Tower | (0'-0'') | Grid A-B/10-16, F-G/10-16 | A | 2022-12-21
| Sub Structure | Ground | IT/250 | 2022-12-16 |  | Curing | Check curing of slab GF Zone 2 I Tower | (+1-9'') | Grid A-B/10-10, 16-16 and B-D/10-16 | A | 2022-12-21
| Sub Structure | Basement | IT/251 | 2022-12-17 |  | Steel Fixing | Check steel fixing of beam Zone 3 | (0'-0") | Grid A/16-26, A-B/18-26, B-F/24-26,F-G/16-26 | A | 2022-12-28
| Sub Structure | Ground | IT/252 | 2022-12-17 |  | Concrete pouring | Allow for concrete pouring of columns GF |  | Grid 8B, B-F/3, B-D/4 | A | 2022-12-20
| Sub Structure | Ground | IT/253 | 2022-12-18 |  | Concrete pouring | Allow for concrete pouring of columns GF |  | Grid D-F/9-10, 3F | A | 2022-12-20
| Sub Structure | Ground | IT/254 | 2022-12-18 |  | Concrete pouring | Allow for concrete pouring of columns GF |  | Grid A-D/8 | A | 2022-12-20
| Sub Structure | Basement | IT/255 | 2022-12-19 |  | Primer, membrane | Vertical primer and membrane RTW Zone 1 | (-6'-0'') | Grid A-G/1, A/1-10 | A | 2022-12-28
| Sub Structure | Basement | IT/256 | 2022-12-19 |  | Primer, membrane | Vertical primer and membrane on RTW Zone 2 | (-6'-0'') | Grid A/10-16 | A | 2022-12-20
| Sub Structure | Ground | IT/257 | 2022-12-19 |  | Concrete pouring | allow for concrete pouring of SW1, SW2,GF Zone 1 |  | Grid B-D/8-9 | A | 2022-12-28
15 | Sub Structure | Ground | IT/258 | 2022-12-19 |  | Steel Fixing | Check steel fixing of slab GF Zone 3 | (0'-0'') | Grid A/16-26, A-B/18-26, B-F/24-26. F-G/16-26 | A | 2022-12-20
| Sub Structure | Basement | IT/259 | 2022-12-19 |  | Concrete pouring | allow for concrete pouring of slab and columns Zone 3 | (0'-0'') | Grid A/16-26, A-B/18-26, B-F/24-26, F-G/16-26 | A | 2022-12-27
| Sub Structure | Basement | IT/260 | 2022-12-20 |  | Primer, membrane | Vertical primer, membrane on RTW Zone 2 | (-6'-0'') | Grid A/10-16 | A | 2022-12-20
| Sub Structure | Basement | IT/261 | 2022-12-21 |  | Curing | Check curing of columns on EJ I Tower |  | Grid G/18-26 | A | 2022-12-28
| Sub Structure | Basement | IT/262 | 2022-12-21 |  | Curing | Check curing of RTW I Tower |  | Grid A-G/26 | A | 2022-12-28
| Sub Structure | Basement | IT/263 | 2022-12-21 |  | Curing | Check curing of lift wells I Tower |  | Grid A-B/17-18 | A | 2022-12-27
| Sub Structure | Ground | IT/264 | 2022-12-21 |  | Concrete pouring | Allow for concrete pouring of columns GF I Tower |  | Grid D-F/9-10, 3F | A | 2022-12-28
| Sub Structure | Ground | IT/265 | 2022-12-22 |  | Steel Fixing | Check steel fixing of columns GF I Tower |  | Grid A-F/11-12 | A | 2022-12-27
| Sub Structure | Ground | IT/266 | 2022-12-22 |  | Steel Fixing | Check steel fixing of beam and slab GF I Tower | (+1'-9'') | Grid B-F/16-24, A-B/16-18 | A | 2022-12-27
| Sub Structure | Ground | IT/267 | 2022-12-23 |  | Concrete pouring | allow for concrete pouring of lift GF I Tower | (+1'-9'') | Grid A-B/9-10 | A | 2022-12-27
| Sub Structure | Ground | IT/268 | 2022-12-23 |  | Level, layout | Check level and layout of columns and ramp wall GF I Tower | (0'-0'') | Grid A/16-26, A-B/18-26, B-F/24-26, F-G/16-26 | A | 2022-12-27
| Sub Structure | Ground | IT/269 | 2022-12-22 |  | Concrete pouring | Allow concrete pouring of SW GF |  | Grid B-E/8 | A | 2022-12-27
| Sub Structure | Ground | IT/270 | 2022-12-23 |  | Concrete pouring | Allow for concrete pouring of columns GF |  | Grid A-F/11, 12F | A | 2022-12-27
| Sub Structure | Ground | IT/271 | 2022-12-23 |  | Concrete pouring | Allow for concrete pouring of beam and slab GF I Tower | (+1'-9'') | Grid A-B/16-18, B-F/16,24 | A | 2022-12-27
| Sub Structure | Ground | IT/272 | 2022-12-23 |  | Concrete pouring | Allow concrete pouring of Lift GF I Tower | (+1'-9'') | Grid A-B/17-18 GF Zone 3 | A | 2022-12-30
| Sub Structure | Ground | IT/273 | 2022-12-24 |  | Level, layout | Check level, layout of columns SW, Lift walls GF I Tower | (+1'-9'') | Grid A-B/16-18, B-F/16-24 | A | 2022-12-27
| Sub Structure | Ground | IT/274 | 2022-12-24 |  | Steel Fixing | Steel fixing of columns GF I Tower Zone 2 |  | Grid A-F/13-14 | A | 2022-12-30
| Sub Structure | Ground | IT/275 | 2022-12-26 |  | Steel Fixing | Steel Fixing of columns SW1 and SW2 GF I Tower Zone 2 & Zone 3 |  | Grid A-F/15-18, B-E/18 b/w 19 | A | 2022-12-30
| Sub Structure | Ground | IT/276 | 2022-12-26 |  | Concrete pouring | Allow for concrete pouring of columns GF Zone 2 |  | Grid A-F/12-13, A-D/14, A-F/11 | A | 2022-12-30
| Sub Structure | Ground | IT/277 | 2022-12-28 |  | Concrete pouring | Allow for concrete pouring of columns GF Zone 2 I Tower |  | Grid F/15, A-D/13 | A | 2022-12-30
| Sub Structure | Ground | IT/278 | 2022-12-29 |  | Steel Fixing | Steel fixing of columns GF Zone 3 |  | Grid A-F/19-23 | A | 2022-12-30
| Sub Structure | 1st Floor | IT/279 | 2022-12-30 |  | Steel Fixing | Check steel fixing of beam Zone 1 | (+18'-9'') | Grid A-F/1-8 | A | 2023-01-02
| Sub Structure | Ground | IT/280 | 2022-12-30 |  | Concrete pouring | Allow for concrete pouring of columns GF Zone 2 |  | Grid A-F/13-14, A-F/15 | A | 2023-01-02
| Sub Structure | Ground | IT/281 | 2022-12-31 |  | Concrete pouring | Allow for concrete pouring of lift well Zone 1 GF |  | Grid A-B/9-10 | A | 2023-01-02
| Sub Structure | Ground | IT/282 | 2023-01-01 |  | Concrete pouring | Allow for concrete pouring of columns SW1 and SW2 GF Zone 2 |  | Grid A-F/15,16A, B-D/16+17F, B-D/18 btw 19 | A | 2023-01-10
| Sub Structure | Basement | IT/283 | 2023-01-02 |  | Primer, membrane | Allow for vertical primer and membrane on RTW Zone 3 Basement |  | Grid A/16-26 & A-G/26 | A | 2023-01-20
| Sub Structure | Basement | IT/284 | 2023-01-02 |  | Stair | Check formwork of Stairs Zone 3 |  | Grid A-A/17-18 | A | 2023-01-02
| Sub Structure | Ground | IT/285 | 2023-01-02 |  | Slab | Check Formwork of slab for staircase Zone 1 GF | (+18'-9'') | Grid A-B/8-9 | A | 2023-01-10
| Sub Structure | Ground | IT/286
| Sub Structure | Ground | IT/287
| Sub Structure | Ground | IT/288
| Sub Structure | Ground | IT/289
| Sub Structure | Ground | IT/290
| Sub Structure | Ground | IT/291 | 2023-01-02 |  | Concrete pouring | Allow concrete pouring of columns Zone 2 GF |  | Grid B-E/16 & D/17-18 | A | 2023-01-02
| Sub Structure | Ground | IT/292 | 2023-01-03 |  | Steel Fixing | Check steel fixing of beam Zone 1 GF |  | Grid A-F/8-11 | A | 2023-01-04
| Sub Structure | Ground | IT/293 | 2023-01-03 |  | Steel Fixing | Check top and bottom steel fixing of Slab Zone 1 GF |  | Grid A-F/1-10 | A | 2023-01-05
| Sub Structure | Ground | IT/294 | 2023-01-03 |  | Concrete pouring | Allow for concrete pouring of columns Zone 3 GF |  | Grid A-D/21, 19A, 19F, 24A, D/17-18, 16F, | A | 2023-01-10
| Sub Structure | Ground | IT/295 | 2023-01-04 |  | Steel Fixing | Check steel fixing of columns Zone 3 GF |  | Grid A-F/24-26 | A | 2023-01-05
| Sub Structure | Ground | IT/296 | 2023-01-04 |  | Concrete pouring | Allow for concrete pouring of Slab Zone 3 GF |  | Grid A-F/1-10 | A | 2023-01-07
| Sub Structure | Ground | IT/297 | 2022-01-05 |  | Concrete pouring | Allow for concrete pouring of columns Zone 3 GF |  | Grid B-D/19, B-F/23, F/18-19, A/19-23, B-D/21 | A | 2023-01-05
| Sub Structure | Basement | IT/298 | 2023-01-06 |  | Backfilling | Allow for Backfilling of sand along backside of RTW Zone 1 & 2 |  | Grid A-G/1 & A/1-16 | A | 2023-01-17
| Sub Structure | Ground | IT/299 | 2023-01-07 |  | Concrete pouring | Allow for concrete pouring of Columns I Tower |  | Grid B-F/24, B-D/19, B-F/23, F/21 | A | 2023-01-07
| Sub Structure | Ground | IT/300
| Sub Structure | Ground | IT/301
| Sub Structure | Ground | IT/302
| Sub Structure | Ground | IT/303 | 2023-01-07 |  | Steel Fixing | Check steel fixing of Lift walls SW3, SW4, SW5, SW6, SW7, SW8, WC1, WC2, WC3 Zone 2 GF |  | Grid A-B/17-18 | A | 2023-01-10
| Sub Structure | Ground | IT/304 | 2023-01-16 |  | Concrete pouring | Allow for concrete Pouring of Lift walls Zone 2 GF |  | Grid A-B/17-18 | A | 2023-01-20
| Sub Structure | Ground | IT/305 | 2023-01-08 |  | Steel Fixing | Check steel fixing of Stairs Zone 3 GF |  | Grid A-B/17-18 | A | 2023-01-08
| Sub Structure | Ground | IT/306 | 2023-01-08 |  | Concrete pouring | Allow for concrete pouring of Stairs Zone 3 GF |  | Grid A-B/17-18 | A | 2023-01-09
| Sub Structure | Ground | IT/307 | 2023-01-09 |  | Steel Fixing | Check steel fixing of Beams Zone 2 GF |  | Grid A-F/11-14 | A | 2023-01-20
| Sub Structure | Basement | IT/308 | 2023-01-09 |  | Compaction | Check 1st layer compaction backfilling of sand along backside of RTW Zone 1 | (-17.25' to -16.75') | Grid A-G/1 & A/1-10 | A | 2023-01-17
| Sub Structure | Ground | IT/309 | 2023-01-09 |  | Level, layout | Check level , layout of slab columns SW1, SW2 Lifts Stairs & allow for steel fixing Zone 1 GF |  | Grid A-F/1-10 | A | 2023-01-10
| Sub Structure | Basement | IT/310 | 2023-01-09 |  | Compaction | Check 2nd layer compaction backfilling of sand along backside of RTW Zone 1 | (-16.75' to -16.25') | Grid A-G/1 & A/1-10 | A | 2023-01-17
| Sub Structure | Ground | IT/311 | 2023-01-09 |  | Concrete pouring | After final inspection allow for concrete pouring of columns |  | Grid A-F/25-26, 21F & D/24 | A | 2023-01-10
| Sub Structure | 1st Floor | IT/312 | 2023-01-10 |  | Steel Fixing | Check steel fixing of columns 9 Nos Zone 1 I Tower | (+18'-9'' to +29'-9'') | Grid A-F/1-2, B-D/3 | A | 2023-01-20
| Sub Structure | Basement | IT/313 | 2023-01-10 |  | Backfilling | Check 3rd layer backfilling of sand along RTW | (-16.25' to 17.75') | Grid A-G/1 & A/1-10 | A | 2023-01-17
| Sub Structure | Basement | IT/314 | 2023-01-11 |  | Concrete pouring | After final inspetion allow for concrete pouring of columns |  | Grid A-F/25-26, 21F, & B-F/24 | A | 2023-01-20
| Sub Structure | Basement | IT/315 | 2023-01-12 |  | Primer, membrane | Check Primer & Membrane on RTW I Tower | (-6'-0'') | Grid A/16-26 & A-G/26 | A | 2023-01-20
| Sub Structure | Ground | IT/316 | 2023-01-16 |  | Steel fixing | Check steel fixing of beams Zone 2 GF |  | Grid A-F/14-16 & A & F/11-12, 13-14, 15-16 | A | 2023-01-20
| Sub Structure | Ground | IT/317 | 2023-01-16 |  | Steel fixing | Check Top and Bottom Steel Fixing of Slab Zone 2 GF |  | Grid A-F/10-16 Zone 2 | A | 2023-01-20
| Sub Structure | Ground | IT/318 | 2023-01-16 |  | Stair formwork | Formwork of Stair Zone 1 GF | (+2'-0'' to +10'-6'') | Grid A-B/9-10 | A | 2023-01-17
| Sub Structure | 1st Floor | IT/319 | 2023-01-16 |  | Steel fixing | Check steel fixing of columns SW1 + SW2 Zone 1 1st Floor | (+18'-9'' to +29'-9'') | Grid A-F/6-10, F/3, +SW C-E/8 b/w 9 | A | 2023-01-19
| Sub Structure | Ground | IT/320 | 2023-01-16 |  | Concrete pouring | After final steel inspection allow for concrete pouring of sloab Zone 2 GF |  | Grid A-F/10-16 | A | 2023-01-20
| Sub Structure | Basement | IT/321 | 2023-01-16 |  | Condute UPVC | Check the condute UPVC D class 32mm dia in wall and column as approved Zone 1 |  | Grid 9/A +9F | A | 2023-01-20
| Sub Structure | Ground | IT/322 | 2023-01-17 |  | Level, layout | Check level & Layout of slab & Columns and allow for steel fixing Zone 2 GF | (+18'-9'') | Grid A-F/10-16 | B | 2023-01-20
| Sub Structure | 1st Floor | IT/323 | 2023-01-19 |  | Steel Fixing | Check steel fixing of columns Zone 2 1st Floor |  | Grid A-F/11-13 | A | 2023-01-21
| Sub Structure | 1st Floor | IT/324 | 2023-01-19 |  | Steel Fixing | Check steel fixing of lift wall SW3, SW4, SW5, SW6, SW7, SW8, WC2, WC3 Zone 1 1st Floor |  | Grid A-F/9-10 | A | 2023-01-20
| Sub Structure | Ground | IT/325 | 2023-01-19 |  | Formwork Stair | Formwork of Stair Step & Steel Fixing of Stairs Zone 1 GF | (+2'-0'' to +10'-6'') | Grid A-B/9-10 | A | 2023-01-20
| Sub Structure | Ground | IT/326 | 2023-01-19 |  | Steel inspection | Final steel inspection of stairs and allow for concrete pouring of stair Zone 1 GF | (+2'-0'' to +10'-6'') | Grid A-B/9-10 | A | 2023-01-20
| Sub Structure | Ground | IT/327 | 2023-01-19 |  | Steel inspection | After final inspection of steel allow for concrete pouring of columns Zone 1 GF |  | Grid A-B/1-4 | A | 2023-02-02
| Sub Structure | Ground | IT/328 | 2023-01-20 |  | Steel Fixing | Steel fixing of Balcony and allow for concrete pouring Zone 1 GF |  | Grid A/2-8 | A | 2023-02-02
| Sub Structure | Ground | IT/329 | 2023-01-21 |  | Concrete pouring | Allow for concrete pouring of lift walls GF Zone 2 |  | Grid A-B/17-18 | A | 2023-02-02
| Sub Structure | Ground | IT/330 | 2023-01-23 |  | Steel reinforcement | Check steel reinforcement of columns Zone 2 GF |  | Grid A-F/14-16 | A | 2023-02-02
| Sub Structure | 1st Floor | IT/331 | 2023-01-23 |  | Steel reinforcement | Final reinforcement Inspection and placing of concrete pouring of columns, SW1, SW2 Zone 1 1st Fl |  | Grid A-F/3-10 | A | 2023-02-02
| Sub Structure | Basement | IT/332 | 2023-01-23 |  | Surface preparation | Check surface preparation and allow for backfilling of sand along backside of RTW Zone-3 |  | Grid A-G/26 & A/16-26 | A | 2023-02-02
| Sub Structure | Ground | IT/333 | 2023-01-23 |  | Steel reinforcement | Check formwork and steel reinforcement of stair and allow placing of concrete Zone 1 GF | (+10'-6'' to +19'-0'') | Grid A-B/9-10 | A | 2023-02-02
| Sub Structure | Ground | IT/334 | 2023-01-23 |  | Steel reinforcement | Final inspection of steel reinforcement of beam of balcony and allow placing concrete Z-1 GF |  | Grid F/8-10, F/17-21, A-D/26 | A | 2023-02-02
| Sub Structure | Ground | IT/335 | 2023-01-24 |  | Beams Reinforcement | Check beams reinforcement Zone 3 GF |  | Grid A-F/16-26 | A | 2023-02-02
| Sub Structure | Ground | IT/336 | 2023-01-26 |  | Slab formwork | Check formwork of slab along stairs GF Zone 3 |  | Grid A-B/17-18 | A | 2023-02-02
| Sub Structure | Ground | IT/337 | 2023-01-27 |  | Slab reinforcement | Check top and bottom reinforcement of slab GF Slab Zone 3 |  | Grid A-F/16-26 | A | 2023-02-02
| Sub Structure | Ground | IT/338 | 2023-01-27 |  | Slab reinforcement | After final slab reinforcement check, allow for placing of concrete GF Zone 3 |  | Grid A-F/16-26 | A | 2023-02-02
| Sub Structure | 1st Floor | IT/339 | 2023-01-31 |  | Reinforcement | After final reinforcement check, allow for placing of concrete of columns 1st Floor Zone 2 |  | Grid A-F/11-13D, 13F | A | 2023-02-02
| Sub Structure | Basement | IT/340 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 17'-3'' to 13'-3'') Zone 3 | (-17'-3'' to -13'-3'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/341 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 13'-3'' to 12'-9'') | (-13'-3'' to -12'-9'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/342 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 12'-9'' to 12'-3'') | (-12'-9'' to -12'-3'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/343 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 12'-3'' to 11'-9'') | (-12'-3'' to -11'-9'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/344 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 11'-9'' to 11'-3'') | (-11'-9'' to -11'-3'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/345 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 11'-3'' 10'-9'') | (-11'-3'' to -10'-9'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/346 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 10'-9'' to 10'-3'') | (-10'-9'' to -10'-3'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/347 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 10'-3'' to 9'-9'') | (-10'-3'' to -9'-9'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/348 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 9'-9'' to 9'-3'') | (-9'-9'' to -9'-3'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/349 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 9'-3'' to 8'-9'') | (-9'-3'' to -8'-9'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/350 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 (Level 8'-9'' to 8'-3'') | (-8'-9'' to -8'-3'') | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Basement | IT/351 | 2023-01-31 |  | Backfilling | Check backfilling of sand along I Tower Zone 3 up to level 91.8 NSL | (351 NSL) | Grid A-G/26 | A | 2023-02-06
| Sub Structure | Ground | IT/352 | 2023-02-01 |  | Level, layout | Check level and layout of columns SWs, Lift walls of GF Slab and allow for steel fixing Zone 3 |  | Grid A-F/16-26 | A | 2023-02-02
| Sub Structure | 1st Floor | IT/353 | 2023-02-02 |  | Reinforcement | Final reinforcement inspection of lift and allow for placing of concrete 1st Floor Zone 1 |  | Grid A-B/9-10 | A | 2023-02-06
| Sub Structure | Ground | IT/354 | 2023-02-02 |  | Layout | Check layout of balconies GF Zone 1 |  | Grid A/2-8, F/6-10 | A | 2023-02-06
| Sub Structure | Basement | IT/355 | 2023-02-02 |  | Compaction | Check 1st layer compaction backfilling of sand along backside of RTW Zone 2 & 3 | (-17.25' to -16.75') | Grid A/10-26 | A | 2023-02-06
| Sub Structure | Basement | IT/356 | 2023-02-02 |  | Compaction | Check 2nd layer compaction backfilling of sand along backside of RTW Zone 2 & 3 | (-16.75' to -16.25') | Grid A/10-26 | A | 2023-02-06
| Sub Structure | Basement | IT/357 | 2023-02-03 |  | Compaction | Check 3rd layer compaction backfilling of sand along backside of RTW Basement Zone 2 & 3 | (-16.25' to -15.75') | Grid A/10-26 | A | 2023-02-06
| Sub Structure | Basement | IT/358 | 2023-02-03 |  | Compaction | Check 4th layer compaction backfilling of sand along backside of RTW Basement Zone 2 & 3 | (-15.75' to -15.25') | Grid A/10-26 | A | 2023-02-06
| Sub Structure | Basement | IT/359 | 2023-02-03 |  | Compaction | Final steel inspection of FB3 beam & balcony and allow for placing of concrete Basement Zone 1 |  | Grid A-E/1 | A | 2023-02-15
16 | Sub Structure | 1st Floor | IT/360 | 2023-02-03 |  | Reinforcement | Check reinforcement of columns & SW1 & SW2 1st floor Zone 3 |  | Grid A-F/17-26 | A | 2023-02-06
17 | Sub Structure | 1st Floor | IT/361 | 2023-02-06 |  | Reinforcement | Final reinforcement check of columns and allow for concrete Pouring 1st Floor Zone 2 |  | Grid A-F/13-15, 16A | A | 2023-02-06
18 | Sub Structure | 1st Floor | IT/362 | 2023-02-08 |  | Reinforcement | Final reinforcement check of columns and allow for concrete pouring 1st Floor Zone 2 |  | Grid B-F/16-24, A-B/16-18 | A | 2023-02-15
19 | Sub Structure | 1st Floor | IT/363 | 2023-02-08 |  | Reinforcement | Check reinforcement of lift walls SW3, SW4, SW5, SW6, SW7, SW8, WC1, WC2, WC3 1st floor Zone 3 |  | Grid A-B/17-18 | A | 2023-02-15
20 | Sub Structure | 2nd Floor | IT/364 | 2023-02-08 |  | Beam reinforcement | Check beam reinforcement 2nd Floor Zone 1 |  | Grid A-F/1-8 | A | 2023-02-15
21 | Sub Structure | 1st Floor | IT/365 | 2023-02-10 |  | Beam reinforcement | Check beam reinforcement 1st Floor Zone 1 |  | Grid A-F/8-11 | A | 2023-02-15
22 | Sub Structure | 1st Floor | IT/366 | 2023-02-10 |  | Reinforcement | Final reinforcement check and allow for placing of column concrete 1st Floor Zone 3 |  | Grid A-F/25-26, D-F/24 | A | 2023-02-15
23 | Sub Structure | 1st Floor | IT/367 | 2023-02-11 |  | Slab reinforcement | Check reinforcement of slab 1st Floor Zone 1 |  | Grid A-F/1-11 | A | 2023-02-15
24 | Sub Structure | 1st Floor | IT/368 | 2023-02-11 |  | Reinforcement | Final reinforcement check and allow for placing of column concrete 1st Floor Zone 3 |  | Grid A-F/21-23 | A | 2023-02-15
25 | Sub Structure | 1st Floor | IT/369 | 2023-02-14 |  | Reinforcement | Final reinforcement check of slab and allow for placing of concrete 1st Floor Zone 1 & 2 |  | Grid A-F/1-12 | A | 2023-02-15
26 | Sub Structure | 1st Floor | IT/370 | 2023-02-13 |  | Reinforcement | Final reinforcement check of columns SW1, SW2 and allow for placing of concrete 1st Floor Z-3 |  | Grid A-F/17-19 | A | 2023-02-15
27 | Sub Structure | 1st Floor | IT/371 | 2023-02-13 |  | Slab | Check beam reinforcement 1st Floor Zone 2 |  | Grid A-F/11-15 | A | 2023-02-15
28 | Sub Structure | 1st Floor | IT/372 | 2023-02-14 |  | Slab | Check top and bottom slab reinforcement 1st Floor Zone 2 |  | Grid A-F/10-13 | A | 2023-02-15
29 | Sub Structure | 1st Floor | IT/373 | 2023-02-14 |  | Stair formwork | Check stair formwork, reinforcement and allow for placing of concrete of stair 1st Floor Z-1 | (+18'-9'' to +29'-9'') | Grid A-F/9-10 | A | 2023-02-15
30 | Sub Structure | 1st Floor | IT/374 | 2023-02-15 |  | Level, layout | Check level & Layout of slab, columns, lift, shear walls and balconies Zone 1 & 2 1st floor |  | Grid A-F/1-12 | A | 2023-02-22
31 | Sub Structure | Basement | IT/375 | 2023-02-15 |  | Backfilling | Check 1st layer backfilling of sand along RTW Basement Zone 1 | (-17'-3'' to -13'-3'') | Grid A-G/1 | A | 2023-02-22
32 | Sub Structure | Basement | IT/376 | 2023-02-15 |  | Backfilling | Check 2nd layer backfilling of sand along RTW Basement Zone 1 | (-13'-3'' to -12'-9'') | Grid A-G/1 | A | 2023-02-22
33 | Sub Structure | Basement | IT/377 | 2023-02-16 |  | Backfilling | Check 3rd layer backfilling of sand along RTW Basement Zone 1 | (12'-9'' to -12'-3'') | Grid A-G/1 | A | 2023-02-22
34 | Sub Structure | Basement | IT/378 | 2023-02-16 |  | Backfilling | Check 4th layer backfilling of sand along RTW Basement Zone 1 | (-12'-3'' to -11'-9'') | Grid A-G/1 | A | 2023-02-22
35 | Sub Structure | 1st Floor | IT/379 | 2023-02-16 |  | Reinforcement | Check reinforcement of Beam 1st Floor Zone 2 & 3 |  | Grid A-F/15-17 | A | 2023-02-22
36 | Sub Structure | 1st Floor | IT/380 | 2023-02-16 |  | Reinforcement | Final reinforcement check of lift and allow for placing of concrete pouring Zone 3 |  | Grid A-F/17-18 | A | 2023-02-22
37 | Sub Structure | 2nd Floor | IT/381 | 2023-02-16 |  | Column reinforcement | Check columns reinforcement 2nd Floor Zone 1 |  | Grid A-F/1-5, 6A, 6B | A | 2023-02-22
38 | Sub Structure | 2nd Floor | IT/382 | 2023-02-17 |  | Reinforcement | Final reinforcement check and allow for concrete pouring of columns 2nd Floor Zone 1 |  | Grid A-F/1-3 | A | 2023-02-22
39 | Sub Structure | 2nd floor | IT/383 | 2023-02-17 |  | Columns | Check columns reinforcement 2nd Floor Zone 1 |  | Grid A-F/4-10 | A | 2023-02-22
40 | Sub Structure | 2nd Floor | IT/384 | 2023-02-18 |  | Columns | Check columns reinforcement & SWS1, SW2 2nd Floor Zone 1 & 2 |  | Grid A-F/11-12, A-F/8-9 | A | 2023-02-22
41 | Sub Structure | 2nd Floor | IT/385 | 2023-02-18 |  | Reinforcement | Final reinforcement check and allow for concrete pouring of columns 2nd Floor Zone 1 |  | Grid A-F/4-8 | A | 2023-02-22
42 | Sub Structure | Basement | IT/386 | 2023-02-18 |  | Backfilling | Check 5th layer backfilling of sand along RTW Basement Zone 1 | (-11'-9'' to -11'-3'') | Grid A-G/1 | A | 2023-02-22
43 | Sub Structure | Basement | IT/387 | 2023-02-18 |  | Backfilling | Check 6th layer backfilling of sand along RTW Basement Zone 1 | (-11'-3'' to -10'-9'') | Grid A-G/1 | A | 2023-02-22
44 | Sub Structure | 2nd floor | IT/388 | 2023-02-18 |  | UPVC | Check condute UPVC D class 32mm in column for earthing wire raft to roof 2nd Floor Zone 1 |  | Grid F/9-26 | A | 2023-02-22
45 | Sub Structure | 2nd Floor | IT/389 | 2023-02-20 |  | reinforcement | Final reinforcement check and allow for concrete pouring of columns & SW1 and SW2 2nd Floor Zone 1 |  | Grid A-F/8-9, F/9-12 | A | 2023-02-22
46 | Sub Structure | Basement | IT/390 | 2023-02-20 |  | backfilling | Check 7th layer backfilling of sand along RTW Basement Zone 1 | (-10'-9'' to -10'-3'') | Grid A-G/1 | A | 2023-02-22
47 | Sub Structure | Basement | IT/391 | 2023-02-20 |  | backfilling | Check 8th layer backfilling of sand along RTW Basement Zone 1 | (-10'-3'' to 9'-9'') | Grid A-G/1 | A | 2023-02-22
48 | Sub Structure | 6th Floor | IT/392 | 2023-02-20 |  | backfilling | Check 9th layer backfilling of sand along RTW Basement Zone 1 | (-9'-9'' to -9'-3'') | Grid A-G/1 | A | 2023-02-22
49 | Sub Structure | 2nd Floor | IT/393 | 2023-02-20 |  | Lift wall | Check lift wall reinforcement SW3 to SW8 and WC1 to WC3 Zone 1 |  | Grid A-B/9-10 | A | 2023-03-01
50 | Sub Structure | 1st Floor | IT/394 | 2023-02-20 |  | Reinforcement | Final reinforcement inspection of balcony and allow for placing of concrete 1st Floor Zone 3 |  | Grid A/19-25, F/17-21 | A | 2023-02-22
51 | Sub Structure | 1st Floor | IT/395 | 2023-02-21 |  | Reinforcement | Check reinforcement of Beams 1st Floor Zone 3 |  | Grid A-F/15-26 | A | 2023-03-01
52 | Sub Structure | 2nd floor | IT/396 | 2023-02-21 |  | Reinforcement | Final reinforcement check and allow for concrete pouring of columns 2nd Floor Zone 2 |  | Grid A-F/11-12 | A | 2023-03-01
53 | Sub Structure | 1st Floor | IT/397 | 2023-02-21 |  | Level, layout | Check level and layout of balconies |  | Grid A-F/13-26 | A | 2023-03-01
54 | Sub Structure | 1st Floor | IT/398 | 2023-02-21 |  | Level, layout | Check level and layout of stair 1st Floor Zone 3 | (+1'-9'' to 19'-9'') | Grid A-F/17-18 | A | 2023-03-01
55 | Sub Structure | 1st Floor | IT/399 | 2023-02-22 |  | Steel Fixing | Formwork, steel fixing of stair and allow for placing of concrete 1st Floor Zone 3 | (+1'-9'' to 10'-6'') | Grid A-F/17-18 | A | 2023-03-01
56 | Sub Structure | Basement | IT/400 | 2023-02-22 |  | Backfilling | Check 10th layer backfilling of sand along RTW Basement Zone 1 | (-9'-3'' to -8'-9'') | Grid A-G/1 | A | 2023-03-01
57 | Sub Structure | Basement | IT/401 | 2023-02-22 |  | Backfilling | Check 11th layer backfilling of sand along RTW Basement Zone 1 | (-8'-9'' to -8'-2'') | Grid A-G/1 | A | 2023-03-01
58 | Sub Structure | Basement | IT/402 | 2023-02-22 |  | Backfilling | Check backfilling of sand along RTW on left side Basement Zone 1 | 92.24 | Grid A-G/1 | A | 2023-03-01
59 | Sub Structure | Basement | IT/403 | 2023-02-22 |  | Backfilling | Check backfilling of sand along RTW on back side Basement Zone 1-2-3 | (-17'-3'' to -13'-3'') | Grid A/1-26 | A | 2023-03-01
60 | Sub Structure | Basement | IT/404 | 2023-02-22 |  | Backfilling | Check 2nd layer backfilling of sand along RTW on back side Basement Zone 1-2-3 | (-13'-3'' to -12'-9'') | Grid A/1-26 | A | 2023-03-01
61 | Sub Structure | 2nd floor | IT/405 | 2023-02-23 |  | Steel fixing | Check steel fixing of SW5 as per new IFC Folio No. 04 2nd Floor Zone 1 | (+29'-9'' to +40'-9'') | Grid A-B/9-10 | A | 2023-03-01
62 | Sub Structure | Basement | IT/406 | 2023-02-23 |  | Backfilling | Check 3rd layer backfilling of sand along RTW Basement Zone 1-2-3 | (-12'-9'' to -12'-3'') | Grid A/1-26 | A | 2023-03-01
63 | Sub Structure | Basement | IT/407 | 2023-02-23 |  | Backfilling | Check 4th layer backfilling of sand along RTW Basement Zone 1-2-3 | (-12'-3'' to -11'-9'') | Grid A/1-26 | A | 2023-03-01
64 | Sub Structure | 1st floor | IT/408 | 2023-02-24 |  | Slab reinforcement | Check Top and bottom slab reinforcement 1st Floor Zone 3 | (+29'-9'') | Grid A-F/12-26 | A | 2023-03-01
65 | Sub Structure | 1st Floor | IT/409 | 2023-02-24 |  | Slab reinforcement | Final reinforcement check of slab reinforcement and allow for placing of concrete 1st floor Zone 3 | (+29'-9'') | Grid A-F/12-26 | A | 2023-03-01
66 | Sub Structure | 2nd Floor | IT/410 | 2023-02-25 |  | Beam reinforcement | Check beam reinforcement 2nd Floor Zone 1 | (+29'-9'') | Grid A-F/1-6 | A | 2023-03-01
67 | Sub Structure | 1st Floor | IT/411 | 2023-02-25 |  | Level, layout | Check level, layout of columns, balconies, SW1, SW2 and Lift walls 1st Floor Zone 2 | (+29'-9'') | Grid A-F/12-26 | A | 2023-03-28
68 | Sub Structure | 2nd floor | IT/412 | 2023-02-25 |  | Reinforcement | Check reinforcement of columns 2nd floor Zone 2+3 |  | Grid B-F/13-14, F/15-19 | A | 2023-03-01
69 | Sub Structure | 2nd floor | IT/413 | 2023-02-25 |  | Reinforcement | Check reinforcement of columns 2nd Floor Zone 2+3 |  | Grid A/13-14, A-D/15-16, D/17-19 | A | 2023-03-01
70 | Sub Structure | 2nd Floor | IT/414 | 2023-02-27 |  | Reinforcement | Final reinforcement inspection of lift and allow for concrete pouring 2nd Floor Zone 1 I Tower | (+29'-9'') | Grid A-B/9-10 | A | 2023-03-01
71 | Sub Structure | 2nd Floor | IT/415 | 2023-02-27 |  | Reinforcement | Final reinforcement inspection of columns and allow for concrete pouring 2nd Floor Zone 2 | (+29'-9'' to +40'-9'') | Grid B-F/13-14, F/15-16 | A | 2023-03-01
72 | Sub Structure | 2nd Floor | IT/416 | 2023-02-27 |  | Reinforcement | Check reinforcement of columns 2nd Floor Zone 3 | (+29'-9'' to +40'-9'') | Grid A-F/19-26 | A | 2023-03-01
73 | Sub Structure | 1st Floor | IT/417 | 2023-02-27 |  | Steel fixing | Check formwork, steel fixing of stair ST-2 and allow for concrete pouring of stair 1st Floor Zone 3 | (+18'-9'' to +29'-9'') | Grid A-B/18-18 Level +18'-18'' to 29'-9'' | A | 2023-03-01
74 | Sub Structure | 1st Floor | IT/418 | 2023-02-27 |  | Level, layout | Check level and layout of Stair ST-2 1st Floor Zone 3 I Tower | (+18'-9'' to +29'-9'') | Grid A-B/18-18 Level +18'-18'' to 29'-9'' | A | 2023-03-01
75 | Sub Structure | 2nd Floor | IT/419 | 2023-02-27 |  | Reinforcement | Check reinforcement of sW1 & SW2 2nd Floor Zone 3 | (+29'-9'' to +40'-9'') | Grid A-F/18-19 | A | 2023-03-01
| Sub Structure | 2nd Floor | IT/420 | 2023-02-28 |  | Reinforcement | Final inspection of columns reinforcement and allow for concrete placing of columns 2nd Floor Zone 2-3 | (+29'-9'' to +40'-9'') | Grid A./13-14, A-D/15-16, D-F/17 | A | 2023-03-01
| Sub Structure | GF/1st Floor | IT/421 | 2023-02-28 |  | Steel Fixing | Check formwork, steel fixing and allow for concrete pouring of Stair ST-1 Zone 3 | (+10'-6+'' to +18'-9'') | Grid A-B/17-18 level +10'-6'' to +18'-9'' | A | 2023-03-01
| Sub Structure | Basement | IT/422 | 2023-02-28 |  | Backfilling | Check 5th layer backfilling of sand along RTW on back side Basement Zone --3 | (-11'-9'' to -11'-3'') | Grid A/1-26 | A | 2023-03-01
| Sub Structure | Basement | IT/423 | 2023-02-28 |  | Backfilling | Check 6th layer backfilling of sand along RTW on back side Basement Zone --3 | (-11'-3'' to -10'-9'') | Grid A/1-26 | A | 2023-03-01
| Sub Structure | 2nd Floor | IT/424 | 2023-03-02 |  | Reinforcement | Check reinforcement of lift wall SW3, SW4, SW5, SW6, SW7, SW8, WC1, WC2, WC3 2nd Floor Zone 3 | (+29'-9'' to +40'-9'') | Grid A-B/17-18 | A | 2023-03-03
| Sub Structure | 2nd Floor | IT/425 | 2023-03-01 |  | Reinforcement | Final reinforcement of columns and allow for concrete placing 2nd Floor Zone 3 | (+29'-9'' to +40'-9'') | Grid A-B/18-21 | A | 2023-03-01
| Sub Structure | 2nd Floor | IT/426 | 2023-03-01 |  | Reinforcement | Final reinforcement of columns and allow for concrete placing 2nd floor Zone 3 | (+29'-9'' to +40'-9'') | Grid A-B/23-26 | A | 2023-03-03
| Sub Structure | 3rd Floor | IT/427 | 2023-03-01 |  | Reinforcement | Check beam reinforcement 3rd Floor Zone 1 | (+40'-9'') | Grid A-F/6-10 | A | 2023-03-03
| Sub Structure | 3rd Floor | IT/428 | 2023-03-01 |  | Slab formwork | Check slab formwork portion in fron of ST-3 3rd Floor Zone 1 | (+40'-9'') | Grid A-B/8-9 | A | 2023-03-03
| Sub Structure | 3rd Floor | IT/429 | 2023-03-01 |  | Slab reinforcement | Check top and bottom slab reinforcement 3rd Floor Zone 1 | (+40'-9'') | Grid A-F/1-10 | A | 2023-03-03
| Sub Structure | 3rd Floor | IT/430 | 2023-03-01 |  | Slab reinforcement | Final check of slab reinforcement and allow for concrete pouring 3rd Floor Zone 1 | (+40'-9'') | Grid A-F/1-10 | A | 2023-03-03
| Sub Structure | 3rd Floor | IT/431 | 2023-03-02 |  | Level, layout | Check level and layout of columns, SW1, SW2 & Lift walls 3rd floor Zone 1 | (+40'-9'') | Grid A-F/1-10 | A | 2023-03-03
| Sub Structure | 2nd Floor | IT/432 | 2023-03-02 |  | Reinforcement | Final reinforcement check of SW1 & SW2 and allow for concrete pouring 2nd Floor Zone 3 | (+29'-9'' to +40'-9'') | Grid A-F/18-19 | A | 2023-03-03
| Sub Structure | 3rd Floor | IT/433 | 2023-03-02 |  | Column reinforcement | Check column reinforcement 3rd Floor Zone 3 | (+40'-9'' to +51'-9'') | Grid A-F/1-3 | A | 2023-03-03
| Sub Structure | 3rd Floor | IT/434 | 2023-03-03 |  | Column reinforcement | Check column reinforcement and SW1 and SW2 3rd floor Zone 1 | (+40'-9'' to +51'-9'') | Grid A-F/4-10 | A | 2023-03-08
| Sub Structure | 3rd floor | IT/435 | 2023-03-03 |  | Column reinforcement | Final column reinforcement check and allow for concrete pouring 3rd floor Zone 1 | (+40'-9'' to +51'-9'') | Grid A-F/1-3 | A | 2023-03-08
| Sub Structure | 1st Floor | IT/436 | 2023-03-04 |  | Level, layout | Check level and layout of ST-1 1st Floor Zone 3 | (+18'-9'' to +29'-9'') | Grid A-F/17-18 | A | 2023-03-13
| Sub Structure | 2nd Floor | IT/437 | 2023-03-04 |  | Beam reinforcement | Check beam reinforcement 2nd floor Zone 2 level +40'-9'' | (+40'-9'') | Grid A-F/10-16 | A | 2023-03-08
| Sub Structure | 3rd floor | IT/438 | 2023-03-04 |  | Concrete pouring | Final column reinforcement check and allow for concrete pouring 3rd floor Zone 1 | (+40'-9'' to +51'-9'') | Grid A-F/3-6 | A | 2023-03-08
| Sub Structure | 3rd Floor | IT/439 | 2023-03-06 |  | Condute UPVC | Check condute UPVC D class 32 mm in lift wall and column 3rd Floor Zone 1 |  | Grid A-F/9 | A | 2023-03-08
| Sub Structure | 3rd Floor | IT/440 | 2023-03-06 |  | Reinforcement | Check reinforcement of lift wall SW3, SW4, SW5, SW6, SW7, WC1, WC2, WC3 3rd Floor Zone 1 | (+40'-9'' to +51'-9'') | Grid A-F/9-10 | A | 2023-03-08
| Sub Structure | 3rd Floor | IT/441 | 2023-03-06 |  | Reinforcement | Final reinforcement check and allow for concrete pouring of columns and SW1 and SW2 3rd floor Z-1 | (+40'-9'' to +51'-9'') | Grid A-F/8-10 | A | 2023-03-08
| Sub Structure | Basement | IT/442 | 2023-03-06 |  | Backfilling | Check 7th layer backfilling of sand along RTW on back side Basement Zone 1-3 | (-10'-9'' to -10'-3'') | Grid A/1-26 | A | 2023-03-08
| Sub Structure | Basement | IT/443 | 2023-03-06 |  | Backfilling | Check 8th layer backfilling of sand along RTW on back side Basement Zone 1-3 | (-10'-3'' to -9'-9'') | Grid A/1-26 | A | 2023-03-08
| Sub Structure | 3rd Floor | IT/444 | 2023-03-06 |  | Slab reinforcement | Check Top and Bottom Slab reinforcement 3rd floor Zone 2 | (+40'-9'') | Grid A-F/10-16 | A | 2023-03-08
| Sub Structure | 3rd Floor | IT/445 | 2023-03-07 |  | Slab reinforcement | Final slab reinforcement check and allow for placing of concrete 3rd Floor Zone 2 | (+40'-9'') | Grid A-F/10-16 | A | 2023-03-13
| Sub Structure | 2nd floor | IT/446 | 2023-03-07 |  | Reinforcement | Final reinforcement check of lift and allow for placing of concrete of lift walls 2nd Floor Zone 3 | (+29'-9'' to +40'-9'') | Grid A-B/17-18 | A | 2023-03-13
| Sub Structure | 1st Floor | IT/447 | 2023-03-08 |  | Level, layout | Check level and layout of Stair 1st Floor Zone 1 level +29'-9'' to +40'-9'' | (+29'-9'' to +40'-9'') | Grid A-B/9-10 | A | 2023-03-13
| Sub Structure | GF | IT/448 | 2023-03-08 |  | Level, layout | Check level and layout of Stair Ground Floor Zone 1 Level +18'-9'' to +29'-9'' | (+18'-9'' to +29'-9'') | Grid A-B/8-9 | A | 2023-03-13
| Sub Structure | 1st Floor | IT/449 | 2023-03-08 |  | Steel Fixing | Check Formwork, Steel Fixing and allow for Concrete Pouring of Stair ST-1 1st Floor Zone 1 | (+29'-9'' to +40'-9'') | Grid A-B/9-10 | A | 2023-03-13
| Sub Structure | 1st floor | IT/450 | 2023-03-08 |  | Reinforcement | Check reinforcement of hanging Beam SB16 of ST-3low for concrete Pouring 1st floor to 2nd floor | (+18'-9'' to +29'-9'') | Grid A/18-18 | A | 2023-03-13
| Sub Structure | 2nd floor | IT/451 | 2023-03-08 |  | Level, layout | Check level and layout of columns 2nd Floor Zone 2 | (+40'-9'') | Grid A-F/10-16 | A | 2023-03-13
| Sub Structure | Basement | IT/452 | 2023-03-08 |  | Backfilling | Check 9th layer backfilling along RTW on back side of I Tower Basement Zone 1-2-3 | (-9'-9'' to -9'-3'') | Grid A/1-26 | A | 2023-03-08
| Sub Structure | Basement | IT/453 | 2023-03-08 |  | Backfilling | Check 10th layer backfilling along RTW on back side of I Tower Basement Zone 1-2-3 | (-9'-3'' to -8'-9'') | Grid A/1-26 | A | 2023-03-08
| Sub Structure | Basement | IT/454 | 2023-03-08 |  | Backfilling | Check 11th layer backfilling along RTW on back side of I Tower Basement Zone 1-2-3 | (-8'-9'' to -8'-2'') | Grid A/1-26 | A | 2023-03-08
| Sub Structure | 2nd Floor | IT/455 | 2023-03-08 |  | Reinforcement | Check beam reinforcement 2nd Floor Zone 3 | (+40'-9'') | Grid A-F/16-26 | A | 2023-03-13
| Sub Structure | 3rd floor | IT/456 | 2023-03-08 |  | Column reinforcement | Check columns reinforcement 3rd floor Zone 2 | (+40'-9'' to +51'-9'') | Grid A-F/11-13 | A | 2023-03-13
| Sub Structure | 2nd floor | IT/457 | 2023-03-09 |  | Column reinforcement | Check columns reinforcement 2nd floor Zone 2 | (+40'-9'' to +51'-9'') | Grid A-F/13-16 | A | 2023-03-13
| Sub Structure | 2nd floor | IT/458 | 2023-03-09 |  | Column reinforcement | Final columns reinforcement check and allow for placing of concrete Zone 2 | (+40'-9'' to +51'-9'') | Grid A-F/11-12 | A | 2023-03-13
| Sub Structure | 2nd Floor | IT/459 | 2023-03-10 |  | Column reinforcement | Final columns reinforcement check and allow for placing of concrete 2nd Floor Zone 2 | (+40'-9'' to +51'-9'') | Grid A-F/13-16 | A | 2023-03-13
| Sub Structure | 2nd Floor | IT/460 | 2023-03-10 |  | Slab reinforcement | Check top and bottom slab reinforcement 2nd floor Zone 3 | (+40'-9'' | Grid A-F/16-26 | A | 2023-03-13
| Sub Structure | 2nd Floor | IT/461 | 2023-03-11 |  | Reinforcement | Final reinforcement check of slab and allow for placing of concrete 2nd floor Zone 3 | (+40'-9'' | Grid A-F/16-26 | A | 2023-03-13
| Sub Structure | 2nd Floor | IT/462 | 2023-03-11 |  | Formwork slab | Check formwork of slab along Stair ST-3 2nd Floor Zone 3 | (+40'-9'' | Grid A-B/17-18 | A | 2023-03-20
| Sub Structure | 3rd Floor | IT/463 | 2023-03-11 |  | Reinforcement | Final reinforcement check of lift wall and allow for placing of concrete 3rd floor Zone 1 | (+40'-9'' to +51'-9'') | Grid A-F/9-10 | A | 2023-03-13
| Sub Structure | 3rd floor | IT/464 | 2023-03-11 |  | Reinforcement | Final reinforcement check of columns and allow for placing of concrete 3rd floor Zone 2 | (+40'-9'' to +51'-9'') | Grid A-F/15-16 | A | 2023-03-13
| Sub Structure | 2nd Floor | IT/465 | 2023-03-13 |  | Level, layout | Check level and layout of columns SW1, SW2, Lift of Zone 3 Slab | (+40'-9'') | Grid A-F/16-26 | A | 2023-03-20
| Sub Structure | 3rd floor | IT/466 | 2023-03-13 |  | Steel fixing | Check steel fixing of columns (22 Nos) Zone 3 | (+40'-9'') | Grid A-F/17-26 | A | 2023-03-20
| Sub Structure | 3rd Floor | IT/467 | 2023-03-13 |  | Beam reinforcement | Check beam reinforcement Zone 1 | (+51'-9'') | Grid A-F/1-11 | A | 2023-03-20
| Sub Structure | 3rd floor | IT/468 | 2023-03-13 |  | Slab formwork | Check slab formwork along Stairs Zone 1 | (+51'-9'') | Grid A-F/8-9, F/9-12 | A | 2023-03-20
| Sub Structure | 2nd floor | IT/469 | 2023-03-14 |  | Reinforcement | Final reinforcement check and allow for concrete pouring of columns Zone 3 | (+40'-9'' to +51'-9'') | Grid A-F/17-20 | A | 2023-03-20
| Sub Structure | 2nd floor | IT/470 | 2023-03-14 |  | Reinforcement | Check reinforcement of SW1, SW2 and lift wall Zone 3 | (+40'-9'' to +51'-9'') | Grid A-F/17-19 | A | 2023-03-20
| Sub Structure | 3rd floor | IT/471 | 2023-03-14 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 1 | (+51'-9'') | Grid A-F/1-10 | A | 2023-03-20
| Sub Structure | 2nd Floor | IT/472 | 2023-03-14 |  | Reinforcement | Final reinforcement check and allow for placing of concrete 2nd floor Zone 3 | (+40'-9'') | Grid A-D/19-21 | A | 2023-03-20
| Sub Structure | 2nd Floor | IT/473 | 2023-03-15 |  | Reinforcement | Final reinforcement check of columns and SW1 and SW2 and allow for placing of concrete Z-3 | (+40'-9'' to +51'-9'') | Grid A/23-26, 26B, D-F/24-26, A-F/18-19 | A | 2023-03-20
| Sub Structure | 3rd Floor | IT/474 | 2023-03-15 |  | Slab reinforcement | Final reinforcement check of slab and allow for concrete pouring 3rd floor Zone 1 | (+51'-9'') | Grid A-F/1-10 | A | 2023-03-20
| Sub Structure | 1st floor | IT/475 | 2023-03-15 |  | Steel fixing | Check formwork, steel fixing of ST-3 and allow for concrete Zone 1 | (+18'-9'' to +29'-9'') | Grid A-F/8-9 | A | 2023-03-28
| Sub Structure | 3rd Floor | IT/476 | 2023-03-16 |  | Level, layout | Check level and layout of columns, SW1, SW2 Lift walls and FB2 Beam 3rd floor Zone 1 | (+51'-9'') | Grid A-F/1-10 | A | 2023-03-20
| Sub Structure | 3rd floor | IT/477 | 2023-03-16 |  | Beam reinforcement | Check beam reinforcement 3rd floor Zone 2 | (+51'-9'') | Grid A-F/11-17 | A | 2023-03-22
| Sub Structure | 3rd floor | IT/478 | 2023-03-16 |  | Column reinforcement | Check columns (12 Nos) Reinforcement Zone 1 | (+51'-9'') | Grid A-F/1-4, D-F/6 | A | 2023-03-20
| Sub Structure | 3rd Floor | IT/479 | 2023-03-17 |  | Columns reinforcement | Check columns (12) , SW1 & SW2 reinforcement 3rd floor Zone 1 | (+51'-9'') | Grid A-F/4-10 | A | 2023-03-22
| Sub Structure | 2nd floor | IT/480 | 2023-03-18 |  | Level, layout | Check level and layout of Stair ST-1 2nd floor Zone 1 | (+40'-9'' to +51'-9'') | Grid A-B/9-10 | A | 2023-03-22
| Sub Structure | 2nd floor | IT/481 | 2023-03-18 |  | Reinforcement | Check formwork, reinforcement of ST-1 and allow for concrete pouring Zone 1 | (+40'-9'' to +51'-9'') | Grid A-B/9-10 | A | 2023-03-22
| Sub Structure | 3rd floor | IT/482 | 2023-03-18 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 2 | (+51'-9'') | Grid A-F/10-16 | A | 2023-03-22
| Sub Structure | 3rd floor | IT/483 | 2023-03-18 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 2 | (+51'-9'') | Grid A-F/10-16 | A | 2023-03-22
| Sub Structure | 3rd floor | IT/484 | 2023-03-18 |  | Column reinforcement | Check columns reinforcement and allow for concrete pouring Zone 1 | (+51'-9'' to +62'-9'') | Grid A-F/1-4, D-F/6 | A | 2023-03-22
| Sub Structure | 3rd Floor | IT/485 | 2023-03-18 |  | Reinforcement | Check lift reinforcement5 Sw3, SW4, SW5, SW6, SW7, SW8, SW8, WC1, WC2, WC3 Zone 1 | (+51'-9'' to +62'-9'') | Grid A-F/9-10 | A | 2023-03-22
| Sub Structure | 2nd floor | IT/486 | 2023-03-18 |  | Reinforcement | Final lift reinforcement check Sw3, SW4, SW5, SW6, SW7, SW8, SW8, WC1, WC2, WC3 & allow for concrete | (+40'-9'' to +51'-9'') | Grid A-F/17-18 | A | 2023-03-22
| Sub Structure | 4th Floor | IT/487 | 2023-03-20 |  | Condute UPVC | Check condute UPVC D class 32mm in lift wall and column Zone 1 | (+51'-9'' to +62'-9'') | Grid A-F/9 | A | 2023-03-22
| Sub Structure | 4th Floor | IT/488 | 2023-03-20 |  | reinforcement | Final columns +SW1+SW2 reinforcement check and allow for concrete pouring Zone 1 | (+51'-9'' to +62'-9'') | Grid A-F/5-10 | A | 2023-03-22
| Sub Structure | 3rd Floor | IT/489 | 2023-03-20 |  | Level, layout | Check level and layout of columns & FB2 Beams Zone 2 | (+51'-9'') | Grid A-F/10-16 | A | 2023-03-28
| Sub Structure | 3rd Floor | IT/490 | 2023-03-20 |  | Columns reinforcement | Check columns (8 No) reinforcement Zone 2 | (+51'-9'' to +62'-9'') | Grid A-F/11-12 | A | 2023-03-22
| Sub Structure | 3rd Floor | IT/491 | 2023-03-21 |  | Beam reinforcement | Check beam reinforcement 3rd floor Zone 3 | (+51'-9'') | Grid A-F/16-26 | A | 2023-03-28
| Sub Structure | 3rd Floor | IT/492 | 2023-03-21 |  | Column reinforcement | Check column (16 No.) Reinforcement 3rd floor Zone 2 | (+51'-9'' to +62'-9'') | Grid A-F/13-16 | A | 2023-03-28
| Sub Structure | 3rd Floor | IT/493 | 2023-03-22 |  | Slab reinforcement | Check top and Bottom Slab reinforcement Zone 3 | (+51'-9'') | Grid A-F/16-26 | A | 2023-03-28
| Sub Structure | 3rd Floor | IT/494 | 2023-03-22 |  | Slab reinforcement | Final slab reinforcement check and allow for concrete pouring Zone 3 | (+51'-9'') | Grid A-F/16-26 | A | 2023-03-28
| Sub Structure | 3rd Floor | IT/495 | 2023-03-21 |  | Column reinforcement | Final columns reinforcement check and allow for concrete pouring Zone 2 | (+51'-9'' to +62'-9'') | Grid A-F/11 | A | 2023-03-28
| Sub Structure | 3rd Floor | IT/496 | 2023-03-22 |  | Column reinforcement | Final columns reinforcement check and allow for concrete pouring Zone 2 | (+51'-9'' to +62'-9'') | Grid A-F/12-16 | A | 2023-03-28
| Sub Structure | 3rd Floor | IT/497 | 2023-03-22 |  | Column reinforcement | Check columns reinforcement (8 Nos) Zone 3 | (+51'-9'' to +62'-9'') | Grid A-F/17-19 | A | 2023-03-28
| Sub Structure | 3rd Floor | IT/498 | 2023-03-23 |  | Level, layout | Check level, layout of columns, SW1, SW2, B2 beams & Lift Zone 3 | (+51'-9'') | Grid A-F/17-26 | A | 2023-03-28
| Sub Structure | 4th floor | IT/499 | 2023-03-24 |  | Beam reinforcement | Check beam reinforcement Zone 1 | (+62'-9'') | Grid A-F/1-8 | A | 2023-03-28
| Sub Structure | 4th floor | IT/500 | 2023-03-22 |  | Reinforcement | Final reinforcement check and allow for concrete pouring of lift Zone 1 | (+51'-9'') | Grid A-F/9-10 | A | 2023-03-28
| Sub Structure | 4th floor | IT/501 | 2023-03-24 |  | Reinforcement | Final reinforcement and allow for concrete pouring of columns Zone 2 & 3 | (+51'-9'' to +62'-9'') | Grid A-F/15-18, B-E/18 b/w 19 | A | 2023-03-28
| Sub Structure | 4th floor | IT/502 | 2023-03-24 |  | Columns reinforcement | Check columns reinforcement (14 Nos) Zone 3 | (+51'-9'' to +62'-9'') | Grid A-F/19-26 | A | 2023-03-28
| Sub Structure | 4th floor | IT/503 | 2023-03-25 |  | Slab formwork | Check slab formwork along Stair Zone 1 | (+62'-9'') | Grid A-F/8-9 | A | 2023-03-28
| Sub Structure | 4th floor | IT/504 | 2023-03-26 |  | Beam reinforcement | Check beam reinforcement Zone 1 | (+62'-9'') | Grid A-F/8-11 | A | 2023-03-28
| Sub Structure | 4th floor | IT/505 | 2023-03-27 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 1 | (+62'-9'') | Grid A-F/1-10 | A | 2023-03-28
| Sub Structure | 4th floor | IT/506 | 2023-03-27 |  | Slab reinforcement | Final slab reinforcement and allow for concrete Pouring Zone 1 | (+62'-9'') | Grid A-F/1-10 | A | 2023-03-28
| Sub Structure | 3rd floor | IT/507 | 2023-03-27 |  | Column reinforcement | Final columns reinforcement check and allow for concrete pouring Zone 3 | (+51'-9'') | Grid 21A, A-F/22-26 | A | 2023-04-03
| Sub Structure | 3rd floor | IT/508 | 2023-03-27 |  | Lift reinforcement | Check SW1, SW2 and Lift reinforcement SW3, SW4, SW5, SW6, SW7, SW8, WC1, WC2, WC3 Zone 3 | (+51'-9'') | Grid 21A, A-F/22-26 | A | 2023-04-03
| Sub Structure | 1st floor | IT/509 | 2023-03-27 |  | Steel fixing | Check formwork, steel fixing of stair ST-3 and allow for concrete pouring Zone 3 | (+29'-9'' to 40'-9'') | Grid A-F/18-19 | A | 2023-03-28
| Sub Structure | 3rd floor | IT/510 | 2023-03-28 |  | Level, layout | Check level and layout of columns SW's and lift walls Zone 1 | (+62'-9'') | Grid A-F/1-10 | A | 2023-03-28
| Sub Structure | 4th floor | IT/511 | 2023-03-28 |  | Column reinforcement | Check columns reinforcement (9 Nos) Zone 1 | (+62'-9'' to +73'-9'') | Grid A-F/1-3 | A | 2023-04-07
| Sub Structure | 4th Floor | IT/512 | 2023-03-29 |  | Column reinforcement | Check columns reinforcement (5 Nos) Zone 1 | (+62'-9'' to +73'-9'') | Grid A-F/4-6 | A | 2023-04-03
| Sub Structure | 4th floor | IT/513 | 2023-03-28 |  | Reinforcement | Final reinforcement Check of SW's and allow for concrete pouring Zone 3 | (+51'-9'' to +62'-9'') | Grid A-F/18-19 | A | 2023-04-03
| Sub Structure | 4th floor | IT/514 | 2023-03-29 |  | Beam reinforcement | Check beam reinforcement Zone 3 | (+62'-9'') | Grid A-F/10-16 | A | 2023-04-03
| Sub Structure | 5th floor | IT/515 | 2023-03-30 |  | Reinforcement | Check columns (8 Nos) SW1, SW2, Lift walls, SW3-SW8 and WC1, WC2, WC3 reinforcement Zone 1 | (+62'-9'' to +73'-9'') | Grid A-F/8-10 | A | 2023-04-03
| Sub Structure | 4th floor | IT/516 | 2023-03-31 |  | Slab steel fixing | Check top and bottom slab steel fixing Zone 2 | (+62'-9'') | Grid A-F/10-16 | A | 2023-04-03
| Sub Structure | 5th floor | IT/517 | 2023-03-31 |  | UPVC | Check condute UPVC D class 32 mm dia in wall and column for earthing wire Zone 1 | (+62'-9'' to +73'-9'') | Grid 9/A+9F | A | 2023-04-03
| Sub Structure | 4th floor | IT/518 | 2023-04-01 |  | Slab reinforcement | Final slab reinforcement and allow for concrete pouring Zone 2 | (+62'-9'') | Grid A-F/10-16 | A | 2023-04-07
| Sub Structure | 4th floor | IT/519 | 2023-04-01 |  | Lift reinforcement | Final lift wall reinforcement and allow for concrete pouring Zone 3 | (+51'-9'' to +62'-9'') | Grid A-F/17-18 | A | 2023-04-07
| Sub Structure | 4th floor | IT/520 | 2023-04-01 |  | Column reinforcement | Check columns reinforcement (8 Nos) Zone 2 | (+62'-9'' to +73'-9'') | Grid A-F/11-12 | A | 2023-04-07
| Sub Structure | 4th floor | IT/521 | 2023-04-02 |  | Level, layout | Check level & Layout columns Zone 2 | (+62'-9'') | Grid A-F/11-16 | A | 2023-04-06
| Sub Structure | 4th floor | IT/522 | 2023-04-03 |  | Beam reinforcement | Check beam reinforcement Zone 3 | (+62'-9'') | Grid A-F/16-26 | A | 2023-04-07
| Sub Structure | 4th floor | IT/523 | 2023-04-03 |  | Column reinforcement | Check column (8 Nos) reinforcement Zone 2 | (+62'-9'') | Grid A-F/13-14 | A | 2023-04-07
| Sub Structure | 2nd Floor | IT/524 | 2023-03-25 |  | Level, layout | Check level and layout of Stair ST-3 Zone 3 | (+29'-9'' to +40'-9'') | Grid A-F/17-18 | A | 2023-04-06
| Sub Structure | 2nd Floor | IT/525 | 2023-04-03 |  | Level, layout | Check Level and layout of Stair ST-3 Zone 1 | (+29'-9'' to +40'-9'') | Grid A-F/8-8 | A | 2023-04-06
| Sub Structure | 4th floor | IT/526 | 2023-04-03 |  | Level, layout | Check level and layout of Stair ST-1 Zone 1 | (+51'-9'' to -62'-9'') | Grid A-F/9-10 | A | 2023-04-06
| Sub Structure | 2nd floor | IT/527 | 2023-04-03 |  | Steel fixing | Check formwork, steel fixing and allow for concrete pouring Zone 1 | (+29'-9'' to +40'-9'') | Grid A-F/8-8 | A | 2023-04-07
| Sub Structure | 4th floor | IT/528 | 2023-04-04 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 3 | (+62'-9'') | Grid A-F/16-26 | A | 2023-04-07
| Sub Structure | 4th floor | IT/529 | 2023-04-04 |  | Slab reinforcement | Final slab reinforcement and allow for concrete pouring Zone 3 | (+62'-9'') | Grid A-F/16-26 | A | 2023-04-07
| Sub Structure | 4th floor | IT/530 | 2023-04-05 |  | Slab formwork | Check formwork of slab and B18 beam along stair Zone 3 | (+62'-9'') | Grid A-F/16-28 | A | 2023-04-07
| Sub Structure | 4th floor | IT/531 | 2023-04-06 |  | Column reinforcement | Check column reinforcement (8 Nos) Zone 2 | (+62'-9'' to +73'-9'') | Grid A-F/15-16 | A | 2023-04-07
| Sub Structure | 3rd Floor | IT/532 | 2023-04-06 |  | Level, layout | Check level, layout of stair ST-3 Zone 1 | (+40'-9'' to +51'-9'') | Grid A-B/8-9 | A | 2023-04-10
| Sub Structure | 3rd Floor | IT/533 | 2023-04-06 |  | Level, layout | Check level, layout of stair ST-3 Zone 3 | (+40'-9'' to +51'-9'') | Grid A-B/18-19 | A | 2023-04-10
| Sub Structure | 1st Floor | IT/534 | 2023-04-06 |  | Level, layout | Check level, layout of Stair ST-1 Zone 3 | (+18'-9'' to +29'-9'') | Grid A-B/17-18 | A | 2023-04-10
| Sub Structure | 4th floor | IT/535 | 2023-04-06 |  | Level, layout | Check level, layout of columns SW and Lift walls Zone 3 | (+62'-9'') | Grid A-B/17-26 | A | 2023-04-10
| Sub Structure | 5th Floor | IT/536 | 2023-04-07 |  | Column reinforcement | Check columns (19 Nos) reinforcement Zone 3 | (+62'-9'') | Grid A-F/17-26 | A | 2023-04-14
| Sub Structure | 5th Floor | IT/537 | 2023-04-07 |  | Reinforcement | Final columns reinforcement (17 Nos) and allow for concrete pouring of columns Zone 1 & 2 | (+62'-9 to +73'-9'') | Grid D-F/1-12, 8B, B-D/8-9 | A | 2023-04-14
| Sub Structure | 4th floor | IT/538 | 2023-04-08 |  | Steel fixing | Check formwork, steel fixing of Stari ST-1 and allow for concrete pouring Zone 1 | (+51'-9'' to +62'-9'') | Grid A-B/9-10 | A | 2023-04-14
| Sub Structure | Basement | IT/539 | 2023-04-08 |  | Termite Proofing | Horizontal and vertical anti termite proofing along I Tower backfilling area |  | Grid A-F/1, A/1-26, A-F/26 | A | 2023-05-08
| Sub Structure | 5th Floor | IT/540 | 2023-04-08 |  | Reinforcement | Check reinforcement of columns (3 Nos) SW1, SW2 & Lift walls SW3, SW4, SW5, SW6, SW7, SW8, WC1, WC2, WC3 Z3 | (+62'-9 to +73'-9'') | Grid B-F/24, B-D/18-19, A-B/17-18 | A | 2023-04-14
| Sub Structure | 5th Floor | IT/541 | 2023-04-09 |  | Reinforcement | Final reinforcement of columns (9 Nos) and allow for placing of concrete Zone 2 | (+62'-9 to +73'-9'') | Grid A-B/1-8 | A | 2023-04-14
| Sub Structure | 5th Floor | IT/542 | 2023-04-11 |  | Reinforcement | Final reinforcement of columns (11 Nos) and allow for placing of concrete Zone 2 | (+62'-9'' to +73'-9'') | Grid D-F/13-16, B/12-14 | A | 2023-04-14
| Sub Structure | 5th Floor | IT/543 | 2023-04-13 |  | Reinforcement | Final reinforcement check of lift and allow for concrete pouring Zone 1 | (+62'-9'' to +73'-9'') | Grid A-F/9-10 | A | 2023-04-14
| Sub Structure | 5th Floor | IT/544 | 2023-04-13 |  | Reinforcement | Final reinforcement check of columns and allow for concrete pouring Zone 2 | (+62'-9'' to +73'-9'') | Grid A/11-16, B/11, 15, 16 | A | 2023-04-14
| Sub Structure | 2nd Floor | IT/545 | 2023-04-13 |  | Reinforcement | Check Formwork, Steel fixing of sT-1 and allow for concrete pouring Zone 3 | (+29'-9'' to +41'-9'') | Grid A-B/17-18 | A | 2023-05-08
| Sub Structure | 5th Floor | IT/546 | 2023-04-15 |  | Beam reinforcement | Check beam reinforcement Zone 1 | (+73'-9'') | Grid A-B/1-10 | A | 2023-04-19
| Sub Structure | 5th Floor | IT/547 | 2023-04-15 |  | Slab reinforcement | Check top and Bottom Slab reinforcement Zone 1 | (+73'-9'') | Grid A-B/1-10 | A | 2023-04-19
| Sub Structure | 5th Floor | IT/548 | 2023-04-15 |  | Slab reinforcement | Final slab reinforcement and allow for concrete pouring Zone 1 | (+73'-9'') | Grid A-B/1-10 | A | 2023-04-19
| Sub Structure | 5th Floor | IT/549 | 2023-04-16 |  | Slab formwork | Check formwork of slab & B18 Beam along Stair Zone 1 | (+73'-9'') | Grid A-B/8-9 | A | 2023-04-19
| Sub Structure | 5th Floor | IT/550 | 2023-04-17 |  | Level, layout | Check level & Layout of columns SW's lift walls and B2 Beams Zone 1 | (+73'-9'') | Grid A-B/8-9 | A | 2023-04-19
| Sub Structure | 6th Floor | IT/551 | 2023-04-18 |  | Reinforcement | Check columns (09 Nos) reinforcement Zone 1 I Tower | (+73'-9'' to +84'-9'') | Grid A-F/1-4, 6A, 6F | A | 2023-05-08
| Sub Structure | 6th Floor | IT/552 | 2023-04-19 |  | Reinforcement | Check columns (6 Nos) reinforcement Zone 1 | (+73'-9'' to +84'-9'') | Grid A-F/8-9 | A | 2023-05-08
| Sub Structure | 6th Floor | IT/553 | 2023-05-02 |  | Reinforcement | Final columns reinforcement and allow for concrete pouring Zone 3 I Tower | (+62'-9'' to +73'-9'') | Grid A-F/17-18, D-F/19 | A | 2023-05-08
| Sub Structure | 6th Floor | IT/554 | 2023-05-02 |  | Reinforcement | Final columns SW1, SW2 reinforcement and allow for concrete pouring Zone 3 I Tower | (+62'-9'' to +73'-9'') | Grid B-D/18-19, A-F/19-21 | A | 2023-05-08
| Sub Structure | 6th Floor | IT/555 | 2023-05-01 |  | Reinforcement | Final columns reinforcement and allow for concrete pouring Zone 3 I Tower | (+62'-9'' to +73'-9'') | Grid A-F/21-26 | A | 2023-05-08
| Sub Structure | 2nd Floor | IT/556 | 2023-05-02 |  | Level, layout | Check level, layout of ST-1 Zone 3 | (+29'-9'' to +40'-9'') | Grid A-B/17-18 | A | 2023-05-08
| Sub Structure | 2nd floor | IT/557 | 2023-05-02 |  | Beam reinforcement | Check beam reinforcement Zone 2 | (+29'-9'' to +40'-9'') | Grid A-F/11-17 | A | 2023-05-08
| Sub Structure | 6th Floor | IT/558 | 2023-05-04 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 2 I Tower | (+73'-9'') | Grid A-F/10-16 | A | 2023-05-08
| Sub Structure | 6th Floor | IT/559 | 2023-05-04 |  | Slab reinforcement | Final slab reinforcement and allow for concrete pouring Zone 2 | (+73'-9'') | Grid A-F/10-16 | A | 2023-05-08
| Sub Structure | 6th floor | IT/560 | 2023-05-05 |  | Column reinforcement | Check columns (7 Nos) and SW1, SW2 reinforcement Zone 1 | (+73'-9'' to +84'-9'') | Grid B-F/3, B-D/6, D/8-9 | A | 2023-05-08
| Sub Structure | 1st to 2nd | IT/561 | 2023-04-29 |  | Beam formwork | Check hanging beam formwork along Stair ST-2 and allow for concrete pouring Zone 1 | (+18'-9'' to +29'-9'') | Grid A-B/8-9 | A | 2023-05-08
| Sub Structure | 6th floor | IT/562 | 2023-05-05 |  | Level, layout | Check level, layout of columns Zone 2 | (+73'-9'') | Grid A-B/11-16 | A | 2023-05-08
| Sub Structure | 6th to 7th | IT/563 | 2023-05-06 |  | Columns reinforcement | Check columns (12 Nos) reinforcement Zone 2 I Tower | (+73'-9'' to +84'-9'') | Grid A-F/11-13 | A | 2023-05-08
| Sub Structure | 5th-6th Floor | IT/564 | 2023-05-08 |  | Reinforcement | Final reinforcement of lift and allow for concrete pouring Zone 3 I Tower | (+62'-9'' o +73;-9'') | Grid A-B/17-18 | A | 2023-05-08
| Sub Structure | 6th-7th Floor | IT/565 | 2023-05-08 |  | Reinforcement | Check lift reinforcement Zone 1 I Tower | (+73'-9'' to +84'-9'') | Grid A-B/9-10 | A | 2023-05-17
| Sub Structure | 6th-7th Floor | IT/566 | 2023-05-08 |  | Reinforcement | Check columns (12 Nos) reinforcement Zone 2 I Tower | (+73'-9'' to +84'-9'') | Grid A-F/14-16 | A | 2023-05-17
| Sub Structure | 6th to 7th | IT/567 | 2023-05-09 |  | Condute UPVC | Condute UPVC D class 32mm dia for earthing wire raft to roof in column and lift wall Zone 1 | (+73'-9'' to +84'-9'') | Grid F/9 | A | 2023-05-17
| Sub Structure | 6th Floor | IT/568 | 2023-05-09 |  | Beam reinforcement | check beam reinforcement Zone 3 | (+73'-9'') | Grid A-F/16-26 | A | 2023-05-17
| Sub Structure | 6th to 7th | IT/569 | 2023-05-10 |  | Reinforcement | Check columns, SW1, SW2 reinforcement and allow for concrete pouring Zone 1 | (+73'-9'' to +84'-9'') | Grid A-F/1-10 | A | 2023-05-17
| Sub Structure | 6th floor | IT/570 | 2023-05-10 |  | Slab reinforcement | Check top and bottom Slab reinforcement Zone 3 | (+73'-9'') | Grid A-F/16-26 | A | 2023-05-17
| Sub Structure | 6th floor | IT/571 | 2023-05-10 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 3 | (+73'-9'') | Grid A-F/16-26 | A | 2023-05-17
| Sub Structure | 5th Floor | IT/572 | 2023-05-10 |  | Slab formwork | Check Slab formwork along stair ST-2 Zone 3 | (+73'-9'') | Grid A-F/17-18 | A | 2023-05-17
| Sub Structure | 6th Floor | IT/573 | 2023-05-11 |  | Level, layout | Check level, layout of columns, SW1, SW2, Lift wall and B2 beams Zone 3 | (+73'-9'') | Grid A-F/16-26 | A | 2023-05-17
| Sub Structure | 6th to 7th | IT/574 | 2023-05-11 |  | Columns reinforcement | Check columns (6Nos) Reinforcement Zone 3 | (+73'-9'' to +84'-9'') | Grid D-F/17-19 | A | 2023-05-17
| Sub Structure | 6th to 7th | IT/575 | 2023-05-13 |  | Column reinforcement | Check column (16 Nos) Reinforcement Zone 3 | (+73'-9'' to +84'-9'') | Grid A-F/19-26 | A | 2023-05-17
| Sub Structure | 1st to 2nd | IT/576 | 2023-05-13 |  | Steel fixing | Check formwork, steel fixing of Stair St-1 and allow for concrete pouring Zone 3 | (+29'-9'' to +40'-9'') | Grid A-F/17-18 | A | 2023-05-17
| Sub Structure | 6th 7th Floor | IT/577 | 2023-05-15 |  | Lift wall | Check reinforcement of lift wall and allow for concrete pouring, Zone 1 I Tower | (+73'-9'' to +84'-9'') | Grid A-F/9-10 | A | 2023-05-17
| Sub Structure | 6th 7th Floor | IT/578 | 2023-05-15 |  | SW1, SW2 | Check SW1 and SW2 reinforcement Zone 3 I Tower | (+73'-9'' to +84'-9'') | Grid A-F/18-19 | A | 2023-05-17
| Sub Structure | 6th to 7th | IT/579 | 2023-05-17 |  | Lift reinforcement | Check lift reinforcement Zone 3 | (+73'-9'' to +84'-9'') | Grid A-B/17-18 | A | 2023-05-23
| Sub Structure | 6th to 7th | IT/580 | 2023-05-17 |  | Column reinforcement | Final columns (12 Nos) reinforcement and allow for concrete pouring Zone 2 | (+73'-9'' to +84'-9'') | Grid B-F/12-14, D-F/11, 15D | A | 2023-05-23
| Sub Structure | 7th Floor | IT/581 | 2023-05-17 |  | Beam reinforcement | Check beam reinforcement Zone 1 | (+84'-9'') | Grid A-F/1-10 | A | 2023-05-23
| Sub Structure | 7th Floor | IT/582 | 2023-05-18 |  | Slab reinforcement | Check top and bottom Slab reinforcement Zone 1 | (+84'-9'') | Grid A-F/1-10 | A | 2023-05-23
| Sub Structure | 7th Floor | IT/583 | 2023-05-18 |  | Slab reinforcement | Check reinforcement of slab and allow for concrete pouring Zone 1 | (+84'-9'') | Grid A-F/1-10 | A | 2023-05-23
| Sub Structure | 7th Floor | IT/584 | 2023-05-18 |  | Slab formwork | Check slab formwork along Stair ST-2 Zone 1 | (+84'-9'') | Grid A-F/8-9 | A | 2023-05-23
| Sub Structure | 7th Floor | IT/585 | 2023-05-18 |  | Column reinforcement | Check column reinforcement (14 Nos) and allow for concrete pouring Zone 2 & 3 | (+73'-9'' to +84'-9'') | Grid A/11-16, B/11, B-D/16, B & 15, D-F/17 | A | 2023-05-23
| Sub Structure | 7th Floor | IT/586 | 2023-05-19 |  | Level, layout | Check level, layout of columns, SW1, SW2 and Lift walls, Zone 1 | (+84'-9'') | Grid A-F/1-10 | A | 2023-05-30
| Sub Structure | 3rd to 4th | IT/587 | 2023-05-20 |  | Reinforcement | Check formwork and reinforcement of ST-3 and allow for concrete pouring Zone 3 | (+40'-9'' to +51'-9'') | Grid A-B/17-18 | A | 2023-05-23
| Sub Structure | 6th to 7th | IT/588 | 2023-05-22 |  | Reinforcement | Final reinforcement of columns (20 Nos) SW1, SW2 and allow for concrete pouring Zone 3 | (+73'-9'' to +84'-9'') | Grid A/19-21, A/23-26, B-F/18-26 | A | 2023-05-23
| Sub Structure | 3rd to 4th | IT/589 | 2023-05-22 |  | Level, layout | Check level and layout of Stair ST-3 Zone 1 | (+40'-9'' to +51'-9'') | Grid A-B/8-9 | A | 2023-05-26
| Sub Structure | 3rd to 4th | IT/590 | 2023-05-22 |  | Level, layout | Check level and layout of Stair ST-1 Zone 3 | (+40'-9'' to +51'-9'') | Grid A-B/17-18 | A | 2023-05-26
| Sub Structure | 7th Floor | IT/591 | 2023-05-26 |  | Beam reinforcement | Check beam reinforcement Zone 2 | (+84'-9'') | Grid A-F/10-16 | A | 2023-05-30
| Sub Structure | 7th Floor | IT/592 | 2023-05-27 |  | Slab reinforcement | Check top and bottom reinforcement Zone 2 | (+84'-9'') | Grid A-F/10-16 | A | 2023-05-30
| Sub Structure | 7th Floor | IT/593 | 2023-05-27 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 2 | (+84'-9'') | Grid A-F/10-16 | A | 2023-05-30
| Sub Structure | 3rd to 4th | IT/594 | 2023-05-27 |  | Steel fixing | Check formwork, steel fixing of Stair 3 and allow for concrete pouring Zone 1 | (+40'-9'' to +51'-9'') | Grid A-B/8-9 | A | 2023-05-30
| Sub Structure | 6th Floor | IT/595 | 2023-05-29 |  | Level, layout | Check level, layout of columns Zone 2 | (+84'-9'') | Grid A-F/10-16 | A | 2023-05-30
| Sub Structure | 3rd floor | IT/596 | 2023-05-28 |  | Hanging Beam | Check reinforcement of hanging beam and allow for concrete pouring Zone 3 | (+51'-9'') | Grid A/18-18 | A | 2023-05-30
| Sub Structure | 6th to 7th | IT/597 | 2023-05-29 |  | Column reinforcement | Check columns (10 Nos) Reinforcement Zone 1 | (+84'-9'' to +95'-9'') | Grid A-F/1, A/2-8, 3B | A | 2023-06-16
| Sub Structure | 5th to 6th | IT/598 | 2023-05-29 |  | Reinforcement | Check lift reinforcement and allow for concrete pouring Zone 3 | (+73'-9'' to +84'-9'') | Grid A-B/17-18 | A | 2023-05-30
| Sub Structure | 6th Floor | IT/599 | 2023-05-30 |  | Beam reinforcement | Check beam reinforcement Zone 3 | (+84'-9'') | Grid A-F/16-26 | A | 2023-06-16
| Sub Structure | 6th to 7th | IT/600 | 2023-05-30 |  | Column reinforcement | Check columns (12 Nos) Reinforcement Zone 1 | (+84'-9'' to +95'-9'') | Grid B-F/3-10 | A | 2023-06-16
| Sub Structure | 6th Floor | IT/601 | 2023-06-01 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 3 | (+84'-9'') | Grid A-F/16-26 | A | 2023-06-16
| Sub Structure | 6th Floor | IT/602 | 2023-06-01 |  | Slab reinforcement | Final slab reinforcementand allow for concrete pouring Zone 3 | (+84'-9'') | Grid A-F/16-26 | A | 2023-06-16
| Sub Structure | 6th Floor | IT/603 | 2023-06-01 |  | Slab formwork | Check slab formwork along Stairs Zone 3 | (+84'-9'') | Grid A-B/17-18 | A | 2023-06-16
| Sub Structure | 6th 7th Floor | IT/604 | 2023-06-02 |  | SW Reinforcement | Check SW1, SW2 reinforcement Zone 1 | (+84'-9'' to +95'-9'') | Grid A-F/8 btw 9 | A | 2023-06-16
| Sub Structure | 6th Floor | IT/605 | 2023-06-03 |  | Level, layout | Check level, layout of columns, SW's and lift walls Zone 3 | (+84'-9'') | Grid A-F/16-26 | A | 2023-06-16
| Sub Structure | 6th to 7th | IT/606 | 2023-06-06 |  | Columns reinforcement | Check columns (5 Nos) Reinforcement Zone 3 | (+84'-9'' to +95'-9'') | Grid A-F/26 | A | 2023-06-16
| Sub Structure | 6th to 7th | IT/607 | 2023-06-05 |  | Column reinforcement | Check columns (29 Nos) Reinforcement and SW1, SW2 reinforcement Zone 2-3 | (+84'-9'' to +95'-9'') | Grid A-F/11-12, 16-25 | A | 2023-06-16
| Sub Structure | 6th to 7th | IT/608 | 2023-06-05 |  | Lift reinforcement | Check lift reinforcement Zone 1 I Tower | (+84'-9'' to +95'-9'') | Grid A-F/9-10 | A | 2023-06-16
| Sub Structure | 6th to 7th | IT/609 | 2023-06-07 |  | Lift reinforcement | check lift reinforcement Zone 3 | (+84'-9'' to +95'-9'') | Grid A-F/17-18 | A | 2023-06-16
| Sub Structure | 2nd to 3rd | IT/610 | 2023-06-07 |  | Steel fixing | Check formwork and steel fixing of stair ST-1 and allow for concrete pouring Zone 3 | (+40'-9'' to +51'-9'') | Grid A-F/17-18 | A | 2023-06-16
| Sub Structure | 6th to 7th | IT/611 | 2023-06-08 |  | Column reinforcement | Check columns (9 Nos) reinforcement Zone 2 | (+84'-9'' to +95'-9'') | Grid A-D/13-16, F/16 | A | 2023-06-16
| Sub Structure | 6th to 7th | IT/612 | 2023-06-09 |  | Reinforcement | Check columns and SW1, SW2 reinforcement and allow for concrete pouring Zone 3 | (+84'-9'' to +95'-9'') | Grid A-F/17-26 | A | 2023-06-16
| Sub Structure | 4th to 5th | IT/613 | 2023-06-09 |  | Level, layout | Check level, layout of Stair ST-3 Zone 3 | (+51'-9'' to +62'-9'') | Grid A-F/17-18 | A | 2023-06-16
| Sub Structure | 4th to 5th | IT/614 | 2023-06-10 |  | Level, layout | Check level and layout of Stair ST-3 Zone 1 | (+51'-9'' to +62'-9'') | Grid A-F/8-9 | A | 2023-06-16
| Sub Structure | 7th Floor | IT/615 | 2023-06-10 |  | Condute UPVC | Check condute UPVC D class 32mm dia in column and lift wall earthing wire raft to roof Zone 1 | (+84'-9'' to +95'-9'') | Grid 9/F | A | 2023-06-16
| Sub Structure | 3rd to 4th | IT/616 | 2023-06-12 |  | Formwork, steel fixing | Check formwork and steel fixing of Stair ST-3 and allow for concrete pouring Zone 3 | (+51'-9'' to +62'-9'') | Grid A-F/17-18 | A | 2023-06-16
| Sub Structure | 3rd to 4th | IT/617 | 2023-06-12 |  | Level, layout | Check level, layout of Stair ST-1 Zone 1 | (+51'-9'' to +62'-9'') | Grid A-F/9-10 | A | 2023-06-16
| Sub Structure | 6th to 7th | IT/618 | 2023-06-14 |  | Lift reinforcement | Check lift reinforcement and allow for concrete pouring Zone 3 | (+84'-9'' to +95'-9'') | Grid A-F/17-18 | A | 2023-06-16
| Sub Structure | 6th to 7th | IT/619 | 2023-06-14 |  | Column reinforcement | Check columns reinforcement (3 Nos) Zone 2 | (+84'-9'' to +95'-9'') | Grid F/13-15 | A | 2023-06-16
| Sub Structure | Basement | IT/620 | 2023-06-16 |  | Layout, T Crane 2 | Check layout of Tower Crane 2 and allow for dismantling Zone 1 |  | Grid F-G/8-9 | A | 2023-07-12
| Sub Structure | 8th floor | IT/621 | 2023-06-17 |  | Beam reinforcement | Check beam reinforcement Zone 3 |  | Grid A-F/16-26 | A | 2023-07-12
| Sub Structure | 4th floor | IT/622 | 2023-06-17 |  | Stair reinforcement | Check formwork and stair - 3 reinforcement and allow for concrete pouring Zone 1 | (+51'-9'' to +62'-9'') | Grid A-F/8-9 | A | 2023-07-12
| Sub Structure | 8th floor | IT/623 | 2023-06-19 |  | Reinforcement | Check top and bottom slab reinforcement Zone 3 | (+95'-9'') | Grid A-F/16-26 | A | 2023-07-12
| Sub Structure | 8th floor | IT/624 | 2023-06-19 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 3 | (+95'-9'') | Grid A-F/16-26 | A | 2023-07-12
| Sub Structure | 8th floor | IT/625 | 2023-06-19 |  | slab formwork | Check slab formwork along stair - 2 Zone 3 | (+95'-9'') | Grid A-F/18-18 | A | 2023-07-12
| Sub Structure | 4th to 5th | IT/626 | 2023-06-20 |  | Level, layout | Check level and layout of Stair ST-1 Zone 1 | (+62'-9'' to +73'-9'') | Grid A-F/9-10 | A | 2023-07-12
| Sub Structure | Basement | IT/627 | 2023-06-20 |  | dismantling of TC 2 | Check dismantling of Slab tower crane and move with further procedure Zone 1 |  | Grid F-G/8-9 | B | 2023-07-12
| Sub Structure | 8th floor | IT/628 | 2023-06-22 |  | Column reinforcement | Check columns reinforcement and allow for concrete pouring Zone 2 | (+84'-9'' to +95'-9'') | Grid B-F/12-15, D-F/11, 16,+ A-11-16, B/11, 16 | A | 2023-07-12
| Sub Structure | 8th floor | IT/629 | 2023-06-22 |  | Level, layout | Check level, layout of columns SW1, SW2 and lift wall Zone 3 | (+95'-9'') | Grid A-F/16-26 | A | 2023-07-12
| Sub Structure | Basement | IT/630 | 2023-06-25 |  | Reinforcement | Check raft reinforcement, shuttering and allow for concrete pouring Zone Tower Crane 2 Zone 1 |  | Grid F-G/8-9 | A | 2023-07-12
| Sub Structure | Basement | IT/631 | 2023-07-04 |  | Layout | Check layout of Tower crane 2 raft foundation Zone 1 |  | Grid F-G/8-9 | A | 2023-07-12
| Sub Structure | 8th to 9th | IT/632 | 2023-07-11 |  | Column reinforcement | Check columns (18 Nos) reinforcement Zone 3 | (+18'-9'' to +10'-9'') | Grid A-F/19-26 | A | 2023-07-27
| Sub Structure | 5th to 6th | IT/633 | 2023-07-10 |  | Level, layout | Check level, layout of Stair ST-2 Zone 3 | (+62'-9'' to +73'-9'') | Grid A-B/17-18 | A | 2023-07-12
| Sub Structure | 7th to 8th | IT/634 | 2023-07-13 |  | Reinforcement | Check columns and SW reinforcement and allow for concrete pouring (11 Nos) Zone 1 | (+84'-9'' to +95'-9'') | Grid A-F/1-10 | A | 2023-07-27
| Sub Structure | 5th to 6th | IT/635 | 2023-07-14 |  | steel fixing | Check steel fixing, formwork and allow for concrete pouring Zone 1 | (+63'-9'' to +74'-9'') | Grid A-B/9-10 | A | 2023-07-27
| Sub Structure | 5th to 6th | IT/636 | 2023-07-15 |  | steel fixing | Check steel fixing, formwork and allow for concrete pouring Zone 3 | (+63'-9'' to +74'-9'') | Grid A-B/17-18 | A | 2023-07-27
| Sub Structure | 6th to 7th | IT/637 | 2023-07-15 |  | Level, layout | Check level, layout of Stair ST-3 Zone 1 | (+62'-9'' to +73'-9'') | Grid A-B/8-9 | A | 2023-07-27
| Sub Structure | 5th to 6th | IT/638 | 2023-07-14 |  | Reinforcement | Check hanging beam along st-3 and allow for concrete pouring Zone 1 | (+52' to +63') | Grid A-B/8-9 | A | 2023-07-27
| Sub Structure | 7th to 8th | IT/639 | 2023-07-17 |  | Lift reinforcement | Check lift reinforcement and allow for concrete pouring Zone 1 | (+84'-9'' to +95'-9'') | Grid A-B/9-10 | A | 2023-07-27
| Sub Structure | 8th Floor | IT/640 | 2023-07-17 |  | Beam reinforcement | Check beam reinforcement Zone 2 | (+95'-9'') | Grid A-F/10-16 | A | 2023-07-27
| Sub Structure | 8th Floor | IT/641 | 2023-07-19 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 2 | (+95'-9'') | Grid A-F/10-16 | A | 2023-07-27
| Sub Structure | 8th Floor | IT/642 | 2023-07-19 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 2 | (+95'-9'') | Grid A-F/10-16 | A | 2023-07-27
| Sub Structure | 8th Floor | IT/643 | 2023-07-21 |  | Level, layout | Check level and layout of columns (24 Nos) Zone 2 | (+95'-9'') | Grid A-F/10-16 | A | 2023-07-27
| Sub Structure | 8th Floor | IT/644 | 2023-07-24 |  | slab formwork | Check slab formwork along Stair ST-2 Zone 1 | (+95'-9'') | Grid A-F/8-9 | A | 2023-07-27
| Sub Structure | 8th Floor | IT/645 | 2023-07-24 |  | Reinforcement | Check columns (12 Nos) and SW1, sW2 reinforcement Zone 2 & 3 | (+95'-9'' to +106'-9'') | Grid A-F/15-18, B-E/18 b/w 19 | A | 2023-07-27
| Sub Structure | 8th Floor | IT/646 | 2023-07-24 |  | Reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring Zone 3 | (+95'-9'' to +106'-9'') | Grid A-F/26-26 | A | 2023-07-27
| Sub Structure | 8th Floor | IT/647 | 2023-07-25 |  | Lift reinforcement | Check lift reinforcement Zone 3 | (+95'-9'' to +106'-9'') | Grid A-F/17-18 | A | 2023-07-27
| Sub Structure | 8th Floor | IT/648 | 2023-07-25 |  | Reinforcement | check columns (8 Nos) and SW2 reinforcement and allow for concrete pouring Zone 3 | (+95'-9'' to +106'-9'') | Grid D-F/17-21 | A | 2023-07-27
| Sub Structure | 5th to 6th | IT/649 | 2023-07-25 |  | steel fixing | Check steel fixing, formwork of Stair ST-3 and allow for concrete pouring Zone 1 | (+63' to +74') | Grid A-B/8-9 | A | 2023-07-27
| Sub Structure | 6th to 7th | IT/650 | 2023-07-25 |  | Level, layout | Check level, layout of Stair ST-3 Zone 1 | (+74' to +85') | Grid A-B/8-9 | A | 2023-07-27
| Sub Structure | 6th to 7th | IT/651 | 2023-07-25 |  | Level, layout | Check level and layout of Stair ST-3 Zone 3 | (+74' to +85') | Grid A-B/8-9 | A | 2023-07-27
| Sub Structure | 7th Floor | IT/652 | 2023-07-26 |  | Beam reinforcement | Check beam reinforcement Zone 1 | (+95'-9'') | Grid A-F/1-10 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/653 | 2023-07-26 |  | column,sw1 reinforcement | Check columns (4 Nos) & SW1 Reinforcement and allow for concrete pouring Zone 3 | (+95'-9'' to +106'-9'') | Grid A-B/18-21 | A | 2023-07-27
| Sub Structure | 7th Floor | IT/654 | 2023-07-27 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 1 | (+95'-9'') | Grid A-F/1-10 | A | 2023-08-09
| Sub Structure | 7th Floor | IT/655 | 2023-07-27 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 1 | (+95'-9'') | Grid A-F/1-10 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/656 | 2023-07-27 |  | Column reinforcement | Check columns (16 Nos) reinforcement Zone 2 | (+95'-9'' to +106'-9'') | Grid A-F/11-14 | A | 2023-08-09
| Sub Structure | 6th Floor | IT/657 | 2023-07-27 |  | Level, layout | Check level, layout of Stair ST-1 Zone 1 | (+74' to +85') | Grid A-B/9-10 | A | 2023-08-09
| Sub Structure | 7th Floor | IT/658 | 2023-07-31 |  | Level, layout | Check level layout of columns, SW's & lift wall Zone 1 | (+95'-9'') | Grid A-F/1-10 | A | 2023-08-09
| Sub Structure | 7th Floor | IT/659 | 2023-07-31 |  | Reinforcement | Check lift reinforcement and allow for concrete pouring Zone 3 | (+95'-9'' to +106'-9'') | Grid A-B/17-18 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/660 | 2023-07-31 |  | Column reinforcement | Check columns (12 Nos) Reinforcement Zone 1 | (+95'-9'' to +106'-9'') | Grid D-F/1-10 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/661 | 2023-08-02 |  | Column reinforcement | Check columns (8 Nos) Reinforcement and allow for concrete pouring Zone 2 | (+95'-9'' to +106'-9'') | Grid D-F/15-16 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/662 | 2023-08-02 |  | Column, SW1, SW2 | Check columns (10 Nos) Sw1, SW2 and lift reinforcement Zone 1 | (+95'-9'' to +106'-9'') | Grid A-B/1-10 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/663 | 2023-08-02 |  | Condute UPVC | Check condute UPVC D class 32mm in wall and column for earthing wire raft to roof Zone 1 | (+95'-9'' to +106'-9'') | Grid 9/A+9F | A | 2023-08-09
| Sub Structure | 8th Floor | IT/664 | 2023-08-03 |  | Beam reinforcement | Check beam reinforcement Zone 3 | (+106'-9'') | Grid A-F/16-26 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/665 | 2023-08-04 |  | Column reinforcement | Columns (16 Nos) reinforcement and allow for concrete pouring Zone 2 | (+95'-9'' to +106'-9'') | Grid A-F/11-14 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/666 | 2023-08-04 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 3 | (+106'-9'') | Grid A-F/16-26 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/667 | 2023-08-04 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 3 | (+106'-9'') | Grid A-F/16-26 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/668 | 2023-08-04 |  | Slab formwork | Check slab formwork along Stair ST-2 Zone 3 | (+106'-9'') | Grid A-F/18-18 | A | 2023-08-09
| Sub Structure | 8th Floor | IT/669 | 2023-08-07 |  | Level, layout | Check level and layout of columns (22 Nos) SW1, SW2 and lift wall Zone 3 | (+106'-9'') | Grid A-F/16-26 | A | 2023-09-06
| Sub Structure | 5th floor | IT/670 | 2023-08-07 |  | Level, layout | Check level, layout of Stair ST-1 Zone 3 | (+52' to +63') | Grid A-B/17-18 | A | 2023-08-16
| Sub Structure | 9th floor | IT/671 | 2023-08-08 |  | Column reinforcement | Check columns (18 Nos) reinforcement Zone 3 | (+106-9'' to +117'-9'') | Grid A-F/19-26 | A | 2023-08-09
| Sub Structure | 9th floor | IT/672 | 2023-08-09 |  | Beam reinforcement | Check beam reinforcement Zone 2 | (+106'-9'') | Grid A-F/11-16 | A | 2023-08-16
| Sub Structure | 9th Floor | IT/673 | 2023-08-11 |  | Column reinforcement | Check columns (12 Nos) reinforcement and SW1, SW23 and allow for concrete pouring Zone 1 | (+95'-9'' to +106'-9'') | Grid A-F/6-10 | A | 2023-08-16
| Sub Structure | 6th Floor | IT/674 | 2023-08-11 |  | Level, layout | Check level and layout of Stair ST-1 Zone 1 | (+74'-0'' to +85'-0'') | Grid A-B/9-10 | A | 2023-08-16
| Sub Structure | 6th Floor | IT/675 | 2023-08-11 |  | steel fixing | Check formwork, steel fixing of Stair ST-3 and allow for concrete pouring Zone 3 | (+74'-0'' to +85'-0'') | Grid A-B/18-19 | A | 2023-08-16
| Sub Structure | 8th Floor | IT/676 | 2023-08-11 |  | Column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring Zone 1 | (+95'-9'' to +106'-9'') | Grid A-F/1-5 | A | 2023-08-16
| Sub Structure | 9th Floor | IT/677 | 2023-08-12 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 2 | (+106'-9'') | Grid A-F/11-16 | A | 2023-08-16
| Sub Structure | 9th Floor | IT/678 | 2023-08-12 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 2 | (+106'-9'') | Grid A-F/11-16 | A | 2023-08-16
| Sub Structure | 6th Floor | IT/679 | 2023-08-15 |  | Steel fixing | Check formwork, steel fixing and allow for concrete pouring Zone 1 | (+74'-0'' to +85'-0'') | Grid A-B/9-10 | A | 2023-08-16
| Sub Structure | 8th Floor | IT/680 | 2023-08-15 |  | Lift reinforcement | Check lift reinforcement and allow for concrete pouring Zone 1 | (+95'-9'' to +106'-9'') | Grid A-B/9-10 | A | 2023-08-16
| Sub Structure | 8th Floor | IT/681 | 2023-08-15 |  | Level, layout | Check level and layout of slab Zone 2 | (+106'-9'') | Grid A-F/10-16 | A | 2023-08-18
| Sub Structure | 9th Floor | IT/682 | 2023-08-15 |  | Column reinforcement | Check columns (8 Nos) reinforcement Zone 2 | (+106'-9'' to +117'-9'') | Grid A-F/1, A-D/12, 13A | A | 2023-08-16
| Sub Structure | 6th Floor | IT/683 | 2023-08-15 |  | Steel fixing | Check formwork, steel fixing and allow for concrete pouring Zone 3 | (+52' to +63') | Grid A-B/17-18 | A | 2023-08-16
| Sub Structure | 9th Floor | IT/684 | 2023-08-17 |  | Column reinforcement | Check columns (18 Nos) reinforcement and allow for concrete pouring Zone 3 | (+106'-9'' to +117'-9'') | Grid A-F/24-26, F/19-21, D/19 | A | 2023-08-28
| Sub Structure | 6th Floor | IT/685 | 2023-08-17 |  | Level, layout | Check level, layout of Stair ST-1 Zone 3 | (+63'-0'' to +74'-0'') | A-B/17-18 | A | 2023-08-28
| Sub Structure | 8th Floor | IT/686 | 2023-08-17 |  | Level, layout | Check level and layout of Stair ST-3 Zone 3 | (+85'-0'' to +96'-0'') | A-B/18-19 | A | 2023-08-28
| Sub Structure | 9th Floor | IT/687 | 2023-08-17 |  | Column reinforcement | Check columns (20 Nos) & SW1, SW2 reinforcement Zone 2 and 3 | (+106'-9'' to +117'-9'') | Grid A-F/14-18, B-F/13, F/12, B-D/18-19 | A | 2023-08-28
| Sub Structure | 9th Floor | IT/688 | 2023-08-19 |  | Lift reinforcement | Check lift reinforcement Zone 3 | (+106'-9'' to +117'-9'') | Grid A-B/17-18 | A | 2023-08-28
| Sub Structure | 9th Floor | IT/689 | 2023-08-19 |  | Column reinforcement | Check columns (12 Nos) and SW1, SW2 reinforcement Zone 3 | (+106'-9'' to +117'-9'') | Grid A-D/15-19, F/15-18 | A | 2023-08-28
| Sub Structure | 9th Floor | IT/690 | 2023-08-20 |  | Steel fixing | Check formwork, steel fixing and allow for concrete pouring of Stair ST-3 Zone 1 | (+73'-9'' to +84'-9'') | Grid A-B/8-9 | A | 2023-08-28
| Sub Structure | 9th Floor | IT/691 | 2023-08-22 |  | Beam reinforcement | Check beam reinforcement Zone 1 | (+106'-9'') | Grid A-F/1-10 | A | 2023-08-28
| Sub Structure | 9th Floor | IT/692 | 2023-08-23 |  | Column reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 1 | (+106'-9'') | Grid A-F/13-14 | A | 2023-08-28
| Sub Structure | 9th Floor | IT/693 | 2023-08-23 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 1 | (+106'-9'') | Grid A-F/1-10 | A | 2023-08-28
| Sub Structure | 9th Floor | IT/694 | 2023-08-23 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 1 | (+106'-9'') | Grid A-F/1-10 | A | 2023-08-28
| Sub Structure | 9th Floor | IT/695 | 2023-08-23 |  | Column reinforcement | Check columns (8 Nos ) reinforcement and allow for concrete pouring Zone 2 | (+106'-9'') | Grid A-F/11-12 | A | 2023-08-28
| Sub Structure | 9th Floor | IT/696 | 2023-08-25 |  | Level,layout | Check slab level and layout of columns (22 Nos),SW1, SW2 and lift wall Zone 1 | (+106'-9'') | Grid A-F/1-10 | A | 2023-09-01
| Sub Structure | 9th Floor | IT/697 | 2023-08-25 |  | Reinforcement | Check reinforcement of lift and allow for concrete pouring Zone 3 | (+106'-9'' to +117'-9'') | Grid A-F/17-18 | A | 2023-09-01
| Sub Structure | 10th Floor | IT/698 | 2023-08-26 |  | Beam reinforcement | Check beam reinforcement Zone 3 | (+117'-9'') | Grid A-F/16-26 | A | 2023-09-01
| Sub Structure | 10th Floor | IT/699 | 2023-08-26 |  | Column reinforcement | Check column (12 Nos) reinforcement Zone 1 | (+106'-9'' to +117'-9'') | Grid A-F/6-10 | A | 2023-09-01
| Sub Structure | 8th Floor | IT/700 | 2023-08-28 |  | Steel fixing | Check formwork, steel fixing and allow for concrete pouring of Stair ST-3 Zone 3 | (+85' to +96') | Grid A-B/17-18 | A | 2023-09-01
| Sub Structure | 7th Floor | IT/701 | 2023-08-28 |  | Level, layout | Level, layout of stair ST-3 Zone 1 | (+85' to +96') | Grid A-B/8-9 | A | 2023-09-06
| Sub Structure | 7th floor | IT/702 | 2023-08-28 |  | Level, layout | Check level, layout of Stair ST-1 Zone 1 | (+85' to +96') | Grid A-B/9-10 | A | 2023-09-06
| Sub Structure | 10th Floor | IT/703 | 2023-08-29 |  | Column reinforcement | Check columns (10 Nos) and SW1, SW2 reinforcement Zone 1 | (+106'-9'' to +117'-9'') | Grid A-F/1-4, B-D/8-9 | A | 2023-09-01
| Sub Structure | 7th Floor | IT/704 | 2023-08-28 |  | Beam reinforcement | Check hanging beam reinforcement and allow for concrete pouring Zone 3 | (+73'-9'' to +84'-9'') | Grid A-B/17-18 | A | 2023-09-06
| Sub Structure | 5th to 6th | IT/705 | 2023-08-30 |  | Steel fixing | Check formwork, steel fixing of Stair ST-1 and allow for concrete pouring Zone 3 | (+63' to 74') | Grid A-B/17-18 | A | 2023-09-06
| Sub Structure | 10th Floor | IT/706 | 2023-08-30 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 3 | (+117'-9'') | Grid A-F/16-26 | A | 2023-09-06
| Sub Structure | 10th Floor | IT/707 | 2023-08-30 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 3 | (+117'-9'') | Grid A-F/16-26 | A | 2023-09-06
| Sub Structure | 9th Floor | IT/708 | 2023-08-30 |  | Condute UPVC | Check condute UPVC D class 32mm in lift and columns Zone 1 | (+117'-9'') | Grid F/9, A/10 | A | 2023-09-13
| Sub Structure | 9th Floor | IT/709 | 2023-08-31 |  | Lift reinforcement | Check lift reinforcement Zone 1 I Tower | (+106'-9'' to +117'-9'')) | Grid A-B/9-10 | A | 2023-09-13
| Sub Structure | 9th Floor | IT/710 | 2023-08-30 |  | Column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring Zone 1 | (+106'-9'' to +117'-9'')) | Grid D-F/9-10 | A | 2023-09-06
| Sub Structure | 9th Floor | IT/711 | 2023-08-31 |  | Column reinforcement | Check columns (3 Nos) reinforcement and allow for concrete pouring Zone 1 | (+106'-9'' to +117'-9'')) | Grid B-F/8 | A | 2023-09-06
| Sub Structure | 10th Floor | IT/712 | 2023-09-01 |  | slab formwork | Check slab formwork along Stair ST-3 Zone 3 | (+117'-9'') | Grid A-B/17-18 | A | 2023-09-06
| Sub Structure | 10th Floor | IT/713 | 2023-09-02 |  | level, layout | Check slab level and layout of columns SW1, SW2 and lfit wall Zone 3 | (+117'-9'') | Grid A-F/16-26 | A | 2023-09-06
| Sub Structure | 9th Floor | IT/714 | 2023-09-03 |  | Column reinforcement | Check columns (15 Nos) reinforcement and allow for concrete pouring Zone 3 | (+106'-9'' to +117'-9'')) | Grid A-F/1-6, A/8 | A | 2023-09-06
| Sub Structure | 9th floor | IT/715 | 2023-09-05 |  | level, layout | Check level and layout of stair ST-1 Zone 3 | (+74'-9'' to +85'-9'') | Grid A-B/17-18 | A | 2023-09-13
| Sub Structure | 9th floor | IT/716 | 2023-09-05 |  | Beam reinforcement | Check beam reinforcement Zone 2 | (+117'-9'') | Grid A-F/10-16 | A | 2023-09-13
| Sub Structure | 9th Floor | IT/717 | 2023-09-07 |  | Reinforcement | Check Sw1, SW2 and lift reinforcement and allow for concrete pouring Zone 1 | (+106'-9'' to +117'-9'') | Grid A-D/8-9, A-B/9-10 | A | 2023-09-13
| Sub Structure | 9th Floor | IT/718 | 2023-09-08 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 2 | (+117'-9'') | Grid A-F/10-16 | A | 2023-09-13
| Sub Structure | 9th Floor | IT/719 | 2023-09-08 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 2 | (+117'-9'') | Grid A-F/10-16 | A | 2023-09-13
| Sub Structure | 9th Floor | IT/720 | 2023-09-10 |  | Level, layout | Check level and layout of columns (24 Nos) Zone 2 | (+117'-9'') | Grid A-F/10-16 | A | 2023-09-15
| Sub Structure | 7th Floor | IT/721 | 2023-09-10 |  | Steel fixing | Check formwork and steel fixing of Stair ST-1 and allow for concrete pouring Zone 3 | (+73'-9 to +84'-9'') | Grid A-B/17-18 | A | 2023-09-15
| Sub Structure | 10th to 11th | IT/722 | 2023-09-11 |  | Column reinforcement | check columns (28 Nos) and lift reinforcement Zone 2-3 | (+117'-9'' to +130'-9'') | Grid A-F/11-18, A-B/17-18 | A | 2023-09-15
| Sub Structure | 7th to 8th | IT/723 | 2023-09-10 |  | Beam reinforcement | Check hanging beam reinforcement and allow for concrete pouring Zone 3 | (+84'-9'' to +95'-9'') | Grid A/18-19 | A | 2023-09-15
| Sub Structure | 7th 8th | IT/724 | 2023-09-12 |  | Steel fixing | Check formwork and steel fixing of stair and allow for concrete pouring of Stair ST-01 Zone 1 | (+84'-9'' to +85'-9'') | Grid A-B/9-10 | A | 2023-09-15
| Sub Structure | 7th 8th | IT/725 | 2023-09-12 |  | Level, layout | Check level & layout of Stair ST-01 Zone 3 | (+84'-9'' to +85'-9'') | Grid A-B/17-18 | A | 2023-09-15
| Sub Structure | 8th to 9th | IT/726 | 2023-09-12 |  | Level, layout | Check level and layout of stair ST-03 Zone 3 | (+96' to +107'-9'') | Grid A-B/18-19 | A | 2023-09-15
| Sub Structure | 9th Floor | IT/727 | 2023-09-12 |  | Beam reinforcement | Check beam reinforcement Zone 1 | (+117'-9'') | Grid A-F/1-10 | A | 2023-09-15
| Sub Structure | 9th Floor | IT/728 | 2023-09-14 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 1 | (+117'-9'') | Grid A-F/1-10 | A | 2023-09-15
| Sub Structure | 9th floor | IT/729 | 2023-09-14 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 1 | (+117'-9'') | Grid A-F/1-10 | A | 2023-09-20
| Sub Structure | 10th Floor | IT/730 | 2023-09-13 |  | Column reinforcement | Check columns (11 Nos) reinforcement and allow for concrete pouring Zone 2 | (+117'-9'' to +130'-9'') | Grid A-F/11-12, B-F/13 | A | 2023-09-15
| Sub Structure | 10th Floor | IT/731 | 2023-09-14 |  | Column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 2 | (+117'-9'') | Grid A-F/14, A/13, D/15 | A | 2023-09-15
| Sub Structure | 10th Floor | IT/732 | 2023-09-15 |  | Column reinforcement | Check columns (7 Nos) reinforcement and allow for concrete pouring Zone 2 | (+117'-9'' to +130'-9'') | Grid A-F/16, A-B/15, F/15 | A | 2023-09-20
| Sub Structure | 10th Floor | IT/733 | 2023-09-17 |  | level, layout | Check level and layout SW1, SW2, lift walls and balcony beams Zone 1 | (+117'-9'') | Grid A-F/1-10 | A | 2023-09-20
| Sub Structure | 10th Floor | IT/734 | 2023-09-18 |  | Column reinforcement | Check columns (8 Nos) Zone 3 | (+117'-9'' to +130'-9'') | Grid A-F/19-20 | A | 2023-09-20
| Sub Structure | 7th to 8th | IT/735 | 2023-09-18 |  | steel fixing | Check formwork and steel fixing of Stair ST-3 and allow for concrete pouring Zone 1 | (+84'-9'' to +95'-9'') | Grid A-B/8-9 | A | 2023-09-20
| Sub Structure | 8th to 9th | IT/736 | 2023-09-18 |  | steel fixing | Check formwork and steel fixing of stair st-03 and allow for concrete pouring Zone 3
| Sub Structure | 8th to 9th | IT/736 | 2023-09-18 |  | steel fixing | Check formwork and steel fixing of stair st-03 and allow for concrete pouring Zone 3 | (+96'-9'' to +106'-9'') | Grid A-B/18-19 | A | 2023-09-20
| Sub Structure | 10th to 11th | IT/737 | 2023-09-18 |  | Column, SW1, SW2 | Check columns (10 Nos), sw1, sw2 Zone 3 | (+117'-9'' to +130'-9'') | Grid A-B/18-26 | A | 2023-09-20
| Sub Structure | 10th to 11th | IT/738 | 2023-09-18 |  | Column reinforcement | check columns (10 Nos) reinforcement Zone 1 | (+117'-9'' to +130'-9'') | Grid A-F/1-4 | A | 2023-09-20
| Sub Structure | 10th to 11th | IT/739 | 2023-09-20 |  | Column reinforcement | Check columns (12 Nos) SW1, SW2 reinforcement Zone 1 | (+117'-9'' to +130'-9'') | Grid A-F/6-10 | A | 2023-09-22
| Sub Structure | 10th to 11th | IT/740 | 2023-09-20 |  | Column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring Zone 3 | (+117'-9'' to +130'-9'') | Grid D-F/17-18 | A | 2023-09-22
| Sub Structure | 9th to 10th | IT/741 | 2023-09-20 |  | Level, layout | Check level, layout of Stair ST-3 Zone 3 | (+106'-9'' to +117'-9'') | Grid A-B/17-18 | A | 2023-09-22
| Sub Structure | 8th to 9th | IT/742 | 2023-09-20 |  | Level, layout | Check level and layout of Stair ST-1 Zone 3 | (+95'-9'' to +106'-9'') | Grid A-B/9-10 | A | 2023-09-22
| Sub Structure | 8th to 9th | IT/743 | 2023-09-20 |  | Level, layout | Check level and layout of Stair ST-3 Zone 1 | (+95'-9'' to +106'-9'') | Grid A-B/8-9 | A | 2023-09-22
| Sub Structure | 10th to 11th | IT/744 | 2023-09-21 |  | Lift reinforcement | Check lift reinforcement of lift walls Zone 1 | (+117'-9'' to +130'-9'') | Grid A-B/9-10 | A | 2023-09-22
| Sub Structure | 10th to 11th | IT/745 | 2023-09-21 |  | UPVC | Check condute UPVC class 32mm dia in lift walls and column Zone 1 | (+117'-9'' to +130'-9'') | Grid A-F/9-10 | A | 2023-09-22
| Sub Structure | 9th Floor | IT/746 | 2023-09-22 |  | Column reinforcement | Check columns (15 Nos) reinforcement and allow for concrete pouring Zone 1 | (+117'-9'' to +130'-9'') | Grid A-F/1-8 | A | 2023-09-22
| Sub Structure | 10th to 11th | IT/747 | 2023-09-22 |  | Lift reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 3 | (+117'-9'' to +130'-9'') | Grid A-B/17-18 | A | 2023-09-27
| Sub Structure | 10th to 11th | IT/748 | 2023-09-23 |  | Column reinforcement | Check columns (3 Nos) and SW2 reinforcement and allow for concrete pouring Zone 1 | (+117'-9'' to +130'-9'') | Grid A-D/8-9 | A | 2023-09-27
| Sub Structure | 11th Floor | IT/749 | 2023-09-24 |  | Beam reinforcement | Check beam reinforcement Zone 2 | (+130'-9'') | Grid A-F/11-16 | A | 2023-09-27
| Sub Structure | 10th 11th | IT/750 | 2023-09-24 |  | Column reinforcement | Check columns (4 Nos) and SW1 reinforcement and allow for concrete pouring Zone 1 | (+117'-9'' to +130'-9'') | Grid D-F/8-10 | A | 2023-09-27
| Sub Structure | 11th Floor | IT/751 | 2023-09-25 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 2 | (+130'-9'') | Grid A-F/11-16 | A | 2023-09-27
| Sub Structure | 11th Floor | IT/752 | 2023-09-26 |  | Slab reinforcement | Check top and bottom slab reinforcement and allow for concrete pouring Zone 2 | (+130'-9'') | Grid A-F/11-16 | A | 2023-09-27
| Sub Structure | 10th Floor | IT/753 | 2023-09-26 |  | Lift reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 1 | (+117'-9'' to +130'-9'') | Grid A-B/9-10 | A | 2023-09-27
| Sub Structure | 11th Floor | IT/754 | 2023-09-27 |  | level, layout | Check level and layout of columns (24 Nos) Zone 2 | (+130'-9'') | Grid A-F/11-16 | A | 2023-10-04
| Sub Structure | 11th Floor | IT/755 | 2023-09-28 |  | Beam reinforcement | Check beam reinforcement Zone 1 | (+130'-9'') | Grid A-F/1-10 | A | 2023-10-02
| Sub Structure | 10th Floor | IT/756 | 2023-09-28 |  | SW Reinforcement | Check SW reinforcement and allow for concrete pouring Zone 3 | (+117'-9'' to +130'-9'') | Grid B-D/18-19 | A | 2023-10-02
| Sub Structure | 11th Floor | IT/757 | 2023-09-28 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 1 | (+130'-9'') | Grid A-F/1-10 | A | 2023-10-02
| Sub Structure | 11th Floor | IT/758 | 2023-09-28 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 1 | (+130'-9'') | Grid A-F/1-10 | A | 2023-10-02
| Sub Structure | 10th Floor | IT/759 | 2023-09-28 |  | Column reinforcement | Check columns (12 Nos) reinforcement and allow for concrete pouring Zone 3 | (+117'-9'' to +130'-9'') | Grid B-F/19, B-D/21, A/23, B-D/24, A/25, A-C/26 | A | 2023-10-02
| Sub Structure | 10th Floor | IT/760 | 2023-09-29 |  | Column reinforcement | Check column reinforcement (6 Nos) reinforcement and allow for concrete poring Zone 3 | (+117'-9'' to +130'-9'') | Grid A/19-21, F/21-26, E/26 | A | 2023-10-02
| Sub Structure | 11th Floor | IT/761 | 2023-10-02 |  | level, layout | Check level and layout of columns & Balcony beams Zone 1 | (+130'-9'') | Grid A-F/1-10 | A | 2023-10-06
| Sub Structure | 8th to 9th | IT/762 | 2023-10-02 |  | Level, layout | Check level and layout of Stair ST-1 Zone 3 | (+95'-9'' to +106'-9'') | Grid A/17-18 | A | 2023-10-06
| Sub Structure | 7th to 8th | IT/763 | 2023-10-01 |  | Stiair reinforcement | Check stair ST-1 reinforcement and allow for concrete pouring Zone 3 | (+84'-9'' to +95'-9'') | Grid A/17-18 | A | 2023-10-02
| Sub Structure | 7th Floor | IT/764 | 2023-10-01 |  | Beam reinforcement | Check hanging beam reinforcement and allow for concrete pouring Zone 1 | (+84'-9'') | Grid A/8-9 | A | 2023-10-02
| Sub Structure |  | IT/765 | 2023-10-02 |  | Garbage | Check Ms garbage bin (3 Nos) 2 Nos for I Tower and 1 Nos for L1 Tower |  |  | A | 2023-10-02
| Sub Structure | 8th to 9th | IT/766 | 2023-10-04 |  | Steel fixing | Check formwork and steel fixing of stair ST-1 and allow for concrete pouring Zone 1 | (+95'-9'' to +106'-9'') | Grid A/9-10 | A | 2023-10-04
| Sub Structure | 8th floor | IT/767 | 2023-10-04 |  | Steel fixing | Check formwork and steel fixing of hanging beam and allow for concrete pouring Zone 3 | (+95'-9'') | Grid A/18-19 | A | 2023-10-04
| Sub Structure | 11th Floor | IT/768 | 2023-10-04 |  | Beam reinforcement | Check beam reinforcement Zone 3 | (+130'-9'') | Grid A-F/17-26 | A | 2023-10-06
| Sub Structure | 11th Floor | IT/769 | 2023-10-05 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 3 | (+130'-9'') | Grid A-F/17-26 | A | 2023-10-11
| Sub Structure | 11th Floor | IT/770 | 2023-10-06 |  | Slab formwork | Check slab formwork along stair ST-3 & ST-1 Zone 3 | (+130'-9'') | Grid A-B/17-19 | A | 2023-10-11
| Sub Structure | 11th Floor | IT/771 | 2023-10-06 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 3 | (+130'-9'') | Grid A-F/17-26 | A | 2023-10-11
| Sub Structure | 11th Floor | IT/772 | 2023-10-07 |  | Level, layout | Check level and layout of slab, column lift walls Zone 3 | (+130'-9'') | Grid A-F/17-26 | A | 2023-10-11
| Sub Structure | 8th Floor | IT/773 | 2023-10-08 |  | Stair reinforcement | Check formwork and reinforcement of Stair ST-3 and allow for concrete pouring Zone 1 | (+95'-9'' to +106'-9'') | Grid A/8-9 | A | 2023-10-11
| Sub Structure | 9th to 10th | IT/774 | 2023-10-09 |  | Level, layout | Check level and layout of Stair ST-1 Zone 1 | (+106'-9'' to +117'-9'') | Grid A/9-10 | A | 2023-10-18
| Sub Structure | 9th Floor | IT/775 | 2023-10-10 |  | Level, layout | Check level and layout of Stair ST-3 Zone 1 | (+106'-9'' to +117'-9'') | Grid A/8-9 | A | 2023-10-11
| Sub Structure | 9th Floor | IT/776 | 2023-10-11 |  | Reinforcement of stair | Check formwork & reinforcement of stair ST-1 and allow for concrete pouring Zone 3 | (+96'-9'' to +106'-9'') | Grid A/17-18 | A | 2023-10-18
| Sub Structure | 9th to 10th | IT/777 | 2023-10-11 |  | Level, layout | Check level and layout of stair St-01 Zone 03 | (+106'-9'' to +117'-9'') | Grid A/17-18 | A | 2023-10-18
| Sub Structure | 9th to 10th | IT/778 | 2023-10-17 |  | Reinforcement | Check formwork and reinforcement of Stair ST-1 and allow for concrete pouring Zone 1 | (+106'-9'' to +117'-9'') | Grid A/9-10 | A | 2023-10-18
| Sub Structure | 10th Floor | IT/779 | 2023-10-17 |  | Reinforcement | Check formwork and reinforcement of hanging beam and allow for concrete pouring Zone 1 | (+106'-9'') | Grid A./8-9 | A | 2023-10-18
| Sub Structure | 10th Floor | IT/780 | 2023-10-18 |  | Level, layout | Check level and layout of Stair ST-01 Zone 1 | (+117'-9'' to +130'-9'') | Grid A/8-9 | A | 2023-10-18
| Sub Structure | 9th Floor | IT/781 | 2023-10-18 | 2023-10-18 | Reinforcement Stair | Check formwork, reinforcement of Stair ST-03 and allow for concrete pouring Zone 3 | (+106'-9'' to +117'-9'') | Grid A-B/17-18 | A | 2023-10-23
| Sub Structure | 9th Floor | IT/782 | 2023-10-23 | 2023-10-23 | Stair reinforcement | Check formwork and reinforcement of Stair ST-03 and allow for concrete pouring Zone 1 | (+106'-9'' to +117'-9'') | Grid A/8-9 | A | 2023-10-26
| Sub Structure | 9th Floor | IT/783 | 2023-10-23 | 2023-10-23 | Stair reinforcement | Check formwork and stair reinforcement ST-01 and allow for concrete pouring Zone 3 | (+106'-9'' to +117'-9'') | Grid A/18-19 | A | 2023-10-26
| Sub Structure | 10th Floor | IT/784 | 2023-10-24 | 2023-10-24 | Level and layout | Check level and layout of stair ST-1 Zone 3 | (+117'-9'' to +130'-9'') | Grid A/17-18 | A | 2023-10-27
| Sub Structure | 10th Floor | IT/785 | 2023-10-26 | 2023-10-26 | Level and layout | Check level & layout of Stair ST-3 Zone 3 | (+117'-9'' to +130'-9'') | Grid A/18-19 | A | 2023-10-27
| Sub Structure | 10th Floor | IT/786 | 2023-10-26 | 2023-10-26 | Level and layout | Check level & layout of Stair ST-3 Zone 1 | (+117'-9'' to +130'-9'') | Grid A/8-9 | A | 2023-10-27
| Sub Structure | 10th Floor | IT/787 | 2023-10-26 | 2023-10-26 | Steel fixing | Check formwork and steel fixing of ST-1 and allow for concrete pouring Zone 1 | (+117'-9'' to +130'-9'') | Grid A/9-10 | A | 2023-10-31
| Sub Structure | 10th Floor | IT/788 | 2023-10-30 | 2023-10-30 | Steel fixing | Check formwork and steel fixing of ST-1 & allow for concrete pouring Zone 3 | (+117'-9'' to +130'-9'') | Grid A/17-18 | A | 2023-10-31
| Sub Structure | 10th Floor | IT/789 | 2023-10-30 | 2023-10-30 | Steel fixing | Check formwork and steel fixing of hanging beam & allow for concrete pouring Zone 3 | (+117'-9'') | Grid A/18-19 | A | 2023-10-31
| Sub Structure | 10th Floor | IT/790 | 2023-11-01 | 2023-11-01 | Steel fixing | Check formwork and steel fixing of hanging beam and allow for concrete pouring Zone 1 | (+117'-9'') | Grid A/8-9 | A | 2023-11-08
| Sub Structure | 10th Floor | IT/791 | 2023-11-04 | 2023-11-04 | Steel fixing | Check formwork & steel fixing of stair ST-3 and allow for concrete pouring Zone 3 | (+117'-9'' to +130'-9'') | Grid A/18-19 | A | 2023-11-08
| Sub Structure | 10th Floor | IT/792 | 2023-11-06 | 2023-11-06 | Steel Fixing | Check formwork and steel fixing of Stair ST-3 and allow for concrete pouring Zone 1 | (+117'-9'' to +130'-9'') | Grid A/8-9 | A | 2023-11-08
| Sub Structure | 11th Floor | IT/793 | 2023-11-18 | 2023-11-18 | Column reinforcement | Check columns 97 Nos) reinforcement Zone 1 | (+130'-9'' to +145'-9'') | Grid A-F/1, A/2, F/3 | A | 2023-11-24
| Sub Structure | 11th Floor | IT/794 | 2023-11-19 | 2023-11-19 | Column reinforcement | Check columns (7 Nos) reinforcement and allow for concrete pouring Zone 1 | (+130'-9'' to +145'-9'') | Grid A-F/1, A/2, B/3 | A | 2023-11-24
| Sub Structure | 11th Floor | IT/795 | 2023-11-20 | 2023-11-20 | Column reinforcement | Check columns (10 Nos) reinforcement Zone 1 | (+130'-9'' to +145'-9'') | Grid B-D/3, A/4, A-F/6-8 | A | 2023-11-24
| Sub Structure | 11th Floor | IT/796 | 2023-11-23 | 2023-11-23 | Column reinforcement | Check columns (16 Nos) & Shear walls SW-01, SW-02 reinforcement Zone 1 & 2 | (+130'-9'' to +145'-9'') | Grid A-F/9-13 | A | 2023-11-24
| Sub Structure | 11th Floor | IT/797 | 2023-11-24 | 2023-11-24 | Lift reinforcement | Check lift wall reinforcement Zone 1 | (+130'-9'' to +145'-9'') | Grid A-B/9-10 | A | 2023-11-25
| Sub Structure | 11th Floor | IT/798 | 2023-11-24 | 2023-11-24 | Column reinforcement | Check column (6 Nos) reinforcement and allow for concrete pouring Zone 1 | (+130'-9'' to +145'-9'') | Grid D-F/3, A/4, B-F/6 | A | 2023-11-24
| Sub Structure | 11th Floor | IT/799
| Sub Structure | 11th Floor | IT/800
| Sub Structure | 11th Floor | IT/801 | 2023-11-27 | 2023-11-26 | Beam reinforcement | Check formwork and reinforcement of hanging beam and allow for concrete pouring Zone 3 | (+130'-9'') | Grid A/18-19 | A | 2023-11-28
| Sub Structure | 11th Floor | IT/802 | 2023-11-27 | 2023-11-27 | Column reinforcement | Check columns (12 Nos) reinforcement Zone 2 I Tower | (+130'-9'' to +145'-9'') | Grid A-F/14-16 | A | 2023-11-30
| Sub Structure | 11th Floor | IT/803 | 2023-11-27 | 2023-11-27 | Column reinforcement | Check columns (10 Nos), SW-01 pour 2 and columns (2 Nos) pour 1 reinforcement and allow for concrete pouring Zone 1 | (+130'-9'' to +145'-9'') | Grid A/1-8, B/1-6, D-F/8, F/9 | A | 2023-11-28
| Sub Structure | 11th Floor | IT/804 | 2023-11-28 | 2023-11-28 | Column reinforcement | Check columns (7 Nos), SW-2 reinforcement and allow for concrete pouring Zone 1 & 2 | (+130'-9'' to +145'-9'') | Grid D/9, D-F/10, A-F/11 | A | 2023-11-29
| Sub Structure | 11th Floor | IT/805 | 2023-11-29 | 2023-11-29 | Lift reinforcement | Check lift wall reinforcement Zone 3 | (+130'-9'' to +145'-9'') | Grid A-B/17-18 | A | 2023-11-30
| Sub Structure | 11th Floor | IT/806 | 2023-11-30 | 2023-11-29 | column, sw2 reinforcement | Check columns (7 Nos), SW-02 & columns (6 Nos) reinforcement and allow for concrete pouring Zone 1 & 2 | (+130'-9'' to +145'-9'') | Grid B/8, D-F/9-10, A-F/11-12 | A | 2023-11-30
| Sub Structure | 11th Floor | IT/807 | 2023-12-01 | 2023-12-01 | Column reinforcement | Check columns (6 Nos) and (4 Nos) reinforcement and allow for concrete pouring Zone 2 | (+130'-9'' to +145'-9'') | Grid A-B/11, A-F/12-13 | A | 2023-12-05
| Sub Structure | 11th Floor | IT/808 | 2023-12-02 | 2023-12-02 | Lift reinforcement | Check lift walls reinforcement and allow for concrete pouring Zone 1 | (+130'-9'' to +145'-9'') | Grid A-B/9-10 | A | 2023-12-05
| Sub Structure | 11th Floor | IT/809 | 2023-12-06 | 2023-12-05 | Lift wall reinforcement | Check lift walls Reinforcement and allow for concrete pouring Zone 1 | (+130'-9'' to +145'-9'') | Grid A-B/9-10 | A | 2023-12-11
| Sub Structure | 11th Floor | IT/810 | 2023-12-06 | 2023-12-06 | Column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring Zone 1 | (+130'-9'' to +145'-9'') | Grid A-F/13, D-F/14 | A | 2023-12-11
| Sub Structure | 11th Floor | IT/811 | 2023-12-07 | 2023-12-07 | Column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 2 | (+130'-9'' to +145'-9'') | Grid A-B/14, A-F/15 | A | 2023-12-11
| Sub Structure | 11th Floor | IT/812 | 2023-12-08 | 2023-12-08 | Beam reinforcement | Check beams reinforcement Zone 1 | (+145'-9'') | Grid A-F/1-10 | A | 2023-12-11
| Sub Structure | 11th Floor | IT/813 | 2023-12-08 | 2023-12-08 | Slab formwork | Check slab formwork along stairs ST-3 Zone 1 | (+145'-9'') | Grid A-B/8-9, A/9-10 | A | 2023-12-11
| Sub Structure | Top Roof | IT/814 | 2023-12-09 | 2023-12-09 | Slab reinforcement | Check Top and bottom slab reinforcement Zone 1 | (+145'-9'') | Grid A-B/1-10 | A | 2023-12-18
| Sub Structure | 11th Floor | IT/815 | 2023-12-09 | 2023-12-09 | Column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 2 | (+130'-9'' to +145'-9'') | Grid A/15, B-F/16 | A | 2023-12-18
| Sub Structure | Top Floor | IT/816 | 2023-12-11 | 2023-12-11 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 1 | (+145'-9'') | Grid A-F/1-10 | A | 2023-12-22
| Sub Structure | Top Roof | IT/817 | 2023-12-11 | 2023-12-11 | PW, WP, Ramp, Dowels | Check parapet wall, WTB1 & Swimming Pool, Ramp Dowels reinforcement & layout Zone 1 | (+145'-9'') | Grid A-F/1-10 | A | 2023-12-18
| Sub Structure | 11th Floor | IT/818 | 2023-12-13 | 2023-12-13 | Column reinforcement | check columns (12 Nos) reinforcement and allow for concrete pouring Zone 2 | (+130'-9'' to +145'-9'') | Grid A-F/14-16 | A | 2023-12-18
| Sub Structure | 11th Floor | IT/819 | 2023-12-13 | 2023-12-13 | Beam reinforcement | Check hanging beam reinforcement and allow for concrete pouring Zone 1 | (+130'-9'') | Grid A-F/14-16 | A | 2023-12-18
| Sub Structure | 11th Floor | IT/820 | 2023-12-16 | 2023-12-16 | level, layout | Check level and layout of Stair ST-3 landing level (+138'-7'') Zone 1 | (+130'-9'' to +145'-9'') | Grid A-B/8-9 | A | 2023-12-22
| Sub Structure | top Floor | IT/821 | 2023-12-16 | 2023-12-16 | level, layout | Check level and layout of columns Shear Wall parapet wall & Dowels Zone 1 | (+145'-9'') | Grid A-F/1-10 | A | 2023-12-22
| Sub Structure | 11th Floor | IT/822 | 2023-12-20 | 2023-12-20 | level, layout | Check level and layout of Stair ST-01 landing | (+130'-9'' to +145'-9'') | Grid A-B/9-10 | A | 2023-12-22
| Sub Structure | 11th Floor | IT/823 | 2023-12-20 | 2023-12-20 | Stair reinforcement | Check formwork and reinforcement of Stair ST-03 and allow for concrete pouring Zone 01 | (+130'-9'' to +145'-9'') | Grid A-B/9-10 | A | 2023-12-27
| Sub Structure | Top Floor | IT/824 | 2023-12-23 | 2023-12-23 | Parapet Wall | Check parapet wall reinforcement Zone 1 | (+145'-9'') | Grid A-F/9-1-10 | A | 2024-01-03
| Sub Structure | Top Floor | IT/825 | 2023-12-28 | 2023-12-28 | Beam reinforcement | Check beam reinforcement Zone 2 | (+145'-9'') | Grid A-F/11-16 | A | 2024-01-03
| Sub Structure | Top Floor | IT/826 | 2023-12-28 | 2023-12-28 | column, SW reinforcement | Check columns (22 Nos) SW SW-01, SW-02 reinforcement Zone 3 | (+130'-9'' to +145'-9'') | Grid A-F/11-16 | A | 2024-01-03
| Sub Structure | Top Floor | IT/827 | 2023-12-28 | 2023-12-28 | Stair reinforcement | Check formwork and stair ST-01 reinforcement and allow for concrete pouring Zone 1 | (+130'-9'' to +145'-9'') | Grid A-B/9-10 | A | 2024-01-03
| Sub Structure | 11th Floor to Top | IT/828 | 2023-12-29 | 2023-12-29 | Column reinforcement | Check columns (3 Nos) reinforcement and allow for concrete pouring Zone 3 | (+130'-9'' to +145'-9'') | Grid D-F/17, D/18 | A | 2024-01-03
| Sub Structure | Top Floor | IT/829 | 2023-12-30 | 2024-01-01 | Slab reinforcement | Check top and bottom slab reinforcement Zone 2 | (+145'-9'') | Grid A-F/11-16 | A | 2024-01-03
| Sub Structure | Top Floor | IT/830 | 2023-12-30 | 2024-01-01 | Slab reinforcement | Check slab rienforcement and allow for concrete pouring Zone 2 | (+145'-9'') | Grid A-F/11-16 | A | 2024-01-03
| Sub Structure | 11th Floor to Top | IT/831 | 2024-01-01 | 2023-12-30 | Column reinforcement | Check columns (1 Nos) reinforcement and allow for concrete pouring Zone 3 | (+130'-9'' to +145'-9'') | Grid F/18 | A | 2024-01-03
| Sub Structure | 11th Floor to Top | IT/832 | 2024-01-01 | 2023-12-31 | Column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 3 | (+130'-9'' to +145'-9'') | Grid A-F/19, D-F/21 | A | 2024-01-03
| Sub Structure | Top Floor | IT/833 | 2024-01-01 | 2023-12-30 | PW Reinforcement | Check parapet wall reinforcement Zone 2 | (+145'-9'') | Grid A-F/11-16 | A | 2024-01-03
| Sub Structure | Top Floor | IT/834 | 2024-01-02 | 2024-01-02 | level, layout | Check level and layout of Slab & Parapet Walls, planter dowels & columns dowels Zone 2 | (+145'-9'') | Grid A-F/11-16 | A | 2024-01-03
| Sub Structure | 11th Floor to Top | IT/835 | 2024-01-03 | 2024-01-03 | column, SW reinforcement | Check columns (10 Nos), Columns (2 Nos) and SW-1 and SW-2 reinforcement and allow for concrete pouring Zone 3 | (+130'-9'' to +145'-9'') | Grid D-F/17-18, A-F/19-21 | A | 2024-01-09
| Sub Structure | 11th Floor to top | IT/836 | 2024-01-05 | 2024-01-05 | Lift wall reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 3 | (+130'-9'' to +145'-9'') | Grid A-B/17-18 | A | 2024-01-09
| Sub Structure | 11th Floor to top | IT/837 | 2024-01-05 | 2024-01-05 | column, SW reinforcement | Check columns and SW-1 and SW-2 reinforcement and allow for concrete pouring Zone 3 | (+130'-9'' to +145'-9'') | Grid A-F/26, A/25, A-B/21, B-D/19 | A | 2024-01-09
| Sub Structure | 11th Floor to Top | IT/838 | 2024-01-08 | 2024-01-08 | Column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring Zone 3 | (+130'-9'' to +145'-9'') | Grid A/23, B-F/24, A/25, A-F/26 | A | 2024-01-09
| Sub Structure | 11th Floor to Top | IT/839 | 2024-01-10 | 2024-01-10 | Lift wall reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 3 | (+130'-9'' to +145'-9'') | Grid A-B/17-18 | A | 2024-01-17
| Sub Structure | Top Floor | IT/840 | 2024-01-12 | 2024-01-11 | Hanging Beam | Chek formwork and reinforcement of hanging beam and allow for concrete pouring Zone 1 | (+145'-9'') | Grid A/8-9 | A | 2024-01-17
| Sub Structure | Basement to 10th | IT/841 | 2024-01-16 | 2024-01-16 | Housekeeping | Check complete housekeeping of I Tower with stairs ST-01 & ST-3 Zone 1-2-3 | (-13'-3'' to +117'-9'') | Grid A-F/1-26 | A | 2024-01-24
| Sub Structure | Roof | IT/842 | 2024-01-17 | 2024-01-17 | Beam reinforcement | Check beam reinforcement Zone 3 | (+145'-9'') | Grid A-F/17-26 | A | 2024-01-24
| Sub Structure | Top Floor | IT/843 | 2024-01-19 | 2024-01-20 | Slab reinforcement | Check top and bottom slab reinforcement , ramp & parapet wall reinforcement Zone 3 | (+145'-9'') | Grid A-F/17-26 | A | 2024-01-24
| Sub Structure | top Floor | IT/844 | 2024-01-19 | 2024-01-20 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 3 | (+145'-9'') | Grid A-F/17-26 | A | 2024-01-24
| Sub Structure | top Floor | IT/845 | 2024-01-19 | 2024-01-20 | Slab formwork | Check slab formwork along stair ST-01 Zone 3 | (+145'-9'') | Grid A/18 | A | 2024-01-24
| Sub Structure | Top Floor | IT/846 | 2024-01-22 | 2024-01-22 | level, layout | Check level and layout of slab & parapet wall, ramp Zone 3 | (+145'-9'') | Grid A-F/17-26 | A | 2024-02-01
| Sub Structure | Top Floor | IT/847 | 2024-01-27 | 2024-01-29 | PW Reinforcement | Check parapet wall reinforcement Zone 2 & 3 | (+145'-9'') | Grid A-F/11-26 | A | 2024-02-15
| Sub Structure | 11th Floor | IT/848 | 2024-01-29 | 2024-01-29 | level, layout | Check level & layout of stair ST-03 Zone 3 | (+130'-9'' to +145'-9'') | Grid A-F/18-19 | A | 2024-01-30
| Sub Structure | 11th Floor | IT/849 | 2024-02-01 | 2024-02-01 | Stair reinforcement | Check formwork and stair st-3 reinforcement and allow for concrete pouring Zone 3 | (+130'-9'' to +145'-9'') | Grid A-F/18-19 | A | 2024-02-15
| Sub Structure | 11th Floor | IT/850 | 2024-01-09 | 2024-02-07 | Beam reinforcement | Check hanging beam reinforcement and allow for concrete pouring Zone 3 ST-3 | (+145'-9'') | Grid A-F/14-16 | A | 2024-02-15
| Sub Structure | 11th Floor to Top | IT/851 | 2024-02-11 | 2024-02-12 | level, layout | Check level and layout of stair ST-01 Zone 3 | (+130'-9'' to +145'-9'') | Grid A-B/17-18 | A | 2024-02-15
| Sub Structure | Top Floor | IT/852 | 2024-02-16 | 2024-02-16 | PW Reinforcement | Check PW reinforcement and allow for concrete pouring Zone 1 | (+145'-9'' to +149'-9'') | Grid C-F/1, F/1-9 | A | 2024-02-19
| Sub Structure | 11th Floor to Top | IT/853 | 2024-02-19 | 2024-02-17 | Stair reinforcement | Check formwork and stair ST-1 reinforcement and allow for concrete pouring Zone 3 | (+130'-9'' to +145'-9'') | Grid A-B/17-18 | A | 2024-02-22
| Sub Structure | top Floor | IT/854 | 2024-02-25 | 2024-02-25 | PW Reinforcement | Check PW reinforcement and allow for concrete pouring Zone 1 & 2 | (+145'-9'' to +149'-6'') | Grid F/9-15 | A | 2024-03-05
| Sub Structure | Top Floor | IT/855 | 2024-03-01 | 2024-03-01 | Machine room reinforcement | Check machine room reinforcement Zone 1 | (+145'-9'' to +165'-8''-+145'-9'' to +159'-6'') | Grid A-B/9-10 | A | 2024-03-06
| Sub Structure | Top Floor | IT/856 | 2024-03-01 | 2024-03-01 | Column reinforcement | Check columns (2 Nos) reinforcement Zone 2 | (+145'-9'' to +157'-2'') | Grid A-B/11 | A | 2024-03-06
| Sub Structure | Top Floor | IT/857 | 2024-03-01 | 2024-03-01 | PW Reinforcement | Check PW reinforcement and allow for concrete pouring Zone 2 & 3 | (+145'-9'' to +149'-6'') | Grid F/15-26 | A | 2024-03-06
| Sub Structure | Top Floor | IT/858 | 2024-03-06 | 2024-03-06 | UPVC | Check condute UPVC D class 32 mm in lift wall/machine room Zone 1 | (+145'-9'' to +159'-6'') | Grid A/9 | A | 2024-03-08
| Sub Structure | top floor to Mumty | IT/859 | 2024-03-07 | 2024-03-07 | Column reinforcement | Check columns (2 Nos) reinforcement Zone 3 top floor to mumty | (+145'-9'' to +165'-8'' & +145'-9'' to +159'-6'') | Grid A-B/17-18, A-B/16 | A | 2024-03-08
| Sub Structure | Top Floor | IT/860 | 2024-03-13 | 2024-03-12 | PW Reinforcement | Check Parapet wall reinforcement and allow for concrete pouring Zone 3 | +145'-9'' to +159'-6'') | Grid A-F/26, A/19-26 | A | 2024-03-14
| Sub Structure | top Floor | IT/861 | 2024-03-24 | 2024-03-24 | wall reinforcement | Check PW reinforcement and allow for concrete pouring Zone 2 & 3 | (+145'-9'' to +149'-6'') | Grid A/11-16 | A | 2024-04-02
| Sub Structure | Basement | IT/862 | 2024-06-26 | 2024-06-27 | Primer, membrane | Check vertical primer & membrane Zone 1, 2 & 3 |  | Grid A/1-26, A-G/1, A-G/26 | A | 2024-07-01
| Sub Structure | GF | IT/863 | 2024-07-03 | 2024-07-03 | Primer, membrane | Check vertical primer, membrane of RTW Zone 1 & 3 |  | Grid A-G/1 & 26 | A | 2024-07-04
| Sub Structure | GF | IT/864 | 2024-07-24 | 2024-07-24 | Epoxy rebaring | Check epoxy rebaring for stair Zone 1 & 3 | (+1'-9'' to +10'-6'') | Grid A-B/8-9, A-B/18-18 | A | 2024-07-26
| Sub Structure | GF | IT/865 | 2024-07-24 | 2024-07-24 | level, layout | Check level & layout of stair Zone 1 | (+1'-9'' to +10'-6'') | Grid A-B/8-9 | A | 2024-07-30
| Sub Structure | basement | IT/866 | 2024-07-24 | 2024-07-24 | Stair reinforcement | Check formwork and stair st-3 reinforcement & allow for concrete pouring Zone 1 | (+1'-9'' to +10'-6'') | Grid A-B/8-9 | A | 2024-07-26
| Sub Structure | GF to 1st floor | IT/867 | 2024-07-27 | 2024-07-27 | Epoxy rebaring | Check epoxy rebaring fo rhanging beam of st-03 with hilti RE-100 Zone 1 | (+16'-0'') | Grid A/8-9 | A | 2024-07-30
| Sub Structure | GF to 1st floor | IT/868 | 2024-07-29 | 2024-07-29 | Level, layout | Check level layout of stair st-3 Zone 1 & 3 | (+10'-6'' to +18'-9'' to +1'-9'' to +10'-6'') | Grid A-B/8-9, A-B/18-18 | A | 2024-07-31
| Sub Structure | GF to 1st floor | IT/869 | 2024-07-29 | 2024-07-29 | reinforcement | Check formwork and stair st-3 reinforcement and allow for concrete pouring Zone 3 | (+1'-9'' to +10'-6'') | Grid A-B/18-18 | A | 2024-08-03
| Sub Structure | GF to 1st floor | IT/870 | 2024-07-31 | 2024-07-30 | formwork, reinforcement | Check formwork & reinforcement of stair ST-03 & column reinforcement and allow for concrete work | (+10'-6'' to +18'-9') | Grid A-B/8-9 | A | 2024-08-03
| Sub Structure | GF to 1st floor | IT/871 | 2024-08-02 | 2024-08-02 | formwork | Check formwork and reinforcement of stair st-3 & pickup column and allow for concrete pouring Zone 3 | (+10'-6'' to +18'-9') | Grid A-B/18-18 | A | 2024-08-28
| Sub Structure | 1st floor | IT/872 | 2024-08-05 | 2024-08-04 | stair beam | Check stair st-3 beam and allow for concrete pouring Zone 3 | (+16'-6'') | Grid A-B/8-9 | A | 2024-08-07
| Sub Structure | basement | IT/873 | 2024-09-12 | 2024-09-12 | swimming pool | Check layout of swimming pool wall & stair dowel before steel fixing zone 2 | (+15'-9'') | Grid A-F/12-15 | A | 2024-09-18
| Sub Structure | Top Floor | IT/874 | 2024-09-23 | 2024-09-24 | swimming pool | Check swimming pool base slab bottom, top & walls dowels reinforcement | (+145'-9'') | Grid A-F/12-15 | A | 2024-10-02
| Sub Structure | Top floor | IT/875 | 2024-10-02 | 2024-10-01 | reinforcement | Check reinforcement and allow for concrete pouring zone 1 | (+145'-9'' to +156'-6'') | Grid A-B/9-10 | A | 2024-10-09
| Sub Structure | Top floor | IT/876 | 14-oct--24 | 14-oct--24 | reinforcement | Check swimming pool reinforcement & allow for concrete pouring zone 2 | (+145'-9'') | Grid A-F/12-15 | A | 2024-10-18
| Sub Structure | Top floor | IT/877 | 14-oct--24 | 14-oct--24 | water stopper | Check water stopper of swimming pool base slab | (+145'-9'') | Grid A-F/12-15 | A | 2024-10-18
| Sub Structure | Top floor | IT/878 | 2024-10-16 | 2024-10-16 | level, | Check level of swimming pool base slab zone 2 | (+145'-9'') | Grid A-F/12-15 | A | 2024-10-24 | A
| Sub Structure | top floor | IT/879 | 2024-10-17 | 2024-10-17 | Steel Fixing | Check steel fixing of swimming wall zone 2 | (+145'-9'') | Grid A-F/12-15 | A | 2024-10-24
| Sub Structure | top floor | IT/880 | 2024-10-23 | 2024-10-22 | reinforcement | Check mumty columns (2 Nos) reinforcement and allow for concrete pouring zone 2 | (+145'-9'' to +156'-6'') | Grid A-B/11 | A | 2024-10-30
| Sub Structure | Top floor | IT/881 | 2024-10-30 | 2024-10-30 | joint treatment | Check expansion joint treatment in RW outer side zone 3 & 4 | (-13'-00'' to +0'-00'') | Grid G/26 | A | 2024-11-06
| Sub Structure | Top floor | IT/882 | 2024-11-02 | 2024-11-02 | epoxy | Check epoxy rebaring for pick up columns with Hilti RE-100 dia 6 (16 Nos) zone 1 & 2 | (+145'-9'') | Grid A/11, A/16 | A | 2024-11-06
| Sub Structure | top floor | IT/883 | 2024-11-04 | 2024-11-04 | layout | Check layout of pickup columns zone 1 & 2 | (+145'-9'') | Grid A/11, A/16 | A | 2024-11-06
| Sub Structure | top floor | IT/884 | 2024-11-07 | 2024-11-07 | reinforcement | Check Kids pool wall reinforcement and allow for concrete pouring zone 2 | (+145'-9'' to +147'-9'') | Grid D-F/10-12 | A | 2024-11-09
| Sub Structure | Top floor | IT/885 | 2024-11-08 | 2024-11-09 | Beam reinforcement | Check Mummty beam reinforcement zone 1 & 2 | (+159'-6'') | Grid A-B/9-11 | A | 2024-11-14
| Sub Structure | top floor | IT/886 | 2024-11-08 | 2024-11-08 | reinforcement | Check Mummty slab top and bottom reinforcement zone 1 & 2 | (+159'-6'') | Grid A-B/9-11 | A | 2024-11-08
| Sub Structure | top floor | IT/887 | 2024-11-10 | 2024-11-10 | Column reinforcement | Check pickup column reinforcement zone 1 | (+159'-0'') | Grid A/11 | A | 2024-11-14
| Sub Structure |  | IT/888
| Sub Structure | top floor | IT/889 | 2024-11-10 | 2024-11-10 | reinforcement | Check pickup columns reinforcement and allow for concrete pouring zone 1 | (+159'-0'') | Grid A/11 | A | 2024-11-14
| Sub Structure | top floor | IT/890 | 2024-11-11 | 2024-11-11 | level | Check level of mummty slab & upstand beam layout, wall zone 1 & 2 | (+159'-0'') | Grid A-B/9-11 | A | 2024-11-14
| Sub Structure | Top floor | IT/891 | 2024-11-15 | 2024-11-15 | reinforcement | Check lounging pool wall reinforcement zone 2 | (+145'-9'' to +148'-9'') | Grid B-F/15-16 | A | 2024-11-28
| Sub Structure | top floor | IT/892 | 2024-11-15 | 2024-11-15 | reinforcement | Check mumty columns & pickup column reinforcement zone 1 & 2 | (+145'-9'' to +159'-0'') | Grid A-B/16, A/16 | A | 2024-11-22
| Sub Structure | basement | IT/893 | 2024-11-29 | 2024-11-29 | RW Treatment | Check expansion joint treatment in RW inner zone 3 & 4 | (-12'-3'' to +0'-00'') | Grid G/26 | A | 2024-12-02
| Sub Structure | Mumty Roof | IT/894 | 2024-11-30 | 2024-11-29 | reinforcement | Check mummty upstand beam reinforcement and allow to start concrete pouring zone 1 & 2 | (+159'-0'' to +159'-11'') | Grid A-B/9-11 | A | 2024-12-02
| Sub Structure | top to mummy | IT/895 | 2024-12-01 | 2024-11-30 | reinforcement | Check machine room reinforcement and allow for concrete pouring zone 3 | (+145'-9'' to +156'-6'') | Grid A-B/17-18 | A | 2024-12-02
| Sub Structure | top to mummy | IT/896 | 2024-12-12 | 2024-12-11 | reinforcement | Check columns (2 Nos) and pickup column (1 No) reinforcement and allow for concrete pouring zone 2 | (+145'-9'' to +156'-6'') | Grid A-B/16, A/16 | A | 2024-12-16
| Sub Structure | top floor | IT/897 | 2024-12-13 | 2024-12-12 | reinforcement | Check lounging pool wall reinforcement and allow for concrete pouring zone 2 | (+145'-9'' to +148'-9'') | Grid D-F/15-16 | A | 2024-12-16
| Sub Structure | GF | IT/898 | 2024-12-13 | 2024-12-13 | reinforcement | Check toe wall reinforcement zone 1 & 3 | (+0'-00'') | Grid A/9-10, A/17-18 | A | 2024-12-19
| Sub Structure | Mumty Roof | IT/899 | 2024-12-20 | 2024-12-20 | Slab reinforcement | Check Mummty slab beam & Top & bottom reinforcement zone 2 & 3 | (+0'-00'') | Grid A-B/1-18 | A | 2024-12-23
| Sub Structure | Mummty | IT/900 | 2024-12-23 | 2024-12-23 | Steel Fixing | Check steel fixing of Mummty slab and allow to concrete pouring zone 2 & 3 | (+159'-00'') | Grid A-B/16-18 | A | 2024-12-31
| Sub Structure | Mummty | IT/901 | 2025-01-04 | 2025-01-04 | level, layout | Check level, layout of mummty slab zone 2 & 3 | (+159'-00'') | Grid A-B/16-18 | A | 2024-12-28
| Sub Structure | GF | IT/902 | 2024-12-27 | 2024-12-27 | wall reinforcement | Check toe wall reinforcement and allow for concrete pouring zone 1 & 3 | (+0'-00'') | Grid A/9-10, A/17-18 | A | 2024-12-31
| Sub Structure | Mummty | IT/903 | 2024-12-31 | 2024-12-30 | reinforcement | Check upstand beam reinforcement and allow for concrete pouring zone 2 & 3 | (+159'-00'' to 159'-11'') | Grid A-B/16-18 | A | 2024-01-02
| Sub Structure | 9th floor | IT/904 | 2025-01-03 | 2025-01-02 | reinforcement | Check parapet wall reinforcement and allow for concrete pouring zone 1 | (+145'-9'' to +149'-6'') | Grid A-C/1, A/1-7 | A | 2025-01-05
| Sub Structure | top floor | IT/905 | 2025-01-08 | 2025-01-08 | reinforcement | Check genset beam reinforcement zone 1 | (+145'-9'') | Grid A-B/1-8 | A | 2025-01-10
| Sub Structure | top floor | IT/906 | 2025-01-17 | 2025-01-16 | reinforcement | Check Genset beam reinforcement and allow for concrete pouring zone 1 | (+145'-9'') | Grid A-B/1-8 | A | 2025-01-17
| Sub Structure | top floor | IT/907 | 2025-01-18 | 2025-01-18 | layout | Check layout of ramp and OHWT zone 1 & 3 | (+145'-9'') | Grid A-B/1-8 | A | 2025-01-22
| Sub Structure | top floor | IT/908 | 2025-01-21 | 2025-01-21 | layout | Check layout of ramp & OHWT zone 1 & 3 | (+145'-9'') | Grid A-B/8-8, A-B/19-19 | A | 2025-01-27
| Sub Structure | Mummty to top | IT/909 | 2025-01-22 | 2025-01-21 | reinforcement | Check machine room walls reinforcement and allow for concrete pouring zone 1 | (+159'-00'' to +165'-00'') | Grid A-B/9-10 | A | 2025-01-22
| Sub Structure | top floor | IT/910 | 2025-01-22 | 2025-01-22 | reinforcement | Check ramp reinforcement zone 1 | (+145'-9'') | Grid 10-11 | A | 2025-01-27
| Sub Structure | top floor | IT/911 | 2025-01-28 | 2025-01-28 | reinforcement | check OHWT reinforcement zone 3 | (++148'-5'') | Grid A-B/18-19 | A | 2025-01-31
| Sub Structure | Mummty to top | IT/912 | 2025-01-31 | 2025-01-30 | reinforcement | check machine room reinforcement and allow for concrete pouring zone 3 | (+159'-0'' to +165'-00'') | Grid A-B/17-17 | A | 2025-02-05
| Sub Structure | Mummty floor | IT/913 | 2025-02-04 | 2025-02-03 | reinforcement | Check machine room slab reinforcement and allow for concrete pouring zone 1 | (+165'-2'') | Grid A-B/9-10 | A | 2025-02-05
| Sub Structure | Mummty floor | IT/914 | 2025-02-04 | 2025-02-04 | layout | Check machine room slab top & layout of parapet zone 1 | (+165'-2'') | Grid A-B/9-10 | A | 2025-02-08
| Sub Structure | top floor | IT/915 | 10--Feb-25 | 2025-02-09 | reinforcement | Check OHWT slab reinforcement and allow for concrete pouring zone 3 | (+148'-5'' to +149'-5'') | Grid A-B/18-19 | A | 2025-02-11
| Sub Structure | top floor | IT/916 | 10--Feb-25 | 10--Feb-25 | level | Check OHWT level slab zone 3 | (+148'-5'') | Grid A-B/18-19 | A | 2025-02-11
| Sub Structure | top floor | IT/917 | 10--Feb-25 | 2025-02-09 | reinforcement | Check Genset Beam GB-5 reinforcement and allow for concrete pouring zone 1 | (+147'-3'' to +148'-3'') | Grid A-B/8 | A | 2025-02-11
| Sub Structure | Top floor | IT/918 | 2025-02-11 | 2025-02-10 | reinforcement | Check OHWT reinforcement base slab zone 1 | (+148'-5'') | Grid A-B/8-8, | A | 2025-02-11
| Sub Structure | top floor | IT/919 | 2025-02-12 | 2025-02-12 | reinforcement | Check OHWT wall reinforcement zone 3 | (+148'-5'' to +159'-00'') | Grid A-B/18-19 | A | 2025-02-14
| Sub Structure | Top floor | IT/920 | 2025-02-13 | 2025-02-11 | reinforcement | Check machine room parapet wall reinforcement zone 1 | (+165'-2'' to +166'-0'') | Grid B-B/9-10 | A | 2025-02-20
| Sub Structure | top floor | IT/921 | 2025-02-14 | 2025-02-13 | reinforcement | Check machine slab reinforcement and allow for concrete pouring zone 3 | (+165'-2'') | Grid A-B/17-18 | A | 2025-02-13
| Sub Structure | Top floor | IT/922 | 2025-02-14 | 2025-02-14 | level | Check level, layout of machine slab zone 3 | (+165'-2'') | Grid A-B/17-18 | A | 2025-02-14
| Sub Structure | Top floor | IT/923 | 2025-02-17 | 2025-02-16 | Reinforcement | Check machine room parapet wall reinforcement and allow for concrete pouring zone 3 | (+159'-00'' to +160'-00'', +166'-2'' to +167'-00'') | Grid A-B/17-18 | A | 2025-02-19
| Sub Structure | Ground floor | IT/924 | 2025-02-20 | 2025-02-20 | reinforcement | Check Toe wall for ramp reinforcement zone 1 & 3 | (+0'-00'') | Grid F/3-4, 12-13, 14,18,19,22-23 | A | 2025-02-27
| Sub Structure | Ground floor | IT/925 | 2025-02-22 | 2025-02-22 | reinforcement | Check Toe wall for ramp (5 Nos) reinforcement and allow for concrete pouring zone 1 & 3 | (+0'-00'') | Grid F/3-4, 12-13, 14,18-19,22-23 | A | 2025-02-27
| Sub Structure | Top floor | IT/926 | 2025-03-10 | 2025-03-10 | reinforcement | Check OHWT Walls einforcement zone 1 | (+148'-5'' to +159'-00'') | Grid A-B/8-8 | A | 2025-03-14
| Sub Structure | Ground floor | IT/927 | 2025-03-10 | 2025-03-10 | layout | Check layout of ramp (2 Nos) zone 2 | (+1'-9'') | Grid A-B/11,15 | A | 2025-03-14
| Sub Structure | Ground floor | IT/928 | 2025-03-15 | 2025-03-14 | reinforcement | Check Toe wall for ramp (2 Nos) reinforcement and allow for concrete pouring zone 2 | (+0'-00'') | Grid A-B/11&15 | A | 2025-03-14
| Sub Structure | Top floor | IT/929 | 2025-04-14 | 2025-04-13 | reinforcement | Check OHWT Base slab reinforcement and allow for concrete work | (+148'-5'') | Grid A-B/8-8 | A | 2025-04-16
| Sub Structure | Top floor | IT/930 | 2025-04-14 | 2025-04-14 | Level and layout | Check level of OHWT zone 1 | (+148'-5'') | Grid A-B/8-8 | A | 2025-04-19
| Sub Structure | Top floor | IT/931 | 2025-04-19 | 2025-04-18 | reinforcement | Check ramp & plaster wall reinforcemetn and allow for c oncrete pouring zone 2 | (+145'-9'') | Grid B-C/10-11,11-12 | A | 2025-04-22
| Sub Structure | Top floor | IT/932 | 2025-04-19 | 2025-04-19 | reinforcement | Check OHWT Walls reinforcement and allow for concrete pouring zone 3 | (+148'-5'' to +159'-00'') | Grid A-B/18-19 | A | 2025-04-24
| Sub Structure | Top floor | IT/933 | 2025-04-22 | 2025-04-22 | reinforcement | Check ramp planters wall reinforcement and allow for concrete pouring zone 2 | (+151'-6'') | Grid B-C/10-11 | A | 2025-04-24
| Sub Structure | Top floor | IT/934 | 2025-04-23 | 2025-04-23 | level | Check level of ramp & planters walls zone 2 | (+145'-9'' to +151'-6'') | Grid B-C/10-11 | A | 2025-05-08
| Sub Structure | Top floor | IT/935 | 2025-04-25 | 2025-04-25 | reinforcement | Check OHWT Slab reinforcement zone 3 | (+159'-00'') | Grid A-B/18-19 | A | 2025-05-09
| Sub Structure | Top floor | IT/936 | 2025-04-27 | 2025-04-27 | reinforcement | Check genset slab top and bottom reinforcement zone 1 | (+148'-5'') | Grid A-B/1-8 | A | 2025-05-09
| Sub Structure | Top floor | IT/937 | 2025-04-28 | 2025-04-27 | reinforcement | Check Genset slab reinforcement and allow for concrete pouring zone 1 | (+148'-5'') | Grid A-B/1-8 | A | 2025-05-09
| Sub Structure | Top floor | IT/938 | 2025-04-28 | 2025-04-27 | reinforcement | Check OHWT slab reinforcement and allow for concrete pouring zone 3 | (+159'-00'') | Grid A-B/18-19 | A | 2025-05-09
| Sub Structure | Top floor | IT/939 | 2025-04-28 | 2025-04-28 | level | Check level & layout of stair zone 2 | (+151'-5'') | Grid B-B/11 | A | 2025-05-09
| Sub Structure | Top floor | IT/940 | 2025-04-28 | 2025-04-28 | level | Check Genset slab level zone 1 | (+148'-5'') | Grid A-B/1-8 | A | 2025-05-09
| Sub Structure | Top floor | IT/941 | 2025-04-28 | 2025-04-28 | level | Check OHWT slab level zone 3 | (+159'-00'') | Grid A-B/18-19 | A | 2025-05-09
| Sub Structure | Top floor | IT/942 | 2025-04-29 | 2025-04-28 | reinforcement | Check OHWT Wall reinforcement & allow for concrete pouring zone 1 | (+148'-5'' to +159'-00'') | Grid A-B/8-9 | A | 2025-05-09
| Sub Structure | Top floor | IT/943 | 2025-04-29 | 2025-04-28 | reinforcement | Check formwork and reinforcement of stair & allow for concrete pouring zone 2 | (+145'-9'' to +151'-6'') | Grid B-B/11 | A | 2025-05-09
| Sub Structure | Top floor | IT/944 | 2025-05-01 | 2025-05-01 | reinforcement | Check ramp slab reinforcement zone 3 | (+145'-3'' to +151'-6'') | Grid B-C/15-16 | A | 2025-05-09
| Sub Structure | Top floor | IT/945 | 2025-05-02 | 2025-05-02 | OHWT Reinforcement | Check OHWT Slab reinforcement zone 1 |  | Grid A-B/8-8 | A | 2025-05-09
| Sub Structure | Top floor | IT/946 | 2025-05-03 | 2025-05-02 | reinforcement | Check OHWT Slab reinforcement and allow for concrete pouring zone 1 | (+159'-00'') | Grid A-B/8-8 | A | 2025-05-09
| Sub Structure | Top floor | IT/947 | 2025-05-03 | 2025-05-03 | level | Check OHWT Slab layout of parapet zone 1 | (+159'-00'') | Grid A-B/8-8 | A | 2025-05-09
| Sub Structure | Top floor | IT/948 | 2025-05-05 | 2025-05-03 | reinforcement | Check ramp & plaster wall reinforcement and allow for concrete pouring zone 2 & 3 | (+145'-9'' to +151'-6'') | Grid B-C/15-17 | A | 2025-05-09
| Sub Structure | Top floor | IT/949 | 2025-05-06 | 2025-05-05 | reinforcement | Check planters walls reinforcement and allow for concrete pouring zone 2 & 3 | (+151'-6'') | Grid B-C/15-17 | A | 2025-05-09
| Sub Structure | Top floor | IT/950 | 2025-05-07 | 2025-05-06 | reinforcement | Check parapet wall reinforcement and allow for concrete pouring zone 3 | (+159' to +160') | Grid A-B/18-19 | A | 2025-05-07
| Sub Structure | Top floor | IT/951 | 2025-05-08 | 2025-05-07 | reinforcement | Check reinforcement and formwork of swimming pool stair & allow for concrete pouring zone 2 | (+145'-9'') | Grid A-C/12-12 | A | 2025-05-07
| Sub Structure | Top floor | IT/952 | 2025-05-10 | 2025-05-10 | reinforcement | Check OHWT parapet wall & allow for concrete pouring zone 1 | (+159' to +160') | Grid A-B/8-9 | A | 2025-05-10
| Sub Structure | Top floor | IT/953 | 2025-05-10 | 2025-05-10 | reinforcement | Check reinforcement and formwork & water stoppper of swimming pool stair wall & allow for concrete pouring zone 2 | (+145'-9'' to +151'-6'') | Grid B-C/12-12 | A | 2025-05-10
| Sub Structure | Top floor | IT/954 | 2025-05-16 | 2025-05-15 | reinforcement | Check Swimming Pool walls reinforcement and allow for concrete pouring zone 2 | (+145'-9'' to +151'-6'') | Grid A-F/12, A/12, F/12-15 | A | 2025-05-15
| Sub Structure | Top floor | IT/955 | 2025-05-16 | 2025-05-16 | level | Check level & layout of changing room stair zone 2 | (+145'-9'' to +151'-6'') | Grid B/15 | A | 2025-05-17
| Sub Structure | Top floor | IT/956 | 2025-05-16 | 2025-05-16 | formwork | Check formwork and reinforcement of changing room stair and allow to start concrete pouring zone 2 | (+145'-9'' to +151'-6'') | Grid B/15 | A | 2025-05-16
| Sub Structure | Top floor | IT/957 | 2025-05-21 | 2025-05-20 | reinforcement | Check Swimming pool walls reinforcement and allow for concrete pouring zone 2 | (+145'-9'' to +151'-6'') | Grid A/12-14, A-C/15 | A | 2025-05-20
| Sub Structure | Top floor | IT/958 | 2025-05-26 | 2025-05-26 | level | Check level and layout of swimming pool stair zone 2 | (+145'-9'' to +151'-6'') | Grid A-B/15 | A | 2025-05-26
| Sub Structure | Top floor | IT/959 | 2025-05-28 | 2025-05-28 | reinforcement | check formwork and reinforcement of swimming pool stair and allow for concrete pouring zone 2 | (+145'-9'' to +151'-6'') | Grid A-B/15 | A | 2025-05-27
| Sub Structure | Top floor | IT/960 | 2025-05-31 | 2025-05-31 | formwork | check formwork and reinforcement of swimming pool stair support wall and allow for concrete pouring zone 2 | (+145'-9'' to +151'-6'') | Grid C/14-15 | A | 2025-05-31
| Sub Structure | Top floor | IT/961 | 2025-07-21 | 2025-07-21 | Reinforcement | Check reinforcement of kids pool slab top and bottom reinforcement zone 2 |  | Grid D-F/10-12 | A | 2025-07-22
| Sub Structure | Top floor | IT/962 | 2025-07-21 | 2025-07-21 | Reinforcement | Check reinforcement of kids pool slab Nd water stopper and allow to concrete |  | Grid D-F/10-12 | A | 2025-07-22
| Sub Structure | Top floor | IT/963 | 2025-07-21 | 2025-07-21 | level | Check top level for kids pool slab zone 2 |  | Grid D-F/10-12 | A | 2025-07-22
| Sub Structure | Top floor | IT/964 | 2025-07-22 | 2025-07-22 | reinforcement | Check reinforcements of Kids Pool wall & Allow Concrete pouring zone 2 | (+148'-6" to +151'-6") | Grid D-F/10-12 | A | 2025-07-26
| Sub Structure | Top floor | IT/965 | 2025-07-23 | 2025-07-23 | reinforcement | Check reinforcements of Kids Pool wall & Allow Concrete pouring zone 2 |  | Grid D-F/15-16 | A | 2025-07-26
| Sub Structure | Top floor | IT/966 | 2025-07-23 | 2025-07-23 | reinforcement & formwork | Check reinforcements of Kids Pool wall & Allow Concrete pouring zone 2 |  | Grid D/10-12 | A | 2025-07-26
| Sub Structure | Top floor | IT/967 | 2025-07-24 | 2025-07-24 | level | Check the top level of kids pool lounging slab |  | Grid D/10-12 | A | 2025-07-30
| Sub Structure | Top floor | IT/968 | 2025-07-24 | 2025-07-24 | level | Check the level of lounging pool slab |  | Grid D-F/15-16 | A | 2025-07-30
| Sub Structure | Top floor | IT/969 | 2025-07-25 | 2025-07-25 | Reinforcement | Check final Reinforcement of lounging pool walls and planter wall and allow for concrete pouring |  | Grid D-F/15-16, B-C/16-17 | A | 2025-07-28
| Sub Structure | top floor | IT/970 | 2025-07-26 | 2025-07-26 | reinforcement & formwork | Check reinforcements of Kids & lounging Pool Stairl & Allow Concrete pouring zone 2 |  | Grid D-F/10, D/16-17 | A | 2025-07-30
| Sub Structure |  | IT/971
| Sub Structure |  | IT/972
| Sub Structure |  | IT/973
| Sub Structure |  | IT/974
| Sub Structure |  | IT/975
| Sub Structure |  | IT/976
| Sub Structure |  | IT/977
| Sub Structure |  | IT/978
| Sub Structure |  | IT/979
| Sub Structure |  | IT/980
| Sub Structure |  | IT/981
| Sub Structure |  | IT/982
| Sub Structure |  | IT/983
| Sub Structure |  | IT/984
| Sub Structure |  | IT/985
| Sub Structure |  | IT/986
| Sub Structure |  | IT/987
| Sub Structure |  | IT/988
| Sub Structure |  | IT/989
| Sub Structure |  | IT/990
| Sub Structure |  | IT/991
| Sub Structure |  | IT/992
| Sub Structure |  | IT/993
| Sub Structure |  | IT/994
| Sub Structure |  | IT/995
| Sub Structure |  | IT/996
| Sub Structure |  | IT/997
| Sub Structure |  | IT/998
| Sub Structure |  | IT/999
| Sub Structure |  | IT/1000
| Sub Structure |  | IT/1001
| Sub Structure |  | IT/1002
| Sub Structure |  | IT/1003
| Sub Structure |  | IT/1004
| Sub Structure |  | IT/1005
| Sub Structure |  | IT/1006
| Sub Structure |  | IT/1007
| Sub Structure |  | IT/1008
| Sub Structure |  | IT/1009
| Sub Structure |  | IT/1010
| Sub Structure |  | IT/1011
| Sub Structure |  | IT/1012
2023-09-18
[8 empty] | (+62'-9'' to +73'-9'') |  |  | 2023-05-23

## Elements (hidden)
inputs: Don’t delete the highlighted cells |  |  | TOT | Sub Str |  | I-Tower | [13 empty] | L-Tower
|  |  | QTY | Qty | Qty | Ground | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | mumty | Qty | Ground | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | mumty
1 | PCC | 1500 | 1581.5475 | 1581.5475
2 | Raft | 4000 | 8836.5357 | 8836.5357
3 | Foundation | 4000
4 | Column | 5000 | 2879.6849 | 476.5028 | 1029.3083 | 162.9396 | 83.5225 | 85.2212 | 73.8962 | 73.8962 | 73.8962 | 73.8962 | 73.8962 | 73.8962 | 73.8962 | 81.9653 | 98.3866 |  | 1373.8738 | 215.8843 | 110.5611 | 112.9677 | 97.6788 | 97.6788 | 97.6788 | 97.6788 | 97.6788 | 97.6788 | 97.6788 | 108.5792 | 130.2384 | 11.8913 | 0
5 | Ret Wall | 4000 | 525.2006 | 525.2006
6 | Lift Well | 5000 | 3240.2471 | 259.0612 | 1341.5974 | 154.5873 | 93.715 | 93.715 | 93.715 | 93.715 | 93.715 | 93.715 | 93.715 | 93.715 | 93.715 | 102.6335 | 120.4705 | 120.4705 | 1639.5885 | 188.9873 | 114.5249 | 114.5249 | 114.5249 | 114.5249 | 114.5249 | 114.5249 | 114.5249 | 114.5249 | 114.5249 | 125.4253 | 147.226 | 147.226
7 | Shear Wall | 5000
8 | Beam | 4000
9 | Slab | 4000 | 19035.6201 | 2477.9276 | 7105.6387 | 592.3017 | 590.4614 | 590.4614 | 590.4614 | 590.4614 | 590.4614 | 590.4614 | 590.4614 | 590.4614 | 590.4614 | 590.4614 | 574.1816 | 34.5415 | 9452.0538 | 785.2528 | 782.7046 | 782.7046 | 782.7046 | 782.7046 | 782.7046 | 782.7046 | 782.7046 | 782.7046 | 782.7046 | 782.7046 | 761.0454 | 78.7093
10 | Lintel | 3000 | 426.1062 |  | 184.0326 | [13 empty] | 242.0736
11 | Stair | 4000 | 353.9086 | 27.18 | 163.3643 | [13 empty] | 163.3643
12 | Ramp Slab | 4000 | 91.8747 | 91.8747
13 | UGWT Base Slab | 4000 | 97.6788 | 97.6788
14 | UGWT Walls | 4000 | 230.1823 | 230.1823
15 | UGWT Top Slab | 4000 | 62.5711 | 62.5711
16 | Harvest Tank Base Slab | 4000 | 46.2913 | 46.2913
17 | Harvest Tank Walls | 4000 | 102.7751 | 102.7751
18 | Harvest Tank Top Slab | 4000 | 13.4768 | 13.4768
19 | OHWT Base Slab | 4000 | 56.6254 |  | 26.7555 | [13 empty] | 29.8699
20 | OHWT Walls | 4000 | 58.041 |  | 26.8971 | [13 empty] | 31.144
21 | OHWT Top Slab | 4000 | 34.6831 |  | 16.1382 | [13 empty] | 18.5448
22 | Pool Base Slab | 4000 | 32.5596 |  | 32.5596
23 | Pool Walls | 4000 | 16.9876 |  | 16.9876
24 | Parapet Wall | 3000 | 266.7056 |  | 114.6664 | [13 empty] | 152.0392
26
27
28
29
30
31
32
33 |  |  | 37989.3031

## B (hidden)
LAKE CITY ROOF GARDEN LAHORE APPARTMENTS-PHASE 2 STRUCTURAL WORKS
BILL OF QUANTITIES (STRUCTURAL WORKS)
ITEM NO. | SHORT DESCRIPTION OF WORK TO BE READ IN CONJUNCTION WITH GENERAL SPECIFICATIONS | UNIT | TOTAL QTY | RATE | AMOUNT
1 | Earth Works
Excavation for basements, raft foundations in existing soil including cost of dressing, leveling and compaction in approved manners and disposal of surplus excavated soil away from site, all excavated area will be proof rolled as directed by the Consultant/Engineer incharge.
a | Excavation | m3 | 19960.4545 |  | 0
b | Backfilling using local sand with layer thickness 6" in loose state and compacted upto 95% MDD. | m3 | 1562.2949 |  | 0
2 | Termite Proofing |  |  |  | 0
| Providing and carrying out termite proofing on excavation sides only using "Biflex/ Fiprokill/ Mirage" or an approved equivalent as per manufacturers specification. The work shall be carried out by an approved specialist subcontractor who will provide 10 years warranty stating that in case of infestation during the period of warranty, he will carry out the remedial work without charge to the Employer. complete in all respect and as directed by the Consultants. |  |  |  | 0
a | Excavation bed and sides -7.75 ft from EGL | m3 | 11264.7877 |  | 0
3 | Plain Cement Concrete |  |  | 0 | 0
| Laying owner supplied concrete from point of delivery, compacting and finishing blinding concrete (1:4:8) in layers and providing proper curing upto the required time as per drawings/ specifications/ directed by the Consultant. |  |  | 0 | 0
a | 3" thick two layers of PCC 1:4:8 under Raft/Mat foundations. | m3 | 1581.5475 | 10666.5908 | 16869720
0
4 | Reinforced Cement Concrete Work |  |  | 0 | 0
| Laying owner supplied concrete from point of delivery, vibrating, compacting, finishing and curing etc. straight or curved, cast in situ reinforced cement concrete at any floor/height/depth, pumped ready mix concrete, 4000 psi and 5000 Psi (mentioned in parenthesis ) minimum cylinder crushing strength at 28 days, mix using Ordinary Portland Grey Cement, fine aggregate Lawrence pur good quality clean sand free from impurities and Sargodha crushed course aggregate 3/4 '' & 1/2" down well-graded, including vibrations through electro mechanical vibrators, steel form work, moulds, false work and their removal, placing of all pipes and embedded items before concreting curing finishing complete but excluding the cost of steel reinforcement complete in all respect as per drawings and as directed by the Consultant/Engineer incharge. |  |  | 0 | 0
i | Mat foundations (4000 psi) | m3 | 8836.5357 | 14881.0688 | 131497094.9228
0
ii | Ramp slab and beams (4000 psi) |  |  | 0 | 0
| Foundations to GF | m3 | 91.8747 | 13856.7935 | 1273088.9669
0
iii | Columns (5000 psi) |  |  | 0 | 0
| Foundation to Ground Floor | m3 | 476.5028 | 24005.356 | 11438618.5029
|  |  |  | 0 | 0
iv | Lift wells/shearwalls(5000 psi) |  |  | 0 | 0
| Foundation to Ground Floor | m3 | 259.0612 | 15881.7935 | 4114356.7618
|  |  |  | 0 | 0
v | Floor slabs and beams (4000 psi) |  |  | 0 | 0
| GF (7"Th slab+18"drop beams) | m3 | 2477.9276 | 13856.7935 | 34336131.3957
0
vi | Stairs (4000 psi) | m3 | 27.18 | 22262.9147 | 605106.0215
0
vii | Retaining walls(4000 psi) | m3 | 525.2006 | 13856.7935 | 7277596.4053
0
viii | Under Ground water tank (4000 psi) |  |  | 0 | 0
| Base slab | m3 | 97.6788 | 16081.9432 | 1570865.2344
| Walls | m3 | 230.1823 | 26854.4935 | 6181428.0741
| Top slab | m3 | 62.5711 | 25865.5381 | 1618434.3965
0
ix | Rain harvesting tank (4000 psi) |  |  | 0 | 0
| Base slab | m3 | 46.2913 | 16081.9432 | 744453.5241
| Walls | m3 | 102.7751 | 26854.4935 | 2759973.4205
| Top slab | m3 | 13.4768 | 25865.5381 | 348585.87
0
5 | Water Proofing |  |  | 0 | 0
a | Providing and Laying of 4mm thick by Highgrip or equivalent modified Torch applied Bituminous water proofing membrane with Primer @0.25 Liters/ Sq. M, over first layers of blinding concrete of Raft/ foundation after applying 1/2" thick plaster laid in Cement Sand mortar (1:3) . The overlap shall not be less than 6", the membrane shall be well incontact with the concrete face, free from air voids, wrinkles and cuts and to be terminated at the level defined in the drawing. | m2 | 10682.8069 | 1194.9107 | 12765000
b | Providing and Laying of 4mm thick by Higrip or equivalent modified Torch applied Bituminous water proofing membrane with Primer @0.25 Liters/ Sq. M, on external sides of peripheral retaining walls over levelled shoring piles surface( pile gaps to be filled with 1:4:8 PCC( same as item-3) reinforced with 18 gauge wire mesh required and using front form work to contain at place) , complete in all respects as per drawings including 1/2" to 3/4" (1:3) cement local sand plaster cost to get levelled base surface for membrane applying. To avoid sharp bends in membrane 50 x 50 mm chamfer laid in cement sand mortar to be provided under the membrane at the point where retaining wall is joining with the raft/ bed. | m2 | 1811.4325 | 1194.9107 | 2164500
c | Providing and fixing of water stopper 4mm thick and 229 mm wide poly vinyl chloride ribbed bar by Marflex or approved equivalent installed in the centre of x-section of the concrete structure joint of retaining walls and water tanks including proper joint welding complete in all respects as per drawings and as directed by the consultant / Engineer. (considering 2 levels in each retaining wall height) | mtr | 1336.48 | 1105.697 | 1477741.9266
0
6 | Expansion/Isolation joint detail |  |  | 0 | 0
| Providing, applying and treating expansion/isolation joint. Complete in all respects as per satisfaction of engineer incharge. |  |  | 0 | 0
a | 2" x 3" expansion joint maintained with high density thermopore sheet laid at the time of casting slab, applying SIKA primer, inserting polystyrene backup rod filled with polyurethane joint sealant SIKA flex. The joints to be covered with steel joint cover stripe of the design approved by Engineer. The ponding test will be performed by contractor to check the leakage if required by the Engineer | mtr | 289.5459 | 1168.036 | 338200
0
7 | Steel Reinforcement |  |  | 0
| Fabricating/ cut, bend and placing of owner supplied steel from the site stock yard (hot rolled deformed bar of min. yield strength 60,000 psi) for the cement concrete work including testing of bars, providing and binding with annealed wire, removal of rust from the bars, all overlaps, chairs, supports etc. complete in all respect. Only the lengths shown on the drawings at their standard weights shall be paid for in accordance with a bending schedule prepared by the contractor and submitted well in advance to Engineer for approval |  |  | 0 | 0
| Total Steel Quantity | ton | 1850 | 245607 | 454372950
|  |  |  | Total Amount (Rs) | 691753845.4232
641 Million
|  |  |  | Covered Area (Sft) | 115398
|  |  |  | Rate/sft | 5994.5046

## I (hidden)
LAKE CITY ROOF GARDEN LAHORE APPARTMENTS-PHASE 2 STRUCTURAL WORKS I-TOWERS (MATERIAL ONLY)
SR. | ITEM DESCRIPTION | UNIT | TOTAL QTY | RATE | AMOUNT
1 | Reinforced Cement Concrete Work
| Laying owner supplied concrete from point of delivery, vibrating, compacting, finishing and curing etc. straight or curved, cast in situ reinforced cement concrete at any floor/height/depth, pumped ready mix concrete, 4000 psi and 5000 Psi (mentioned in parenthesis ) minimum cylinder crushing strength at 28 days, mix using Ordinary Portland Grey Cement, fine aggregate Lawrence pur good quality clean sand free from impurities and Sargodha crushed course aggregate 3/4 '' & 1/2" down well-graded, including vibrations through electro mechanical vibrators, steel form work, moulds, false work and their removal, placing of all pipes and embedded items before concreting curing finishing complete but excluding the cost of steel reinforcement complete in all respect as per drawings and as directed by the Consultant/Engineer incharge. |  |  |  | 0
i | Columns (5000 psi) |  |  |  | 0
| Ground to First Floor | m3 | 162.9396 | 16918.2019 | 2756645
| 1st to 2nd Floor | m3 | 83.5225 | 16918.2019 | 1413050
| 2nd to 3rd Floor | m3 | 85.2212 | 16918.2019 | 1441790
| 3rd to 4th Floor | m3 | 73.8962 | 16918.2019 | 1250190
| 4th to 5th Floor | m3 | 73.8962 | 16918.2019 | 1250190
| 5th to 6th Floor | m3 | 73.8962 | 16918.2019 | 1250190
| 6th to 7th Floor | m3 | 73.8962 | 16918.2019 | 1250190
| 7th to 8th Floor | m3 | 73.8962 | 16918.2019 | 1250190
| 8th to 9th Floor | m3 | 73.8962 | 16918.2019 | 1250190
| 9th to 10th Floor | m3 | 73.8962 | 16918.2019 | 1250190
| 10th to 11th Floor | m3 | 81.9653 | 16918.2019 | 1386705
| 11th to Roof | m3 | 98.3866 | 16918.2019 | 1664525
ii | Lift wells/shearwalls(5000 psi) |  |  |  | 0
| Ground to First Floor | m3 | 154.5873 | 16918.2019 | 2615340
| 1st to 2nd Floor | m3 | 93.715 | 16918.2019 | 1585490
| 2nd to 3rd Floor | m3 | 93.715 | 16918.2019 | 1585490
| 3rd to 4th Floor | m3 | 93.715 | 16918.2019 | 1585490
| 4th to 5th Floor | m3 | 93.715 | 16918.2019 | 1585490
| 5th to 6th Floor | m3 | 93.715 | 16918.2019 | 1585490
| 6th to 7th Floor | m3 | 93.715 | 16918.2019 | 1585490
| 7th to 8th Floor | m3 | 93.715 | 16918.2019 | 1585490
| 8th to 9th Floor | m3 | 93.715 | 16918.2019 | 1585490
| 9th to 10th Floor | m3 | 93.715 | 16918.2019 | 1585490
| 10th to 11th Floor | m3 | 102.6335 | 16918.2019 | 1736375
| 11th to Roof | m3 | 120.4705 | 16918.2019 | 2038145
| Roof to Mummty | m3 | 120.4705 | 16918.2019 | 2038145
iii | Lintels (3000 psi) | m3 | 184.0326 | 14445.8133 | 2658500
iv | Floor slabs and beams (4000 psi) |  |  |  | 0
| FF (7"Th slab + 18"drop beams) | m3 | 592.3017 | 15258.1696 | 9037440
| 2nd Floor (7"Th slab+18" beams) | m3 | 590.4614 | 15258.1696 | 9009360
| 3rd Floor (7"Th slab+ 18" drop beams) | m3 | 590.4614 | 15258.1696 | 9009360
| 4th Floor (7"Th slab+18" drop beams) | m3 | 590.4614 | 15258.1696 | 9009360
| 5th Floor (7" TH slab with 18" drop beams) | m3 | 590.4614 | 15258.1696 | 9009360
| 6th Floor (7" TH slab with 18" drop beams) | m3 | 590.4614 | 15258.1696 | 9009360
| 7th Floor (7" TH slab with 18" drop beams) | m3 | 590.4614 | 15258.1696 | 9009360
| 8th Floor (7" TH slab with 18" drop beams) | m3 | 590.4614 | 15258.1696 | 9009360
| 9th Floor (7" TH slab with 18"drop beams) | m3 | 590.4614 | 15258.1696 | 9009360
| 10th Floor (7" TH slab with 18" drop beams) | m3 | 590.4614 | 15258.1696 | 9009360
| 11th Floor (7" TH slab with 18"drop beams) | m3 | 590.4614 | 15258.1696 | 9009360
| Roof (7" TH slab with 18" drop beams) | m3 | 574.1816 | 15258.1696 | 8760960
| Mumty Roof (7" TH slab with 18" drop beams) | m3 | 34.5415 | 15258.1696 | 527040
0
v | RCC parapet wall (3000 psi) | m3 | 114.6664 | 14445.8133 | 1656450
vi | Stairs (4000 psi) | m3 | 163.3643 | 15258.1696 | 2492640
vii | Over Head water tank(4000 psi)
| Base slab | m3 | 26.7555 | 15258.1696 | 408240
| Walls | m3 | 26.8971 | 15258.1696 | 410400
| Top slab | m3 | 16.1382 | 15258.1696 | 246240
viii | Swimming Pool (4000 psi)
| Base slab | m3 | 32.5596 | 15258.1696 | 496800
| Walls | m3 | 16.9876 | 15258.1696 | 259200
2 | Water Proofing |  |  |  | 0
a | Providing and fixing of water stopper 4mm thick and 229 mm wide poly vinyl chloride ribbed bar by Marflex or approved equivalent installed in the centre of x-section of the concrete structure joint of retaining walls and water tanks including proper joint welding complete in all respects as per drawings and as directed by the consultant / Engineer. (considering 2 levels in each retaining wall height) | mtr | 109.7226 | 0 | 0
3 | Steel Reinforcement
| Fabricating/ cut, bend and placing of owner supplied steel from the site stock yard (hot rolled deformed bar of min. yield strength 60,000 psi) for the cement concrete work including testing of bars, providing and binding with annealed wire, removal of rust from the bars, all overlaps, chairs, supports etc. complete in all respect. Only the lengths shown on the drawings at their standard weights shall be paid for in accordance with a bending schedule prepared by the contractor and submitted well in advance to Engineer for approval |  |  |  | 0
| Total Steel Quantity | ton | 1810 |  | 0
|  |  | Total Amount (Rs) |  | 157158970
|  |  | Covered Area (Sft) |  | 278256
|  |  | Rate/sft |  | 564.7999

## L (hidden)
LAKE CITY ROOF GARDEN LAHORE APPARTMENTS-PHASE 2 STRUCTURAL WORKS L-TOWERS (MATERIAL ONLY)
SR. | ITEM DESCRIPTION | UNIT | TOTAL QTY | RATE | AMOUNT
1 | Reinforced Cement Concrete Work
| Laying owner supplied concrete from point of delivery, vibrating, compacting, finishing and curing etc. straight or curved, cast in situ reinforced cement concrete at any floor/height/depth, pumped ready mix concrete, 4000 psi and 5000 Psi (mentioned in parenthesis ) minimum cylinder crushing strength at 28 days, mix using Ordinary Portland Grey Cement, fine aggregate Lawrence pur good quality clean sand free from impurities and Sargodha crushed course aggregate 3/4 '' & 1/2" down well-graded, including vibrations through electro mechanical vibrators, steel form work, moulds, false work and their removal, placing of all pipes and embedded items before concreting curing finishing complete but excluding the cost of steel reinforcement complete in all respect as per drawings and as directed by the Consultant/Engineer incharge. |  |  |  | 0
i | Columns (5000 psi)
| Ground to First Floor | m3 | 215.8843 | 16918.2019 | 3652375
| 1st to 2nd Floor | m3 | 110.5611 | 16918.2019 | 1870495
| 2nd to 3rd Floor | m3 | 112.9677 | 16918.2019 | 1911210
| 3rd to 4th Floor | m3 | 97.6788 | 16918.2019 | 1652550
| 4th to 5th Floor | m3 | 97.6788 | 16918.2019 | 1652550
| 5th to 6th Floor | m3 | 97.6788 | 16918.2019 | 1652550
| 6th to 7th Floor | m3 | 97.6788 | 16918.2019 | 1652550
| 7th to 8th Floor | m3 | 97.6788 | 16918.2019 | 1652550
| 8th to 9th Floor | m3 | 97.6788 | 16918.2019 | 1652550
| 9th to 10th Floor | m3 | 97.6788 | 16918.2019 | 1652550
| 10th to 11th Floor | m3 | 108.5792 | 16918.2019 | 1836965
| 11th to Roof | m3 | 130.2384 | 16918.2019 | 2203400
| Roof to Mummty | m3 | 11.8913 | 16918.2019 | 201180
ii | Lift wells/shearwalls(5000 psi) |  |  |  | 0
| Ground to First Floor | m3 | 188.9873 | 16918.2019 | 3197325
| 1st to 2nd Floor | m3 | 114.5249 | 16918.2019 | 1937555
| 2nd to 3rd Floor | m3 | 114.5249 | 16918.2019 | 1937555
| 3rd to 4th Floor | m3 | 114.5249 | 16918.2019 | 1937555
| 4th to 5th Floor | m3 | 114.5249 | 16918.2019 | 1937555
| 5th to 6th Floor | m3 | 114.5249 | 16918.2019 | 1937555
| 6th to 7th Floor | m3 | 114.5249 | 16918.2019 | 1937555
| 7th to 8th Floor | m3 | 114.5249 | 16918.2019 | 1937555
| 8th to 9th Floor | m3 | 114.5249 | 16918.2019 | 1937555
| 9th to 10th Floor | m3 | 114.5249 | 16918.2019 | 1937555
| 10th to 11th Floor | m3 | 125.4253 | 16918.2019 | 2121970
| 11th to Roof | m3 | 147.226 | 16918.2019 | 2490800
| Roof to Mummty | m3 | 147.226 | 16918.2019 | 2490800
iii | Lintels (3000 psi) | m3 | 242.0736 | 14445.8133 | 3496950
iv | Floor slabs and beams (4000 psi) |  |  |  | 0
| FF (7"Th slab + 18"drop beams) | m3 | 785.2528 | 15258.1696 | 11981520
| 2nd Floor (7"Th slab+18" beams) | m3 | 782.7046 | 15258.1696 | 11942640
| 3rd Floor (7"Th slab+ 18" drop beams) | m3 | 782.7046 | 15258.1696 | 11942640
| 4th Floor (7"Th slab+18" drop beams) | m3 | 782.7046 | 15258.1696 | 11942640
| 5th Floor (7" TH slab with 18" drop beams) | m3 | 782.7046 | 15258.1696 | 11942640
| 6th Floor (7" TH slab with 18" drop beams) | m3 | 782.7046 | 15258.1696 | 11942640
| 7th Floor (7" TH slab with 18" drop beams) | m3 | 782.7046 | 15258.1696 | 11942640
| 8th Floor (7" TH slab with 18" drop beams) | m3 | 782.7046 | 15258.1696 | 11942640
| 9th Floor (7" TH slab with 18"drop beams) | m3 | 782.7046 | 15258.1696 | 11942640
| 10th Floor (7" TH slab with 18" drop beams) | m3 | 782.7046 | 15258.1696 | 11942640
| 11th Floor (7" TH slab with 18"drop beams) | m3 | 782.7046 | 15258.1696 | 11942640
| Roof (7" TH slab with 18" drop beams) | m3 | 761.0454 | 15258.1696 | 11612160
| Mumty Roof (7" TH slab with 18" drop beams) | m3 | 78.7093 | 15258.1696 | 1200960
0
v | RCC parapet wall (3000 psi) | m3 | 152.0392 | 14445.8133 | 2196330
vi | Stairs (4000 psi) | m3 | 163.3643 | 15258.1696 | 2492640
vii | Over Head water tank(4000 psi)
| Base slab | m3 | 29.8699 | 15258.1696 | 455760
| Walls | m3 | 31.144 | 15258.1696 | 475200
| Top slab | m3 | 18.5448 | 15258.1696 | 282960
2 | Water Proofing |  |  |  | 0
a | Providing and fixing of water stopper 4mm thick and 229 mm wide poly vinyl chloride ribbed bar by Marflex or approved equivalent installed in the centre of x-section of the concrete structure joint of retaining walls and water tanks including proper joint welding complete in all respects as per drawings and as directed by the consultant / Engineer. (considering 2 levels in each retaining wall height) | mtr | 77.7202 | 0 | 0
3 | Steel Reinforcement
| Fabricating/ cut, bend and placing of owner supplied steel from the site stock yard (hot rolled deformed bar of min. yield strength 60,000 psi) for the cement concrete work including testing of bars, providing and binding with annealed wire, removal of rust from the bars, all overlaps, chairs, supports etc. complete in all respect. Only the lengths shown on the drawings at their standard weights shall be paid for in accordance with a bending schedule prepared by the contractor and submitted well in advance to Engineer for approval |  |  |  | 0
| Total Steel Quantity | ton | 2140 | 235968 | 504971520
|  |  | Total Amount (Rs) |  | 709574765
|  |  | Covered Area (Sft) |  | 390638
|  |  | Rate/sft |  | 1816.4509

## Quotations for Mobile crane (hidden)
|  |  |  | As of: | 2025-12-19
Quotations for Mobile Crane
S.no | Contractor Ref No. | Submittal Ref | Description | Submission date | Receiving date | Status
1 | 17 | ICPL/LCD/22/0901 | Quotation for Monthly Rental Mobile Crane | 2022-09-01 | 2022-09-01 | R
2 | 20 | ICPL/LCD/22/0902 | Quotation daily rental cost for 25 Ton capacity Mobile crane | 2022-09-03 | 2022-09-03 | 575000 Approved
3
4
5
6
7
8
9
10

## Inventory list (hidden)
|  |  | As of: | 2025-12-19
Lake City Roof Gardens (Inventory List)
S.no | Description | Receiving date | Qty | Size | Remarks
1 | Office Table (CM Office) |  | 2 | 2x4 | UNISON
2 | Executive Revolving Chairs (CM office) | 2022-09-06 | 4 |  | UNISON
3 | Revolving Chairs net black Low back (CM office) | 2022-09-06 | 6 |  | UNISON
4 | Visitors steel Chairs (CM Office) |  | 4 |  | UNISON
5 | Bracket Fan (CM Office) |  | 3 |  | UNISON
6 | Exhaust Fan Installed in CM Containers |  | 3 |  | UNISON
7 | Container |  | 1 | 18x10 | Client
8 | Container | 13 June and 17 August-22 | 2 | 40x18 | UNISON
9 | Executive Revolving chair | 2022-09-06 | 1 |  | Client
10 | Printer CM Office | 2022-09-06 | 1 | A4 size | UNISON
11 | Haier Fridge CM Office | 2022-09-10 | 1 | Medium | UNISON
12 | Haier AC Inverter CM Office | 2022-09-10 | 1 | 1.5 Ton | UNISON
13 | Haier AC Inverter CM Office | 2022-09-10 | 1 | 1 Ton | UNISON
14 | Oven CM Office | 2022-09-10 | 1 |  | UNISON
15 | Work station CM Office | 2022-09-13 | 8 |  | UNISON
16 | File Rack CM Office | 2022-09-13 | 5 |  | UNISON
17 | Executive Table with side rack and Drawer | 2022-09-17 | 1 |  | Client
18 | Electric Cattle CM Office | 2022-09-19 | 1 |  | UNISON
19 | Executive Chairs | 2022-09-21 | 2 |  | Client
20 | Containers for Client | 2022-09-29 | 1 | 40x18 | Client
21 | Water Dispenser Enviro CM Office | 2022-09-29 | 1 |  | UNISON
22 | Office Table CM Office | 2022-10-21 | 4 | 2x4 | 2 client
23 | Meeting Table | 2022-10-20 | 2 | 16x4 | Client
24 | Revolving Chairs (Net Black) Low back | 2022-10-20 | 14 |  | Client
25 | Visitors chairs (Stainless Steel) | 2022-10-20 | 8 |  | Client
26 | File Rack | 2022-10-22 | 8 |  | 3 Client
27 | DB | 2022-10-25 | 4

## UET Test Reports (hidden)
UET Steel Test Reports
S.no | Description | Submission date | Test Date | Payment date | Status | Normal Fee | Urgent Fee | Total Payment
2022-07-29
1 | Deformed steel Dia 6 | 2022-07-27 | 2022-07-29 | 2022-07-29 | Ok | 13100 |  | 13100
2 | Deformed steel Dia 8 | 2022-07-27 | 2022-07-29 |  | Ok
2022-09-02
3 | Deformed steel Dia 8 | 2022-09-02 | 2022-09-02 | 2022-09-02 | Ok | 10500 |  | 21000
4 | Deformed steel Dia 6 | 2022-09-02 | 2022-09-02 | 2022-09-05 | Ok |  | 10500
2022-09-05
5 | Deformed steel Dia 4 | 2022-09-05 | 2022-09-05 | 2022-09-05 | Not ok |  | 6000 | 6000
6 | Deformed steel Dia 3 | 2022-09-02 | 2022-09-05 | 2022-09-05 |  | 4600 | 1150 | 5750
7 | Total Payment | [6 empty] | 45850

## ICPL L1 Tower IR
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
|  |  | INSPECTION REQUEST LOG (L1 Tower) | [5 empty] | IR STATUS
[9 empty] | Fully Approved (A) |  | 689
[9 empty] | Approved with comments (B) |  | 3
[9 empty] | Rejected ( R) |  | 1
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 693
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Attachment | Remarks
1 | Sub Structure | Basement | L1/1 | 2022-09-22 |  | Tower Crane | Layout of Tower crane foundation Zone 8 |  | Grid K-M/17-20 | A | 2022-10-06 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\1.pdf
2 | Sub Structure | Basement | L1/2 | 2022-09-23 |  | Surface preparation | Excavation, surface preparation and final bed level I Tower Zone 8 |  | Grid K-M/17-20 | A | 2022-10-06 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\2.pdf
3 | Sub Structure | Basement | L1/3 | 2022-09-23 |  | Termite proofing | Termite proofing for Tower Crane Zone 8 |  | Grid K-M/17-20 | A | 2022-09-28 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\3.pdf
4 | Sub Structure | Basement | L1/4 | 2022-09-24 |  | PCC | PCC as per IFC drawing |  | Grid K-M/17-20 | A | 2022-10-06 |  | 16 | E:\Soft IRs\ICPL\L1-Tower IR's\new\4.pdf
5 | Sub Structure | Basement | L1/5 | 2022-09-24 |  | Tower Crane | Layout of Tower Crane foundation and columns as per IFC Zone 8 |  | Grid K-M/17-20 | A | 2022-10-06 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\5.pdf
6 | Sub Structure | Basement | L1/6 | 2022-10-03 |  | Tower Crane | Steel fixing of Tower Crane foundation and dowels Zone 8 |  | Grid K-M/17-20 | A | 2022-10-06 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\6.pdf
7 | Sub Structure | Basement | L1/7 | 2022-10-04 |  | Raft | Layout and level of raft top of Tower crane columns Zone 8 |  | Grid K-M/18-19 | A | 2022-10-06 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\7.pdf
8 | Sub Structure | Basement | L1/8 | 2022-10-05 |  | Raft concrete | Raft concrete pouring 4000 psi |  | Grid K-M/17-20 | A | 2022-10-06 |  | 65 | E:\Soft IRs\ICPL\L1-Tower IR's\new\8.pdf
9 | Sub Structure | Basement | L1/9 | 2022-10-02 |  | Surface preparation | Layout excavation, surface preparation and final bed level L Tower |  | Grid G-T/15-26 | A | 2022-10-06 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\9.pdf
10 | Sub Structure | Basement | L1/10 | 2022-10-11 |  | Surface preparation | Excavation, Surface preparation and final bed level of Lift, service lift and sumpits |  | Grid G-T/15-26 | A | 2022-10-12 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\10.pdf
11 | Sub Structure | Basement | L1/11 | 2022-10-13 |  | PCC | 1st layer PCC level Layout of lift, service Lift, sumpit |  | Grid G-T/15-26 | A | 2022-10-17 | PC-19 | 9 | E:\Soft IRs\ICPL\L1-Tower IR's\new\11.pdf
12 | Sub Structure | Basement | L1/12 | 2022-10-24 |  | Brick work | Brick work of lift, service lift, sumpit and allow for plaster |  | Grid G-T/15-26 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\12.pdf
13 | Sub Structure | Basement | L1/13 | 2022-10-24 |  | Surface preparation | Surface preparation level and allow for termite proofing 1st Layer PCC |  | Grid F-G/20-26 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\13.pdf
14 | Sub Structure | Basement | L1/14 | 2022-10-25 |  | PCC | 1st layer PCC level and allow for brickwork |  | Grid F-T/26-26 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\14.pdf
15 | Sub Structure | Basement | L1/15
16 | Sub Structure | Basement | L1/16 | 2022-10-25 |  | Termite proofing | Termite proofing before PCC |  | Grid F-G/20-26 | A | 2022-10-25 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\16.pdf
17 | Sub Structure | Basement | L1/17 | 2022-10-26 |  | Brick work | Brick work and allow for plaster of raft protection wall |  | Grid F-H/26 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\17.pdf
18 | Sub Structure | Basement | L1/18 | 2022-10-26 |  | Surface preparation | Surface preparation and allow for termite proofing |  | Grid H-L/20-26 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\18.pdf
19 | Sub Structure | Basement | L1/19 | 2022-10-26 |  | Termite proofing | Termite proofing and allow for PCC |  | Grid H-L/20-26 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\19.pdf
20 | Sub Structure | Basement | L1/20 | 2022-10-27 |  | PCC Level | Layout and 1st PCC Level and allow for bricki work |  | Grid G-L/20 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\20.pdf
21 | Sub Structure | Basement | L1/21 | 2022-10-31 |  | PCC | 1st layer PCC level and allow for primer and membrane |  | Grid F-H/11-20 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\21.pdf
| Sub Structure | Basement | L1/22 | 2022-10-31 |  | PCC | 1st layer of PCC level and allow for primer and membrane |  | Grid G-H/20-26 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L1-Tower IR's\new\22.pdf
| Sub Structure | Basement | L1/23 | 2022-11-01 |  | Primer, membrane | Primer and membrane and allow for 2nd layer PCC |  | Grid G-H/20-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\23.pdf
| Sub Structure | Basement | L1/24 | 2022-11-01 |  | Primer, membrane | Primer and membrane and allow for 2nd layer PCC |  | Grid F-H/11-20, F/20-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\24.pdf
| Sub Structure | Basement | L1/25 | 2022-11-01 |  | PCC | 2nd layer PCC Level |  | Grid F-H/15-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\25.pdf
| Sub Structure | Basement | L1/26 | 2022-11-01 |  | Surface preparation | Surface preparation and allow for termite proofing |  | Grid L-T/15-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\26.pdf
| Sub Structure | Basement | L1/27 | 2022-11-01 |  | Brick work | Brick work and allow for plaster of raft protection wall |  | Grid H-T/26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\27.pdf
| Sub Structure | Basement | L1/28 | 2022-11-03 |  | PCC | 1st layer PCC level and allow for primer and membrane of lift and sumpits |  | L1 Tower lift,sumpits | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\28.pdf
| Sub Structure | Basement | L1/29 | 2022-11-04 |  | Layout,level | Layout and level of RTW1, columns and service lift and allow for steel |  | F-H/20-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\29.pdf
| Sub Structure | Basement | L1/30 | 2022-11-04 |  | PCC | 1st layer of PCC and allow for Primer & Mebrane |  | J-N/20-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\30.pdf
| Sub Structure | Basement | L1/31 | 2022-11-04 |  | PCC | Level of 2nd layer PCC before raft |  | F-H/11-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\31.pdf
| Sub Structure | Basement | L1/32 | 2022-11-04 |  | Primer | Check primer and membrane and allow for 2nd layer PCC |  | J-N/20-26 | A | 2022-11-17
| Sub Structure | Basement | L1/33 | 2022-11-05 |  | Primer and membrane | Primer and membrane of lift and sumpits and allow for 2nd layer of PCC |  | L1 Tower lift,sumpits | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\33.pdf
| Sub Structure | Basement | L1/34 | 2022-11-05 |  | Layout,level | Level and layout of columns and RTW and allow for steel |  | Grid H-L/19-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\26.pdf
| Sub Structure | Basement | L1/35 | 2022-11-05 |  | PCC | 1st layer of PCC and allow for primer and membrane L1 Tower |  | Grid N-T/20-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\35.pdf
| Sub Structure | Basement | L1/36 | 2022-11-05 |  | Primer, membrane | Primer and membrane and allow for 2nd layer of PCC |  | Grid N-T/20-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\36.pdf
| Sub Structure | Basement | L1/37 | 2022-11-07 |  | Surface preparation | Surface preparation and allow for termite proofing |  | Grid M-T/15-15 | A | 2022-11-14
| Sub Structure | Basement | L1/38 | 2022-11-07 |  | Termite proofing | Termite proofing and allow for 1st layer PCC |  | Grid M-T/15-15 | A | 2022-11-14
| Sub Structure | Basement | L1/39 | 2022-11-07 |  | Layout | Layout of columns and allow for steel fixing |  | Grid F-H/12-19 | A | 2022-11-14
| Sub Structure | Basement | L1/40 | 2022-11-07 |  | Excavation | Excavation level and surface preparation isolated footing and allow for termite proofing |  | Grid L-M/14-20 | A | 2022-11-14
| Sub Structure | Basement | L1/41 | 2022-11-07 |  | Termite proofing | Termite proofing of isolated footing and allow for 1st layer of PCC |  | Grid L-M/14-20 | A | 2022-11-14
| Sub Structure | Basement | L1/42 | 2022-11-07 |  | Layout,level | Level and layout of columns , RTW, Sumpit, Shear wall and lift and also allow for stee |  | Grid L-Q/20-26 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L1-Tower IR's\new\42.pdf
| Sub Structure | Basement | L1/43 | 2022-11-08 |  | Core cutting | Core cutting in 1st layer of PCC for earthing Rod conduit Zone 4 & 5 |  | Grid O-R/17-23 | A | 2022-11-14
| Sub Structure | Basement | L1/44 | 2022-11-10 |  | Termite proofing | Termite proofing and allow for 1st layer PCC |  | Grid N-N/15-20 | A | 2022-11-14
| Sub Structure | Basement | L1/45 | 2022-11-10 |  | Surface preparation | Check the surface preparation and allow for brick work |  | Grid N-N/15-20, L-N/20 | A | 2022-11-14
| Sub Structure | Basement | L1/46 | 2022-11-10 |  | Brick Work | Brick Work and allow for plaster |  | Grid N-N/15-20,L-N/20 | A | 2022-11-14
| Sub Structure | Basement | L1/47 | 2022-11-10 |  | Brick work | Brick work and allow for plaster |  | Grid G-K/20 | A | 2022-11-14
| Sub Structure | Basement | L1/48 | 2022-11-10 |  | Plaster | Check the plaster and allow for primer and membrane |  | Grid G-K/20 | A | 2022-11-14
| Sub Structure | Basement | L1/49 | 2022-11-10 |  | Boring | Boring in 1st layer of PCC for earthing rod conduit Zone 4 & 5 |  | Grid O-R/17-23 | A | 22-Nonv-22
| Sub Structure | Basement | L1/50 | 2022-11-11 |  | Layout,level | Level and layout of columns and RTW Zone 4 |  | Grid Q-T/23-26 | A | 2022-11-14
| Sub Structure | Basement | L1/51 | 2022-11-11 |  | Primer | Check the primer and membrane |  | Grid G-K/20 | A | 2022-11-14
| Sub Structure | Basement | L1/52 | 2022-11-11 |  | Steel fixing | Steel fixing of service lift and allow for pouring |  | Grid H-J/23-24 | A | 2022-11-14
| Sub Structure | Basement | L1/53 | 2022-11-12 |  | PCC | 1st layer PCC and allow for primer and membrane L1 Tower |  | Grid N-T/15-20 | A | 2022-11-17
| Sub Structure | Basement | L1/54 | 2022-11-12 |  | Primer | Primer and membrane and allow for 2nd layer PCC |  | Grid N-T/15-20 | A | 2022-11-22
| Sub Structure | Basement | L1/55 | 2022-11-12 |  | Steel fixing | Bottom steel of raft foundation and allow for top steel fixing L1 Tower |  | Grid G-L/20-26 | A | 2022-11-17
| Sub Structure | Basement | L1/56 | 2022-11-16 |  | To steel raft | Top steel raft foundation, Dowel of columns and RTW1 and Bottom+Top steel SOG |  | Grid 18-26/F-L | B | 2022-11-22
| Sub Structure | Basement | L1/57 | 2022-11-16 |  | Water stopper | Water stopper in raft foundation Zone 4 |  | Grid 26/G-L | A | 2022-11-30
| Sub Structure | Basement | L1/58 | 2022-11-16 |  | Construction Joint | Construction Joint as per POUR Plan Zone 4 |  | Grid 20-26/L & 20/K-M | A | 2022-11-30
| Sub Structure | Basement | L1/59 | 2022-11-16 |  | Concrete pouring | Concrete Pouring L1 Tower |  | Grid 20-26/F-L, 18-20/F-K | A | 2022-11-22
| Sub Structure | Basement | L1/60 | 2022-11-16 |  | Layout,Level | The level and layout of columns, Ramp wall and RTW, Zone 4 L1 Tower |  | Grid N-T/19-22, T/19-23 | A | 2022-11-17
| Sub Structure | Basement | L1/61 | 2022-11-16 |  | Earth Rod | Placing of Earth Rod in bore holes as per shop drawing |  | Grid O-R/17-23 | B | 2022-11-22
| Sub Structure | Basement | L1/62 | 2022-11-17 |  | Plaster | Plaster and allow for primer and membrane |  | Grid N-N/15-20, L-N/20 | A | 2022-11-30
| Sub Structure | Basement | L1/63 | 2022-11-17 |  | Primer and membrane | Primer and Membrane |  | Grid N-N/15-20, L-N/20 | A | 2022-11-30
| Sub Structure | Basement | L1/64 | 2022-11-17 |  | Primer and membrane | Primer and membrane and allow for 2nd layer PCC for isolated footing |  | Grid M-M/15-19 | A | 2022-11-30
| Sub Structure | Basement | L1/65 | 2022-11-23 |  | Level, layout | Check level and layout of columns sump;it 1, RTW, Zone 5 |  | Grid M-T/14 b/w 15-19 | A | 2022-12-02
| Sub Structure | Basement | L1/66 | 2022-11-21 |  | Steel fixing | Steel fixing of lift Zone 4 L1 Tower |  | Grid N-P/21-23 | B | 2022-11-22
| Sub Structure | Basement | L1/67 | 2022-11-21 |  | Steel fixing | Steel fixing of raft of SOG Area |  | Grid F-10 to H b/w J | A | 2022-11-22
| Sub Structure | Basement | L1/68 | 2022-11-21 |  | Concrete pouring | Allow concrete pouring of lift Zone 4 L1 Tower |  | Grid N-P/21-23 | A | 2022-11-30
| Sub Structure | Basement | L1/69 | 2022-11-21 |  | Concrete pouring | Allow for concrete pouring of raft of SOG Area |  | F-H/11-18 | A | 2022-11-22
| Sub Structure | Basement | L1/70 | 2022-11-23 |  | Level, layout | Check level and layout of columns and allow for steel fixing |  | Grid G-H/12-18 | A | 2022-12-02
| Sub Structure | Basement | L1/71 | 2022-11-24 |  | Level, layout | Check level and layout of columns & service lift wall and allow for steel fixing |  | Grid G-L/19-26 | A | 2022-12-02
| Sub Structure | Basement | L1/72 | 2022-11-24 |  | Steel fixing | Steel fixing of sumpit in Zone 4 and allow for pouring L1 Tower |  | Grid T/23-25 | A | 2022-11-30
| Sub Structure | Basement | L1/73 | 2022-11-29 |  | Steel fixing | Check bottom steel fixing Zone 4 |  | Grid L-T/19-26 | A | 2022-12-13
| Sub Structure | Basement | L1/74 | 2022-11-29 |  | Curing | Check curing of SOG Raft |  | Grid F-H/11-19 SOG | A | 2022-12-02
| Sub Structure | Basement | L1/75 | 2022-12-01 |  | Curing | Check curing of Raft L1 Tower Zone 4 |  | Grid 20-26/F-L, 18-20/F-K+Main lift | A | 2022-12-02
| Sub Structure | Basement | L1/76 | 2022-12-07 |  | copper conductor | Check the copper conductor & Thermo weld Zone 4 |  | Zone 4 | A | 2022-12-13
| Sub Structure | Basement | L1/77 | 2022-12-09 |  | Steel fixing | Check the steel fixing of raft Zone 4 |  | Grid L-T/19-26 | A | 2022-12-13
| Sub Structure | Basement | L1/78 | 2022-12-09 |  | Water stopper | Check the horizontal water stopper Zone 4 |  | Grid L-T/26, T/19-26 | A | 2022-12-13
| Sub Structure | Basement | L1/79 | 2022-12-09 |  | Construction Joint | Check the construction joint Zone 4 |  | Grud L-T/19 | A | 2022-12-13
| Sub Structure | Basement | L1/80 | 2022-12-10 |  | Concrete pouring | Allow for concrete pouring of raft Zone 4 |  | Grid L-T/19-26 | A | 2022-12-13
| Sub Structure | Basement | L1/81 | 2022-12-12 |  | Steel fixing | Check steel fixing of sumpit Zone 5 |  | Grid R-T/18-19 | A | 2022-12-13
| Sub Structure | Basement | L1/82 | 2022-12-12 |  | Concrete pouring | allow for concrete pouring of sumpit Zone 5 |  | Grid R-T/18-19 | A | 2022-12-13
| Sub Structure | Basement | L1/83 | 2022-12-12 |  | Level, Layout | Check level & Layout of columns, Shear Wall, sumpit, ramp, stairs & RW Zone 5 |  | Grid M-T/20-26 | A | 2022-12-13
| Sub Structure | Basement | L1/84 | 2022-12-14 |  | Conductor | check laying of copper conductor and thermoweld Zone 5 |  | Grid M-T/15-20 | A | 2022-12-28
| Sub Structure | Basement | L1/85 | 2022-12-12 |  | Steel fixing | Check bottom steel fixing of Raft L1 Tower Zone 5 |  | Grid N-T/15-19 | A | 2022-12-21
| Sub Structure | Basement | L1/86 | 2022-12-17 |  | Steel fixing | Check top steel fixing of raft L1 Tower and isolated footing CY area |  | Grid N-T/14-19, M/15-19 | A | 28-Deec-22
| Sub Structure | Basement | L1/87 | 2022-12-19 |  | Water stopper | Check horizontal water stopper Zone 5 |  | Grid T/15-19 | A | 2022-12-28
| Sub Structure | Basement | L1/88 | 2022-12-19 |  | Concrete pouring | allow for concrete pouring of Raft Zone 5 |  | Grid N-T/14-19, M/15-19 | A | 2022-12-28
| Sub Structure | Basement | L1/89 | 2022-12-21 |  | Curing | check curing of raft L1 Tower |  | Grid L-T/19-26 | A | 2022-12-28
| Sub Structure | Basement | L1/90 | 2022-12-21 |  | Level, layout | Level, layout of columns, sumpits and shear wall |  | Grid L-T/14-19 | A | 2022-12-28
| Sub Structure | Basement | L1/91 | 2023-01-02 | 2023-01-02 | curing | Check curing of raft zone 5 |  | Grid N-T/14-19, M/15-19 | A
| Sub Structure | Basement | L1/92 | 2023-01-12 |  | Surface preparation | Check surface preparation and allow for primer and membrane Zone 4 & 5 |  | Grid T/14-26 | A | 2023-01-20
| Sub Structure | Basement | L1/93 | 2023-01-16 |  | Primer, membrane | Check primer and membrane Zone 4 & 5 |  | Grid T/14-26 | A | 2023-01-20
| Sub Structure | Basement | L1/94 | 2023-01-18 |  | Compaction | Check 1st layer compaction backfilling of sand along backside of RTW Zone 4 & 5 |  | Grid T/14-26 | A | 2023-01-20
| Sub Structure | Basement | L1/95 | 2023-01-18 |  | Compaction | Check 2nd layer compaction backfilling of sand along backside of RTW Zone 4 & 5 |  | Grid T/14-26 | A | 2023-01-20
| Sub Structure | Basement | L1/96 | 2023-01-23 |  | Compaction | Check 3rd layer compaction backfilling of sand along bacisides of RTW level 16.25 to 15.75 Zone 4 & 5 |  | Grid T/14-26 | A | 2023-02-02
| Sub Structure | Basement | L1/97 | 2023-01-23 |  | Compaction | Check 4th layer compaction backfilling of sand along bacisides of RTW level 15.75 to 15.25 Zone 4 & 5 |  | Grid T/14-26 | A | 2023-02-02
| Sub Structure | Basement | L1/98 | 2023-01-23 |  | Compaction | Check 5th layer compaction backfilling of sand along bacisides of RTW level 15.25 to 14.75 Zone 4 & 5 |  | Grid T/14-26 | A | 2023-02-02
| Sub Structure | Basement | L1/99 | 2023-01-23 |  | Compaction | Check 6th layer compaction backfilling of sand along bacisides of RTW level 14.75 to 14.25 Zone 4 & 5 |  | Grid T/14-26 | A | 2023-02-02
| Sub Structure | Basement | L1/100 | 2023-01-31 |  | Backfilling | Check backfilling of sand upto level 85.79 RL Zone 4 & 5 |  | Grid T/14-26 | A | 2023-02-06
| Sub Structure | Basement | L1/101 | 2023-02-01 |  | Backfilling | Check backfilling of sand along side of L1 Tower Zone 4 |  | Grid G-T/26 | A | 2023-02-06
| Sub Structure | Basement | L1/102 | 2023-03-22 |  | RTW Reinforcement | Check RTW reinforcement (L=120Rft) Zone 4 |  | Grid F-O/26 | A | 2023-03-28
| Sub Structure | Basement | L1/103 | 2023-03-22 |  | RTW Reinforcement | Check RTW reinforcement (L=72Rft) Zone 4 |  | Grid O-T/26 | A | 2023-03-28
| Sub Structure | Basement | L1/104 | 2023-03-22 |  | RTW Reinforcement | Check RTW Reinforcement (L=95Rft) Zone 4 |  | Grid T/19-26 | A | 2023-03-28
| Sub Structure | Basement | L1/105 | 2023-03-22 |  | Column reinforcement | Check column reinforcement (16 Nos) Zone 4 |  | Grid G-M/20-26 | A | 2023-03-28
| Sub Structure | Basement | L1/106 | 2023-03-24 |  | Condute UPVC | Check condute UPVC Class 32mm in lift & Column Zone4 |  | Grid N/20, O/26 | A | 2023-03-28
| Sub Structure | Basement | L1/107 | 2023-03-27 |  | Reinforcement | Check column reinforcement (8 Nos) Zone 4 Basement |  | Grid G/20-26, N/24, O-Q/26 | A | 2023-04-03
| Sub Structure | Basement | L1/108 | 2023-03-29 |  | Reinforcement | Service lift and columns (7 Nos) reinforcement Zone 4 |  | Grid H-J/23-24, 23-26/P-T | A | 2023-04-03
| Sub Structure | Basement | L1/109 | 2023-03-29 |  | Reinforcement | Final reinforcement check columns (10 Nos) and allow for concrete pouring Zone 4 |  | Grid G-O/26, G/22-24, 24N | A | 2023-04-03
| Sub Structure | Basement | L1/110 | 2023-03-30 |  | Reinforcement | Final reinforcement of RTW (66 Rft) and allow for concrete pouring Zone 4 |  | Grid G-L/26 | A | 2023-04-03
| Sub Structure | Basement | L1/111 | 2023-03-31 |  | Water stopper | Check horizontal and vertical water stopper of RTW (66 RFT) Zone 4 |  | Grid G-L/26 | A | 2023-04-03
| Sub Structure | Basement | L1/112 | 2023-04-01 |  | RTW Reinforcement | Check RTW reinforcement 80'-8'' Zone 4 |  | Grid T/15-19 | A | 2023-04-07
| Sub Structure | Basement | L1/113 | 2023-04-01 |  | Column reinforcement | final column reinforcement and allow for concrete pouring Zone 4 |  | Grid G-L/20-24 | A | 2023-04-07
| Sub Structure | Basement | L1/114 | 2023-04-02 |  | Column reinforcement | Final columns reinforcement and allow for concrete pouring Zone 4 |  | Grid P-T/26, T/23-24, L-M/22, 20M | A | 2023-04-07
| Sub Structure | Basement | L1/115 | 2023-04-03 |  | Column reinforcement | Check columns (3 Nos) and lift reinforcement Zone 4 |  | Grid N-P/20-22, R/20-22, 19T | A | 2023-04-07
| Sub Structure | Basement | L1/116 | 2023-04-05 |  | Column reinforcement | Check columns (5 Nos) reinforcement Zone 4 |  | Grid N-T/19, 18T | A | 2023-04-07
| Sub Structure | Basement | L1/117 | 2023-04-05 |  | Column reinforcement | Final columns (4 Nos) reinforcement and allow foro concrete pouring Zone 4 |  | Grid P-R/24, T/19-21 | A | 2023-04-10
| Sub Structure | Basement | L1/118 | 2023-04-05 |  | RTW Reinforcement | RTW reinforcement and allow for concrete pouring Zone 4 |  | Grid L-R/26 | A | 2023-04-07
| Sub Structure | Basement | L1/119 | 2023-04-06 |  | Column reinforcement | Check columns (13 Nos) and SW8 (2 Nos) reinforcement Zone 4 |  | Grid N-T/15-18 | A | 2023-04-07
| Sub Structure | Basement | L1/120 | 2023-04-07 |  | Reinforcement | Final reinforcement of RTW and allow for placing of concrete Zone 4 |  | Grid R-T/26, T/26-26 | A | 2023-04-16
| Sub Structure | Basement | L1/121 | 2023-04-07 |  | Reinforcement | Final reinforcement of columns (6 Nos) and allow for placing of concrete Zone 4 * 5 |  | Grid R/19-22, T/16-18 | A | 2023-04-14
| Sub Structure | Basement | L1/122 | 2023-04-09 |  | Reinforcement | Final reinforcement of Service lift and allow for placing of concrete Zone 4 |  | Grid H-J/23-24 | A | 2023-04-14
| Sub Structure | Basement | L1/123 | 2023-04-11 |  | Reinforcement | Final reinforcement of RTW 66 RFT and allow for placing of concrete Zone 4 |  | Grid T/19-26 | A | 2023-04-14
| Sub Structure | Basement | L1/124 | 2023-04-11 |  | Reinforcement | Final reinforcement of columns (9 Nos) and allow for placing of concrete Zone 4 |  | Grid P-R/15-19, T/15 | A | 2023-04-14
| Sub Structure | Basement | L1/125 | 2023-04-15 |  | Beam reinforcement | Check Beam reinforcement Zone 4 |  | Grid G-T/26-26, J-N/24-26, N-Q/25-26 | A | 2023-04-19
| Sub Structure | Basement | L1/126 | 2023-04-15 |  | Slab reinforcement | Check top and Bottom Slab reinforcement Zone 4 |  | Grid G-T/26-26, J-N/24-26, N-Q/25-26 | A | 2023-04-19
| Sub Structure | Basement | L1/127 | 2023-04-16 |  | Slab reinforcement | Final slab reinforcement and allow for concrete pouring Zone 4 |  | Grid G-T/26-26, J-N/24-26, N-Q/25-26 | A | 2023-04-19
| Sub Structure | Basement | L1/128 | 2023-04-16 |  | Level, layout | Check level, layout of slab and columns | (0'-0'') | Grid G-T/26-26, J-N/24-26, N-Q/25-26 | A | 2023-04-19
| Sub Structure | Basement | L1/129 | 2023-05-02 |  | Reinforcement | Final reinforcement of RTW and allow for placing of concrete Zone 4 L1 Tower |  | Grid T/16-19 | A | 2023-05-08
| Sub Structure | Basement | L1/130 | 2023-05-04 |  | Water stopper | Check horizontal and verical water stopper on RTW 60 Rft L1 Tower |  | Grid L-R/26 | A | 2023-05-08
| Sub Structure | Basement | L1/131 | 2023-05-04 |  | Water stopper | Check horizontal and vertical water stopper on RTW 66 RFT L1 Tower |  | Grid R-T/26, T/26-26 | A | 2023-05-08
| Sub Structure | Basement | L1/132 | 2023-05-04 |  | Water stopper | check horizontal and vertical water stopper on RTW 66 Rft L1 Tower |  | Grid T/19-26 | A | 2023-05-08
| Sub Structure | Basement | L1/133 | 2023-05-04 |  | Water stopper | check horizontal and vertical water stopper on RTW 60 Rft L1 Tower |  | Grid T/16-19 | A | 2023-05-08
| Sub Structure | Basement | L1/134 | 2023-05-08 |  | Septic Tank | Check Layout of Septic Tank, L1 Tower Zone 4 |  | Grid F-K/26 | A | 2023-05-17
| Sub Structure | Basement | L1/135 | 2023-05-09 |  | Beam reinforcement | Check beam reinforcement Zone 4 |  | Grid G-J/20-26, J-L/20-23 | A | 2023-05-17
| Sub Structure | Basement | L1/136 | 2023-05-10 |  | Column reinforcement | Check columns (3 Nos) reinforcement and allow for concrete pouring Zone 5 |  | Grid N/15, N/17-18 | A | 2023-05-17
| Sub Structure | Basement | L1/137 | 2023-05-11 |  | Thermopore | Check thermopore in expansion joint of column C1, C37 Zone 4 | (-13'-3'' to 0'-0'') | Grid G-G/20-26 | A | 2023-05-17
| Sub Structure | Basement | L1/138 | 2023-05-11 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 | (+1'-9'') | Grid G-J/20-26, J-L/20-24 | A | 2023-05-17
| Sub Structure | Basement | L1/139 | 2023-05-11 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+1'-9'') | Grid G-J/20-26, J-L/20-24 | R | 2023-05-11
| Sub Structure | Basement | L1/140 | 2023-05-12 |  | Beam reinforcement | Check beam reinforcement Zone 4 | (0'-0'') | Grid S-U/15-26 | A | 2023-05-17
| Sub Structure | Basement | L1/141 | 2023-05-12 |  | Reinforcement | Final reinforcement of RTW and allow for concrete pouring Zone 4 |  | Grid T/14-16 | A | 2023-05-17
| Sub Structure | Basement | L1/142 | 2023-05-12 |  | Water stopper | Check horizontal and vertical water stopper Zone 4 |  | Grid T/14-16 | A | 2023-05-17
| Sub Structure | Basement | L1/143 | 2023-05-13 |  | Level, layout | Check level, layout of columns and service lift Zone 4 |  | Grid G-J/20-26, J-L/20-24 | A | 2023-05-17
| Sub Structure | Basement | L1/144 | 2023-05-15 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 L1 Tower |  | Grid S-U/15-26 | A | 2023-05-17
| Sub Structure | Basement | L1/145 | 2023-05-15 |  | Slab reinforcement | Final slab reinforcement and allow for concrete pouring Zone 4 L1 Tower |  | Grid S-U/15-26 | A | 2023-05-23
| Sub Structure | Basement | L1/146 | 2023-05-17 |  | Reinforcement | Check reinforcement of columns and SW8 and allow for concrete pouring Zone 4 L1 Tower |  | Grid P/15, N/16 & 19 | A | 2023-05-23
| Sub Structure | Basement | L1/147 | 2023-05-17 |  | PVC Water stopper | Check UPVC water stopper in septic tank Zone 4 |  | Grid F-K/26 | A | 2023-05-23
| Sub Structure | Basement | L1/148 | 2023-05-17 |  | Reinforcement | Check top and bottom reinforcement of raft foundation of septic tank with its dowel Zone 4 |  | Grid F-K/26 | A | 2023-05-23
| Sub Structure | Basement | L1/149 | 2023-05-17 |  | Shuttering | Check shuttering of septic tank before pouring Zone 4 |  | Grid F-K/26 | A | 2023-05-23
| Sub Structure | Basement | L1/150 | 2023-05-17 |  | Shuttering | Final reinforcement and shuttering and allow for concrete pouring Zone 4 |  | Grid F-K/26 | A | 2023-05-23
| Sub Structure | Basement | L1/151 | 2023-05-17 |  | Column reinforcement | Check columns (8 Nos) reinforcement Zone 4 | (+1'-9'' to +8'-9'') | Grid G-L/20-22 | A | 2023-05-23
| Sub Structure | Basement | L1/152 | 2023-05-17 |  | Level, layout | Check level, layout of columns Zone 4 | (0'-0'') | Grid S-U/15-26 | A | 2023-05-23
| Sub Structure | Basement | L1/153 | 2023-05-17 |  | Reinforcement | Final reinforcement of lift and allow for concrete pouring Zone 4 |  | Grid N-P/20-22 | A | 2023-05-23
| Sub Structure | Basement | L1/154 | 2023-05-18 |  | Level, septic tank | Check top raft level of septic tank Zone 4 |  | Grid F-K/26 | A | 2023-05-23
| Sub Structure | Basement | L1/155 | 2023-05-19 |  | Column reinforcement | Check columns (13 Nos) reinforcement Zone 4 | (0'-00' to +18'-9'') | Grid G-Q/26, G-M/24 | A | 2023-05-23
| Sub Structure | Basement | L1/156 | 2023-05-20 |  | Service lift | Check service lift reinforcement Zone 4 | (1'-9'' to 18'-9'') | Grid H-J/23-24 | A | 2023-05-23
| Sub Structure | Basement | L1/157 | 2023-05-22 |  | Beam reinforcement | Check beam reinforcement Zone 4 | (1'-9'') | Grid M-S/15-26 | A | 2023-05-26
| Sub Structure | Basement | L1/158 | 2023-05-22 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 | (1'-9'') | Grid M-S/15-26 | A | 2023-05-26
| Sub Structure | Basement | L1/159 | 2023-05-22 |  | Slab reinforcement | Final slab reinforcement and allow for concrete pouring Zone 4 | (1'-9'') | Grid M-S/15-26 | A | 2023-05-26
| Sub Structure | Basement | L1/160 | 2023-05-22 |  | Column reinforcement | Check columns (4 Nos) Reinforcement and allow for concrete pouring Zone 4 | (1'-9'' to +18'-9'') | Grid G-K/26 | A | 2023-05-23
| Sub Structure | Basement | L1/161 | 2023-05-24 |  | formwork, concrete | Check steps formwork and concrete, level , layout Zone 4 | (1'-9'') | Grid Q-S/26 | A | 2023-05-26
| Sub Structure | Basement | L1/162 | 2023-05-24 |  | Level,layout | Check level , layout of columns and lift walls Zone 4 | (1'-9'') | Grid N-S/15-26, M-N/20-23 | A | 2023-05-30
| Sub Structure | Basement | L1/163 | 2023-05-24 |  | Columns reinforcement | Check columns (10 Nos) reinforcement Zone 4 | (1'-9'') | Grid S-T/15-26 | A | 2023-05-26
| Sub Structure | Basement | L1/164 | 2023-05-24 |  | Columns reinforcement | Check columns (15 Nos) Reinforcement and allow for concrete pouring Zone 4 | (1'-9'') | Grid G-L/20-23, 26L, M/24-26 | A | 2023-05-26
| Sub Structure | Basement | L1/165 | 2023-05-24 |  | Septic Tank reinforcement | Check septic Tank wall reinforcement Zone 4 |  | Grid G-K/26 | A | 2023-05-26
| Sub Structure | Basement | L1/166 | 2023-05-25 |  | Lift reinforcement | Check lift reinforcement of upper part and allow concrete pouring Zone 4 |  | Grid N-P/20-22 | A | 2023-05-30
| Sub Structure | Basement | L1/167 | 2023-05-26 |  | Reinforcement | Final columns (18 Nos) reinforcement of upper part and allow for concrete pouring Zone 4 | (+10'-9'' to +18'-9'') | Grid G-M/20-26 | A | 2023-05-30
| Sub Structure | Basement | L1/168 | 2023-05-26 |  | Surface preparation | Check surface preparation and allow for vertical membrane on RTW Zone 4-5 | (-6'-0'' to -5'-6'') | Grid G-T/26, T/14-26 | A | 2023-05-30
| Sub Structure | GF | L1/169 | 2023-05-29 |  | Column reinforcement | Check columns (8 Nos) and lift reinforcement Zone 4-5 | (+1'-9'' to +18'-9'') | Grid M-R/20-24, R/19 | A | 2023-05-30
| Sub Structure | GF | L1/170 | 2023-05-29 |  | Reinforcement | Beam GB reinforcement and allow for concrete placing Zone 5 | (+18'-9'')( | Grid S/15-19 | A | 2023-05-30
| Sub Structure | Basement | L1/171 | 2023-05-29 |  | Harvesting tank | Check layout of rain water harvesting tank and fuel tank Zone 4 |  | Grid L-T/26, T/25-26 | A | 2023-05-30
| Sub Structure | GF | L1/172 | 2023-05-29 |  | Condute UPVC | Check condute UPVC class 32mm in lift and column Zone 4 | (+1'-9'' to +18'-9'') | Grid N/20, O/26 | A | 2023-05-30
| Sub Structure | GF | L1/173 | 2023-05-30 |  | Column reinforcement | Check columns (4 Nos) Reinforcement and allow for concrete pouring Zone 4 | (+1'-9'' to +18'-9'') | Grid M/20-22, O/26, S/26 | A | 2023-05-30
| Sub Structure | Basement | L1/174 | 2023-05-30 |  | Primer,membrane | Check vertical primer and membrane on RTW L1 Tower |  | Grid T/26, T/14-26 | A | 2023-06-16
| Sub Structure | Basement | L1/175 | 2023-05-30 |  | Backfilling | Allow for backfilling along RTW L1 Tower |  | Grid G-T/26, T/14-26 | A | 2023-06-16
| Sub Structure | GF | L1/176 | 2023-05-31 |  | Service lift+columns | Check service lift reinforcement and columns (3 Nos) and allow for concrete pouring Zone 4 |  | Grid H-J/23-24 + M/20-22, O/26 | A | 2023-06-16
| Sub Structure | Basement | L1/177 | 2023-06-02 |  | Water stopper | Check PVC Water stopper of ran water harvesting tank, Zone 4 |  | Grid L-T/26 | A | 2023-06-16
| Sub Structure | Basement | L1/178 | 2023-06-02 |  | Raft foundation | Check top and bottom raft foundation of rain water harvesting tank with dowels Zone 4 |  | Grid L-T/26 | A | 2023-06-16
| Sub Structure | Basement | L1/179 | 2023-06-02 |  | Rain water | Check shuttering of rain water harvesting tank before pouring Zone 4 |  | Grid L-T/26 | A | 2023-06-16
| Sub Structure | Basement | L1/180 | 2023-06-02 |  | Reinforcement | Check reinforcement and shuttering and allow for concrete pouring Zone 4 |  | Grid L-T/26 | A | 2023-06-16
| Sub Structure | Basement | L1/181 | 2023-06-02 |  | Water stopper | Check PVC water stopper of fuel tank Zone 4 |  | Grid T/24-26 | A | 2023-06-16
| Sub Structure | Basement | L1/182 | 2023-06-02 |  | Raft foundation | Check top and bottom raft foundation of fuel tank with dowels Zone 4 |  | Grid L-T/26 | A | 2023-06-16
| Sub Structure | Basement | L1/183 | 2023-06-02 |  | Fuel tank | Check shuttering of fuel tank before pouring Zone 4 |  | Grid T/24-26 | A | 2023-06-16
| Sub Structure | Basement | L1/184 | 2023-06-02 |  | Fuel tank | Check reinforcement and shuttering of fuel tank and allow for concrete pouring Zone 4 |  | Grid T/24-26 | A | 2023-06-16
| Sub Structure | Basement | L1/185 | 2023-06-02 |  | Water tank | Check layout under ground water tank for fire fighting and domestinc Zone 4 |  | Grid T/14-24 | A | 2023-06-16
| Sub Structure | Ground floor | L1/186 | 2023-06-03 |  | Column reinforcement | Check columns (8 Nos) reinforcement and service lift upper part and allow for concrete placing Z-4 | (+0'-0'' to +18'-9'') | Grid M-R/24, R/19-22, Q/26, H-J/23-24 | A | 2023-06-16
| Sub Structure | Ground floor | L1/187 | 2023-06-05 |  | Column reinforcement | Check columns (13 Nos) reinforcement and SW8 (2 Nos) Zone 4 | (+0'-0'' to +18'-9'') | Grid N-R/15-19 | A | 2023-06-16
| Sub Structure | Basement | L1/188 | 2023-06-05 |  | Level | Check top raft level and fuel tank Zone 4 | (+0'-0'' to +18'-9'') | Grid M-T/24-26 | A | 2023-06-16
| Sub Structure | Basement | L1/189 | 2023-06-05 |  | Concrete pouring | Final reinforcement and allow for concrete pouring of columns (14 Nos) Zone 4 | (+0'-0'' to +18'-9'') | Grid T/18-26, R/18-24, N-P/24-26 | A | 2023-06-16
| Sub Structure | Basement | L1/190 | 2023-06-05 |  | Concrete pouring | Final reinforcement of lift and columns (7 Nos) and allow for concrete pouring Zone 4 | (+0'-0'' to +18'-9'') | Grid M-P/20-22, T/18-26, S/26 | A | 2023-06-16
| Sub Structure | Basement | L1/191 | 2023-06-06 |  | Column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring Zone 5 | (+0'-0'' to +18'-9'') | Grid N/18, T/15-17 | A | 2023-06-16
| Sub Structure | Basement | L1/192 | 2023-06-06 |  | Concrete pouring | Check columns (9 Nos) reinforcement and allow for concrete pouring Zone 5 | (+0'-0'' to +18'-9'') | Grid N-P/15-19 | A | 2023-06-16
| Sub Structure | Ground floor | L1/193 | 2023-06-06 |  | Beam reinforcement | Check beam reinforcement Zone 4 | ( +18'-9'') | Grid G-M/20-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1/194 | 2023-06-07 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 | (+18'-9'') | Grid G-M/20-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1/195 | 2023-06-07 |  | Slab reinforcement | Final slab reinforcement and allow for concrete pouring Zone 4 | (+18'-9'') | Grid G-M/20-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1/196 | 2023-06-08 |  | Level, layout | Check level, layout of columns and service lift Zone 4 | (+18'-9'') | Grid G-M/20-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1/197 | 2023-06-08 |  | Columns reinforcement | Check columns reinforcement and allow for concrete pouring Zone 4 | (+0'-0'' to +18'-9'') | Grid T/15-17 | A | 2023-06-16
| Sub Structure | Ground floor | L1/198 | 2023-06-09 |  | Lift reinforcement | Check columns & Lift reinforcement and allow for concrete pouring Zone 4 | (0'-0'' to +18'-9'') | Grid N-P/20-22, N-P/15-18, R/15+R/16-17 | A | 2023-06-16
| Sub Structure | 1st Floor | L1/199 | 2023-06-10 |  | Column reinforcement | Check columns (12 Nos) and service lift reinforcement Zone 4 | (+18'-9'' to +29'-9'') | Grid G-K/20-26 | A | 2023-06-16
| Sub Structure | Basement | L1/200 | 2023-06-10 |  | Water harvesting | Check rain water harvesting Tank wall reinforcement Zone 4 |  | Grid L-T/26 | A | 2023-06-16
| Sub Structure | Basement | L1/201 | 2023-06-12 |  | Fuel tank | Check fuel Tank wall reinforcement Zone 4 |  | Grid T/24-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1/202 | 2023-06-12 |  | Beam reinforcement | Check beam reinforcement Zone 4 | (+18'-9'') | Grid M-T/19-26 | A | 2023-06-16
| Sub Structure | 1st Floor | L1/203 | 2023-06-12 |  | Column reinforcement | Check columns (08 Nos) reinforcement Zone 4 | (+18'-9'' to +29'-9'') | Grid L-M/20-26 | A | 2023-06-16
| Sub Structure | Basement | L1/204 | 2023-06-12 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-17'-3'' to -16'-9'') | Grid T/14-26 | A | 2023-06-16
| Sub Structure | Basement | L1/205 | 2023-06-12 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-17'-3'' to -16'-9'') | Grid T/14-26 | A | 2023-06-16
| Sub Structure | Basement | L1/206 | 2023-06-12 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-16'-9'' to -16'-3'') | Grid T/14-26 | A | 2023-06-16
| Sub Structure | Basement | L1/207 | 2023-06-12 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-16'-9'' to -16'-3'') | Grid T/14-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1/208 | 2023-06-10 |  | Concrete pouring | Check columns reinforcement and allow for concrete pouring Zone 4 | (+1'-9'' to +18'-9'') | Grid N-P/19, R/15, R/18 | A | 2023-06-16
| Sub Structure | Ground floor | L1/209 | 2023-06-12 |  | Columns reinforcement | Check columns reinforcement and allow for concrete pouring Zone 5 | (+1'-9'' to +18'-9'') | Grid R/15-18 | A | 2023-06-16
| Sub Structure | Ground Floor | L1/210 | 2023-06-14 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 | (18'-9'') | Grid L-T/20-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1/211 | 2023-06-14 |  | Slab reinforcement | Check slab reinforcement of slab and allow for concrete pouring Zone 4 | (+18'-9'') | Grid L-T/20-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1/212 | 2023-06-14 |  | Slab formwork | Check slab formwork along Stair ST-2 Zone 4 | (+18'-9'') | Grid P-Q/20-21 | A | 2023-06-16
| Sub Structure | Ground floor | L1/213 | 2023-06-14 |  | Slab formwork | Check slab formwork along Stair ST-1 Zone 4 | (+18'-9'') | Grid G-H/25-26 | A | 2023-06-16
| Sub Structure | Basement | L1/214 | 2023-06-14 |  | Raft reinforcement | Check raft reinforcement of under ground water tank Zone 4 |  | Grid T/15-22 | A | 2023-06-16
| Sub Structure | Basement | L1/215 | 2023-06-14 |  | Shuttering | Check shuttering of under ground water tank Zone 4 |  | Grid T/15-22 | A | 2023-06-16
| Sub Structure | Basement | L1/216 | 2023-06-14 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-16'-3'' to -15'-9'') | Grid T/14-26 | A | 2023-06-16
| Sub Structure | Basement | L1/217 | 2023-06-14 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-15'-9'' to -15'-3'') | Grid T/14-26 | A | 2023-06-16
| Sub Structure | Basement | L1/218 | 2023-06-14 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-16'-3'' to -15'-3'') | Grid T/14-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1/219 | 2023-06-15 |  | Level,layout | Check level and layout of columns and lift walls Zone 4 | (+18'-9'') | Grid M-T/19-26 | A | 2023-07-12
| Sub Structure | Basement | L1/220 | 2023-06-15 |  | Termite proofing | Check termite proofing along RTW Zone 4 | (-16'-3'' to -17'-3'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/221 | 2023-06-15 |  | Backfilling | Check backfilling along RTW Zone 4 | (-17'-3'' to -16'-9'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/222 | 2023-06-15 |  | Backfilling | Check backfilling along RTW Zone 4 | (-16'-9'' to -16'-3'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/223 | 2023-06-16 |  | Backfilling | Check backfilling along RTW Zone 4 | (-16'-3'' to -15'-9'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/224 | 2023-06-16 |  | Backfilling | Check backfilling along RTW Zone 4 | (-15'-9'' to -15'-3'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/225 | 2023-06-16 |  | Termite proofing | Check Termite proofing along RTW Zone 4 | (-16'-3'' to -15'-3'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | 1st floor | L1/226 | 2023-07-12 |  | Column reinforcement | Check columns (13 Nos) Reinforcement Zone 4 | (+18'-9'' to +29'-9'') | Grid N-T/20-26 | A | 2023-07-12
| Sub Structure | Basement | L1/227 | 2023-06-17 |  | Termite proofing | Check termite proofing along RTW Zone 4 | (-15'-3'' to -14'-3'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/228 | 2023-06-17 |  | Backfilling | Check backfilling along RTW Zone 4 | (-15'-3'' to -14'-9'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/229 | 2023-06-17 |  | Backfilling | Check backfilling along RTW Zone 4 | (-14'-9'' to -14'-3'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/230 | 2023-06-19 |  | Backfilling | Check backfilling along RTW Zone 4 | (-14'-3'' to -13'-9'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/231 | 2023-06-19 |  | Backfilling | Check backfilling along RTW Zone 4 | (-13'-9'' to -13'-3'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/232 | 2023-06-19 |  | Termite proofing | Check Termite proofing along RTW Zone 4 | (-14'-3'' to -13'-3'') | Grid G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/233 | 2023-06-19 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-15'-3'' to -14'-9'') | Grid T/14-26 | A | 2023-07-12
| Sub Structure | Basement | L1/234 | 2023-06-19 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-14'-9'' to -14'-3'') | Grid T/14-26 | A | 2023-07-12
| Sub Structure | Basement | L1/235 | 2023-06-19 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-14'-3'' to -13'-3'') | Grid T/14-26 | A | 2023-07-12
| Sub Structure | Basement | L1/236 | 2023-06-19 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-13'-9'' to -13'-3'') | Grid T/14-26 | A | 2023-07-12
| Sub Structure | Basement | L1/237 | 2023-06-19 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-15'-3'' to -14'-3'') | Grid T/14-26 | A | 2023-07-12
| Sub Structure | Basement | L1/238 | 2023-06-19 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-14'-3'' to -13'-3''0 | Grid T/14-26 | A | 2023-07-12
| Sub Structure | Basement | L1/239 | 2023-06-20 |  | Termite proofing | check termite proofing RTW Zone 4 & 5 | (-13'-3'' to -12'-3'') | Grid T/23-26 & P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/240 | 2023-06-20 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-12'-3'' to -11'-3'') | Grid T/23-26 & P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/241 | 2023-06-20 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-13'-3'' to -12'-9'') | Grid T/23-26 & P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/242 | 2023-06-20 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-12'-9'' to -12'-3'') | Grid T/23-26 & P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/243 | 2023-06-20 |  | Backfilling | Check backfilling along RTW Zone 4 | (-12'-3'' to -11'-9'') | Grid T/23-26 & P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/244 | 2023-06-20 |  | Backfilling | Check backfilling along RTW Zone 4 | (-11'-9'' to -11'-3'') | Grid T/23-26 & P-T/26 | A | 2023-07-12
| Sub Structure | 1st Floor | L1/245 | 2023-06-20 |  | Lift reinforcement | Check lift reinforcement Zone 4 | (+18'-9'' to +29'-9'') | Grid P-N/20-22 | A | 2023-07-12
| Sub Structure | Ground floor | L1/246 | 2023-06-21 |  | Beam reinforcement | Check beam reinforcement Zone 5 | (+18'-9'') | Grid N-T/15-19 | A | 2023-07-12
| Sub Structure | Basement | L1/247 | 2023-06-21 |  | Backfilling | Check backfilling along RTW Zone 4 | (-11'-3'' to -10'-9'') | Grid T/23-26, P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/248 | 2023-06-21 |  | Backfilling | Check backfilling along RTW Zone 4 | (-10'-9'' to -10'-3'') | Grid T/23-26, P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/249 | 2023-06-21 |  | Backfilling | Check backfilling along RTW Zone 4 | (-10'-3'' to -9'-9'') | Grid T/23-26, P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/250 | 2023-06-21 |  | Backfilling | Check backfilling along RTW Zone 4 | (-9'-9'' to -9'-3'')) | Grid T/23-26, P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/251 | 2023-06-21 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-11'-3'' to -10'-3'') | Grid T/23-26, P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/252 | 2023-06-21 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-10'-3'' to -9'-3'')) | Grid T/23-26, P-T/26 | A | 2023-07-12
| Sub Structure | 1st floor | L1/253 | 2023-06-22 |  | Columns reinforcement | Check columns (5 Nos) Reinforcement and allow for concrete pouring Zone 4 | (+18'-9'' to +29'-9'') | Grid G-L/20, G/22 | A | 2023-07-12
| Sub Structure | Basement | L1/254 | 2023-06-22 |  | Termite proofing | Check termite proofing along RTW Zone 4 | (-9'-3'' to -8'-32'') | Grid T/23-26, P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/255 | 2023-06-22 |  | Backfilling | Check backfilling along RTW Zone 4 | (-9'-3'' to -8'-9'') | Grid T/23-26, P-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/256 | 2023-06-22 |  | Backfilling | Check backfilling along RTW Zone 4 | (-8'-9'' to -8'-2'') | Grid T/23-26, P-T/26 | A | 2023-07-12
| Sub Structure | Ground floor | L1/257 | 2023-06-22 |  | Slab reinforcement | Check top and bottom reinforcement Zone 5 | (+18'-9'') | Grid N-T/15-20 | A | 2023-07-12
| Sub Structure | GF | L1/258 | 2023-06-23 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 5 | (+18'-9'') | Grid N-T/15-20 | A | 2023-07-12
| Sub Structure | GF | L1/259 | 2023-06-24 |  | Level, layout | Check level, layout of columns and sW8 Zone 5 | (+18'-9'') | Grid N-T/15-20 | A | 2023-07-12
| Sub Structure | Basement | L1/260 | 2023-06-24 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-13'-3'' to -12'-3'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/261 | 2023-06-24 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-12'-3'' to -11'-3'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/262 | 2023-06-24 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-11'-3'' to -10'-3'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/263 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-13'-3'' to -12'-9'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/264 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-12'-9'' to -12'-3'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/265 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-12'-3'' to -11'-9'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/266 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-11'-9'' to -11'-3'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/267 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-11'-3 to -10'-9'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/268 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-10'-9'' to -10'-3'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/269 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-10'-3'' to -9'-9'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/270 | 2023-06-24 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-10'-3'' to -9'-3'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/271 | 2023-06-24 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-9'-3'' to -8'-3'') | Grid T/14-23, G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/272 | 2023-06-24 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-8'-3'' to -7'-3'') | Grid T/14-26 & G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/273 | 2023-06-24 |  | Termite proofing | Check termite proofing along RTW Zone 4 & 5 | (-7'-3'' to -6'-6'') | Grid T/14-26 & G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/274 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-9'-9'' to -9'-3'')) | Grid T/14-23 & G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/275 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-9'-3'' to -8'-9'') | Grid T/14-23 & G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/276 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-8'-9'' to -8'-3'') | Grid T/14-23 & G-P/26 | A | 2023-07-12
| Sub Structure | Basement | L1/277 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-8'-3'' to -7'-9'') | Grid T/14-26 & G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/278 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-7'-9'' to -7'-3'') | Grid T/14-26 & G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/279 | 2023-06-24 |  | Backfilling | Check backfilling along RTW Zone 4 & 5 | (-7'-3'' to -6'-6'') | Grid T/14-26 & G-T/26 | A | 2023-07-12
| Sub Structure | Basement | L1/280 | 2023-06-24 |  | Water stopper | Check vertical water stopper and horizontal water stopper Zone 4 & 8 |  | T/13-10 + T/12-22 | A | 2023-07-12
| Sub Structure | Basement | L1/281 | 2023-06-24 |  | Concrete pouring | Check reinforcement of under ground water tank and allow for concrete pouring Zone 4 & 8 |  | Grid T/12-22 | A | 2023-07-12
| Sub Structure | 1st floor | L1/282 | 2023-06-24 |  | Column reinforcement | Check column reinforcement (13 Nos) and SW8 (1 No) Zone 5 | (+18'-9'' to +29'-9'') | Grid N-T/15-19 | A | 2023-07-12
| Sub Structure | 1st floor | L1/283 | 2023-07-07 |  | Column reinforcement | Check column reinforcement (4 Nos) and SW8 (2 Nos) Zone 5 | (+18'-9'' to +29'-9'') | Grid N/16-18, P/15, 17, R/19 | A | 2023-07-12
| Sub Structure | 1st floor | L1/284 | 2023-07-07 |  | Column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring Zone 4 | (+18'-9'' to +29'-9'') | Grid H-L/22, G-K/24, J-M/26, M/20 | A | 2023-07-12
| Sub Structure | Basement | L1/285 | 2023-07-11 |  | Level, layout | Check level under ground water tank (Fire fighting and domestic) Zone 4,5 & 8 |  | Grid T/12-22 | A | 2023-07-27
| Sub Structure | 1st floor | L1/286 | 2023-07-11 |  | Reinforcement | Check columns (9 Nos) Reinforcement and allow for concrete pouring Zone 4 | (+18'-9'' to +29'-9'') | Grid L-P/24, O-S/26, M/22 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/287 | 2023-07-12 |  | Lift reinforcement | Check service lift reinforcement and allow for concrete pouring Zone 4 | (+18'-9'' to +29'-9'') | Grid H-J/22-24 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/288 | 2023-07-14 |  | Reinforcement | Check lift and columns reinforcement (9 Nos) and allow for concrete pouring Zone 4 | (+18'-9'' to +29'-9'') | Grid N-P/20-22, G-H/26, R/19-24, T/23-26 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/289 | 2023-07-14 |  | UPVC Condute | Check condute UPVC D class 32 mm in lift wall and columns Zone 4 | (+18'-9'' to +29'-9'') | Grid N/20, O/26 | A | 2023-07-27
| Sub Structure | basement | L1/290 | 2023-07-16 |  | wall reinforcement | Check vertical wall reinforcement of under ground water tank Zone 4 |  | Grid T/15-22 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/291 | 2023-07-17 |  | Column reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 5 |  | Grid N-T/18-19, T/21 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/292 | 2023-07-18 |  | slab formwork | check slab formwork along Stair ST-4 Zone 4 |  | Grid G-H/25-26 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/293 | 2023-07-18 |  | Columns reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 5 | (+18'-9'' to +29'-9'') | Grid N-T/17, R/16 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/294 | 2023-07-18 |  | Columns,SW reinforcement | Check columns (4 Nos), SW8 (2 Nos) reinforcement and allow for concrete pouring Zone 5 | (+18'-9'' to +29'-9'') | Grid N-T/15, N-Q/16, U/16 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/295 | 2023-07-19 |  | Slab formwork | Check slab formwork along stair ST-2 Zone 4 | (+29'-9'') | Grid P-Q/20-21 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/296 | 2023-07-19 |  | Beam reinforcement | Check beam reinforcement Zone 4 | (+29'-9'') | Grid G-Q/20-26 | A | 2023-07-27
| Sub Structure | 1st floor | L1/297 | 2023-07-24 |  | Beam reinforcement | Check beam reinforcement Zone 4 | (+29'-9'') | Grid Q-U/20-26 | A | 2023-07-27
| Sub Structure | 1st floor | L1/298 | 2023-07-24 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 | (+29'-9'') | Grid G-Q/19-26 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/299 | 2023-07-24 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+29'-9'') | Grid G-Q/19-26 | A | 2023-07-27
| Sub Structure | 1st Floor | L1/300 | 2023-07-25 |  | Level, layout | Check level, layout of columns service lift and lift Zone 4 | (+29'-9'') | Grid G-Q/19-26 | A | 2023-08-09
| Sub Structure | 2nd floor | L1/301 | 2023-07-27 |  | Column reinforcement | Check columns (8 Nos) reinforcement Zone 4 | (+29'-9'' to +40'-9'') | Grid G-H/20-26, K/22 | A | 2023-08-09
| Sub Structure | 2nd Floor | L1/302 | 2023-07-31 |  | Column reinforcement | Check columns (16 Nos), Service Lift and main lift reinforcement Zone 4 | (+29'-9'' to +40'-9'') | Grid J-P/20-26, H-J/23-24, N-P/20-22 | A | 2023-08-09
| Sub Structure | Basement | L1/303 | 2023-07-31 |  | Level,layout | Check level and layout of Stair ST-2 Zone 4 | (-13'-2'' to +1'-9;;) | Grid J, N-P/20-22 | A | 2023-08-09
| Sub Structure | 2nd Floor | L1/304 | 2023-08-02 |  | Column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 4 | (+29'-9'' to +40'-9'') | Grid G-M/20, G/22 | A | 2023-08-09
| Sub Structure | 2nd floor | L1/305 | 2023-08-02 |  | UPVC Condute | Check UPVC D class 32mm in lift wall and columns for raft to roof Zone 4 | (+29'-9'' to +40'-9'') | Grid N/20, O/26 | A | 2023-08-09
| Sub Structure | Basement | L1/306 | 2023-08-02 |  | Steel fixing | Check formwork, steel fixing of St-2 and allow for concrete pouring Zone 4 | (-13'-3'' to +1'-9'') | Grid N-P/20-22 | A | 2023-08-09
| Sub Structure | 2nd floor | L1/307 | 2023-08-03 |  | Column reinforcement | Check columns (8 Nos) and service lift reinforcement and allow for concrete pouring Zone 4 | (-29'-9'' to +40'-9'') | Grid H-N/22-23, H/23-24 | A | 2023-08-09
| Sub Structure | 2nd floor | L1/308 | 2023-08-04 |  | Column reinforcement | Check columns (2 Nos) reinforcement and allow for concrete pouring Zone 4 | (-29'-9'' to +40'-9'') | Grid H-N/22-23, H-J/23-24 | A | 2023-08-09
| Sub Structure | 2nd floor | L1/309 | 2023-08-05 |  | Reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring zone 4 | (-29'-9'' to +40'-9'') | Grid H-P/26, P/24 | A | 2023-08-09
| Sub Structure | 1st Floor | L1/310 | 2023-08-05 |  | Beam reinforcement | Check beam reinforcement Zone 4 & 5 | (29'-9'') | Grid M-U/15-26 | A | 2023-08-09
| Sub Structure | 2nd floor | L1/311 | 2023-08-07 |  | Lift reinforcement | Check lift reinforcement and allow for concrete pouring Zone 4 | (-29'-9'' to +40'-9'') | Grid N-P/20-22 | A | 2023-08-09
| Sub Structure | 1st Floor | L1/312 | 2023-08-07 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 & 5 | (29'-9'') | Grid N-U/15-20, P-U/20-26 | A | 2023-08-09
| Sub Structure | 1st floor | L1/313 | 2023-08-07 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 & 5 | (29'-9'') | Grid N-U/15-20, P-U/20-26 | A | 2023-08-09
| Sub Structure | 1st Floor | L1/314 | 2023-08-09 |  | level, layout | Check level and layout of columns and SW8 Zone 4 & 5 | (29'-9'') | Grid N-U/15-20, P-U/20-26 | A | 2023-08-16
| Sub Structure | 1st Floor | L1/315 | 2023-08-12 |  | Column reinforcement | Check columns (17 Nos) Reinforcement Zone 4 & 5 | (+29'-9'' to +40'-9'') | Grid P/17-19, Q-T/18-26, R/17 | A | 2023-08-16
| Sub Structure | 1st Floor | L1/316 | 2023-08-15 |  | Column reinforcement | Check columns (10 Nos) and SW8 (2 Nos) reinforcement Zone 5 | (+29'-9'' to +40'-9'') | Grid N/15-19, P-T/15-16, T/17 | A | 2023-08-16
| Sub Structure | 1st Floor | L1/317 | 2023-08-15 |  | Level, layout | Check level and layout of Stair ST-2 Zone 4 | (+1'-9'' to +18'-9'') | Grid N-P/20-22 | A | 2023-08-18
| Sub Structure | GF | L1/318 | 2023-08-16 |  | Steel fixing | check formwork, Steel Fixing and allow for concrete pouring of Stair ST-2 Zone 4 | (+1'-9'' to +10'-6'') | Grid N-P/20-22 | A | 2023-09-01
| Sub Structure | 2nd Floor | L1/319 | 2023-08-18 |  | Beam reinforcement | Check beam reinforcement Zone 4 | (+40'-9'') | Grid G-Q/20-26 | A | 2023-08-28
| Sub Structure | 2nd Floor | L1/320 | 2023-08-19 |  | slab formwork | Check slab formwork Stair Zone 4 | (+40'-9'') | Grid G-H/24-25, P-Q/20-21 | A | 2023-09-06
| Sub Structure | 2nd Floor | L1/321 | 2023-08-19 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 |  | Grid G-Q/20-26 | A | 2023-08-28
| Sub Structure | 2nd Floor | L1/322 | 2023-08-19 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+40'-9'') | Grid G-Q/20-26 | A | 2023-08-28
| Sub Structure | 2nd Floor | L1/323 | 2023-08-22 |  | Column reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 4 | (+29'-9'' to +40'-9'') | Grid N-U/15-16 | A | 2023-08-28
| Sub Structure | 2nd Floor | L1/324 | 2023-08-22 |  | level, layout | Check level, layout of columns, Service lift and lift Zone 4 | (+40'-9'') | Grid G-Q/20-26 | A | 2023-08-28
| Sub Structure | 2nd to 3rd | L1/325 | 2023-08-23 |  | Column reinforcement | Check columns (9 Nos) reinforcement Zone 4 | (+40'-9'' to +1'-9'') | Grid G-J/20-26, K/20 | A | 2023-08-28
| Sub Structure | 2nd to 3rd | L1/326 | 2023-08-24 |  | Column reinforcement | Check columns (11 Nos) reinforcement Zone 4 | (+40'-9'' to +51'-9'') | Grid K-M/20-26 | A | 2023-09-01
| Sub Structure | 2nd to 3rd | L1/327 | 2023-08-25 |  | Column service lift | Check column (4 Nos) and service lift reinforcement Zone 4 | (+40'-9'' to +51'-9'') | Grid N-Q/24-26, H-J/23-24 | A | 2023-09-01
| Sub Structure | 2nd to 3rd | L1/328 | 2023-08-25 |  | Column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 4 | (+40'-9'' to +51'-9'') | Grid G-L/20, K-L/22 | A | 2023-09-01
| Sub Structure | 2nd to 3rd | L1/329 | 2023-08-26 |  | Lift reinforcement | Check lift reinforcement Zone 4 | (+40'-9'' to +51'-9'') | Grid N-P/20-22 | A | 2023-09-01
| Sub Structure | 2nd to 3rd | L1/330 | 2023-08-26 |  | Condute UPVC | check condute UPVC D class 32mm in lift and column Zone 4 | (+40'-9'' to +51'-9'') | Grid N/20, O/26 | A | 2023-09-01
| Sub Structure | 2nd to 3rd | L1/331 | 2023-08-26 |  | Column reinforcement | Check columns (12 Nos) reinforcement and allow for concrete pouring Zone 4 | (+40'-9'' to +51'-9'') | Grid G-H/22-24, J-L/26, K-L/24, M/20-22, Q/24-26 | A | 2023-09-01
| Sub Structure | 2nd to 3rd | L1/332 | 2023-08-27 |  | column, service lift | Check columns (6 Nos) and service lift reinforcement and allow for concrete pouring Zone 4 | (+40'-9'' to +51'-9'') | Grid H-J/23-24, G-H/26, M-P/24-26 | A | 2023-09-01
| Sub Structure | 2nd to 3rd | L1/333 | 2023-08-28 |  | Column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring Zone 4 | (+29'-9'' to +40'-9'') | Grid S-U/19, T-U/26 | A | 2023-09-01
| Sub Structure | GF | L1/334 | 2023-09-01 |  | steel fixing | Check formwork, steel fixing and allow for concrete pouring Zone 4 | (+10'-9'' to +18'-9'') | Grid N-P/20-22 | A | 2023-09-06
| Sub Structure | 2nd Floor | L1/335 | 2023-09-01 |  | Garbage chute | Check garbage chute Zone 4 | (+0'-0'' to +40'-9'') | Grid G/20-21 | A | 2023-09-06
| Sub Structure | 3rd Floor | L1/336 | 2023-09-01 |  | slab formwork | Check slab formwork along Stair ST-4 Zone 4 | (+51'-9'') | Grid G-H/24-25 | A | 2023-09-06
| Sub Structure | 3rd Floor | L1/337 | 2023-09-01 |  | Beam reinforcement | Check beam reinforcement Zone 4 | (+51'-9'') | Grid G-M/20-26 | A | 2023-09-06
| Sub Structure | 3rd Floor | L1/338 | 2023-09-04 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 | (+51'-9'') | Grid G-M/20-26 | A | 2023-09-06
| Sub Structure | 3rd Floor | L1/339 | 2023-09-04 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+51'-9'') | Grid G-M/20-26 | A | 2023-09-13
| Sub Structure | 2nd Floor | L1/340 | 2023-09-03 |  | Column reinforcement | Check lift and columns (3 Nos) reinforcement and allow for concrete pouring Zone 4 | (+51'-9'') | Grid N-P/20-22 | A | 2023-09-06
| Sub Structure | 3rd Floor | L1/341 | 2023-09-05 |  | level, layout | Check slab level and layout of columns and service lift Zone 4 | (+51'-9'') | Grid G-M/20-26 | A | 2023-09-13
| Sub Structure | GF | L1/342 | 2023-09-06 |  | level, layout | Check level and layout of Stair ST-2 Zone 4 | (+18'-9'' to +29'-9'') | Grid N-P/20-22 | A | 2023-09-13
| Sub Structure | 3rd Floor | L1/343 | 2023-09-06 |  | columns lift reinforcement | Check columns (20 Nos) and service lift reinforcement Zone 4 | (+51'-9'' to +62'-9'') | Grid G-M/20-26 | A | 2023-09-13
| Sub Structure | 2nd Floor | L1/344 | 2023-09-08 |  | Column reinforcement | Check columns (14 Nos) reinforcement and allow for concrete pouring Zone 4-5 | (+29'-9'' to +40'-9'') | Grid N-U/17-18, N-Q/19, S/20-24, R/26 | A | 2023-09-13
| Sub Structure | 1st Floor | L1/345 | 2023-09-11 |  | steel fixing | Check formwork and steel fixing of stair ST-2 and allow for concrete pouring Zone 4 | (18'-9'' to +29'-9'') | Grid N-P/20-22 | A | 2023-09-13
| Sub Structure | 1st floor | L1/346 | 2023-09-12 |  | Level, layout | Check level and layout of Stair ST-2 Zone 4 | (+30'-41') | Grid N-P/20-22 | A | 2023-09-15
| Sub Structure | 3rd floor | L1/347 | 2023-09-12 |  | Column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 4 | (+51'-9'' to +62'-9'') | Grid K-L/20-22, H/20 | A | 2023-09-15
| Sub Structure | 2nd Floor | L1/348 | 2023-09-16 |  | Beam reinforcement | Check beam reinforcement Zone 4-5 | (+40'-9'') | Grid Q-U/20-26, M-U/15-20 | A | 2023-09-20
| Sub Structure | 2nd Floor | L1/349 | 2023-09-17 |  | Slab reinforcement | Check top and bottom slab reinforcement Zone 4-5 | (+40'-9'') | Grid Q-U/20-26, M-U/15-20 | A | 2023-09-20
| Sub Structure | 2nd Floor | L1/350 | 2023-09-17 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4-5 | (+40'-9'') | Grid Q-U/20-26, M-U/15-20 | A | 2023-09-20
| Sub Structure | 2nd Floor | L1/351 | 2023-09-18 |  | Steel fixing | Check formwork and steel fixing of stair st-02 and allow for concrete pouring Zone 4 | (+29'-9'' to +40'-9'') | Grid N-Q/20-21 | A | 2023-09-20
| Sub Structure | 3rd Floor | L1/352 | 2023-09-19 |  | Level, layout | Check level and layout of columns (27 nos) , SW8 (2 Nos) Zone 5 | (+40'-9'') | Grid R-U/20-26, N-U/15-26 | A | 2023-09-22
| Sub Structure | 3rd Floor | L1/353 | 2023-09-22 |  | Column reinforcement | Check columns (21 Nos) and sw8 (2 Nos) reinforcement zone 4-5 | (+40'-9'' to +51'-9'') | Grid R-U/20-26, N-U/15-19 | A | 2023-09-27
| Sub Structure | 3rd Floor | L1/354 | 2023-09-26 |  | Column reinforcement | Check columns (6 Nos) and SW8 (2 Nos) reinforcement Zone 4-5 | (+40'-9'' to +51'-9'') | Grid S/22-24, N-Q/15, N/16, Q/18, N-Q/19 | A | 2023-10-02
| Sub Structure | 4th Floor | L1/355 | 2023-09-28 |  | Column reinforcement | Check column (11 Nos) and service lift reinforcement and allow for concrete pouring Zone 4 | (+51'-9'' to +62'-9'') | Grid G/20-22, H/22, H-J/23-24, K/24-26, L/24-26, M/20-26 | A | 2023-10-02
| Sub Structure | 4th Floor | L1/356 | 2023-10-01 |  | Column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring Zone 4 | (+51'-9'' to +62'-9'') | Grid G/24-26, H-J/26 | A | 2023-10-02
| Sub Structure | 3rd Floor | L1/357 | 2023-10-03 |  | Column reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 4 | (+40'-9'' to +51'-9'') | Grid R-U/26, S-U/24, U/23, S/20-22 | A | 2023-10-04
| Sub Structure | 3rd Floor | L1/358 | 2023-10-03 |  | Column reinforcement | Check columns (13 Nos) reinforcement and allow for concrete pouring Zone 4 | (+40'-9'' to +51'-9'') | Grid U/21, N-U/17-19 | A | 2023-10-04
| Sub Structure | 4th Floor | L1/359 | 2023-10-06 |  | column SW8 reinforcement | Check columns (6 Nos) and SW8 (2 Nos) reinforcement and allow for concrete pouring Zone 5 | (+40'-9'' to +51'-9'') | Grid N-U/15-16 | A | 2023-10-11
| Sub Structure | 5th Floor | L1/360 | 2023-10-07 |  | Beam reinforcement | Check beam reinforcement Zone 4 | (+62'-9'') | Grid N-U/20-26 | A | 2023-10-11
| Sub Structure | 5th Floor | L1/361 | 2023-10-07 |  | Slab formwork | Check slab formwork along Stair ST-4 Zone 4 | (+62'-9'') | Grid G-H/24-25 | A | 2023-10-11
| Sub Structure | 5th Floor | L1/362 | 2023-10-09 |  | Reinforcement | Check top and bottom reinforcement Zone 4 | (+62'-9'') | Grid G-M/20-26 | A | 2023-10-11
| Sub Structure | 5th Floor | L1/363 | 2023-10-09 |  | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+62'-9'') | Grid G-M/20-26 | A | 2023-10-11
| Sub Structure | 4th Floor | L1/364 | 2023-10-09 |  | Slab formwork | Check slab formwork along stair ST-2 Zone 4 | (+51'-9'') | Grid Q/20-21 | A | 2023-10-11
| Sub Structure | 5th Floor | L1/365 | 2023-10-11 |  | Level and layout | Check level and layout of columns (20 Nos) + Service lift Zone 4 | (+62'-9'') | Grid G-M/20-26 | A | 2023-10-18
| Sub Structure | 4th Floor | L1/366 | 2023-10-11 |  | Beam reinforcement | Check beam reinforcement Zone 4-5 | (+51'-9'') | Grid M-U/20-26, N-U/15-26 | A | 2023-10-18
| Sub Structure | 5th to 6th Floor | L1/367 | 2023-10-12 |  | Column reinforcement | Check columns (10 Nos) reinforcement Zone 4 | (+62'-9'' to +73'-9'') | Grid G-M/20-22 | A | 2023-10-18
| Sub Structure | 4th to 5th | L1/368 | 2023-10-13 |  | Column reinforcement | check columns (10 Nos) reinforcement Zone 4 | (+62'-9'' to +73'-9'') | Grid G-M/24-26 | A | 2023-10-18
| Sub Structure | 4th to 5th | L1/369 | 2023-10-13 |  | Service reinforcement | Check service Lift reinforcement Zone 4 | (+62'-9'' to +73'-9'') | Grid H-J/23-24 | A | 2023-10-18
| Sub Structure | 4th Floor | L1/370 | 2023-10-14 |  | Slab reinforcement | Check slab, beam reinforcement and allow for concrete pouring Zone 4-5 | (+51'-9'') | Grid M-U/15-26 | A | 2023-10-18
| Sub Structure | 5th to 6th Floor | L1/371 | 2023-10-14 |  | Column reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 4 | (+62'-9'' to +73'-9'') | Grid H-M/20-22 | A | 2023-10-18
| Sub Structure | 4th to 5th | L1/372 | 2023-10-14 |  | Column reinforcement | Check columns (10 Nos) reinforcement Zone 4 | (+51'-9'' to +62'-9'') | Grid N-U/23-26 | A | 2023-10-18
| Sub Structure | 4th Floor | L1/373 | 2023-10-14 |  | Level, layout | Check level and layout of columns, lift wall and balcony beam Zone 4 | (+51'-9'') | Grid M-U/15-26 | A | 2023-10-18
| Sub Structure | 4th to 5th | L1/374 | 2023-10-16 |  | Column reinforcement | Check SW8 & columns (21 Nos) reinforcement Zone 5 | (+51'-9'' to +62'-9'') | Grid N-U/15-22 | A | 2023-10-18
| Sub Structure | 5th to 6th Floor | L1/375 | 2023-10-16 |  | Column reinforcement | Check service lift and columns (12 Nos) reinforcement and allow for concrete pouring Zone 4 | (+62'-9'' to +73'-9'') | Grid G-M/20-26 | A | 2023-10-18
| Sub Structure | 3rd to 4th Floor | L1/376 | 2023-10-17 |  | Level, layout | Check level and layout of Stair ST-02 Zone 4 | (+40'-9'' to +51'-9'') | Grid P-Q/20-21 | A | 2023-10-18
| Sub Structure | 4th to 5th | L1/377 | 2023-10-17 |  | Lift reinforcement | Check lift wall reinforcement Zone 4 | (+51'-9'' to +62'-9'') | Grid N-Q/20-22 | A | 2023-10-18
| Sub Structure | 4th to 5th | L1/378 | 2023-10-17 |  | UPVC Condute | Check condute UPVC D class 32 mm in lift and column Zone 4 | (+40'-9'' to +51'-9'') | Grid N/20, P/26 | A | 2023-10-18
| Sub Structure | 3rd to 4th Floor | L1/379 | 2023-10-18 | 2023-10-18 | Reinforcement | Check formwork and reinforcement of Stair st-2 and allow for concrete pouring Zone 4 | (+40'-9'' to +51'-9'') | Grid N-Q/20-22 | A | 2023-10-23
| Sub Structure | 4th Floor | L1/380 | 2023-10-18 | 2023-10-18 | Column reinforcement | Check columns (12 Nos) reinforcement and (2 Nos) SW8 reinforcement Zone 5 | (+51'-9'' to +62'-9'') | Grid N-U/15-17, N-Q/18 | A | 2023-10-23
| Sub Structure | 4th Floor | L1/381 | 2023-10-20 |  | Column reinforcement | Check column reinforcement (2 Nos) and allow for concrete pouring Zone 5 | (+51'-9'' to +62'-9'') | Grid S-U/18 | A | 2023-10-23
| Sub Structure | 6th Floor | L1/382 | 2023-10-20 |  | slab formwork | Check slab formwork along stair ST-4 Zone 4 | (+73'-9'') | Grid G-H/24-25 | A | 2023-10-23
| Sub Structure | 6th Floor | L1/383 | 2023-10-21 | 2023-10-21 | Beam reinforcement | Check beams reinforcement Zone 4 | (+73'-9'') | Grid G-M/20-26 | A | 2023-10-23
| Sub Structure | 4th Flor | L1/384 | 2023-10-20 | 2023-10-20 | Column reinforcement | Check columns (14 Nos) reinforcement and allow for concrete pouring Zone 4-5 | (+51'-9'' to +62'-9'') | Grid N-U/19, S/20, U/21, S/22, U/23, Q-U/24, R-U/26 | A | 2023-10-23
| Sub Structure | 4th Floor | L1/385 | 2023-10-21 | 2023-10-21 | Lift wall reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 4 | (+51'-9'' to +62'-9'') | Grid N-Q/20-22 | A | 2023-10-26
| Sub Structure | 4th Floor | L1/386 | 2023-10-21 | 2023-10-21 | Column reinforcement | Check columns (3 Nos) reinforcement and allow for concrete pouring Zone 4 | (+51'-9'' to +62'-9'') | Grid N/24, P/Q/26 | A | 2023-10-23
| Sub Structure | 6th Floor | L1/387 | 2023-10-23 | 2023-10-23 | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 | (+73'-9'') | Grid G-M/20-26 | A | 2023-10-26
| Sub Structure | 6th Floor | L1/388 | 2023-10-24 | 2023-10-24 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+73'-9'') | Grid G-M/20-26 | A | 2023-10-26
| Sub Structure | 5th Floor | L1/389 | 2023-10-25 | 2023-10-25 | Beam reinforcement | Check beams reinforcement Zone 4 & 5 | (+62'-9'') | Grid M-U/20-26, N-U/15-26 | A | 2023-10-26
| Sub Structure | 6th Floor | L1/390 | 2023-10-26 | 2023-10-26 | Level and layout | Check level and layout of columns & Service lift Zone 4 | (+73'-9'') | Grid G-M/20-26 | A | 2023-10-28
| Sub Structure | 5th Floor | L1/391 | 2023-10-27 | 2023-10-27 | Slab reinforcement | Check slab top and bottom reinforcement Zone 4 & 5 | (+62'-9'') | Grid M-U/20-26 & N-U/15-19 | A | 2023-10-31
| Sub Structure | 6th Floor | L1/392 | 2023-10-27 | 2023-10-27 | Column reinforcement | Check column (10 Nos) reinforcement Zone 4 | (+73'-9'') | Grid G-M/20-22 | A | 2023-10-31
| Sub Structure | 5th Floor | L1/393 | 2023-10-28 | 2023-10-28 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 & 5 | (+62'-9'') | Grid M-U/20-26, N-U/15-19 | A | 2023-10-31
| Sub Structure | 5th Floor | L1/394 | 2023-10-28 | 2023-10-28 | Slab formwork | Check slab formwork along Stair ST-2 Zone 4 | (+62'-9'') | Grid Q/20-21 | A | 2023-10-31
| Sub Structure | 6th Floor | L1/395 | 2023-10-28 | 2023-10-28 | column formwork | Check columns (10 Nos) reinforcement Zone 4 | (+73'-9'' to +84'-9'') | Grid G-M/24-26 | A | 2023-10-31
| Sub Structure | 5th Floor | L1/396 | 2023-10-30 | 2023-10-30 | Level, layout | Check level and layout of columns (33 Nos) & lift walls Zone 4 | (+62'-9'') | Grid M-U/20-26, & N-U/15-19 | A | 2023-11-02
| Sub Structure | 4ht floor | L1/397 | 2023-10-30 | 2023-10-30 | Level, layout | Check level & layout of Stair ST-02 Zone 4 | (+51'-9'' to +62'-9'') | Grid N-Q/20-22 | A | 2023-10-31
| Sub Structure | 5th Floor | L1/398 | 2023-10-30 | 2023-10-30 | Column reinforcement | Check columns (31 Nos) & SW-8 (2 Nos) reinforcement Zone 4 & 5 | (+62'-9'' to +73'-9'') | Grid N-U/20-26, N-U/15-19 | A | 2023-10-31
| Sub Structure | 6ht Floor | L1/399 | 2023-10-30 | 2023-10-30 | Service lift reinforcement | Check service lift reinforcement Zone 4 | (+73'-9'' to +84'-9'') | Grid H-J/23-24 | A | 2023-10-31
| Sub Structure | 6th Floor | L1/400 | 2023-10-29 | 2023-10-29 | Column reinforcement | Check column (6 Nos) reinforcement and allow for concrete pouring Zone 4 | (+73'-9'' to +84'-9'') | Grid L-M/20-24 | A | 2023-10-31
| Sub Structure | 6ht Floor | L1/401 | 2023-10-30 | 2023-10-30 | Column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 4 | (+73'-9'' to +84'-9'') | Grid L-M/26, K/20-26 | A | 2023-10-31
| Sub Structure | 5th Floor | L1/402 | 2023-10-31 | 2023-10-31 | walls reinforcement | Check lift walls reinforcement Zone 4 | (+62'-9'' to +73'-9'') | Grid N-Q/20-22 | A | 2023-11-08
| Sub Structure | 5th Floor | L1/403 | 2023-10-31 | 2023-10-31 | Column reinforcement | Check columns (18 Nos) & SW-8 (2 Nos) reinforcement & allow for concrete pouring Zone 5 | (+62'-9'' to +73'-9'') | Grid N-U/15-19 | A | 2023-11-08
| Sub Structure | 5th Floor | L1/404 | 2023-10-31 | 2023-10-31 | Condute UPVC | Check condute UPVC class 32 mm in lift & column Zone 4 | (+62'-9'' to +73'-9'') | Grid N/20, O/26 | A | 2023-10-31
| Sub Structure | 4th Floor | L1/405 | 2023-11-01 | 2023-11-01 | Steel fixing | Check formwork and steel fixing of ST-2 and allow for concrete pouring Zone 4 | (+51'-9'' to +62'-9'') | Grid N-Q/20-21 | A | 2023-11-08
| Sub Structure | 6th Floor | L1/406 | 2023-11-01 | 2023-11-01 | Column reinforcement | Check column (6 Nos) reinforcement and allow for concrete pouring Zone 4 | (+73'-9'' to +84'-9'') | Grid G-H/20-22, G/24, J/26 | A | 2023-11-08
| Sub Structure | 5th Floor | L1/407 | 2023-11-02 | 2023-11-01 | Column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 4 | (+62'-9'' to +73'-9'') | Grid S/20-24, U/21-24 | A | 2023-11-08
| Sub Structure | 5th Floor | L1/408 | 2023-11-02 | 2023-11-02 | Column reinforcement | check columns (5 Nos) reinforcement and allow for concrete pouring Zone 4 | (+62'-9'' to +73'-9'') | Grid P/26, N-Q/24 | A | 2023-11-08
| Sub Structure | 6th Floor | L1/409 | 2023-11-03 | 2023-11-03 | Service lift reinforcement | Check service lift reinforcement and allow for concrete pouring Zone 4 | (+73'-9'' to +84'-9'') | Grid H-J/23-24 | A | 2023-11-08
| Sub Structure | 6th Floor | L1/410 | 2023-11-04 | 2023-11-04 | Column reinforcement | Check columns (2 Nos) reinforcement and allow for concrete pouring Zone 4 | (+73'-9'' to +84'-9'') | Grid G-H/26 | A | 2023-11-18
| Sub Structure | 5th Floor | L1/411 | 2023-11-04 | 2023-11-04 | Lift wall reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 4 | (+62'-9'' to +73'-9'') | Grid N-Q/20-22 | A | 2023-11-08
| Sub Structure | 5th Floor | L1/412 | 2023-11-03 | 2023-11-03 | column reinforcement | Check columns (2 Nos) reinforcement and allow for concrete pouring Zone 4 | (+62'-9'' to +73'-9'') | Grid N/20-22 | A | 2023-11-08
| Sub Structure | 6th Floor | L1/413 | 2023-11-07 | 2023-11-06 | Beam reinforcement | Check beam reinforcement Zone 4 & 5 | (+73'-9'') | Grid M-U/20-26, N-U/15-19 | A | 2023-11-11
| Sub Structure | 6th Floor | L1/414 | 2023-11-07 | 2023-11-06 | Slab formwork | Check slab formwork along stair St-2 Zone 4 | (+73'-9'') | Grid P-Q/20-21 | A | 2023-11-08
| Sub Structure | 6th Floor | L1/415 | 2023-11-08 | 2023-11-08 | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 & 5 | (+73'-9'') | Grid M-U/20-26, N-U/15-19 | A | 2023-11-11
| Sub Structure | 6th Floor | L1/416 | 2023-11-11 | 2023-11-11 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 & 5 | (+73'-9'') | Grid M-U/20-26 & N-U/15-19 | A | 2023-11-11
| Sub Structure | 6th Floor | L1/417 | 2023-11-10 | 2023-11-10 | Level, layout | Check level and layout of columns (33 Nos) , lift walls Zone 4 & 5 | (+73'-9'') | Grid M-U/20-26, N-U/15-19 | A | 2023-11-13
| Sub Structure | 6th to 7th floor | L1/418 | 2023-11-11 | 2023-11-11 | Column reinforcement | Check columns (9 Nos) reinforcement Zone 4 | (+73'-9'' to +84'-9'') | Grid N-U/24-26 | A | 2023-11-18
| Sub Structure | 6ht Floor | L1/419 | 2023-11-13 | 2023-11-11 | Column reinforcement | Check columns (2 Nos) reinforcement and allow for concrete pouring Zone 4 | (+73'-9'' to +84'-9'') | Grid P-Q/26 | A | 2023-11-18
| Sub Structure | 5th Floor | L1/420 | 2023-11-13 | 2023-11-12 | Level, layout | Check level and layout of stair ST-2 Zone 4 | (+62'-9'' to +73'-9'') | Grid P-Q/20-21 | A | 2023-11-15
| Sub Structure | 6ht Floor | L1/421 | 2023-11-13 | 2023-11-13 | Column reinforcement | Check columns and SW8 reinforcement (24 Nos) Zone 5 | (+73'-9'' to +84'-9'') | Grid N-U/15-23 | A | 2023-11-18
| Sub Structure | 7th Floor | L1/422 | 2023-11-13 | 2023-11-12 | Column reinforcement | Check columns (7 Nos) reinforcement and allow for concrete pouring Zone 4 | (+73'-9'' to +84'-9'') | Grid N-U/24-26 | A | 2023-11-18
| Sub Structure | 6th Floor | L1/423 | 2023-11-14 | 2023-11-14 | Lift reinforcement | Check lift reinforcement Zone 4 | (+73'-9'' to +84'-9'') | Grid N-Q/20-22 | A | 2023-11-18
| Sub Structure | 6th Floor | L1/424 | 2023-11-14 | 2023-11-13 | Column reinforcement | Check columns (13 Nos) reinforcement and allow for concrete pouring Zone 4 & 5 | (+73'-9'' to +84'-9'') | Grid N-U/17-23 | A | 2023-11-18
| Sub Structure | 6th Floor | L1/425 | 2023-11-14 | 2023-11-14 | Column reinforcement | Check columns (11 Nos) and SW8 reinforcement and allow for concrete pouring Zone 4 & 5 | (+73'-9'' to +84'-9'') | Grid N-U/15-17 | A | 2023-11-18
| Sub Structure | 6th Floor | L1/426 | 2023-11-14 | 2023-11-14 | slab formwork | Check slab formwork along stair ST-04 Zone 4 | (+84'-9'') | Grid G-H/24-26 | A | 2023-11-18
| Sub Structure | 5th to 6th Floor | L1/427 | 2023-11-14 | 2023-11-14 | steel fixing | Check formwork and steel fixing of ST-2 and allow for concrete pouring Zone 4 | (+62'-9'' to +73'-9'') | Grid N-Q/20-21 | A | 2023-11-20
| Sub Structure | 6th Floor | L1/428 | 2023-11-16 | 2023-11-16 | Condute UPVC | Check condute UPVC class 32mm in lift & column Zone 4 | (+73'-9'' to +84'-9'') | Grid N/20, P/26 | A | 2023-11-18
| Sub Structure | 6th Floor | L1/429 | 2023-11-16 | 2023-11-16 | Lift reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 4 | (+73'-9'' to +84'-9'') | Grid N-Q/20-22 | A | 2023-11-18
| Sub Structure | 7th Floor | L1/430 | 2023-11-17 | 2023-11-17 | beam reinforcement | Check beams reinforcement Zone 4 | (+84'-9'') | Grid G-S/19-26 | A | 2023-11-18
| Sub Structure | 7th Floor | L1/431 | 2023-11-18 | 2023-11-18 | Slab reinforcement | Chek top and bottom slab reinforcement Zone 4 | (+84'-9'') | Grid G-S/19-26 | A | 2023-11-24
| Sub Structure | 5th Floor | L1/432 | 2023-11-18 | 2023-11-18 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+84'-9'') | Grid G-S/19-26 | A | 2023-11-28
| Sub Structure | 7th Floor | L1/433 | 2023-11-18 | 2023-11-18 | slab formwork | Check slab formwork along stair Zone 4 | (+84'-9'') | Grid P-Q/20-21 | A | 2023-11-18
| Sub Structure | 7th Floor | L1/434 | 2023-11-20 | 2023-11-20 | level, layout | Check level & layout of columns (25 Nos) & lift walls Zone 4 | (+84'-9'') | Grid P-Q/20-21 | A | 2023-11-20
| Sub Structure | 7th Floor | L1/435 | 2023-11-20 | 2023-11-20 | Column reinforcement | Check columns (13 Nos) reinforcement Zone 4 | (+84'-9'' to +95'-9'') | Grid G-K/20-22, K-M/24-26, L/22 | A | 2023-11-24
| Sub Structure | 7th Floor | L1/436 | 2023-11-20 | 2023-11-20 | Beam reinforcement | Check beams reinforcement Zone 4 & 5 | (+84'-9'') | Grid S-U/20-26, N-U/15-19 | A | 2023-11-24
| Sub Structure | 1st to 2nd floor | L1/437 | 2023-11-20 | 2023-11-20 | level, layout | Check level and layout of Stair ST-4 Zone 4 | (+18'-9'' to +29'-9'') | Grid G-H/26 | A | 2023-11-29
| Sub Structure | 6th Floor | L1/438 | 2023-11-20 | 2023-11-20 | level, layout | Check level & layout of Stair ST-2 Zone 4 | (+73'-9'' to +84'-9'') | Grid N-Q/20-22 | A | 2023-11-23
| Sub Structure | 7th Floor | L1/439 | 2023-11-21 | 2023-11-21 | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 & 5 | (+84'-9'') | Grid S-U/20-26, N-U/15-19 | A | 2023-11-23
| Sub Structure | 7th Floor | L1/440 | 2023-11-21 | 2023-11-21 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 & 5 | (+84'-9'') | Grid S-U/20-26, N-U/15-19 | A | 2023-12-04
| Sub Structure | 7th Floor | L1/441 | 2023-11-21 | 2023-11-21 | Lift reinforcement | Check service lift reinforcement Zone 4 | (+84'-9'') | Grid H-J/23-24 | A | 2023-11-23
| Sub Structure | 7th Floor | L1/442 | 2023-11-21 | 2023-11-21 | Column reinforcement | Check column (12 Nos) reinforcement Zone 4 | (+84'-9'' to +95'-9'') | Grid G-J/24-26, L/20, M/20-22, N-R/24-26 | A | 2023-11-25
| Sub Structure | 7th Floor | L1/443 | 2023-11-22 | 2023-11-22 | Lift reinforcement | Check lift wall reinforcement Zone 4 | (+84'-9'' to +95'-9'') | Grid N-Q/20-22 | A | 2023-11-24
| Sub Structure | 7th Floor | L1/444 | 2023-11-23 | 2023-11-23 | Condute UPVC | Check conduit UPVC class 32 mm in lift and column Zone 4 | (+84'-9'' to +95'-9'') | Grid N/20, P/26 | A | 2023-11-24
| Sub Structure | 7th Floor | L1/445 | 2023-11-22 | 2023-11-22 | Column reinforcement | Chek columns (7 Nos) reinforcement and allow for concrete pouring Zone 4 | (+84'-9'' to +95'-9'') | Grid G-L/20, H-K/22, K/24 | A | 2023-11-24
| Sub Structure | 6th Floor | L1/446 | 2023-11-23 | 2023-11-23 | stair reinforcement | Check formwork and stair ST-2 reinforcement and allow for concrete pouring Zone 4 | (+73'-9'' to +84'-9'') | Grid N-Q/20-21 | A | 2023-11-25
| Sub Structure | 7th Floor | L1/447 | 2023-11-23 | 2023-11-23 | Column reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 4 | (+84'-9'' to +95'-9'') | Grid G/22, K/26, L/22-26, M/22-26, P/26 | A | 2023-11-24
| Sub Structure | 5th Floor | L1/448 | 2023-11-24 | 2023-11-24 | Column reinforcement | Check columns (10 Nos) and service lift reinforcement and allow for concrete pouring Zone 4 | (+84'-9'' to +95'-9'') | Grid G/24-26, H-J/26, M/22-24, N-Q/24, Q-R/26, H-J/23-24 | A | 2023-11-25
| Sub Structure | 1st floor to 2nd | L1/449 | 2023-11-27 | 2023-11-27 | stair reinforcement | Check formwork and stair ST-2 reinforcement and allow for concrete pouring Zone 45 | (+18'-9'' to +29'-9'') | Grid G-H/26 | A | 2023-11-29
| Sub Structure | 7th Floor | L1/450 | 2023-11-28 | 2023-11-28 | Lift wall reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 4 | (+84'-9'' to +95'-9'') | Grid N-Q/20-22 | A | 2023-11-29
| Sub Structure | 2nd Floor | L1/451 | 2023-11-29 | 2023-11-29 | level, layout | Check level and layout of stair ST-04 Zone 4 | (+29'-9'' to +40'-9'') | Grid G-H/1-3 | A | 2023-11-30
| Sub Structure | 7th Floor | L1/452 | 2023-11-29 | 2023-11-29 | Beam reinforcement | Check beams reinforcement Zone 4 | (+95'-9'') | Grid G-M/20-26 | A | 2023-12-04
| Sub Structure | 2nd Floor | L1/453 | 2023-12-01 | 2023-12-01 | stair reinforcement | Check formwork and stair ST-04 reinforcement and allow for concrete pouring Zone 4 | (+29'-9'' to +40'-9'') | Grid G-H/1-3 | A | 2023-12-05
| Sub Structure | 8th floor | L1/454 | 2023-12-01 | 2023-12-01 | stair formwork | Check formwork along stair ST-04 Zone 4 | (+95'-9'') | Grid G-H/24-25 | A | 2023-12-04
| Sub Structure | 7th Floor | L1/455 | 2023-12-01 | 2023-12-01 | level, layout | Check level and layout of columns (26 Nos) & SW-08 (2 Nos) Zone 4 & 5 | (+84'-9'') | Grid S-U/20-26, N-U/15-26 | A | 2023-12-05
| Sub Structure | 7th Floor | L1/456 | 2023-12-01 | 2023-12-01 | Column reinforcement | Check columns (12 Nos) reinforcement Zone 4 & 5 | (+84'-9'' to +95'-9'') | Grid N-U/19, S/20, U/21, S/22, U/23, S-U/24, T-U/26 | A | 2023-12-05
| Sub Structure | 7th Floor | L1/457 | 2023-12-01 | 2023-12-01 | Column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 4 & 5 | (+84'-9'' to +95'-9'') | Grid N-S/19, S/20-24 | A | 2023-12-05
| Sub Structure | 8th Floor | L1/458 | 2023-12-02 | 2023-12-02 | slab formwork | Check slab formwork along stair ST-2 Zone 4 | (+95'-9'') | Grid P-Q/20-21 | A | 2023-12-05
| Sub Structure | 7th Floor | L1/459 | 2023-12-02 | 2023-12-02 | column, sw-08 reinforcement | Check columns (14 Nos) and SW-08 (2 Nos) reinforcement Zone 4 | (+84'-9'' to +95'-9'') | Grid N-U/15-26 | A | 2023-12-04
| Sub Structure | 8th Floor | L1/460 | 2023-12-02 | 2023-12-04 | Beam reinforcement | Check beams reinforcement Zone 4 | (+95'-9'') | Grid M-S/19-26 | A | 2023-12-05
| Sub Structure | 8th Floor | L1/461 | 2023-12-02 | 2023-12-04 | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 | (+95'-9'') | Grid G-S/19-26 | A | 2023-12-05
| Sub Structure | 7th Floor | L1/462 | 2023-12-02 | 2023-12-02 | Column reinforcement | Check columns (7 Nos) reinforcement and allow for concrete pouring Zone 4 & 5 | (+84'-9'' to +95'-9'') | Grid N-S/18, U/19-26, T/26 | A | 2023-12-04
| Sub Structure | 8th Floor | L1/463 | 2023-12-04 | 2023-12-04 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+95'-9'') | Grid G-S/19-26 | A | 2023-12-11
| Sub Structure | 7th Floor | L1/464 | 2023-12-04 | 2023-12-04 | column, SW-8 reinforcement | Check columns (6 Nos) and SW-08 reinforcement and allow for concrete pouring Zone 5 | (+84'-9'' to +95'-9'') | Grid N-S/18, Q-U/17, N/16 | A | 2023-12-11
| Sub Structure | 7th Floor | L1/465 | 2023-12-05 | 2023-12-05 | column, sw-08 reinforcement | Check columns (7 Nos) & SW-08 (1 Nos) reinforcement and allow for concrete pouring Zone 5 | (+84'-9'' to +95'-9'') | Grid N/17, Q-U/16, N-U/15 | A | 2023-12-11
| Sub Structure | 7th Floor | L1/466 | 2023-12-06 | 2023-12-06 | Column reinforcement | Check columns (1 Nos) reinforcement and allow for concrete pouring Zone 5 | (+84'-9'' to +95'-9'') | Grid Q/16 | A | 2023-12-08
| Sub Structure | 8th Floor | L1/467 | 2023-12-09 | 2023-12-09 | Column reinforcement | Check columns (8 Nos) reinforcement Zone 4 | (+95'-9'' to +106'-9'') | Grid G-L/20-22 | A | 2023-12-18
| Sub Structure | 8th Floor | L1/468 | 2023-12-09 | 2023-12-09 | level, layout | Check level and layout of columns (25 Nos) & Service lift, lift walls Zone 4 | (+95'-9'') | Grid G-S/20-26 | A | 2023-12-11
| Sub Structure | 8th Floor | L1/469 | 2023-12-11 | 2023-12-11 | column, SL reinforcement | Check columns (17 Nos) and service lift reinforcement Zone 4 | (+95'-9'' to +106'-9'') | Grid G-R/24-26, M/20-22 | A | 2023-12-18
| Sub Structure | 7th Floor | L1/470 | 2023-12-12 | 2023-12-12 | level, layout | Check level and layout of Stair ST-02 Zone 4 | (+84'-9'' to +95'-9'') | Grid N-Q/20-21 | A | 2023-12-18
| Sub Structure | 8th Floor | L1/471 | 2023-12-12 | 2023-12-12 | Column reinforcement | Check columns (16 Nos) reinforcement and allow for concrete pouring Zone 4 | (+95'-9'' to +106'-9'') | Grid G-H/20-24, J/26, K-L/20-26, M/20-22 | A | 2023-12-18
| Sub Structure | 8th Floor | L1/472 | 2023-12-13 | 2023-12-13 | Lift wall reinforcement | Check lift wall reinforcement Zone 4 | (+95'-9'' to +106'-9'') | Grid N-Q/20-22 | A | 2023-12-18
| Sub Structure | 8th Floor | L1/473 | 2023-12-13 | 2023-12-13 | Beam reinforcement | Check beam reinforcement Zone 4 & 5 | (+95'-9'') | Grid S-U/19-26, N-U/15-19 | A | 2023-12-18
| Sub Structure | 8th to 9th Floor | L1/474 | 2023-12-13 | 2023-12-13 | Lift reinforcement | Check service lift reinforcement and allow for concrete pouring Zone 4 | (+95'-9'' to +106'-9'') | Grid H-J/23-24 | A | 2023-12-18
| Sub Structure | 7th to 8th Floor | L1/475 | 2023-12-13 | 2023-12-13 | stair reinforcement | Check formwork and Stair ST-2 reinforcement and allow for concrete pouring Zone 4 | (+84'-9'' to +95'-9'') | Grid N-Q/20-21 | A | 2023-12-18
| Sub Structure | 8th to 9th Floor | L1/476 | 2023-12-15 | 2023-12-14 | Column reinforcement | Check columns (9 Nos) reinforcement and allow for concrete pouring Zone 4 | (+95'-9'' to +106'-9'') | Grid G-R/26 | A | 2023-12-18
| Sub Structure | 8th Floor | L1/477 | 2023-12-15 | 2023-12-15 | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 & 5 | (+95'-9'') | Grid N-U/15-26 | A | 2023-12-18
| Sub Structure | 8th Floor | L1/478 | 2023-12-16 | 2023-12-16 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 5 | (+95'-9'') | Grid R-U/15-26 | A | 2023-12-22
| Sub Structure | 8th to 9th Floor | L1/479 | 2023-12-16 | 2023-12-16 | Lift reinforcement | Check lift reinforcement and allow for concrete pouring Zone 4 | (+95'-9'' to +106'-9'') | Grid N-Q/20-22 | A | 2023-12-22
| Sub Structure | 2nd to 3rd | L1/480 | 2023-12-16 | 2023-12-16 | level, layout | Check level and layout of Stair ST-04 Zone 4 | (+40'-9'' to +51'-9'') | Grid G-H/24-26 | A | 2023-12-22
| Sub Structure | 8th Floor | L1/481 | 2023-12-18 | 2023-12-18 | level, layout | Check level and layout of columns and SW Zone 05 | (+95'-9'') | Grid N-Q/20-22 | A | 2023-12-22
| Sub Structure | 8th to 9th Floor | L1/482 | 2023-12-18 | 2023-12-18 | Column reinforcement | Check columns (8 Nos) reinforcement Zone 4 | (+95'-9'' to +106'-9'') | Grid S-U/20-26 | A | 2023-12-22
| Sub Structure | 8th to 9th Floor | L1/483 | 2023-12-19 | 2023-12-19 | column, SW reinforcement | Check columns (18 Nos) and SW SW-08 reinforcement Zone 5 | (+95'-9'' to +106'-9'') | Grid N-U/15-19 | A | 2023-12-22
| Sub Structure | 3rd to 4th Floor | L1/484 | 2023-12-20 | 2023-12-20 | stair reinforcement | Check formwork and reinforcement of stair ST-04 and allow for concrete pouring Zone 4 | (+40'-9'' to +51'-9'') | Grid G-H/24-26 | A | 2023-12-27
| Sub Structure | 8th to 9th Floor | L1/485 | 2023-12-20 | 2023-12-19 | Column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring Zone 4 | (+95'-9'' to +106'-9'') | Grid S/20-24, T/26 | A | 2023-12-22
| Sub Structure | 8th to 9th Floor | L1/486 | 2023-12-21 | 2023-12-20 | Column reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 4 & 5 | (+95'-9'' to +106'-9'') | Grid U/21-26, N-U/19 | A | 2023-12-27
| Sub Structure | 8th to 9th Floor | L1/487 | 2023-12-21 | 2023-12-21 | Column reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 5 | (+95'-9'' to +106'-9'') | Grid N-U/17-18 | A | 2023-12-27
| Sub Structure | 9th Floor | L1/488 | 2023-12-21 | 2023-12-21 | slab formwork | Check slab formwork along ST-02 & ST-04 Zone 4 | (+106'-9'') | Grid G-H/24-25, P-Q/20-21 | A | 2023-12-27
| Sub Structure | 9th Floor | L1/489 | 2023-12-23 | 2023-12-23 | beam reinforcement | Check Beam Reinforcement Zone 4 | (+106'-9'') | Grid G-S/19-26 | A | 2023-12-27
| Sub Structure | 9th Floor | L1/490 | 2023-12-23 | 2023-12-25 | Top and bottom reinforcement | Check Top and bottom slab reinforcement Zone 4 | (+106'-9'') | Grid G-S/19-26 | A | 2023-12-27
| Sub Structure | 9th Floor | L1/491 | 2023-12-23 | 2023-12-25 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+106'-9'') | Grid G-S/19-26 | A | 2023-12-27
| Sub Structure | 9th Floor | L1/492 | 2023-12-27 | 2023-12-27 | level, layout of columns | Check level and layout of columns, service lift & lift walls Zone 4 | (+106'-9'') | Grid G-S/19-26 | A | 2024-01-03
| Sub Structure | 9th Floor | L1/493 | 2023-12-29 | 2023-12-29 | Column reinforcement | Check columns (25 Nos) reinforcement Zone 4 | (+106'-9'' to +117'-9'') | Grid G-M/20-26, N-R/24-26 | A | 2024-01-03
| Sub Structure | 9th Floor | L1/494 | 2023-12-29 | 2023-12-29 | Column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 4 | (+106'-9'' to +117'-9'') | Grid G-H/20-22, K/20 | A | 2024-01-03
| Sub Structure | 9th Floor | L1/495 | 2023-12-30 | 2023-12-30 | Service reinforcement | Check service lift reinforcement Zone 4 | (+106'-9'' to +117'-9'') | Grid H-J/23-24 | A | 2024-01-03
| Sub Structure | 8th Floor | L1/496 | 2023-12-30 | 2023-12-30 | level, layout | Check level and layout of Stair ST-02 Zone 4 | (+95'-9'' to +106'-9'') | Grid N-Q/20-22 | A | 2024-01-03
| Sub Structure | 9th Floor | L1/497 | 2023-12-30 | 2023-12-30 | Column reinforcement | Check columns (13 Nos) reinforcement and allow for concrete pouring Zone 4 | (+106'-9'' to +117'-9'') | Grid G/24, J/26, K/22-26, L-M/20-26 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/498 | 2024-01-01 | 2024-01-01 | Condute UPVC | Check condute UPVC D class 32 mm in lift & column Zone 4 | (+106'-9'' to +117'-9'') | Grid N/20, P/26 | A | 2024-01-03
| Sub Structure | 9th Floor | L1/499 | 2024-01-01 | 2023-12-31 | Column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 4 | (+106'-9'' to +117'-9'') | Grid P-R/26, N-Q/24 | A | 2024-01-03
| Sub Structure | 9th Floor | L1/500 | 2024-01-02 | 2024-01-02 | Lift wall reinforcement | Check lift wall reinforcement Zone 4 | (+106'-9'' to +117'-9'') | Grid N-Q/20-22 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/501 | 2024-01-02 | 2024-01-02 | beam reinforcement | Check beams reinforcement Zone 5 | (+106'-9'') | Grid N-U/15-26 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/502 | 2024-01-02 | 2024-01-02 | Column reinforcement | Check columns (2 Nos) & Service lift reinforcement and allow for concrete pouring Zone 4 | (+106'-9'') | Grid G-H/26, H-J/23-24 | A | 2024-01-09
| Sub Structure | 8th Floor | L1/503 | 2024-01-03 | 2024-01-03 | Reinforcement | Check formwork and reinforcement of Stair ST-2 and allow for concrete pouring Zone 4 | (+95'-9'' to +106'-9'') | Grid N-Q/20-22 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/504 | 2024-01-04 | 2024-01-04 | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 | (+106'-9'') | Grid S-U/20-26, N-U/15-26 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/505 | 2024-01-04 | 2024-01-04 | Slab reinforcement | Chek slab reinforcement and allow for concrete pouring Zone 4 | (+106'-9'') | Grid S-U/20-26, N-U/15-26 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/506 | 2024-01-04 | 2024-01-04 | Lift reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 4 | (+106'-9'' to +117'-9'') | Grid N-Q/20-22 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/507 | 2024-01-05 | 2024-01-05 | Column reinforcement | Check columns (6 Nos) reinforcement Zone 4 & 5 | (+106'-9'' to +117'-9'') | Grid S/20-24, N-S/19 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/508 | 2024-01-05 | 2024-01-05 | level, layout | Check level & layout of columns & SW-08 Zone 4 & 5 | (+106'-9'') | Grid N-U/15-26 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/509 | 2024-01-06 | 2024-01-06 | column, SW reinforcement | Check columns (20 Nos) and SW-08 reinforcement Zone 4 & 5 | (+106'-9'' to +117'-9'') | Grid N-U/15-18, U/19-26, T/26 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/510 | 2024-01-05 | 2024-01-05 | Column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 4 & 5 | (+106'-9'' to +117'-9'') | Grid S/20-24, Q/19 | A | 2024-01-09
| Sub Structure | Basement | L1/511 | 2024-01-06 | 2024-01-06 | UGWT | Check UGWT for domestic reinforcement and allow for concrete pouring Zone 5 | (-13'-3'' to -1'-00'') | Grid U/15-17 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/512 | 2024-01-07 | 2024-01-07 | Column reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 4 & 5 | (+106'-9'' to +117'-9'') | Grid U/18-26, N/19 | A | 2024-01-09
| Sub Structure | 9th Floor | L1/513 | 2024-01-08 | 2024-01-08 | columns | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 5 | (+106'-9'' to +117'-9'') | Grid N-Q/18, N-U/17, S-U/16 | A | 2024-01-09
| Sub Structure | 10th Floor | L1/514 | 2024-01-08 | 2024-01-08 | slab formwork | Check slab formwork along stairs ST-04 and ST-02 Zone 5 | (+117'-9'') | Grid G-H/24, Q/20-21 | A | 2024-01-09
| Sub Structure | 10th Floor | L1/515 | 2024-01-08 | 2024-01-08 | Beam reinforcement | Check beam reinforcement Zone 4 | (+117'-9'') | Grid G-S/19-26 | A | 2024-01-09
| Sub Structure | 10th Floor | L1/516 | 2024-01-09 | 2024-01-09 | Slab reinforcement | Check slab top and bottom reinforcement Zone 4 | (+117'-9'') | Grid G-S/19-26 | A | 2024-01-17
| Sub Structure | 10th Floor | L1/517 | 2024-01-09 | 2024-01-09 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+117'-9'') | Grid G-S/19-26 | A | 2024-01-17
| Sub Structure | 9th Floor | L1/518 | 2024-01-10 | 2024-01-09 | column, SW reinforcement | Check columns (4 Nos) and SW-08 (02) reinforcement and allow for concrete pouring Zone 5 | (+106'-9'' to +117'-9'') | Grid N-U/15, N-Q/16 | A | 2024-01-17
| Sub Structure | 10th Floor | L1/519 | 2024-01-10 | 2024-01-10 | level, layout | Check level and layout of columns (25 Nos) & service lift walls Zone 4 | (+117'-9'') | Grid G-S/19-26 | A | 2024-01-17
| Sub Structure | 10th Floor | L1/520 | 2024-01-10 | 2024-01-10 | Column reinforcement | Check columns (14 Nos) reinforcement Zone 4 | (+117'-9'' to +130'-9'') | Grid K-M/20-26, N-Q/24 | A | 2024-01-17
| Sub Structure | 10th Floor | L1/521 | 2024-01-11 | 2024-01-11 | column & Service lift | Check columns (11 Nos) and service lift reinforcement Zone 4 | (+117'-9'' to +130'-9'') | Grid G-J/20-26, P-R/26 | A | 2024-01-17
| Sub Structure | 4th Floor | L1/522 | 2024-01-12 | 2024-01-11 | hanging beam | Check formwork and reinforcement of hanging beam and allow for concrete pouring Zone 4 | (+51'-9'') | Grid G-H/26 | A | 2024-01-17
| Sub Structure | 10th Floor | L1/523 | 2024-01-12 | 2024-01-12 | Lift wall reinforcement | Check lift wall reinforcement Zone 4 | (+117'-9'' to +130'-9'') | Grid N-Q/20-22 | A | 2024-01-17
| Sub Structure | 10th Floor | L1/524 | 2024-01-12 | 2024-01-12 | Condute UPVC | Check condute UPVC class 32 mm in lift & columns Zone 4 | (+117'-9'' to +130'-9'') | Grid N/20, P/26 | A | 2024-01-17
| Sub Structure | 10th Floor | L1/525 | 2024-01-13 | 2024-01-12 | Column reinforcement | Check columns (11 Nos) reinforcement and allow for concrete pouring Zone 4 | (+117'-9'' to +130'-9'') | Grid H/20-22, K-L/20-24, M/20-24, N/24 | A | 2024-01-17
| Sub Structure | 9th to 10th Floor | L1/526 | 2024-01-13 | 2024-01-13 | Level,layout | Check level and layout of stair ST-02 Zone 4 | (+106'-9'' to +117'-9'') | Grid N-Q/20-22 | A | 2024-01-17
| Sub Structure | 10th Floor | L1/527 | 2024-01-13 | 2024-01-13 | Beam reinforcement | Check beam reinforcement Zone 4 & 5 | (+117'-9'') | Grid S-U/20-26, N-U/15-19 | A | 2024-01-17
| Sub Structure | 10th Floor | L1/528 | 2024-01-13 | 2024-01-13 | Column reinforcement | Check columns (5 Nos), Service lift reinforcement and allow for concrete pouring Zone 4 | (+117'-9'' to +130'-9'') | Grid G/20-24, K/26, M/20, H-J/23-24 | A | 2024-01-17
| Sub Structure | 9th to 10th Floor | L1/529 | 2024-01-14 | 2024-01-14 | Reinforcement | Check formwork and reinforcement of stair ST-02 and allow for concrete pouring Zone 4 | (+106'-9'' to +117'-9'') | Grid N-Q/20-22 | A | 2024-01-17
| Sub Structure | 10th to 11th Floor | L1/530 | 2024-01-15 | 2024-01-15 | Lift reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 4 | (+117'-9'' to +130'-9'') | Grid N-Q/20-22 | A | 2024-01-17
| Sub Structure | 11th Floor | L1/531 | 2024-01-14 | 2024-01-14 | Column reinforcement | Check columns (9 Nos) reinforcement and allow for concrete pouring Zone 4 | (+117'-9'' to +130'-9'') | Grid G-J/26, L-R/26, Q/24 | A | 2024-01-17
| Sub Structure | 10th Floor | L1/532 | 2024-01-16 | 2024-01-16 | Slab reinforcement | Check top and bottom slab reinforcement | (+117'-9'') | Grid N-Q/15-26 | A | 2024-01-24
| Sub Structure | 10th Floor | L1/533 | 2024-01-16 | 2024-01-16 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 & 5 | (+117'-9'') | Grid N-Q/15-26 | A | 2024-01-24
| Sub Structure | 4th to 5th | L1/534 | 2024-01-16 | 2024-01-16 | level, layout | Check level and layout of stair ST-04 Zone 4 | (+51'-9'' to +62'-9'') | Grid G-H/24-26 | A | 2024-01-17
| Sub Structure | 4th to 5th | L1/535 | 2024-01-17 | 2024-01-17 | stair reinforcement | Check formwork and stair reinforcement ST-04 and allow for concrete pouring Zone 4 | (+51'-9'' to +62'-9'') | Grid G-H/24-26 | A | 2024-01-24
| Sub Structure | 4th to 5th | L1/536 | 2024-01-19 | 2024-01-18 | hanging beam | Check formwork & reinforcement of hanging beam and allow for concrete pouring Zone 4 | (+62'-9'') | Grid G-H/26 | A | 2024-01-24
| Sub Structure | 10th Floor | L1/537 | 2024-01-19 | 2024-01-19 | level, layout | Check level and layout of slab and column (26 Nos) & SW-8 (2 Nos) Zone 4 | (+117'-9'') | Grid N-U/15-26 | A | 2024-01-24
| Sub Structure | 10th Floor | L1/538 | 2024-01-19 | 2024-01-19 | Column reinforcement | Check columns (6 Nos) reinforcement Zone 4 & 5 | (+117'-9'' to +130'-9'') | Grid N-S/19-24 | A | 2024-01-24
| Sub Structure | 5th to 6th Floor | L1/539 | 2024-01-19 | 2024-01-19 | level, layout | Check level and layout of stair ST-04 Zone 4 | (+62'-9'' to +73'-9'') | Grid G-H/26 | A | 2024-01-24
| Sub Structure | 10th Floor | L1/540 | 2024-01-20 | 2024-01-20 | Column reinforcement | Check columns (10 Nos) reinforcement Zone 4 & 5 | (+117'-9'' to +130'-9'') | Grid N-U/18, T-U/19-26 | A | 2024-01-24
| Sub Structure | 10th Floor | L1/541 | 2024-01-20 | 2024-01-21 | Column reinforcement | Check columns (10 Nos) and SW-08 (2 Nos) reinforcement Zone 5 | (+117'-9'' to +130'-9'') | Grid N-U/15-17 | A | 2024-01-24
| Sub Structure | 10th Floor | L1/542 | 2024-01-20 | 2024-01-20 | Column reinforcement | Check columns (7 Nos) reinforcement and allow for concrete pouring Zone 4 & 5 | (+117'-9'' to +130'-9'') | Grid N-S/19-24, T/26 | A | 2024-01-24
| Sub Structure | 11th Floor | L1/543 | 2024-01-22 | 2024-01-22 | beam reinforcement | Check beam reinforcement Zone 4 | (+130'-9'') | Grid G-R/19-26 | A | 2024-01-24
| Sub Structure | 11th Floor | L1/544 | 2024-01-22 | 2024-01-22 | slab formwork | Check slab formwork along stairs ST-04 & ST-02 Zone 4 | (+130'-9'') | Grid G-H/24, Q/20-21 | A | 2024-01-24
| Sub Structure | 5th to 6th Floor | L1/545 | 2024-01-22 | 2024-01-22 | stair reinforcement | Check formwork and reinforcement stair ST-04 and allow for concrete pouring Zone 4 | (+62'-9'' to +73'-9'') | Grid G-H/26 | A | 2024-01-24
| Sub Structure | 10th Floor | L1/546 | 2024-01-23 | 2024-01-22 | Column reinforcement | Check columns (9 Nos) and allow for concrete pouring Zone 4 & 5 | (+117'-9'' to +130'-9'') | Grid N-U/18, U/19-26 | A | 2024-01-24
| Sub Structure | 11th Floor | L1/547 | 2024-01-23 | 2024-01-23 | Slab reinforcement | Check top and bottom slab reinforcement Zone 4 | (+130'-9'') | Grid G-S/19-26 | A | 2024-01-24
| Sub Structure | 11th Floor | L1/548 | 2024-01-23 | 2024-01-23 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+130'-9'') | Grid G-S/19-26 | A | 2024-01-30
| Sub Structure | 10th Floor | L1/549 | 2024-01-24 | 2024-01-23 | Column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring Zone 5 | (+117'-9'' to +130'-9'') | Grid N-U/17 | A | 2024-01-30
| Sub Structure | 11th Floor | L1/550 | 2024-01-24 | 2024-01-24 | level, layout | Check level and layout of slab, columns (15 Nos) & Service lift Zone 4 | (+130'-9'') | Grid G-L/20-26 | A | 2024-01-30
| Sub Structure | 10th Floor | L1/551 | 2024-01-25 | 2024-01-24 | column, SW reinforcement | Check columns (4 Nos) and SW-08 (2 Nos) reinforcement and allow for concrete pouring Zone 5 | (+117'-9'' to +130'-9'') | Grid N-Q/15, N-U/16 | A | 2024-01-30
| Sub Structure | 10th Floor | L1/552 | 2024-01-25 | 2024-01-25 | Column reinforcement | Check columns (2 Nos) reinforcement and allow for concrete pouring Zone 5 | (+117'-9'' to +130'-9'') | Grid S-U/15-26 | A | 2024-01-30
| Sub Structure | 11th Floor | L1/553 | 2024-01-25 | 2024-01-25 | column, Service lift | Check columns (16 Nos) and service lift reinforcement Zone 4 | (+130'-9'' to +145'-9'') | Grid G-L/20-26 | A | 2024-01-30
| Sub Structure | 6th Floor | L1/554 | 2024-01-25 | 2024-01-25 | Beam reinforcement | Check hanging beam reinforcement and allow for concrete pouring Zone 4 | (+73'-9'') | Grid G-H/26 | A | 2024-01-30
| Sub Structure | 6th to 7th floor | L1/555 | 2024-01-26 | 2024-01-26 | level, layout | Check level and layout of stair st-4 Zone 4 | (+73'-9'' to +84'-9'') | Grid G-H/26 | A | 2024-01-30
| Sub Structure | 11th Floor | L1/556 | 2024-01-26 | 2024-01-26 | level, layout | Check level and layout of slab columns & lift walls Zone 4 | (+130'-9'') | Grid L-S/19-26 | A | 2024-01-30
| Sub Structure | 11th Floor | L1/557 | 2024-01-26 | 2024-01-26 | Column reinforcement | Check columns (9 Nos) reinforcement Zone 4 | (+130'-9'' to +145'-9'') | Grid M/20-26, N-R/24-26 | A | 2024-01-30
| Sub Structure | 11th Floor | L1/558 | 2024-01-26 | 2024-01-26 | Column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring Zone 4 | (+130'-9'' to +145'-9'') | Grid G-H/20-22, K-L/20-24 | A | 2024-01-30
| Sub Structure | 11th Floor | L1/559 | 2024-01-27 | 2024-01-28 | Lift wall reinforcement | Check lift wall reinforcement Zone 4 | (+130'-9'' to +145'-9'') | Grid N-Q/20-22 | A | 2024-02-01
| Sub Structure | Basement | L1/560 | 2024-01-27 | 2024-01-27 | UGWT | Check UGWT for domestic & fire outer wall inner wall, centre wall and allow to concrete pouring Zone 5 | (-13'-3'' to -1'-00'') | Grid U/17-22, U/15-17 | A | 2024-01-30
| Sub Structure | Basement | L1/561 | 2024-01-27 | 2024-01-27 | Water stopper | Check PVC Water stopper verticals in tank wall Zone 5 | (-13'-3'' to -1'-00'') | Grid U/17-22, U/15-17 | A | 2024-01-30
| Sub Structure | 6th to 7th floor | L1/562 | 2024-01-28 | 2024-01-28 | stair reinforcement | Check formwork and stair reinforcement ST-04 and allow for concrete pouring Zone 4 | (+73'-84'') | Grid G-H/26 | A | 2024-01-30
| Sub Structure | 11th Floor | L1/563 | 2024-01-28 | 2024-01-28 | Column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring Zone 4 | (+145'-9'' to +145'-9'') | Grid G-H/20-22, K-L/20-24, G/24, H-J/23-24, K-M/26, M/20-24, P/26 | A | 2024-01-30
| Sub Structure | 11th Floor | L1/564 | 2024-01-29 | 2024-01-29 | Beam reinforcement | Check beam reinforcement Zone 5 | (+130'-9'') | Grid S-U/19-26, N-U/15-26 | A | 2024-02-01
| Sub Structure | 11th Floor | L1/565 | 2024-01-30 | 2024-01-30 | Condute UPVC | Check condute UPVC D class 32mm in lift and columns Zone 4 | (+130'-9'' to +145'-9'') | Grid N/20, P/26 | A | 2024-02-01
| Sub Structure | 11th Floor | L1/566 | 2024-01-31 | 2024-01-31 | Slab reinforcement | Check top and bottom slab reinforcement Zone 5 | (+130'-9'') | Grid N-U/15-26 | A | 2024-02-01
| Sub Structure | 11th Floor | L1/567 | 2024-01-31 | 2024-01-31 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 5 | (+130'-9'') | Grid N-U/15-26 | A | 2024-02-01
| Sub Structure | 11th Floor | L1/568 | 2024-01-31 | 2024-01-30 | column, lift reinforcement | Check columns (13 Nos) and lift reinforcement and allow for concrete pouring Zone 4 | (+130'-9'' to +145'-9'') | Grid G-J/23-26, K-L/26, M/20-26, N-Q/24, Q-R/26 | A | 2024-02-01
| Sub Structure | 11th Floor | L1/569 | 2024-01-31 | 2024-01-31 | level, layout | Check level and layout of stair st-2 Zone 4 | (+117'-9'' to +130'-9'') | Grid N-Q/20-22 | A | 2024-02-01
| Sub Structure | 7th Floor | L1/570 | 2024-01-31 | 2024-01-30 | Beam reinforcement | Check hanging beam reinforcement and formwork and allow for concrete pouring Zone 4 | (+84'-9'') | Grid G-H/26 | A | 2024-02-01
| Sub Structure | 11th Floor | L1/571 | 2024-02-01 | 2024-02-01 | stair reinforcement | Check formwork and stair ST-2 reinforcement and allow for concrete pouring Zone 4 | (+117'-9'' to +130'-9'') | Grid N-Q/20-22 | A | 2024-02-17
| Sub Structure | 11th Floor | L1/572 | 2024-02-01 | 2024-02-01 | level, layout | Check level and layout of slab and columns (26 Nos) & SW-8 Zone 5 | (+130'-9'') | Grid N-U/15-26 | A | 2024-02-06
| Sub Structure | 11th Floor | L1/573 | 2024-02-01 | 2024-02-01 | Column reinforcement | Check columns (12 Nos) reinforcement Zone 4 & 5 | (+130'-9'' to +145'-9'') | Grid N-U/118, S-U/20-26 | A | 2024-02-15
| Sub Structure | 11th Floor | L1/574 | 2024-02-01 | 2024-02-01 | Column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 4 | (+130'-9'' to +145'-9'') | Grid Q-R/26, N-Q/24, H-J/26 | A | 2024-02-22
| Sub Structure | 11th Floor | L1/575 | 2024-02-02 | 2024-02-02 | Column reinforcement | Check columns (8 Nos) reinforcement Zone 5 | (+130'-9'' to +145'-9'') | Grid N-U/17-18 | A | 2024-02-15
| Sub Structure | 11th Floor | L1/576 | 2024-02-02 | 2024-02-02 | Lift wall reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 4 | (+130'-9'' to +145'-9'') | Grid N-Q/20-22 | A | 2024-02-03
| Sub Structure | 11th Floor | L1/577 | 2024-02-03 | 2024-02-03 | Column reinforcement | Check columns (6 Nos) and SW-8 (2 Nos) reinforcement Zone 5 | (+130'-9'' to +145'-9'') | Grid N-U/15-16 | A | 2024-02-05
| Sub Structure | 7th Floor | L1/578 | 2024-02-03 | 2024-02-03 | level, layout | Check level and layout of Stair ST-04 Zone 4 | (+84'-9'' to +95'-9'') | Grid G-H/26 | A | 2024-02-06
| Sub Structure | 11th Floor | L1/579 | 2024-02-03 | 2024-02-03 | Column reinforcement | Check columns (14 Nos) reinforcement and allow for concrete pouring Zone 4-5 | (+130'-9'' to +145'-9'') | Grid N-U/19, S-U/20-26, G/26 | A | 2024-02-15
| Sub Structure | 11th Floor | L1/580 | 2024-02-05 | 2024-02-05 | Column reinforcement | Check columns (13 Nos) reinforcement and allow for concrete pouring Zone 4 & 5 | (+130'-9'' to +145'-9'') | Grid N-U/19, S-U/20-26, G/26 | A | 2024-02-15
| Sub Structure | 11th Floor | L1/581 | 2024-02-05 | 2024-02-05 | Lift reinforcement | Check lift reinforcement and allow for concrete pouring Zone 4 | (+130'-9'' to +145'-9'') | Grid N-Q/20-22 | A | 2024-02-15
| Sub Structure | Top Floor | L1/582 | 2024-02-06 | 2024-02-06 | beam reinforcement | Check beam reinforcement Zone 4 | (+145'-9'') | Grid G-M/20-26 | A | 2024-02-15
| Sub Structure | 7th to 8th Floor | L1/583 | 2024-02-06 | 2024-02-06 | stair reinforcement | Check formwork and stair st-04 reinforcement and allow for concrete pouring Zone 4 | (+84'-9'' to +95'-9'') | Grid G-H/26 | A | 2024-02-15
| Sub Structure | 11th Floor | L1/584 | 2024-02-06 | 2024-02-06 | Reinforcement | Check reinforcement and allow for concrete pouring Zone 5 | (+130'-9'' to +145'-9'') | Grid N-U/16-17, S-U/15 | A | 2024-02-15
| Sub Structure | Top floor | L1/585 | 2024-02-07 | 2024-02-07 | formwork, | Check formwork along stair ST-04 Zone 4 | (+145'-9'') | Grid G-H/24-24 | A
| Sub Structure | Top floor | L1/586 | 2024-02-08 | 2024-02-08 | formwork, | Check formwork along st-2 zone 4 | (145'-9'') | Grid P-Q/20-21 | A
| Sub Structure | Basement | L1/587 | 2024-02-07 | 2024-02-07 | WT Reinforcement | Check under ground domestic water tank wall | (-13'-3'' to -1-00'') | Grid T/17-22 | A | 2024-02-15
| Sub Structure | Top Floor | L1/588 | 2024-02-09 | 2024-02-10 | beam reinforcement | Check beam reinforcement Zone 4 | (+145'-9'') | Grid M-R/19-26 | A | 2024-02-15
| Sub Structure | top Floor | L1/589 | 2024-02-09 | 2024-02-10 | PW Reinforcement | Check Top and bottom parapet wall reinforcement Zone 4 | (+145'-9'') | Grid G-R/19-26 | A | 2024-02-15
| Sub Structure | Top Floor | L1/590 | 2024-02-10 | 2024-02-10 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+145'-9'') | Grid G-R/19-26 | A | 2024-02-15
| Sub Structure | Top Floor | L1/591 | 2024-02-11 | 2024-02-11 | level, layout | Check level and layout of columns, service lift and pw Zone 4 | (+145'-9'') | Grid G-P/22-26 | A | 2024-02-15
| Sub Structure | 11th Floor | L1/592 | 2024-02-10 | 2024-02-10 | Column reinforcement | Check columns (1N) and SW-8 (1 Nos) reinforcement Zone 5 | (+130'-9'' to +145'-9'') | Grid N-Q/15 | A | 2024-02-22
| Sub Structure | 7th Floor | L1/593 | 2024-02-11 | 2024-02-11 | beam reinforcement | Check Hanging beam reinforcement and allow for concrete pouring Zone 4 | (+95'-9'') | Grid G-H/26 | A | 2024-02-15
| Sub Structure | 7th to 8th Floor | L1/594 | 2024-02-13 | 2024-02-13 | level, layout | Check level and layout of stair ST-4 Zone 4 | (+95'-9'' to +106'-9'') | Grid G-H/24-26 | A | 2024-02-17
| Sub Structure | GF | L1/595 | 2024-02-14 | 2024-02-14 | Slab reinforcement | Check top and bottom slab reinforcement Zone 5 | (+00) | Grid U/15-22 | A | 2024-02-17
| Sub Structure | GF | L1/596 | 2024-02-14 | 2024-02-14 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 5 | (+00) | Grid U/15-22 | A | 2024-02-19
| Sub Structure | Top Floor | L1/597 | 2024-02-14 | 2024-02-14 | Beam reinforcement | Check beam reinforcement Zone 4 & 5 | (+145'-9'') | Grid N-U/20-26, N-U/18-20 | A | 2024-02-17
| Sub Structure | Basement | L1/598 | 2024-02-13 | 2024-02-13 | RW, UGWT TW | Check UGWT Fuel Tank and Rain Water Reinforcement and allow for concrete pouring Zone 4 | (-13'-3'' to +00) | Grid U/25-26, T-R/26 | A | 2024-02-17
| Sub Structure | 11th Floor | L1/599 | 2024-02-07 | 2024-02-07 | column, SW reinforcement | Check columns (14 Nos) and SW-8 (2 Nos) reinforcement Zone 5 | (+130'-9'' to +145'-9'') | Grid N-U/15-18, S-U/15, N-Q/15 | A | 2024-02-17
| Sub Structure | Top Floor | L1/600 | 2024-02-16 | 2024-02-16 | level, layout | Check level , layout , pw, columns and lift walls Zone 4 & 5 | (+145'-9'') | Grid N-U/20-26, N-U/18-20 | A | 2024-03-06
| Sub Structure | top floor | L1/601 | 2024-02-15 | 2024-02-15 | Slab, PW Reinforcement | Check slab and top and bottom slab reinforcement Zone 4 & 5 | (+145'-9'') | Grid N-U/20-26, N-U/18-20 | A | 2024-02-17
| Sub Structure | Top Floor | L1/602 | 2024-02-15 | 2024-02-15 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 & 5 | (+145'-9'') | Grid N-U/20-26, N-U/18-20 | A | 2024-02-19
| Sub Structure | GF | L1/603 | 2024-02-15 | 2024-02-15 | level, layout | Check level and layout of slab Zone 5 | (+00) | Grid U/15-22 | A | 2024-02-19
| Sub Structure | 8th to 9th Floor | L1/604 | 2024-02-16 | 2024-02-16 | stair reinforcement | Check formwork and Stair ST-4 reinforcement and allow for concrete pouring Zone 4 | (+95'-9'' to +106'-9'') | Grid G-H/24-26 | A | 2024-02-19
| Sub Structure | Top Floor | L1/605 | 2024-02-17 | 2024-02-17 | Beam reinforcement | Check beam reinforcement Zone 5 | (+145'-9'') | Grid N-U/15-18 | A | 2024-02-19
| Sub Structure | 10th Floor | L1/606 | 2024-02-19 | 2024-02-18 | Beam reinforcement | Check formwork and hanging beam reinforcement and allow for concrete pouring Zone 4 | (+106'-9'') | Grid G-H/26 | A | 2024-02-22
| Sub Structure | 11th Floor | L1/607 | 2024-02-19 | 2024-02-19 | Level and layout | Check level and layout of Stair ST-02 Zone 4 | (+130'-9'' to +145'-9'') | Grid N-Q/20-22 | A | 2024-02-22
| Sub Structure | Top Floor | L1/608 | 2024-02-19 | 2024-02-19 | Beam reinforcement | Check bracket beam reinforcement and allow for concrete pouring Zone 5 | (+142'-9'') | Grid N-U/15 | A | 2024-02-22
| Sub Structure | Top Floor | L1/609 | 2024-02-19 | 2024-02-19 | Beam reinforcement | Check bracket beam reinforcement Zone 5 | (+142'-2'') | Grid N-U/15 | A | 2024-02-22
| Sub Structure | Top Floor | L1/610 | 2024-02-19 | 2024-02-19 | Slab reinforcement | Check top and bottom slab reinforcement Zone 5 | (+145'-9'') | Grid N-U/15-18 | A | 2024-02-22
| Sub Structure | Top Floor | L1/611 | 2024-02-20 | 2024-02-20 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 5 | (+145'-9'') | Grid N-U/15-18 | A | 2024-02-27
| Sub Structure | top Floor | L1/612 | 2024-02-21 | 2024-02-21 | level, layout | Check level and layout of slab and parapet wall, bracket beam Zone 5 | (+145'-9'') | Grid N-U/15-17 | A | 2024-03-06
| Sub Structure | 9th to 10th Floor | L1/613 | 2024-02-21 | 2024-02-21 | level , layout | Check level and layout of stair st-4 Zone 45 | (+106'-9'' to +117'-9'') | Grid G-H/26 | A | 2024-02-27
| Sub Structure | 11th Floor | L1/614 | 2024-02-21 | 2024-02-21 | Reinforcement | Check formwork and stair st-2 reinforcement and allow for concrete pouring Zone 4 | (+130'-9'' to +145'-9'') | Grid N-Q/20-22 | A | 2024-02-27
| Sub Structure | Basement | L1/615 | 2024-02-22 | 2024-02-22 | Epoxy rebar | Check epoxy rebar for main ramp dowels (20 No) | (-13'-3'') | Grid Q-S/21 | A | 2024-02-27
| Sub Structure | Basement | L1/616 | 2024-02-22 | 2024-02-22 | level, layout | Check level and layout of main ramp Zone 5 | (-13'-3'') | Grid Q-S/15-21 | A | 2024-02-26
| Sub Structure | Basement | L1/617 | 2024-02-22 | 2024-02-22 | PCC Ramp | Check PCC Ramp Zone 5 | (-13'-3'') | Grid Q-S/6-8 | A | 2024-02-27
| Sub Structure | Basement | L1/618 | 2024-02-22 | 2024-02-22 | Reinforcement | Check fuel and Rain water UGWT reinforcement and allow for concrete pouring Zone 4 | (-11'-5'' to -1'-00'') | Grid T/25-26, S-T/26 | A | 2024-02-27
| Sub Structure | Basement | L1/619 | 2024-02-23 | 2024-02-23 | Slab reinforcement | Check beam slab reinforcement Zone 5 | (-13'-3'') | Grid Q-S/15-21 | A | 2024-02-26
| Sub Structure | 9th to 10th Floor | L1/620 | 2024-02-23 | 2024-02-23 | stair reinforcement | Check formwork and stair st-4 reinforcement and allow for concrete pouring Zone 4 | (+106'-9'' to +117'-9'') | Grid G-H/26 | A | 2024-02-26
| Sub Structure | Basement | L1/621 | 2024-02-24 | 2024-02-24 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 5 | (-13'-3'') | Grid Q-S/15-21 | A | 2024-02-26
| Sub Structure | Basement | L1/622 | 2024-02-25 | 2024-02-25 | level, layout | Check level and layout of main ramp Zone 5 | (-13'-3'') | Grid Q-S/15-21 | A | 2024-03-06
| Sub Structure | 10th Floor | L1/623 | 2024-02-25 | 2024-02-25 | Beam reinforcement | Check formwork and hanging beam reinforcement and alow for concrete pouring Zone 4 | (+117'-9'') | Grid G-H/26 | A | 2024-02-26
| Sub Structure | Basement | L1/624 | 2024-02-26 | 2024-02-26 | Beam reinforcement | Check main ramp beam reinforcement and allow for concrete pouring Zone 5 | (-13'-3'') | Grid S/15-21 | A | 2024-03-06
| Sub Structure | Basement | L1/625 | 2024-02-28 | 2024-02-28 | Reinforcement | Check main ramp beam reinforcement and allow for concrete pouring Zone 5 | (-13'-3'') | Grid Q/15-21 | A | 2024-03-06
| Sub Structure | 10th to 11th Floor | L1/626 | 2024-02-29 | 2024-02-29 | level, layout | Check level and layout of stair ST-4 Zone 4 | (+117'-9'' to +130'-9'') | Grid G-H/24-26 | A | 2024-03-06
| Sub Structure | 10th to 11th Floor | L1/627 | 2024-02-29 | 2024-02-29 | stair reinforcement | Check formwork and stair st-4 reinforcement and allow for concrete pouring Zone 4 | (+117'-9'' to +130'-9'') | Grid G-H/24-26 | A | 2024-03-06
| Sub Structure | 11th Floor | L1/628 | 2024-03-02 | 2024-03-02 | Beam reinforcement | Check formwork and hanging beam reinforcement and allow for concrete pouring Zone 4 | (+130'-9'') | Grid G-H/26 | A | 2024-03-06
| Sub Structure | 11th to top | L1/629 | 2024-03-04 | 2024-03-04 | level, layout | Check level and layout of Stair ST-4 Zone 4 | (+130'-9'' to +145'-9'') | Grid G-H/24-26 | A | 2024-03-06
| Sub Structure | 11th to top | L1/630 | 2024-03-04 | 2024-03-04 | stair reinforcement | Check formwork and stair ST-4 reinforcement and allow for concrete pouring Zone 4 | (+130'-9'' to +145'-9'') | Grid G-H/24-26 | A | 2024-03-06
| Sub Structure | top Floor | L1/631 | 2024-03-07 | 2024-03-07 | Beam reinforcement | Check formwork & hanging beam reinforcement and allow for concrete pouring Zone 4 | (+145'-9'') | Grid G-H/26 | A | 2024-03-08
| Sub Structure | Top Floor | L1/632 | 2024-03-14 | 2024-03-15 | Lift reinforcement | Check machine room/lift wall reinforcement Zone 4 | (+145'-9'' to +159'-6'') | Grid N-Q/20-22 | A | 2024-03-18
| Sub Structure | Roof Floor | L1/633 | 2024-05-11 | 2024-05-11 | column, PW reinforcement | Check service lift, columns (4 Nos) & Parapet wall reinforcement Zone 4 & 5 | (+145'-9'' to +165'-8'') | Grid H-J/23-24, G/24-26, H-J/26, J-U/26, G/20-23, G-N/20, N/15 | A | 2024-05-16
| Sub Structure | basement | L1/634 | 2024-07-14 | 2024-07-14 | Reinforcement | Check rain harvesting UGWT reinforcement and allow for concrete pouring Zone 4 | (-11'-5'' to -1'-00) | Grid T-L/26 | A | 2024-07-20
| Sub Structure | basement | L1/635 | 2024-07-22 | 2024-07-21 | Reinforcement | Check septic tank UGWT reinforcement and allow for concrete pouring Zone 4 | (-11'-5'' to -1'-00) | Grid G-K/26 | A | 2024-07-30
| Sub Structure | basement | L1/636 | 2024-07-24 | 2024-07-23 | Reinforcement | Check rain harvesting Tank UGWT reinforcement and allow for concrete pouring Zone 4 | (-11'-5'' to -1'-00) | Grid L-S/26 | A | 2024-07-26
| Sub Structure | basement | L1/637 | 2024-07-25 | 2024-07-25 | Epoxy rebar | check epoxy rebaring for stair ST-04 Zone 4 | (+1'-9'' to +10'-9'') | Grid G-H/24-26 | A | 2024-07-29
| Sub Structure | 1st floor | L1/638 | 2024-08-05 | 2024-08-05 | Slab reinforcement | Check formwork and slab reinforcement of stair st-4 and allow for concrete pouring Zone 4 | (+1'-9'' to +18'-9'') | Grid G-H/24-26 | A | 2024-08-07
| Sub Structure | GF | L1/639 | 2024-08-09 | 2024-08-10 | Slab reinforcement | Check top & bottom slab reinforcement Zone 4 | (+0'-00'') | Grid L-U/26 | A | 2024-08-15
| Sub Structure | GF | L1/640 | 2024-08-10 | 2024-08-10 | Slab reinforcement | Check slab top and bottom reinforcement and allow for concrete pouring Zone 4 | (+0'-00'') | Grid L-U/26 | A | 2024-08-20
| Sub Structure | GF to 1st floor | L1/641 | 2024-08-09 | 2024-08-09 | Reinforcement | Check formwork, reinforcement & level layout of stair ST-4 and allow to start concrete work | (+10'-9'' to +18'-9'') | Grid G-H/24-26 | A | 2024-08-13
| Sub Structure | GF | L1/642 | 2024-08-13 | 2024-08-13 | level, layout | Check level, layout of rain harvesting tank Zone 4 | (+0'-00'') | Grid M-U/26 | A | 2024-08-20
| Sub Structure | GF | L1/643 | 2024-08-21 | 2024-08-21 | Slab reinforcement | Check slab top and bottom reinforcement Zone 4 | (+0'-00'') | Grid G-L/26 | A | 2024-08-24
| Sub Structure | GF | L1/644 | 2024-08-21 | 2024-08-21 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 | (+0'-00'') | Grid G-L/26 | A | 2024-08-28
| Sub Structure | GF | L1/645 | 2024-08-23 | 2024-08-23 | level | Check level of slab septic tank Zone 4 | (+0'-00'') | Grid G-L/26 | A | 2024-08-24
| Sub Structure | BF to GF | L1/646 | 2024-09-26 | 2024-09-26 | primer, membrane | Check vertical primer and membrane on RTW zone 4 | (+0'-00'') | Grid G-T/26 | A | 2024-09-30
| Sub Structure | Ground floor | L1/647 | 2024-12-16 | 2024-12-16 | Ground floor | Check ramp wall rienforcement zone 4 & 5 | (+0'-00'') | Grid N/15-20, H-M/20 | A | 2024-12-19
| Sub Structure | GF | L1/648 | 2025-01-10 | 2025-01-09 | wall reinforcement | Check ramp wall reinforcement and allow for concrete pouring zone 4 & 5 | (+0'-00'') | Grid N/15-20, M/20 | A | 2025-01-10
| Sub Structure | Top floor | L1/649 | 2025-02-25 | 2025-02-24 | Reinforcement | Check parapet wall reinforcement and allow for concrete pouring zone 5 | (+145'-9'' to +149'-6'') | Grid U/15-19, U-U/15 | A | 2025-02-27
| Sub Structure | Top floor | L1/650 | 2025-02-26 | 2025-02-26 | Reinforcement | Check parapet wall reinforcement and allow for concrete pouring zone 4 | (+145'-9'' to +149'-6'') | Grid U/19-26, Q-U/26 | A | 2025-03-04
| Sub Structure | Top floor | L1/651 | 2025-03-01 | 2025-02-28 | Reinforcement | check parapet wall reinforcement and allow for concrete pouring zone 5 | (+145'-9'' to +149'-6'') | Grid N/15-18, N-P/15 | A | 2025-03-04
| Sub Structure | Top floor | L1/652 | 2025-03-03 | 2025-03-02 | Reinforcement | check parapet wall reinforcement and allow for concrete pouring zone 4 | (+145'-9'' to +149'-6'') | Grid G-N/20, G/20 | A | 2025-03-03
| Sub Structure | Ground floor | L1/653 | 2025-03-04 | 2025-03-03 | Reinforcement | Check ramp wall reinforcement and allow for concrete pouring zone 4 | (+0'-00'') | Grid G-L/20 | A | 2025-03-04
| Sub Structure | Top floor | L1/654 | 2025-03-05 | 2025-03-04 | Reinforcement | check parapet wall reinforcement and allow for concrete pouring zone 4 | (+145'-9'' to +149'-6'') | Grid J-Q/26 | A | 2025-03-06
| Sub Structure | Top floor | L1/655 | 2025-03-07 | 2025-03-07 | Reinforcement | Check Mummty column reinforcement and allow for concrete pouring zone 4 | (+145'-9'' to +159'-00'') | Grid G-J/24-26 | A | 2025-03-12
| Sub Structure | basement | L1/656 | 2025-03-10 | 2025-03-08 | Reinforcement | Check septic tank wall reinforcement and allow for concrete pouring zone 4 | (-11'-9'' to +0'-00'') | Grid F-G/26 | A | 2025-03-12
| Sub Structure | Top floor to mummty | L1/657 | 2025-03-13 | 2025-03-12 | Reinforcement | check service lift reinforcement and allow for concrete pouring zone 4 | (+145'-9'' to +159'-0'') | Grid H-J/3-3 | A | 2025-03-14
| Sub Structure | Top floor | L1/658 | 2025-03-13 | 2025-03-12 | layout | Check layout of Genset beam zone 4 | (+145'-9'') | Grid H-L/24-26 | A | 2025-03-19
| Sub Structure | basement | L1/659 | 2025-03-15 | 2025-03-14 | Reinforcement | Check septic tank wall reinforcement and allow for concrete pouring zone 4 | (-11'-9'' to +0'-00'') | Grid F-G/26 | A | 2025-03-15
| Sub Structure | Top floor | L1/660 | 2025-03-15 | 2025-03-15 | Reinforcement | Check genset reinforcement zone 4 | (+145'-9'') | Grid J-L/24-26 | A | 2025-03-19
| Sub Structure | Ground floor | L1/661 | 2025-03-17 | 2025-03-17 | Reinforcement | check slab fuel tank reinforcement zone 4 | (+0'-00'') | Grid Gu/23-26 | A | 2025-03-18
| Sub Structure | Ground floor | L1/662 | 2025-03-19 | 2025-03-18 | Reinforcement | Check slab fuel tank reinforcement and allow for concrete pouring zone 4 | (+0;-00'') | Grid U/22-26 | A | 2025-03-19
| Sub Structure | Ground floor | L1/663 | 2025-03-19 | 2025-03-19 | level | Check slab fuel tank level zone 4 | (+0;-00'') | Grid U/22-26 | A | 2025-03-21
| Sub Structure | Top floor | L1/664 | 2025-03-21 | 2025-03-20 | Reinforcement | Check lift wall reinforcement and allow for concrete pouring zone 4 | (+145'-9'' to +159'-00'') | Grid N-Q/20-22 | A | 2025-03-21
| Sub Structure | Top floor | L1/665 | 2025-03-21 | 2025-03-21 | layout | Check OHWT & FSS Tank layout Zone 4 | (+145'-9'') | Grid N-Q/19-20 | A | 2025-03-24
| Sub Structure | Top floor | L1/666 | 2025-03-25 | 2025-03-25 | Reinforcement | Check base slab of OHWT & FSS Tank reinforcemetn zone 5 | (+147'-2'') | Grid N-Q/19-20 | A | 2025-03-27
| Sub Structure | Ground floor | L1/667 | 2025-04-04 | 2025-03-26 | Reinforcement | check RTW reinforcement along fuel tank and fule tank wall and allow for concrete pouring | (+0'-00'') | Grid T/25-26 | A | 2025-04-08
| Sub Structure | Mummty beam | L1/668 | 2025-04-11 | 2025-04-11 | Slab reinforcement | Check mummty beam & slab top and bottom reinforcement zone 4 | (+159') | Grid G-J/24-26 | A | 2025-04-14
| Sub Structure | Mummty | L1/669 | 2025-04-14 | 2025-04-14 | Reinforcement | Check Mummty beam & slab top and bottom reinforcement zone 4 | (+159') | Grid N-Q/20-22 | A | 2025-04-16
| Sub Structure | Mummty | L1/670 | 2025-04-15 | 2025-04-14 | Reinforcement | Check slab reinforcement znd allow for concrete pouring zone 4 | (+159') | Grid G-J/24-26 | A | 2025-04-16
| Sub Structure | Mummty top | L1/671 | 2025-04-15 | 2025-04-15 | layout | Check mummty slab top and layout of parapet zone 4 | (+159') | Grid G-J/24-26 | A | 2025-04-19
| Sub Structure | Mummty | L1/672 | 2025-04-17 | 2025-04-16 | Reinforcement | Check Mummty slab rienforcement and allow for concrete pouring zone 4 | (+159') | Grid N-Q/20-22 | A | 2025-04-19
| Sub Structure | Mummty | L1/673 | 2025-04-17 | 2025-04-17 | level | Check Mummty slab level & layout of parapet zone 4 | (+159') | Grid N-Q/20-22 | A | 2025-04-22
| Sub Structure | Top roof to mummty | L1/674 | 2025-04-21 | 2025-04-21 | Reinforcement | Check OHWT & FSS Tank reinforcement zone 4 | (+147'-3'' to +159'') | Grid N-Q/19-20 | A | 2025-04-24
| Sub Structure | Top floor | L1/675 | 2025-04-22 | 2025-04-21 | Reinforcement | Check OHWT & FSS reinforcement and allow for concrete pouring zne 4 | (+147'-3'') | Grid N-Q/19-20 | A | 2025-04-24
| Sub Structure | Top floor | L1/676 | 2025-04-22 | 2025-04-22 | level | Check OHWT & FSS level zone 4 | (+147'-3'') | Grid N-Q/19-20 | A | 2025-05-08
| Sub Structure | Top floor | L1/677 | 2025-04-26 | 2025-04-26 | Reinforcement | Check machine room wall service lift reinforcement and allow for concrete pouring zone 4 | (+159' to +165') | Grid H-J/24 | A | 2025-05-08
| Sub Structure | Top floor | L1/678 | 2025-04-29 | 2025-04-29 | Reinforcement | Check machine room slab of service lift reinforcement zone 4 | (+165'-2'') | Grid H-J/23-24 | A | 2025-05-09
| Sub Structure | Top floor | L1/679 | 2025-04-30 | 2025-04-29 | Reinforcement | Check machine room wall reinforcement and allow for concrete pouring zone 4 | (+159' to +165'-2'') | Grid N-Q/21-22 | A | 2025-05-08
| Sub Structure | Top floor | L1/680 | 2025-05-01 | 2025-05-01 | steel fixing | Check steel fixing of main lift machine room zone 4 | (+165'-3'') | Grid N-Q/21-22 | A | 2025-05-08
| Sub Structure | Top floor | L1/681 | 2025-05-01 | 2025-05-01 | steel fixing | Check service lift machine room slab steel fixing and allow for pouring zone 4 | (+165'-3'') | Grid H-J/22-24 | A | 2025-05-08
| Sub Structure | Top floor | L1/682 | 2025-05-01 | 2025-05-01 | level, layout | Check level, layout of machine room slab of service lift zone 4 | (+165'-3'') | Grid H-J/22-24 | A | 2025-05-08
| Sub Structure | Top floor | L1/683 | 2025-05-02 | 2025-05-01 | Reinforcement | Check machine room parapet of service lift reinforcement and allow for concrete pouring Zone 4 | (+159 to +160& +165'-2'') | Grid G-J/24-26 | A | 2025-05-08
| Sub Structure | Top floor | L1/684 | 2025-05-03 | 2025-05-02 | Reinforcement | Check lift machine room slab reinforcement and allow for concrete pouring zone 4 | (+165'-2'') | Grid N-Q/21-22 | A | 2025-05-08
| Sub Structure | Top floor | L1/685 | 2025-05-03 | 2025-05-03 | level | Check machine room slab level and layout of parapet zone 4 | (+165'-2'') | Grid N-Q/21-22 | A | 2025-05-09
| Sub Structure | Top floor | L1/686 | 2025-05-05 | 2025-05-04 | Reinforcement | Check machine room parapet lift reinforcement and allow for concrete pouring zone 4 | (+159' to +160', +165'-2'' to +166') | Grid N-Q/20-22 | A | 2025-05-09
| Sub Structure | Top floor | L1/687 | 2025-05-09 | 2025-05-09 | Reinforcement | Check OHWT & FSS wall reinforcement and allow for concrete pouring zone 5 | (+148'-3'' to +159'-0'') | Grid N-Q/20-22 | A | 2025-05-09
| Sub Structure | Top floor | L1/688 | 2025-05-10 | 2025-05-10 | steel fixing | Check steel fixing of genset slab zone 4 | (+148'-6'') | Grid J-L/24-26 | A | 2025-05-13
| Sub Structure | Top floor | L1/689 | 2025-05-12 | 2025-05-12 | Reinforcement | Check OHWT & FSS Tank reinforcement zone 5 | (+159'-0'') | Grid N-Q/20-22 | A | 2025-05-12
| Sub Structure | Top floor | L1/690 | 2025-05-15 | 2025-05-14 | Reinforcement | Check OHWT & FSS Tank slab reinforcement and allow for concrete pouring zone 5 | (+159'-0'') | Grid N-Q/20-22 | A | 2025-05-14
| Sub Structure | Top floor | L1/691 | 2025-05-15 | 2025-05-14 | Reinforcement | Check genset reinforcement and beam and allow for concrete pouring zone 4 | (+148'-3'') | Grid J-L/24-26 | A | 2025-05-14
| Sub Structure | Top floor | L1/692 | 2025-05-15 | 2025-05-15 | level | check OHWT level & FSS tank slab zone 5 | (+159'-0'') | Grid N-Q/20-22 | A | 2025-05-17
| Sub Structure | Top floor | L1/693 | 2025-05-15 | 2025-05-15 | level | Check Genset slab level zone 4 | (+148'-3'') | Grid J-L/24-26 | A | 2025-05-17
| Sub Structure | Top floor | L1/694 | 2025-05-22 | 2025-05-21 | Reinforcement | check OHWT & FSS reinforcement and allow for concrete pouring zone 5 | (+159'-0'' to +160') | Grid N-Q/20-22 | A | 2025-05-21
| Sub Structure |  | L1/695
| Sub Structure |  | L1/696
| Sub Structure |  | L1/697
| Sub Structure |  | L1/698
| Sub Structure |  | L1/699
| Sub Structure |  | L1/700
| Sub Structure |  | L1/701
| Sub Structure |  | L1/702
| Sub Structure |  | L1/703
| Sub Structure |  | L1/704
| Sub Structure |  | L1/705
| Sub Structure |  | L1/706
| Sub Structure |  | L1/707
| Sub Structure |  | L1/708
| Sub Structure |  | L1/709
| Sub Structure |  | L1/710
| Sub Structure |  | L1/711
| Sub Structure |  | L1/712
| Sub Structure |  | L1/713
| Sub Structure |  | L1/714
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
|  |  |  | 2023-10-30 | [6 empty] | 2023-04-07

## L2 Tower ICPL
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (L2 Tower) | [5 empty] | Fully Approved (A) |  | 799
[9 empty] | Approved with comments (B) |  | 5
[9 empty] | Rejected ( R) |  | 0
[9 empty] | Open/Pending (OP) |  | 3
[9 empty] | Total |  | 807
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description |  | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Attachment | Remarks
I TOWER
1 | Sub Structure | Basement | L2/1 | 2022-10-17 |  | Excavation level | Excavation level and surface preparation of service lift L2 Tower Zone 2 |  | Grid G-T/1-7 | A | 2022-10-20 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\1.pdf
2 | Sub Structure | Basement | L2/2
3 | Sub Structure | Basement | L2/3 | 2022-10-18 |  | Layout of PCC | Level and layout of PCC 1st layer of service lift |  | Grid F-G/1-11 | A | 2022-10-20 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\3.pdf
4 | Sub Structure | Basement | L2/4 | 2022-10-18 |  | Excavation level | Excavation level, surface preparation for PCC |  | Grid G-K/1-7 | A | 2022-10-20 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\4.pdf
5 | Sub Structure | Basement | L2/5 | 2022-10-19 |  | 1st PCC level | Layout and 1st PCC level |  | Grid G-K/1-7, F-G/11-13 | A | 2022-10-20 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\5.pdf
6 | Sub Structure | Basement | L2/6 | 2022-10-19 |  | Layout of isolated | Layout of isolated footing for termite proofing and PCC |  | Grid F-J/7-11 | A | 2022-10-20 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\6.pdf
7 | Sub Structure | Basement | L2/7 | 2022-10-19 |  | Brick work | Brickwork of service lift and brickwork for raft protection |  | Grid F-H/H-J/3-3 | A | 2022-10-24 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\7.pdf
8 | Sub Structure | Basement | L2/8 | 2022-10-20 |  | Plaster | Plaster of Raft Protection wall |  | Grid F-H/1 | A | 2022-10-24 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\8.pdf
9 | Sub Structure | Basement | L2/9 | 2022-10-24 |  | Layout | Layout of Service Lift, column, foooting and retaining wall of SOG area for steel fixing |  | Grid F-J/1-7 & F-H/7-11 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\9.pdf
10 | Sub Structure | Basement | L2/10 | 2022-10-21 |  | Plaster | Plaster of service lift wall and allow for primer and membrane on wall |  | Grid H-J/2-4 | A | 2022-10-24 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\10.pdf
11 | Sub Structure | Basement | L2/11 | 2022-10-21 |  | Primer | Primer and membrane for 2nd layer of PCC |  | Grid F-K/1-7 | A | 2022-10-24 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\11.pdf
| Sub Structure | Basement | L2/12 | 2022-10-21 |  | Level | Level for 2nd layer of PCC of SOG Area L2 Tower |  | Grid F-K/1-7 & F-H/7-11 | A | 2022-10-24 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\12.pdf
12 | Sub Structure | Basement | L2/13 | 2022-10-17 |  | Termite proofing | Termite proofing before PCC |  | Grid F-K/1-7 & F-H/7-11 | A | 2022-10-20 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\13.pdf
13 | Sub Structure | Basement | L2/14 | 2022-10-26 |  | Steel fixing | Steel fixing of Raft L2 Tower |  | Grid F-G/1-7 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\14.pdf
14 | Sub Structure | Basement | L2/15 | 2022-10-27 |  | Joint | Construction Joint and chicken Mesh of Pour 6 of L2 Tower |  | Grid F-G/1-7 & H/7-11 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\15.pdf
15 | Sub Structure | Basement | L2/16 | 2022-10-27 |  | Water stopper | PVC water stopper placing and fixing in raft foundation Zone 7 |  | Grid F-G/1 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L2 -Tower IR's\new\16.pdf
16 | Sub Structure | Basement | L2/17 | 2022-10-27 |  | Steel fixing | Steel fixing of SOG Area and footing Zone 8 and allow for pouring |  | Grid F-G/1-7, F-H/7-11 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\17.pdf
17 | Sub Structure | Basement | L2/18 | 2022-10-27 |  | Layout, level | Level and layout of SOG Area and isolated footing and allow for termite proofing |  | Grid F-J/11-20, J-K/17-20 | A | 2022-11-08 |  |  | E:\14.Soft IRs\ICPL\L2 -Tower IR's\new\18.pdf
18 | Sub Structure | Basement | L2/19 | 2022-10-27 |  | Termite proofing | Termite proofing and allow for 1st layer of PCC of SOG Area |  | Grid F-J/11-20, J-K/17-20 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\19.pdf
19 | Sub Structure | Basement | L2/20 | 2022-10-29 |  | Layout, level | RCC raft top level and layout of column and RTW Zone 7 L2 Tower |  | Grid F/1-13, G-H/1-7 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\20.pdf
20 | Sub Structure | Basement | L2/21 | 2022-10-31 |  | Steel fixing | Steel fixing of columns and allow for pouring |  | Grid G/1-11 | A | 2022-11-01 |  |  | E:\Soft IRs\ICPL\L2 -Tower IR's\new\21.pdf
21 | Sub Structure | Basement | L2/22 | 2022-11-05 |  | Curing | Check the curing of Raft L2 Tower |  | Grid G-K/1-7, F/1-7 | A | 2022-11-14
22 | Sub Structure | Basement | L2/23 | 2022-11-08 |  | Water stopper | PVC vertical water stopper for expansion joint as per IFC |  | Grid G/1 | A | 2022-11-14
23 | Sub Structure | Basement | L2/24 | 2022-11-08 |  | Water stopper | PVC Horizontal water stopper in RCC wall |  | Grid F-G/1 | A | 2022-11-14
24 | Sub Structure | Basement | L2/25 | 2022-11-15 |  | PCC | 1st layer of PCC and allow for primer and membrane for isolated footing |  | Grid M-M/15-19 | A | 2022-11-17
| Sub Structure | Basement | L2/26 | 2022-12-28 |  | Level, layout | Excavation, Level, Layout, Surface Bed preparation of Tower Crane |  | Grid K-M/7-10 | A | 2022-12-30
25 | Sub Structure | Basement | L2/27 | 2022-12-28 |  | Termite proofing | Termite Proofing & Allow for PCC of Tower Crane Foundation Zone 8 |  | Grid K-M/7-10 | A | 2022-12-30
26 | Sub Structure | Basement | L2/28 | 2022-12-31 |  | Level, layout | Check level & Layout of PCC layer of Tower Crane Foundation Zone 8 |  | Grid K-M/7-10 | A | 2023-01-02
27 | Sub Structure | Basement | L2/29 | 2023-01-05 |  | Steel fixing | Check top and bottom steel fixing of Tower Crane Foundation Zone 8 SOG |  | Grid K-M/7-10 | A | 2023-01-05
28 | Sub Structure | Basement | L2/30 | 2023-01-05 |  | Concrete Pouring | Allow for concrete pouring of Tower Crane Foundation Zone 8 SOG |  | Grid K-M/7-10 | A | 2023-01-06
29 | Sub Structure | Basement | L2/31 | 2023-01-09 |  | Level, layout | Check top raft level & layout of Tower Crane Zone 8 |  | Grid K-M/7-10 | A | 2023-01-10
30 | Sub Structure | Basement | L2/32 | 2023-01-10 |  | Backfilling | Check 1st layer backfilling of sand along sides of Tower Crane 2 Zone 8 |  | Grid K-M/7-10 SOG | A | 2023-01-17
31 | Sub Structure | Basement | L2/33 | 2023-01-10 |  | Backfilling | Check 2nd layer backfilling of sand along sides of Tower Crane 2 Zone 8 |  | Grid K-M/7-10 SOG | A | 2023-01-17
32 | Sub Structure | Basement | L2/34 | 2023-01-11 |  | Backfilling | Check 3rd layer backfilling of sand along sides of Tower crane 2 Zone 8 SOG |  | Grid K-M/7-10 | A | 2023-01-17
33 | Sub Structure | Basement | L2/35 | 2023-01-11 |  | Backfilling | Check 4th layer backfilling of sand along sides of Tower crane 2 Zone 8 SOG |  | Grid K-M/7-10 | A | 2023-01-17
34 | Sub Structure | Basement | L2/36 | 2023-01-12 |  | Backfilling | Check 5th layer backfilling of sand along sides of Tower crane 2 Zone 8 |  | Grid K-M/7-10 | A | 2023-01-17
35 | Sub Structure | Basement | L2/37 | 2023-01-12 |  | Backfilling | Check 6th layer backfilling of sand along sides of Tower Crane 2 Zone 8 |  | Grid K-M/7-10 | A | 2023-01-17
36 | Sub Structure | Basement | L2/38 | 2023-04-08 |  | Excavation | Check excavation of footing F3 and Sumpit and allow for termite proofing Zone 8 |  | K8 & K-L/9-10 | A | 2023-04-14
37 | Sub Structure | Basement | L2/39 | 2023-04-08 |  | Level, layout | Check level and layout of excavation of footing F3 and Sumpit SP2 Zone 8 |  | K8 & K-L/9-10 | A | 2023-04-14
38 | Sub Structure | Basement | L2/40 | 2023-04-08 |  | Termite proofing | Check Anti Termite proofing of Footing F3 and sumpit and allow for 1st layer PCC Z-8 |  | K8 & K-L/9-10 | A | 2023-04-14
39 | Sub Structure | Basement | L2/41 | 2023-04-08 |  | PCC | Check 1st layer PCC of footing and sumpit and allow for water proofing Zone 8 |  | K8, K-L/9-10 | A | 2023-04-19
40 | Sub Structure | Basement | L2/42 | 2023-04-08 |  | Level, layout | Check level, layout of 1st layer PCC of footing F3 and Sumpit and allow for Brickwork Z-8 |  | K8 & K-L/9-10 | A | 2023-04-14
41 | Sub Structure | Basement | L2/43 | 2023-04-09 |  | Excavation | Check excavation of SOG area & Footing F1, F2, F5 Zone 8 |  | J-L/12-18, M-O/13-14 | A | 2023-04-14
42 | Sub Structure | Basement | L2/44 | 2023-04-09 |  | Level, layout | Check level, layout of Excavation of SOG Area & Footing Zone 8 |  | J-L/12-18, M-O/13-14 | A | 2023-04-14
43 | Sub Structure | Basement | L2/45 | 2023-04-09 |  | Termite proofing | Check anti Termite proofing of Excavation of SOG Area footing Zone 8 |  | J-L/12-18, M-O/13-14 | A | 2023-04-14
44 | Sub Structure | Basement | L2/46 | 2023-04-09 |  | PCC | Check 1st layer PCC of SOG Area and footings Zone 8 |  | J-L/16-18, J-K/13,15,16 | A | 2023-04-19
45 | Sub Structure | Basement | L2/47 | 2023-04-09 |  | Level, layout | Check level, layout of 1st layer of PCC Top of SOG Area Zone 8 |  | J-L/16-18, J-K/13, 15,16 | A | 2023-04-14
46 | Sub Structure | Basement | L2/48 | 2023-04-10 |  | PCC | Check 1st layer of PCC of SOG Area and footings Zone 8 |  | Grid 12-16/J-L | A | 2023-04-14
47 | Sub Structure | Basement | L2/49 | 2023-04-11 |  | PCC | Check 1st layer PCC Top level of SOG Area and footings Zone 8 |  | Grid 12-16/J-L | A | 2023-04-14
48 | Sub Structure | Basement | L2/50 | 2023-04-11 |  | Excavation SOG | Check Excavation of SOG area and footings Zone 8 SOG |  | Grid J-M/8-12 | A | 2023-04-14
49 | Sub Structure | Basement | L2/51 | 2023-04-11 |  | Level, layout | Check level, layout of Excavation of SOG area and footings, allow for Termite Z-8 |  | Grid J-M/8-12 | A | 2023-04-14
50 | Sub Structure | Basement | L2/52 | 2023-04-11 |  | Termite proofing | Check Anti Termite Proofing of SOG area and footings and allow for 1st layer PCC Z-8 |  | Grid J-M/8-12 | A | 2023-04-14
51 | Sub Structure | Basement | L2/53 | 2023-04-12 |  | PCC | Check 1st Layer PCC of Footing and SOG Area Zone 8 |  | Grid J-M/8-12 | A | 2023-04-14
52 | Sub Structure | Basement | L2/54 | 2023-04-12 |  | PCC | Check 1st layer PCC Top level of footing and SOG Area Zone 8 |  | Grid J-M/8-12 | A | 2023-04-14
53 | Sub Structure | Basement | L2/55 | 2023-04-13 |  | Brick work | Allow for plaster and brickwork of Sumpit 1 & 2 Zone 8 SOG |  | Grid K-L/9-10, 17-18 | A | 2023-04-14
54 | Sub Structure | Basement | L2/56 | 2023-04-13 |  | Primer/membrane | Allow for primer and membrane of footing and SOG Area Zone 8 SOG |  | Grid J-M/14-17 | A | 2023-04-14
55 | Sub Structure | Basement | L2/57 | 2023-04-13 |  | Primer/membrane | Check primer and membrane of footing and SOG area and allow for 2nd layer PCC Z-8 |  | Grid J-M/14-17 | A | 2023-04-14
56 | Sub Structure | Basement | L2/58 | 2023-04-13 |  | Primer/membrane | Allow for primer and membrane of footing and SOG Area Zone 8 SOG |  | Grid J-K/12-14 | A | 2023-04-14
57 | Sub Structure | Basement | L2/59 | 2023-04-15 |  | PCC | Check 2nd layer PCC Level and layout of columns Zone 8 |  | Grid N-T/12-14 | A | 2023-04-19
58 | Sub Structure | Basement | L2/60 | 2023-04-14 |  | Level, layout | Check level, layout of excavation of footing and SOG Zone 8 |  | Grid N-T/12-14 | A | 2023-04-19
59 | Sub Structure | Basement | L2/61 | 2023-04-14 |  | PCC | Check 1st layer PCC SOG Area and footing Zone 8 |  | Grid L-M/8-9, M-N/13-14 | A | 2023-04-19
60 | Sub Structure | Basement | L2/62 | 2023-04-14 |  | Level, layout | Check level, layout of 1st layer PCC top of SOG Area and footing Zone 8 |  | Grid L-M/8-9, M-N/13-14 | A | 2023-04-19
61 | Sub Structure | Basement | L2/63 | 2023-04-14 |  | PCC | Check 2nd layer PCC of SOG and footing Zone 8 |  | Grid J-L/14-18 | A | 2023-04-19
62 | Sub Structure | Basement | L2/64 | 2023-04-14 |  | PCC | Check 2nd layer PCC level and layout of columns of SOG Area Zone 8 |  | Grid J-L/14-18 | A | 2023-04-19
63 | Sub Structure | Basement | L2/65 | 2023-04-15 |  | Termite proofing | Check Anti Termite proofing over excavated area and allow for 1st layer PCC Zone 8 |  | Grid M-T/12-14 | A | 2023-04-19
64 | Sub Structure | Basement | L2/66 | 2023-04-15 |  | Level, layout | Check level, layout of 1st layer PCC Top of footing and SOG Area Zone 8 |  | Grid M-T/8-14 | A | 2023-04-19
65 | Sub Structure | Basement | L2/67 | 2023-04-14 |  | Primer,membrane | Allow for primer and membrane Zone 8 |  | Grid J-M/8-12, L-M/13-14 | A | 2023-04-19
66 | Sub Structure | Basement | L2/68 | 2023-04-14 |  | Primer,membrane | Check Primer and membrane of SOG Area and allow for 2nd layer PCC Zone 8 |  | Grid J-L/8-14 | A | 2023-04-19
67 | Sub Structure | Basement | L2/69 | 2023-04-15 |  | Primer,membrane | Allor for primer and membrane of SOG Area Zone 8 |  | Grid M-T/8-14 | A | 2023-04-19
68 | Sub Structure | Basement | L2/70 | 2023-04-17 |  | Primer,membrane | Check primer and membrane of SOG Area and allow for 2nd layer PCC Zone 8 |  | Grid M/8-12, M-T/8-14 | A | 2023-04-19
69 | Sub Structure | Basement | L2/71 | 2023-04-18 |  | PCC | Check 2nd layer PCC Top and layout of columns Basement Zone 8 SOG |  | Grid M/8-12, M-T/8-14 | A | 2023-04-19
70 | Sub Structure | Basement | L2/72 | 2023-04-29 |  | PCC | Check 2nd layer PCC Top level and layout of SP2 (2 Nos) Zone 8 |  | Grid K-L/8-10, K-L/17-18 | A | 2023-05-08
71 | Sub Structure | Basement | L2/73 | 2023-05-01 |  | Raft | Check raft top level and layout of SP2 SOG Area Zone 8 SOG |  | Grid K-L/8-10 | A | 2023-05-08
72 | Sub Structure | Basement | L2/74 | 2023-05-02 |  | Steel fixing | Check steel fixing of wall of SP2 and allow for shuttering and concrete pouring Zone 8 |  | Grid K-L/8-10 | A | 2023-05-08
73 | Sub Structure | Basement | L2/75 | 2023-05-02 |  | Water stopper | Check water stopper in SP2 wall, Zone 8 |  | Grid K-L/8-10 | A | 2023-05-08
74 | Sub Structure | Basement | L2/76 | 2023-05-02 |  | Reinforcement | Check top and bottom raft steel reinforcement of SOG area and allow concrete Zone 8 |  | Grid K-L/8-10 | A | 2023-05-08
75 | Sub Structure | Basement | L2/77 | 2023-05-04 |  | Raft | Check top level and layout of SOG Area of columns and Sp2 zone 8 |  | Grid J-O/8-16 | A | 2023-05-08
76 | Sub Structure | Basement | L2/78 | 2023-05-04 |  | Water stopper | Check water stopper in SP2 wall, Zone 8 |  | Grid K-L/17-18 | A | 2023-05-08
77 | Sub Structure | Basement | L2/79 | 2023-05-04 |  | Steel fixing | Check steel fixing of wall of SP2 and allow for concrete pouring Zone 8 |  | Grid K-L/17-18 | A | 2023-05-08
78 | Sub Structure | Basement | L2/80 | 2023-05-06 |  | Reinforcement | Check top and bottom reinforcement of SOG Raft and allow for concrete pouring Zone 8 |  | Grid J-L/15-18, O-T/12-14 | A | 2023-05-08
79 | Sub Structure | Basement | L2/81 | 2023-05-06 |  | Water stopper | Check formwork and water stopper 52 Rft of SOG before pouring Zone 8 |  | Grid T/12-14 | A | 2023-05-08
80 | Sub Structure | Basement | L2/82 | 2023-05-08 |  | Level, layout | Check level, layout of columns on SOG Raft Zone 8 |  | Grid J-L/15-18, O-T/12-14 | A | 2023-05-08
81 | Sub Structure | Basement | L2/83 | 2023-05-11 |  | RW reinforcement | Check RW reinforcement Zone 8 |  | Grid T/12-14 | A | 2023-05-17
82 | Sub Structure | Basement | L2/84 | 2023-06-22 |  | RW reinforcement | Check RW reinforcement and allow for concrete pouring Zone 8 |  | Grid T/12-14 | A | 2023-07-12
83 | Sub Structure | Basement | L2/85 | 2023-06-23 |  | Layout | Checl layout of under Ground Water Tank for Domestic Zone 8 SOG |  | Grid T/12-14 | A | 2023-07-12
84 | Sub Structure | Basement | L2/86 | 2023-06-24 |  | Reinforcement | Check raft reinforcement of under ground water tank for domestic Zone 8 SOG |  | Grid T/12-15 | A | 2023-07-12
85 | Sub Structure | Basement | L2/87 | 2023-06-24 |  | Shuttering | Check shuttering of under ground water tank for domestic Zone 8 SOG |  | Grid T/12-15 | A | 2023-07-12
86 | Sub Structure | Basement | L2/88 | 2023-06-24 |  | Water stopper | Check horizontal and vertical water stopper on RTW Zone 8 |  | Grid T/12-14 | A | 2023-07-12
| Sub Structure | Basement | L2/89 | 2023-06-24 |  | excavation | Check excavation level of L2 Tower Zone 6 & 7 |  | Grid K-T/1-7, N-T/7-12 | A | 2023-08-16
| Sub Structure | Basement | L2/90 | 2023-08-11 |  | Surface preparation | Check surface preparation and allow for vertical primer and membrane upto (-5'-6'' Zone 6 & 7 |  | Grid T/12-14 | A | 2023-08-16
| Sub Structure | Basement | L2/91 | 2023-08-12 |  | Primer | Check vertical primer and membrane Zone 8 SOG Area |  | Grid T/12-14 | A | 2023-08-16
| Sub Structure | Basement | L2/92 | 2023-08-12 |  | Backfilling | Allow for Backfilling along RTW Zone 8 SOG Area |  | Grid T/12-14 | A | 2023-08-16
| Sub Structure | Basement | L2/93 | 2023-10-03 |  | Backfilling | Check backfilling of sand along RTW (-15'-3'' to -10'-9'') (6 layers) Zone 8 SOG |  | Grid T/12-14 | A | 2023-10-04
| Sub Structure | Basement | L2/94 | 2023-10-03 |  | Backfilling | Check backfilling of Sand along RTW (-10'-9'' to -6'-6'') (6 layers) Zone 8 SOG Area |  | Grid T/12-14 | A | 2023-10-04
87 | Sub Structure | Basement | L2/95 | 2023-10-03 |  | Termite proofing | Check termite proofing along RTW (-15'-3'' to -10'-9'') (6 layers) Zone 8 SOG |  | Grid T/12-14 | A | 2023-10-04
| Sub Structure | Basement | L2/96 | 2023-10-03 |  | Termite proofing | Check termite proofing along RTW ( -10'-9' to -6'-6'')') (6 layers) Zone 8 SOG |  | Grid T/12-14 | A | 2023-10-04
| Sub Structure | Basement | L2/97 | 2023-10-07 |  | column reinforcement | Check column (15 Nos) reinforcement Zone 8 SOG |  | Grid M-T/13-15 | A | 2023-10-11
| Sub Structure | Basement | L2/98 | 2023-10-09 |  | column reinforcement | Check columns (32 Nos) reinforcement Zone 8 SOG |  | Grid G-H/9-19, M/16, K-M/17-19 | A | 2023-10-11
| Sub Structure | Basement | L2/99 | 2023-10-09 |  | Thermopore | Check thermopore in expansion joint of columns (9 Nos) (-13'-3'' to 0'-0'') Zone 8 SOG |  | Grid N-P/15, G/15-19 | A | 2023-10-18
| Sub Structure | SOG | L2/100 | 2023-10-11 |  | column reinforcement | Check columns (12 Nos) reinforcement and allow for concrete pouring (-13'-3'' to 0'-0'') Zone 8 |  | Grid K-M/15-18 | A | 2023-10-18
| Sub Structure | SOG | L2/101 | 2023-10-11 |  | Thermopore | Check Thermopore in expansion joint of columns (6 Nos) (-13'-3'' to 0'-0'') Zone 8 SOG |  | Grid G/9-14-18 | A | 2023-10-18
| Sub Structure | Basement | L2/102 | 2023-10-12 |  | column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring Zone 8 SOG |  | Grid G-M/16-19 | A | 2023-10-18
| Sub Structure | Basement | L2/103 | 2023-10-12 |  | column reinforcement | Check column (10 Nos) reinforcement and allow for concrete pouring Zone 8 SOG (-13'-3'' to +0'-0'') |  | Grid G-H & M-Q/13-16 | A | 2023-10-18
| Sub Structure | Basement | L2/104 | 2023-10-14 |  | column reinforcement | Check column (21 Nos) reinforcement Zone 8 SOG Area (-13'-3'' to +0'-0'') |  | Grid K-M/8-14 | A | 2023-10-18
| Sub Structure | Basement | L2/105 | 2023-10-17 |  | column reinforcement | Check columns (6 Nos) reinforcement & allow for concrete pouring Zone 8 SOG (-13'-3'' to +0'-0'') |  | Grid G-H/14, K-L/13-14 | A | 2023-10-18
| Sub Structure | GF | L2/106 | 2023-10-18 |  | Beam reinforcement | Check beams reinforcement Zone 8 SOG |  | Grid G-M/13-19 | A | 2023-10-23
| Sub Structure | GF | L2/107 | 2023-10-18 | 2023-10-18 | Thermopore | Check thermopore Sheet along Beams Zone 8 SOG Area |  | Grid G-M/13-19 | A | 2023-10-23
| Sub Structure | GF | L2/108 | 2023-10-20 | 2023-10-20 | Reinforcement | Check slab top and bottom reinforcement Zone 8 SOG Area |  | Grid G-M/13-19 | A | 2023-10-23
| Sub Structure | GF | L2/109 | 2023-10-20 | 2023-10-20 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 8 SOG Area |  | Grid G-M/13-19 | A | 2023-10-23
| Sub Structure | Basement | L2/110 | 2023-10-20 | 2023-10-20 | column reinforcement | Check column (8 Nos) reinforcement and allow for concrete pouring Zone 8 SOG | (-13'-3'' to 0'-0'') | Grid G-H/13, L-M/12, R-T/13-14 | A | 2023-10-23
| Sub Structure | GF | L2/111 | 2023-10-21 | 2023-10-21 | Level, layout | Check level and layout of slab Zone 8 SOG Area | (+0'-00'') | Grid G-M/13-20 | A | 2023-11-02
| Sub Structure | GF | L2/112 | 2023-10-22 | 2023-10-22 | column reinforcement | Check column (3 Nos) reinforcement and allow for concrete pouring Zone 8 SOG Area | (-13'-3'' to 0'-0'') | Grid P-Q/15 | A | 2023-10-23
| Sub Structure | Basement | L2/113 | 2023-10-24 | 2023-10-24 | column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 8 SOG | (-13'-3'' to +0'-0'') | Grid G-K/12, G-H/11 | A | 2023-10-26
| Sub Structure | Basement | L2/114 | 2023-10-24 | 2023-10-24 | column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 8 SOG Area | (-13'-3'' to +0'-0'') | Grid G-M/10, K-L/11 | A | 2023-10-26
| Sub Structure | GF | L2/115 | 2023-10-25 | 2023-10-25 | column reinforcement | Check columns (12 Nos) reinforcement and allow for concrete pouring Zone 8 SOG Area | (-13'-3'' to +0'-0'') | Grid G-M/8-9, L-M/10 | A | 2023-10-26
| Sub Structure | GF | L2/116 | 2023-10-31 | 2023-10-31 | Beam reinforcement | Check beams reinforcement Zone 8 SOG Area | (+0'-00'') | Grid G-M/8-13 | A | 2023-11-08
| Sub Structure | GF | L2/117 | 2023-11-02 | 2023-11-02 | Slab reinforcement | Check top and bottom slab reinforcement Zone 8 SOG Area | (+0'-00'') | Grid G-M/9-14 | A | 2023-11-08
| Sub Structure | GF | L2/118 | 2023-11-02 | 2023-11-02 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 8 SOG Area | (+0'-00'') | Grid G-M/9-14 | A | 2023-11-08
| Sub Structure | GF | L2/119 | 2023-11-02 | 2023-11-02 | Thermopore | Check thermopore Sheet along Beams Zone 8 SOG Area | (+0'-00'') | Grid G/9-14 | A | 2023-11-08
| Sub Structure | Basement | L2/120 | 2023-11-06 | 2023-11-06 | wall reinforcement | check vertical wall reinforcement of under ground water tankd and allow for concrete pouring Z-8 SOG | (-13'-3'' to 10'') | Grid T/13-15 | A | 2023-11-08
| Sub Structure | Basement | L2/121 | 2023-11-03 | 2023-11-02 | wall reinforcement | Check vertical wall reinforcement of under ground water tank and allow for concrete pouring Z-8 |  | Grid T/15-13 | A | 2023-11-08
| Sub Structure | GF | L2/122 | 2023-11-03 | 2023-11-03 | Level, layout | Check level and layout of of Slab Zone 8 SOG Area | (+0'-00'') | Grid G-M/9-13 | A | 2023-11-03
| Sub Structure | GF | L2/123 | 2023-11-10 | 2023-11-10 | Beam reinforcement | Check beams reinforcement Zone 8 SOG Area | (+0'-00'') | Grid K-U/12-15 | A | 2023-11-11
| Sub Structure | GF | L2/124 | 2023-11-13 | 2023-11-12 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 8 SOG Area | (+0'-00'') | Grid K-U/12-14 | A | 2023-11-18
| Sub Structure | GF | L2/125 | 2023-11-13 | 2023-11-13 | Level, layout | Check level and layout of Slab Zone 8 SOG Area | (+0'-00'') | Grid K-U/12-14 | A | 2023-11-14
| Sub Structure | GF | L2/126 | 2023-11-12 | 2023-11-12 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 8 SOG Area | (+0'-00'') | Grid K-U/12-14 | A | 2023-11-18
| Sub Structure | GF | L2/127 | 2023-12-18 | 2023-12-18 | Beam reinforcement | Check top and bottom beam reinforcement Zone 8 Courtyard Area | (+0'-00'') | Grid G-N/7-8 | A | 2023-12-22
| Sub Structure | GF | L2/128 | 2023-12-19 | 2023-12-19 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 4 courtyard area | (+0'-00'') | Grid G-N/7-8 | A | 2023-12-27
| Sub Structure | GF | L2/129 | 2023-12-23 | 2023-12-23 | Slab level, layout | Check slab level and layout Zone 8 SOG Area | (+0'-00'') | Grid G-N/7-8 | A | 2023-12-27
| Sub Structure | Basement | L2/130 | 2024-03-06 | 2024-03-06 | Excavation | Check Trench excavation Zone 7 |  |  | OP
| Sub Structure | Basement | L2/131 | 2024-03-11 | 2024-03-11 | compaction | Check dressing and compaction of bed & allow for Anti termite proofing Zone 6 |  | Grid K-M/1-7, M-O/1-3, O-R/1-2 | A | 2024-03-15
| Sub Structure | Basement | L2/132 | 2024-03-11 | 2024-03-11 | Termite proofing | Check anti termite proofing & Allow for 1st layer of PCC Zone 6 |  | Grid K-M/1-7, M-O/1-3, O-R/1-2 | A | 2024-03-15
| Sub Structure | Basement | L2/133 | 2024-03-11 | 2024-03-11 | Excavation | Check excavated L |  | K-M/1-7, M-O/1-3, O-R/1-2 | A | 2024-03-14
| Sub Structure | Basement | L2/134 | 2024-03-12 | 2024-03-12 | PCC Layer | PCC Layer Zone 7 |  | K-M/1-7, M-O/1-3, O-R/1-2 | A | 2024-03-18
| Sub Structure | Basement | L2/135 | 2024-03-12 | 2024-03-12 | Brick work | Check brick work Zone 7 |  | Grid G-R/1 | A | 2024-03-14
| Sub Structure | Basement | L2/136 | 2024-03-13 | 2024-03-13 | Surface | Check top surface of PCC 1st layer and allow for membrane Zone 7 |  | Grid K-M/1-7, M-O/1-3, O-R/1-2 | A | 2024-03-13
| Sub Structure | Basement | L2/137 | 2024-03-13 | 2024-03-13 | sumpit | Check excavated level of sum pit Zone 6 |  | Grid R-S/8-9 | A | 2024-03-18
| Sub Structure | Basement | L2/138 | 2024-03-13 | 2024-03-13 | sumpit | Check compaction and dressing of sumpit SP1 along RTW and allow for PCC Zone 6 |  | Grid R-S/8-9 | A | 2024-03-18
| Sub Structure | Basement | L2/139 | 2024-03-13 | 2024-03-13 | level, layout | Check level and layout of sumpit 1st layer PCC Top Zone 6 |  | Grid R-S/8-9 | A | 2024-03-18
| Sub Structure | Basement | L2/140 | 2024-03-13 | 2024-03-13 | level, layout | Check level, layout of brick work along RTW & SP1 Zone 6 & 7 |  | Grid G-T/1 & R-S/8-9 | A | 2024-03-14
| Sub Structure | Basement | L2/141 | 2024-03-13 | 2024-03-13 | Lift wall | Check excavated level of Lift wall Zone 7 |  | Grid N-O/5-7 | A | 2024-03-18
| Sub Structure | Basement | L2/142 | 2024-03-13 | 2024-03-13 | Lift wall | Check dressing & compaction of lift wall & allow for Anti Termite proofing Zone 7 |  | Grid N-O/5-7 | A | 2024-03-18
| Sub Structure | Basement | L2/143 | 2024-03-13 | 2024-03-13 | Lift wall | Check dressing and compaction of lift wall & allow for PCC 1st layer proofing Zone 7 |  | Grid N-O/5-7 | A | 2024-03-18
| Sub Structure | Basement | L2/144 | 2024-03-13 | 2024-03-13 | Level | Check excavated area & level of L2 Tower Zone 6 & 7 |  | Grid P-Q/2-4, M-T/4-7, N-T/8-12 | A | 2024-03-18
| Sub Structure | Basement | L2/145 | 2024-03-13 | 2024-03-13 | compaction | Check compaction and dressing of bed and allow for termite proofing Zone 6 & 7 |  | Grid P-Q/2-4, M-T/4-7, N-T/8-12 | A | 2024-03-15
| Sub Structure | Basement | L2/146 | 2024-03-13 | 2024-03-13 | Termite proofing | Check anti termite proofing and allow for concrete pouring Zone 6 & 7 |  | Grid P-Q/2-4, M-T/4-7, N-T/8-12 | A | 2024-03-14
| Sub Structure | Basement | L2/147 | 2024-03-13 | 2024-03-13 | layout | Check level and layout of lift wall & PCC Top and allow for brick work Zone 7 |  | Grid N-O/5-7 | A | 2024-03-14
| Sub Structure | Basement | L2/148 | 2024-03-14 | 2024-03-14 | Plaster brick work | Check plaster of brick wall Zone 7 |  | Grid G-R/1 | A | 2024-03-18
| Sub Structure | Basement | L2/149 | 2024-03-14 | 2024-03-14 | primer&membrane | Check primer & membrane of horizontal vertical Zone 7 |  | Grid G-M/1, K-M/1-7 | A | 2024-03-18
| Sub Structure | Basement | L2/150 | 2024-03-14 | 2024-03-14 | membrane | Check membrane and allow for 2nd layer of PCC Zone 7 |  | Grid K-L/1-7 | A | 2024-03-18
| Sub Structure | Basement | L2/151 | 2024-03-14 | 2024-03-14 | brick work | Check brick work of sumpit and allow for plaster Zone 6 |  | Grid R-S/8-9 | A | 2024-03-18
| Sub Structure | Basement | L2/152 | 2024-03-14 | 2024-03-14 | PCC | Check PC level and allow for primer & membrane Zone 6 & 7 |  | Grid N-Q/9-12, N-P/4-9, P-R/3-4 | A | 2024-03-18
| Sub Structure | Basement | L2/153 | 2024-03-15 | 2024-03-15 | Surface preparation | Cehck surface preparation of chamfer and allow for PCC Zone 6 |  | Grid M/8-12, N-T/8-12 | A | 2024-03-18
| Sub Structure | Basement | L2/154 | 2024-03-15 | 2024-03-15 | PCC | Check 1st layer PCC Top and allow for primer and membrane Zone 6 |  | Grid R-T/4-12 | A | 2024-03-18
| Sub Structure | Basement | L2/155 | 2024-03-15 | 2024-03-16 | PCC | Check 2nd layer PCC top and allow for footings, columns and RTW Zone 7 |  | Grid J-M/1-7, M-N/1-4 | A | 2024-03-18
| Sub Structure | Basement | L2/156 | 2024-03-15 | 2024-03-15 | primer, membrane | Check Primer and membrane Zone 7 |  | Grid N-Q/1-2 | A | 2024-03-18
| Sub Structure | Basement | L2/157 | 2024-03-15 | 2024-03-15 | primer, membrane | Check primer, membrane and allow for 2nd PCC Zone 7 |  | Grid N-Q/1-2 | A | 2024-03-18
| Sub Structure | Basement | L2/158 | 2024-03-16 | 2024-03-16 | Primer, membrane | Check primer, membrane Zone 6 & 7 |  | Grid M-T/1-4, N-T/7-12 | A | 2024-03-22
| Sub Structure | Basement | L2/159 | 2024-03-16 | 2024-03-16 | Brick work | Check brick work of lift wall and allow for plaster Zone 7 |  | Grid N-P/5-7 | A | 2024-03-18
| Sub Structure | Basement | L2/160 | 2024-03-16 | 2024-03-18 | Service lift reinforcement | Check service lift reinforcement Zone 7 | (-22'-4'') | Grid H-J/3-4 | A | 2024-03-22
| Sub Structure | Basement | L2/161 | 2024-03-16 | 2024-03-18 | Reinforcement | check service lift reinforcement and allow for concrete pouring Zone 7 | (-22'-4'' to 18'-10'') | Grid H-J/3-4 | A | 2024-03-22
| Sub Structure | Basement | L2/162 | 2024-03-18 | 2024-03-18 | Raft | Check brick work of raft protection wall & allow for plaster Zone 7 |  | Grid R-T/1 | A | 2024-03-22
| Sub Structure | Basement | L2/163 | 2024-03-18 | 2024-03-18 | membrane | Check membrane & allow for PCC 2nd layer of main lift wall |  | Grid N-P/4-5 | A | 2024-03-22
| Sub Structure | Basement | L2/164 | 2024-03-18 | 2024-03-18 | Primber, membrane | Check primer & membrane of slope portion |  | Grid N-T/12, L-M/7 | A | 2024-03-22
| Sub Structure | Basement | L2/165 | 2024-03-19 | 2024-03-19 | Plaster | Check plaster and allow for vertical membrane raft protection wall |  | Grid R-T/1 | A | 2024-03-22
| Sub Structure | Basement | L2/166 | 2024-03-19 | 2024-03-19 | PCC | Check 2nd layer PCC level and layout and allow for steel fixing main lift |  | Grid N-P/4-6 | A | 2024-03-22
| Sub Structure | Basement | L2/167 | 2024-03-19 | 2024-03-19 | service lift | Check bed level of service lift and allow for formwork Zone 7 |  | Grid H-J/3-3 | A | 2024-03-26
| Sub Structure | Basement | L2/168 | 2024-03-20 | 2024-03-20 | Primer, membrane | Check primer, membrane of SP-1 and allow for 2nd layer PCC Zone 6 |  | Grid R-S/8-9 | A | 2024-03-22
| Sub Structure | Basement | L2/169 | 2024-03-20 | 2024-03-20 | formwork | Check service lift formwork |  | Grid H-J/3-3 | A | 2024-03-26
| Sub Structure | Basement | L2/170 | 2024-03-20 | 2024-03-20 | steel fixing | Check steel fixing of raft bottom & top steel & vertical steel of columns and walls |  | Grid G-K/1-8 | A | 2024-03-22
| Sub Structure | Basement | L2/171 | 2024-03-20 | 2024-03-20 | PCC | Check 2nd layer PCC, layout of columns, RW and Lift wall and allow for steel fixing Zone 6 & 7 |  | Grid N-Q, N-T/1-12 | A | 2024-03-26
| Sub Structure | Basement | L2/172 | 2024-03-20 | 2024-03-20 | excavation | Check excavation level and allow for termite proofing Zone 7 |  | Grid R-T/1-4 | A | 2024-03-26
| Sub Structure | Basement | L2/173 | 2024-03-20 | 2024-03-20 | Termite proofing | Check termite proofing and allow for 1st layer pcc Zone 7 |  | Grid R-T/1-4 | A | 2024-03-26
88 | Sub Structure | Basement | L2/174 | 2024-03-21 | 2024-03-21 | Water stopper, chicken mesh | Check water stopper & chicken mesh Zone 7 |  | Grid G-K/1, K/1-8 | A | 2024-03-26
89 | Sub Structure | Basement | L2/175 | 2024-03-21 | 2024-03-21 | Water bore, Motor placing | Check water bores and motor placing Zone 7 |  | Grid M/6 | A | 2024-04-02 |  |  |  |  | 2024-03-21
90 | Sub Structure | Basement | L2/176 | 2024-03-21 | 2024-03-22 | Lift well reinforcement | Check lift well reinforcement Zone 7 | (-22'-4'' to +8'-3'') | Grid N-P/5-7 | A | 2024-03-26
91 | Sub Structure | Basement | L2/177 | 2024-03-21 | 2024-03-22 | Lift well reinforcement | Check lift well reinforcement and allow for concrete pouring Zone 7 | (-22'-4 1/2 to -18'--10 1/2) | Grid N-P/5-7 | A | 2024-03-26
92 | Sub Structure | Basement | L2/178 | 2024-03-21 | 2024-03-21 | PCC Layout | Check 2nd PCC and layout and allow for steel fixing Zone 6 |  | Grid R-S/8-9 | A | 2024-03-26
93 | Sub Structure | Basement | L2/179 | 2024-03-21 | 2024-03-21 | membrane | Check 1st PCC and allow for membrane Zone 6 |  | Grid R-T/1-4 | A | 2024-03-26
94 | Sub Structure | Basement | L2/180 | 2024-03-21 | 2024-03-21 | Reinforcement | Check raft reinforcement and allow for concrete pouring Zone 7 |  | Grid G-K/1-8 | A | 2024-03-26
95 | Sub Structure | Basement | L2/181 | 2024-03-20 | 2024-03-20 | Termite proofing | Check termite and allow for PCC of chamfer strip & Horizontal area pouring Zone 7 |  | Grid R-T/1-4, M-T/8-12 | A | 2024-03-26
96 | Sub Structure | Basement | L2/182 | 2024-03-22 | 2024-03-22 | Primer | Check primer & membrane Zone 7 |  | Grid N-Q/2-4, R-T/1-4 | A | 2024-03-26
97 | Sub Structure | Basement | L2/183 | 2024-03-22 | 2024-03-22 | level, layout | Check level and layout of columns (12 Nos) & service lift of raft Zone 7 | (-13'-3'') | Grid G-K/1-7 | A | 2024-03-26
98 | Sub Structure | Basement | L2/184 | 2024-03-22 | 2024-03-22 | membrane | Check membrane and allow for 2nd PCC Zone 7 |  | Grid R-T/1-4 | A | 2024-03-26
99 | Sub Structure | Basement | L2/185 | 2024-03-24 | 2024-03-24 | Reinforcement | Check raft bottom reinforcement and top steel, vertical steel of c olumns |  | Grid K-M/1-7 | A | 2024-03-26
100 | Sub Structure | Basement | L2/186 | 2024-03-24 | 2024-03-25 | Reinforcement | Check raft bottom reinforcement & top steel & vertical steel of columns & RTW and allow for concrete pouring |  | Grid K-M/1-7 | A | 2024-04-02
101 | Sub Structure | Basement | L2/187 | 2024-03-23 | 2024-03-23 | level, layout | Check level & layout of lift bed and allow for formwork Zone 7 |  | Grid N-P/5-7 | A | 2024-03-26
102 | Sub Structure | Basement | L2/188 | 2024-03-23 | 2024-03-23 | PCC, lvel | Check level and 2nd PCC top & layout of raft footings and allow for steel fixing Zone 6 & 7 |  | Grid R-T/1-4, R-T/1-8 | A | 2024-03-26
103 | Sub Structure | Basement | L2/189 | 2024-03-25 | 2024-03-25 | column reinforcement | Check columns (12 Nos) and service lift reinforcement Zone 7 |  | Grid G-K/1-7 | A | 2024-03-26
104 | Sub Structure | Basement | L2/190 | 2024-03-25 | 2024-03-25 | water stopper | Check water stopper in RTW and chicken mesh in Raft Zone 7 |  | Grid K-M/1, K-M/1-7 | A | 2024-03-26
105 | Sub Structure | Basement | L2/191 | 2024-03-23 | 2024-03-23 | Earthing Bore | Check earting bore (9 Nos) as per shop drawing Zone 6 & 7 |  |  | A | 2024-03-23
106 | Sub Structure | Basement | L2/192 | 2024-03-26 | 2024-03-26 | Reinforcement | Check sumpit reinforcement Zone 6 |  | Grid R-S/8-9 | A | 2024-04-02
107 | Sub Structure | Basement | L2/193 | 2024-03-26 | 2024-03-26 | Reinforcement | Check sumpit reinforcement and allow for concrete pouring Zone 6 |  | Grid R-S/8-9 | A | 2024-04-02
108 | Sub Structure | Basement | L2/194 | 2024-03-26 | 2024-03-26 | level, layout | Checkl level & layout of columns & RTW Zone 7 | (-13'-3'') | Grid K-M/1-7 | A | 2024-04-02
109 | Sub Structure | Basement | L2/195 | 2024-03-27 | 2024-03-27 | level, layout | Check level and layout of sumpit bed & allow for formwork Zone 6 |  | Grid R-S/8-9 | A | 2024-04-02
110 | Sub Structure | Basement | L2/196 | 2024-03-27 | 2024-03-27 | raft reinforcement | Check Bottom and Top raft reinforcement & vertical dowels of columns & RTW Zone 7 |  | Grid M-T/1-3 | A | 2024-04-02
111 | Sub Structure | Basement | L2/197 | 2024-03-27 | 2024-03-28 | raft reinforcement | Check raft reinforcement and allow for concrete pouring Zone 7 |  | Grid M-T/1-2 | A | 2024-04-02
112 | Sub Structure | Basement | L2/198 | 2024-03-27 | 2024-03-27 | raft formwork | Check raft formwork Zone 7 |  | Grid T/1-7 | A | 2024-04-02
113 | Sub Structure | Basement | L2/199 | 2024-03-28 | 2024-03-28 | Chicken Mesh | Check chicken mesh & water stopper Zone 7 |  | Grid M-T/1&2, M-T/2 | A | 2024-04-02
114 | Sub Structure | Basement | L2/200 | 2024-03-30 | 2024-03-30 | formwork | Check lift wall formwork and raft protection Zone 6 & 7 |  | Grid T/7-12, N-P/5-7 | A | 2024-04-01
115 | Sub Structure | Basement | L2/201 | 2024-03-30 | 2024-03-30 | copper condutor | Check DDE Execution , laying of Bare copper condutor of 95 mm & 70 mm, & Thermoweld joints Z6-7 |  |  | B | 2024-04-01
116 | Sub Structure | Basement | L2/202 | 2024-03-30 | 2024-03-30 | raft reinforcement | Check raft reinforcement, top & vertical dowels Zone 6 & 7 |  | Grid M-T/3-8 | A | 2024-04-01
117 | Sub Structure | Basement | L2/203 | 2024-03-30 | 2024-03-30 | water stopper | Check water stopper (RTW) & Chicken mesh in raft Zone 6 & 7 |  | Grid R/2-8, R-T/8 | A | 2024-04-01
118 | Sub Structure | Basement | L2/204 | 2024-03-30 | 2024-03-31 | Reinforcement | Check raft reinforcement and allow for concrete pouring Zone 6 & 7 |  | Grid R-T/2-8 | A | 2024-04-01
119 | Sub Structure | Basement | L2/205 | 2024-03-30 | 2024-03-30 | level, layout | Check level layout of raft, columns & RTW Zone 7 |  | Grid M-T/1-2 | A | 2024-04-05
120 | Sub Structure | Basement | L2/206 | 2024-04-01 | 2024-04-01 | raft reinforcement | Check raft reinforcement and allow for concrete pouring Zone 6 & 7 |  | Grid M-R/2-8 | A | 2024-04-05
121 | Sub Structure | Basement | L2/207 | 2024-04-01 | 2024-04-01 | Chicken Mesh | Check Chicken Mesh in raft Zone 6 |  | Grid M-R/8 | A | 2024-04-02
122 | Sub Structure | Basement | L2/208 | 2024-04-01 | 2024-04-01 | raft reinforcement | Check raft reinforcement, top and verticals dowels of columns & RTW, wall footing Zone 6 |  | Grid Q-T/8-12 | A | 2024-04-05
123 | Sub Structure | Basement | L2/209 | 2024-04-01 | 2024-04-01 | level, layout | Check level , layout of Raft, columns & RTW Zone 6 & 7 |  | Grid S-T/2-8 | A | 2024-04-05
124 | Sub Structure | Basement | L2/210 | 2024-04-02 | 2024-04-02 | water stopper | Check water stopper in RTW and chicken mesh in raft Zone 6 |  | Grid Q-S/8-12, T/8-12 | A | 2024-04-05
125 | Sub Structure | Basement | L2/211 | 2024-04-02 | 2024-04-02 | raft reinforcement | Check raft reinforcement and allow for concrete pouring Zone 6 & 7 |  | Grid Q-S/8-9, S-T/9-12 | A | 2024-04-05
126 | Sub Structure | Basement | L2/212 | 2024-04-02 | 2024-04-02 | SP formwork | Check SP1 Zone 6 |  | Grid R-S/8-9 | A | 2024-04-05
127 | Sub Structure | Basement | L2/213 | 2024-04-02 | 2024-04-02 | raft reinforcement | Check raft bottom reinforcement, Top & verticals dowels of columns, SW Zone 6 |  | Grid M-Q/8-12 | A | 2024-04-05
128 | Sub Structure | Basement | L2/214 | 2024-04-03 | 2024-04-03 | raft reinforcement | Check raft reinforcement and allow for concrete pouring Zone 6 |  | Grid M-Q/8-12, Q-S/9-12 | A | 2024-04-22
129 | Sub Structure | Basement | L2/215 | 2024-04-03 | 2024-04-03 | Chicken Mesh | Check Chicken Mesh in Raft Zone 6 |  | Grid M-S/10 | A | 2024-04-05
130 | Sub Structure | Basement | L2/216 | 2024-04-03 | 2024-04-03 | level, layout | Check Raft level & layout of lift walls, columns, ramp & stair dowels, SP1 & RTW Zone 6 & 7 |  | Grid M-S/2-8, R-T/8-12 | A | 2024-04-22
131 | Sub Structure | Basement | L2/217 | 2024-04-05 | 2024-04-05 | column reinforcement | Check column (8 Nos) , RTW & Lift wall reinforcement Zone 7 |  | Grid G-N/1, L-M/1-7, N-P/5-7 | A | 2024-04-22
132 | Sub Structure | Basement | L2/218 | 2024-04-05 | 2024-04-05 | level, layout | Check level of raft, layout of columns Shear walls Zone 6 |  | Grid N-Q/8-12, Q-S/10-12 | A | 2024-04-22
133 | Sub Structure | Basement | L2/219 | 2024-04-22 | 2024-04-22 | condute UPVC | Check condute UPVC D class 32 mm in lift & column Zone 7 | (-13'-3'' to +1'-9'') | Grid N/7, O/1 | A | 2024-05-04
134 | Sub Structure | Basement | L2/220 | 2024-04-23 | 2024-04-23 | Thermopore | Check thermopore sheet in joint columns Zone 7 | (-13'-3'' to +1'-9'') | Grid F/1-7 | OP
135 | Sub Structure | Basement | L2/221 | 2024-04-29 | 2024-04-29 | column reinforcement | Check columns (13 Nos) reinforcement &: RTW Zone 6 & 7 | (-13'-3'' to +1'-9'') | Grid N-T/1, T/1-12, N-T/1-7 | A | 2024-05-04
136 | Sub Structure | Basement | L2/222 | 2024-05-07 | 2024-05-07 | column reinforcement | Check columns (22 Nos) reinforcement Zone 6 | (-13'-3'' to +1'-9'') | Grid N-T/8-12 | A | 2024-05-16
137 | Sub Structure | Basement | L2/223 | 2024-05-20 | 2024-05-20 | column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (-13'-3'' to +1'-9'') | Grid T/1-11, Q-S/1 | A | 2024-05-22
138 | Sub Structure | Basement | L2/224 | 2024-05-22 | 2024-05-21 | column reinforcement | Check columns (11 Nos) & allow for concrete pouring Zone 7 | (-13'-3'' to +1'-9'') | Grid G-P/1, L-M/7 | A | 2024-05-22
139 | Sub Structure | Basement | L2/225 | 2024-05-22 | 2024-05-22 | column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (-13'-3'' to +1'-9'') | Grid G/3, H-K/7, N/10, S-U/12 | A | 2024-05-29
140 | Sub Structure | Basement | L2/226 | 2024-05-23 | 2024-05-23 | column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (-13'-3'' to +1'-9'') | Grid G-H/5, K/3, N/12, S/12 | A | 2024-05-29
141 | Sub Structure | Basement | L2/227 | 2024-05-24 | 2024-05-24 | Thermopore | Check Thermopore in columns (4 Nos) Zone 6 | (-13'-3'' to +1'-9'') | Grid N-U/12 | A | 2024-05-29
142 | Sub Structure | Basement | L2/228 | 2024-05-24 | 2024-05-24 | column reinforcement | Check columns (3) reinforcement and allow for concrete pouring Zone 6 & 7 | (-13'-3'' to +1'-9'') | Grid G/7, P/12, U/12 | A | 2024-05-29
143 | Sub Structure | Basement | L2/229 | 2024-05-25 | 2024-05-25 | column reinforcement | Check columns (4 No) reinforcment and allow for concrete pouring Zone 6 & 7 | (-13'-3'' to +1'-9'') | Grid K/5, L/3, N/11-12, P/12 | A | 2024-05-29
144 | Sub Structure | Basement | L2/230 | 2024-05-27 | 2024-05-27 | column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (-13'-3'' to +1'-9'') | Grid L/5, N/9, P-R/10, P/11 | A | 2024-05-29
145 | Sub Structure | Basement | L2/231 | 2024-05-29 | 2024-05-28 | column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (-13'-3'' to +1'-9'') | Grid R/11, P-R/9, N/8, M/5 | A | 2024-06-05
146 | Sub Structure | basement | L2/232 | 2024-05-31 | 2024-05-30 | column reinforcement | Check columns (3 Nos) reinforcement and allow for concrete pouring Zone 7 | (-13'-3'' to +1'-9'') | Grid M/3, P-R/3 | A | 2024-06-03
147 | Sub Structure | basement | L2/233 | 2024-06-03 | 2024-06-01 | column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (-13'-3'' to +1'-9'') | Grid P-R/8, R/5-7 | A | 2024-06-07
148 | Sub Structure | basement | L2/234 | 2024-06-03 | 2024-06-02 | RTW reinforcement | Check RTW reinforcement and water stopper & allow for conrete pouring Zone 6 & 8 | (-13'-3'' to +1'-9'') | Grid T/10-13 | A | 2024-06-07
149 | Sub Structure | basement | L2/235 | 2024-06-05 | 2024-06-05 | RTW reinforcement | Check RTW reinforcement and water stopper & allow for concrete pouring Zone 6 | (-13'-3'' to +1'-9'') | Grid T/7-110 | A | 2024-06-12
150 | Sub Structure | basement | L2/236 | 2024-06-08 | 2024-06-08 | water stopper | Check RTW reinforcement and water stopper and allow for concrete pouring Zone 7 | (-13'-3'' to +1'-9'') | Grid T/2-7 | A | 2024-06-12
151 | Sub Structure | basement | L2/237 | 2024-06-11 | 2024-06-11 | ramp, beam reinforcement | Check ramp salab & beam reinforcement Zone 6 & 7 |  | Grid Q-S/6-12 | A | 2024-06-12
152 | Sub Structure | basement | L2/238 | 2024-06-11 | 2024-06-11 | water stopper | Check RTW reinforcement and water stopper & allow for concrete pouring Zone 7 | (-13'-3'' to +1'-9'') | Grid T/1, T/1-2 | A | 2024-06-12
153 | Sub Structure | basement | L2/239 | 2024-06-12 | 2024-06-11 | Reinforcement | Check reinforcement and allow for concrete pouring ramp slab & beam Zone 6 & 7 |  | Grid P-R/6-12 | A | 2024-06-14 | Not scanned
154 | Sub Structure | basement | L2/240 | 2024-06-12 | 2024-06-12 | level, layout | Check level & layout ramp slab & beam Zone 6 & 7 |  | Grid P-R/6-12 | A | 2024-06-14
| Sub Structure | basement | L2/241 | 2024-06-13 | 2024-06-13 | RTW reinforcement | Check RTW reinforcement and water stopper & allow for concrete pouring Zone 7 |  | Grid Q-T/1 | A | 2024-06-14
| Sub Structure | basement | L2/242 | 2024-06-13 | 2024-06-13 | ramp beam reinforcement | Check beam reinforcement & allow for concrete pouring Zone 6 |  | Grid Q-S/6-11 | A | 2024-06-27
| Sub Structure | basement | L2/243 | 2024-06-26 | 2024-06-26 | Level, layout | Check level & layout of UGWT Zone 6 |  | Grid T/5, T/12 | A | 2024-07-01
| Sub Structure | basement | L2/244 | 2024-06-29 | 2024-06-29 | slab, beam reinforcement | Check beam & slab top and bottom reinforcement Zone 8 SOG Area |  | Grid M-U/12-13 | A | 2024-07-01
| Sub Structure | basement | L2/245 | 2024-06-29 | 2024-06-30 | slab, beam reinforcement | Check slab and beam top and bottom reinforcement Zone 8 SOG Area |  | Grid M-U/12-13 | A | 2024-07-01
| Sub Structure | basement | L2/246 | 2024-07-01 | 2024-07-01 | slab level | Check top level of slab Zone 8 SOG Area | 0 | Grid M-U/12-13 | A | 2024-07-01
| Sub Structure | basement | L2/247 | 2024-06-30 | 2024-06-30 | RTW reinforcement | Check RTW reinforcement and water stopper and allow for concrete pouring Zone 7 |  | Grid L-Q/1 | A | 2024-07-01
| Sub Structure | basement | L2/248 | 2024-07-02 | 2024-07-02 | Reinforcement | Check Lift reinforcement & allow for concrete pouring Zone 7 | (-13'-3'' to +0.00) | Grid H-J/3-4 | A | 2024-07-02
| Sub Structure | basement | L2/249 | 2024-07-04 | 2024-07-04 | Thermopore | Check Thermopore Sheet along beams Zone 6 | (+0'-0'') | Grid N/8-12, N-U/12 | A | 2024-07-04
| Sub Structure | basement | L2/250 | 2024-07-04 | 2024-07-05 | Slab reinforcement | Check slab top and bottom reinforcement Zone 6 |  | Grid N-U/8-12 | A | 2024-07-08
| Sub Structure | basement | L2/251 | 2024-07-05 | 2024-07-05 | Slab reinforcement | Check slab rienforcement and allow for concrete pouring Zone 6 |  | Grid N-U/8-12 | A | 2024-07-08
| Sub Structure | basement | L2/252 | 2024-07-05 | 2024-07-05 | column reinforcement | Check columns (6 Nos) reinforcement and allow for concrete pouring Zone 6 |  | Grid S/7-8-9, Q/8-10 | A | 2024-07-08
| Sub Structure | basement | L2/253 | 2024-07-05 | 2024-07-05 | RTW reinforcement | Check RTW reinforcement, water stopper & thermopore sheet in RTW and Allow for concrete pouring Zone 7 | (-13'-3'' to +00'') | Grid G-L/1 | A | 2024-07-08
| Sub Structure | basement | L2/254 | 2024-07-06 | 2024-07-06 | layout | Check level, layout of slab & column Zone 6 | (+00) | Grid S-U/8-12 | A | 2024-07-08
| Sub Structure | basement | L2/255 | 2024-07-07 | 2024-07-07 | level, layout | Check level & layout of slab, columns & SW-08 Zone 6 | (+00) | Grid N-Q/8-12, Q-S/8-8 | A | 2024-07-08
| Sub Structure | basement | L2/256 | 2024-07-08 | 2024-07-08 | lift reinforcement | Check lift walls reinforcement and allow for concrete pouring Zone 7 | (-13'-3'' to +00'') | Grid N-Q/5-7 | A | 2024-07-10
| Sub Structure | basement | L2/257 | 2024-07-08 | 2024-07-08 | Beam reinforcement | Check beam reinforcement Zone 7 | (+00 & +1'-9'') | Grid G-N/1-7 | A | 2024-07-10
| Sub Structure | basement | L2/258 | 2024-07-08 | 2024-07-09 | Slab reinforcement | Check top and bottom slab reinforcement Zone 7 | (+00 & +1'-9'') | Grid G-N/1-7 | A | 2024-07-10
| Sub Structure | basement | L2/259 | 2024-07-08 | 2024-07-09 | Thermopore sheet | Check Thermopore sheet in expansion joints Zone 7 | (+00 & +1'-9'') | Grid G/1-7, G-N/7 | A | 2024-07-10
| Sub Structure | basement | L2/260 | 2024-07-08 | 2024-07-08 | ramp beam reinforcement | Check beam & ramp beam & allow for concrete pouring Zone 6 | (+00 & +1'-9'') | Grid Q-S/8, S/8-12 | A | 2024-07-10
| Sub Structure | basement | L2/261 | 2024-07-09 | 2024-07-09 | Slab reinforcement | Check slab reinforcement & allow for concrete pouring Zone 7 | (+00'') | Grid G-N/1-3 | A | 2024-07-10
| Sub Structure | basement | L2/262 | 2024-07-10 | 2024-07-10 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 7 | (+1'-9'') | Grid G-J/1-7, J-M/3-7 | A | 2024-07-20
| Sub Structure | basement | L2/263 | 2024-07-10 | 2024-07-10 | level, layout | Check level, layout of slab & columns Zone 7 | (+00') | Grid G-N/1-3 | B | 2024-07-10
| Sub Structure | basement | L2/264 | 2024-07-11 | 2024-07-11 | level, layout | Check level & layout of slab columns & service lift Zone 7 | (+1'-9'') | Grid G-J/1-7, J-M/3-7 | A | 2024-07-18
| Sub Structure | basement | L2/265 | 2024-07-12 | 2024-07-12 | level, layout | Check level & layout of stair ST-02 Zone 7 |  | Grid N-Q/6-7 | A | 2024-07-18
| Sub Structure | basement | L2/266 | 2024-07-13 | 2024-07-13 | Beam reinforcement | Check beam reinforcement Zone 7 | (-13'-3'' to +1'-9'') | Grid N-U/1-7 | A | 2024-07-18
| Sub Structure | basement | L2/267 | 2024-07-13 | 2024-07-13 | Slab reinforcement | Check top & bottom slab reinforcement Zone 7 | (+0'-00'') | Grid N-Q/1-1, Q-S/1, S-U/1-7 | A | 2024-07-18
| Sub Structure | basement | L2/268 | 2024-07-13 | 2024-07-14 | Slab reinforcement | Check slab reinforcement & allow for concrete pouring Zone 7 | (+0'-00'') | Grid N-Q/1-1, Q-S/1, S-U/1-7 | A | 2024-07-20
| Sub Structure | basement | L2/269 | 2024-07-13 | 2024-07-13 | formwork, reinforcement | Cehck formwork & reinforcement of stair ST-02 & allow for concrete pouring Zone 7 |  | Grid N-Q/6-7 | A | 2024-07-20
| Sub Structure | basement | L2/270 | 2024-07-13 | 2024-07-15 | Slab reinforcement | Check top and bottom slab reinforcement Zone 7 | (+1'-9'') | Grid N-S/2-7 | A | 2024-07-18
| Sub Structure | basement | L2/271 | 2024-07-13 | 2024-07-15 | Slab reinforcement | Check slab reinforcement & allow for concrete pouring Zone 7 | (+1'-9'') | Grid N-S/2-7 | A | 2024-07-20
| Sub Structure | basement | L2/272 | 2024-07-15 | 2024-07-15 | level, layout | Check level & layout of columns & slab Zone 7 | (+0'-00'') | Grid N-Q/1-1, Q-S/1, S-U/1-7 | A | 2024-07-20
| Sub Structure | basement | L2/273 | 2024-07-16 | 2024-07-16 | level, layout | Check level & layout of columns & slab, lift walls Zone 7 | (+1'-9'') | Grid N-Q/3-7, Q-S/1-7 | A | 2024-07-20
| Sub Structure | basement | L2/274 | 2024-07-16 | 2024-07-16 | stair reinforcement | Check formwork & reinforcement of stair & allow for concrete pouring Zone 7 | (-4.47'-+1'-9'') | Grid N-Q/6-7 | A | 2024-07-20
| Sub Structure | basement | L2/275 | 2024-07-16 | 2024-07-16 | level, layout | Check level & layout of stair ST-02 Zone 7 | (-4.47' to +1'-9'') | Grid N-Q/6-7 | A | 2024-07-20
| Sub Structure | basement | L2/276 | 2024-07-18 | 2024-07-19 | column reinforcement | Check columns (8 Nos) reinforcement Zone 7 | (+1'-9'' to +18'-9'') | Grid S/10-12, U/8-12 | A | 2024-07-20
| Sub Structure | basement | L2/277 | 2024-07-19 | 2024-07-20 | column reinforcement | Check columns (6 Nos) reinforcement & SW-08 (2 Nos) reinforcement Zone 6 | (+1'-9'' to +18'-9'') | Grid N-Q/8-12, S/8-9 | A | 2024-07-23
| Sub Structure | basement | L2/278 | 2024-07-20 | 2024-07-20 | column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 6 | (+0-0 to +18-9) | Grid U/8-12 | A | 2024-07-29
| Sub Structure | basement | L2/279 | 2024-07-20 | 2024-07-20 | column reinforcement | Check columns (12 Nos) reinforcement Zone 6 & 7 | (+1-9 to +18-9) | Grid G-H/1-7, J/1, N-Q/8-9 | A | 2024-07-23
| Sub Structure | basement | L2/280 | 2024-07-22 | 2024-07-21 | column reinforcement | Check columns (11 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (+1-9 to +18-9) | Grid S/10-12, S/8, N/12, G/1, G/5-7, H/1, H/7, J/1 | A | 2024-07-23
| Sub Structure | basement | L2/281 | 2024-07-22 | 2024-07-22 | lift reinforcement | Check lift wall reinforcement Zone 7 | (+1-9 to +18-9) | Grid N-Q/5-7 | A | 2024-07-23
| Sub Structure | basement | L2/282 | 2024-07-22 | 2024-07-22 | column reinforcement | Check columns (8 Nos) reinforcement Zone 7 | (+0'-00'' to +1'-9'' to +18'-9'') | Grid K-M/1&7, P-Q/1 | A | 2024-07-23
| Sub Structure | basement | L2/283 | 2024-07-23 | 2024-07-22 | column reinforcement | Check columns (11 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (+1'-9'' to +18'-9'') | Grid H/3, K-L/7, N/9-10, Q/11, S/9, U/9-12 | A | 2024-07-23
| Sub Structure | basement | L2/284 | 2024-07-23 | 2024-07-23 | column reinforcement | Check columns (10 Nos) reinforcement Zone 7 | (+0-00'' to +1'-9'') | Grid K-N/3, R-U/1, U/3-6 | B | 2024-07-26
| Sub Structure | basement | L2/285 | 2024-07-23 | 2024-07-23 | condute UPVC | Check conduit UPVC D class in lift & column, Zone 7 | (+1'-9'' to +18'-9'') | Grid N/7, O/1 | A | 2024-07-23
| Sub Structure | basement | L2/286 | 2024-07-24 | 2024-07-24 | column reinforcement | check column (7 Nos) and service lift reinforcement Zone 7 | (+0'-00'' to +1'-9'') | Grid H-J/3-4, K-S/5, Q-S/3, S/7 | A | 2024-07-26
| Sub Structure | basement | L2/287 | 2024-07-24 | 2024-07-23 | column reinforcement | Check columns (6 Nos) column for reinforcement and allow for concrete pouring Zone 6 & 7 | (+1'-9'' to +18'-9'') | Grid N/9-10, N&S/12, N/8, M/1, K-L/1, H/5, G/3 | A | 2024-07-26
| Sub Structure | basement | L2/288 | 2024-07-24 | 2024-07-24 | column reinforcement | Check column (12 Nos) ande SW-08 (1) reinforcement and allow for concrete pouring Zone 6 & 7 | (+1'-9'' to +18'-9'') | Grid P-R/1, N/3, M/3-5, Q/9-10,12, G-K/7, G/5 | A | 2024-07-26
| Sub Structure | GF to 1st Floor | L2/289 | 2024-07-26 | 2024-07-25 | column reinforcement | Check columns (12 Nos) and SW-8 (1 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (+1'-9'' to +18'-9'') | Grid N/11, Q/8, S/5-7, G-P/1, L-M/7 | A | 2024-07-30
| Sub Structure | Basement to GF | L2/290 | 2024-07-26 | 2024-07-26 | raft foundation | Check UGWT for domestic raft foundation and walls reinforcement Zone 6 & 7 | (-13'-3'' to +0'-00'') | Grid T/5-12 | A | 2024-07-30
| Sub Structure | basement | L2/291 | 2024-07-26 | 2024-07-26 | level, layout | Check leve, layout of UGWT for septic Zone 1-7 | (-13'-3'') | Grid F-K/1 | A | 2024-07-30
| Sub Structure | basement | L2/292 | 2024-07-27 | 2024-07-27 | level, layout | Check level & layout of UGWT for rain harvesting tank Zone 7 | (-13'-3'') | Grid M-T/1 | A | 2024-07-29
| Sub Structure | basement | L2/293 | 2024-07-27 | 2024-07-27 | formwork, reinforcement | check formwork, reinforcement & water stopper of UGWT for domestic & allow for concrete pouring Zone 7 & 8 | (-13'-3'') | Grid T/5-12 | A | 2024-07-29
| Sub Structure | GF to 1st Floor | L2/294 | 2024-07-27 | 2024-07-26 | column reinforcement | Check columns (13 Nos) and allow for concrete pouring Zone 7 | (+1'-9'' to +18'-9'') | Grid M/3-5, N/3, Q-R/1, L/3-5, Q/3, T/1, U/1-6 | A | 2024-07-30
| Sub Structure | basement | L2/295 | 2024-07-28 | 2024-07-28 | level, layout | Check level, layout of UGWT for domestic Zone 7 & 8 | (-13'-3'') | Grid T/5-12 | A | 2024-07-31
| Sub Structure | GF to 1st Floor | L2/296 | 2024-07-29 | 2024-07-27 | column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring Zone 7 | (+1'-9'' to +18'-9'') | Grid U/3-5, K/3 | A | 2024-07-31
| Sub Structure | GF to 1st Floor | L2/297 | 2024-07-29 | 2024-07-28 | column reinforcement | Check columns (2 Nos) and allow for concrete pouring Zone 7 | (+1'-9'' to +18'-9'') | Grid K/3-5 | A | 2024-07-31
| Sub Structure | GF | L2/298 | 2024-07-29 | 2024-07-15 | level, layout | Check formwork and concrete also check level, layout Zone 7 | (+1'-9'') | Grid Q-S/1 | A | 2024-07-31
| Sub Structure | Raft to GF | L2/299 | 2024-07-29 | 2024-07-29 | raft | Check UGWT for septic raft foundation and walls reinforcement Zone 1 & 7 | (-13'-3'' to +10'-00'') | Grid F-K/1 | A | 2024-08-03
| Sub Structure | Raft to GF | L2/300 | 2024-07-29 | 2024-07-29 | rain harvesting | Check UGWT for rain harvesting raft foundation and walls reinforcement Zone 7 | (-13'-3'' to +10'-00'') | Grid M-T/1 | A | 2024-08-03
| Sub Structure | GF to 1st Floor | L2/301 | 2024-07-30 | 2024-07-29 | lift reinforcement | Check Lift wall reinforcement & allow to start concrete work Zone 7 | (+1'-9'' to +18'-9'') | Grid N-Q/5-7 | A | 2024-07-31
| Sub Structure | GF to 1st Floor | L2/302 | 2024-07-31 | 2024-07-30 | lift reinforcement | Check service lift reinforcement and allow for concrete pouring Zone 7 | (+1'-9'' to +18'-9'') | Grid H-J/3-4 | A | 2024-08-03
| Sub Structure | GF to 1st Floor | L2/303 | 2024-07-31 | 2024-07-30 | column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring Zone 7 | (+1'-9'' to +18'-9'') | Grid T-U/1, Q/3, S/3 | A | 2024-08-03
| Sub Structure | 1st floor | L2/304 | 2024-08-02 | 2024-08-02 | steel fixing | Check steel fixing of beam Zone 6 | (+18'-9'') | Grid N-U/7-12 | A | 2024-08-05
| Sub Structure | 1st floor | L2/305 | 2024-08-03 | 2024-08-04 | Steel fixing | Check steel fixing of slab top and bottom Zone 6 | (+18'-9'') | Grid N-U/7-12 | A | 2024-08-05
| Sub Structure | 1st floor | L2/306 | 2024-08-05 | 2024-08-04 | steel fixing | Check steel fixing of slab and allow for concrete pouring Zone 6 | (+18'-9'') | Grid N-U/7-12 | A | 2024-08-07
| Sub Structure | 1st floor | L2/307 | 2024-08-05 | 2024-08-05 | level, layout | Check level & layout of slab, columns shear walls Zone 6 | (+18'-9'') | Grid N-U/7-12 | A | 2024-08-07
| Sub Structure | 1st floor | L2/308 | 2024-08-05 | 2024-08-05 | steel fixing | Check steel fixing of beam Zone 7 | (+18'-9'') | Grid G-M/1-7 | A | 2024-08-07
| Sub Structure | 1st to 2nd floor | L2/309 | 2024-08-05 | 2024-08-05 | steel fixing | Check steel fixing of columns (4 Nos) Zone 6 | (+18'-9'' to +29'-9'') | Grid U/8-12 | A | 2024-08-07
| Sub Structure | 1st to 2nd floor | L2/310 | 2024-08-06 | 2024-08-06 | steel fixing | Check steel fixing of columns (5 Nos) Zone 6 | (+18'-9'' to +29'-9'') | Grid S/8-12 | A | 2024-08-07
| Sub Structure | 1st to 2nd floor | L2/311 | 2024-08-06 | 2024-08-06 | steel fixing | Check steel fixing of columns (4 Nos) Zone 6 | (+18'-9'' to +29'-9'') | Grid Q/8-11 | A | 2024-08-07
| Sub Structure | 1st to 2nd floor | L2/312 | 2024-08-07 | 2024-08-06 | steel fixing | Check steel fixing of columns (5 Nos) & allw for concrete pouring Zone 6 | (+18'-9'' to +29'-9'') | Grid U/8-11 | A | 2024-08-07
| Sub Structure | 1st to 2nd floor | L2/313 | 2024-08-07 | 2024-08-07 | steel fixing | Check steel fixing of columns (4 Nos) & SW-8 (02 Nos) Zone 6 | (+18'-9'' to +29'-9'') | Grid N-Q/8-12 | A | 2024-08-13
| Sub Structure | 1st floor | L2/314 | 2024-08-07 | 2024-08-07 | steel fixing | Check steel fixing of slab top and bottom Zone 7 | (18'-9'') | Grid G-M/1-7 | A | 2024-08-13
| Sub Structure | 1st to 2nd floor | L2/315 | 2024-08-07 | 2024-08-07 | steel fixing | Check steel fixing of columns (3 Nos) & allow for concrete pouring | (+18'-9'' to +29'-9'') | Grid S/10-12 | A | 2024-08-07
| Sub Structure | 1st floor | L2/316 | 2024-08-08 | 2024-08-07 | steel fixing | Check steel fixing of slab & allow for concrete pouring Zone 7 | (+18'-9'') | Grid G-M/1-7 | A | 2024-08-13
| Sub Structure | 1st floor | L2/317 | 2024-08-08 | 2024-08-08 | level, layout | Check level, layout of slab ,columns & service lift Zone 7 | (+18'-9'') | Grid G-M/1-7 | A | 2024-08-13
| Sub Structure | 1st floor | L2/318 | 2024-08-08 | 2024-08-08 | steel fixing | Check steel fixing of beam Zone 7 | (+18'-9'') | Grid M-U/1-7 | A | 2024-08-13
| Sub Structure | 1st to 2nd floor | L2/319 | 2024-08-09 | 2024-08-09 | steel fixing | Check steel fixing of column Zone 7 | (+18'-9'' to +29'-9'') | Grid G-M/5-7 | A | 2024-08-13
| Sub Structure | 1st floor | L2/320 | 2024-08-09 | 2024-08-09 | steel fixing | Check steel fixing of column Zone 7 | (+18'-9'') | Grid M-U/1-7 | A | 2024-08-13
| Sub Structure | GF to 1st Floor | L2/321 | 2024-08-09 | 2024-08-08 | formwork, steel fixing | Check layout formwork and steel fixing and allow for concrete pouring Zone 7 | (+1'-9'' to +18'-9'') | Grid N-Q/6-7 | A | 2024-08-13
| Sub Structure | 1st foor to 2nd | L2/322 | 2024-08-09 | 2024-08-09 | steel fixing | Check steel fixing of column Zone 7 | (+18'-9'' to +29'-9'') | Grid K-M/5-7 | A | 2024-08-13
| Sub Structure | 1st foor to 2nd | L2/323 | 2024-08-09 | 2024-08-09 | steel fixing | Check steel fixing of column & service lift Zone 7 | (+18'-9'' to +29'-9'') | Grid G-M/5-7 | A | 2024-08-15
| Sub Structure | 1st foor to 2nd | L2/324 | 2024-08-09 | 2024-08-08 | steel fixing | Check steel fixing of column Zone 6 | (+18'-9'' to +29'-9'') | Grid N-S/8-12 | A | 2024-08-13
| Sub Structure | 1st foor to 2nd | L2/325 | 2024-08-09 | 2024-08-09 | steel fixing | Check steel fixing of column Zone 6 | (+18'-9'' to +29'-9'') | Grid N/8-12 | A | 2024-08-15
| Sub Structure | st floor | L2/326 | 2024-08-09 | 2024-08-09 | Slab reinforcement | Check slab rienforcement and allow for concrete poring Zone 7 | (+18'-9'') | Grid M-U/1-7 | A | 2024-08-15
| Sub Structure | GF to 1st Floor | L2/327 | 2024-08-09 | 2024-08-09 | lift reinforcement | Check lift wall rienforcement & allow to start concrete pouring Zone 7 | (+1'-9'' to +18'-9'') | Grid N-Q/5-7 | A | 2024-08-15
| Sub Structure | 1st floor | L2/328 | 2024-08-10 | 2024-08-10 | level, layout | Check level, layout of columns & slab & lift walls Zone 7 | (+18'-9'') | Grid M-U/1-7 | A | 2024-08-13
| Sub Structure | 1st to 2nd floor | L2/329 | 2024-08-10 | 2024-08-10 | column reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring Zone 7 | (+18'-9'' to +29'-9'') | Grid G-L/5-7 | A | 2024-08-15
| Sub Structure | basement | L2/330 | 2024-08-11 | 2024-08-11 | Reinforcement | Check formwork, reinforcement, water stopper of UGWT and allow for concrete pouring Zone 1 & 7 | (-13'-3'') | Grid F-K/1 | A | 2024-08-20
| Sub Structure | 1st to 2nd floor | L2/331 | 2024-08-12 | 2024-08-12 | column reinforcement | Check columns (13 Nos) reinforcement Zone 7 | (+18'-9'' to +29'-9'') | Grid N-U/1-7 | A | 2024-08-15
| Sub Structure | 1st to 2nd floor | L2/332 | 2024-08-12 | 2024-08-13 | lift reinforcement | Check lift wall reinforcement Zone 7 | (+18'-9'' to +29'-9'') | Grid N-Q/5-7 | A | 2024-08-20
| Sub Structure | basement | L2/333 | 2024-08-12 | 2024-08-12 | level, layout | Check level, layout of septic tank base slab Zone 1 & 7 | (-13'-3'') | Grid F-K/1 | A | 2024-08-20
| Sub Structure | 1st to 2nd floor | L2/334 | 2024-08-13 | 2024-08-12 | column reinforcement | Check columns (12 Nos) reinforcement and allow for concrete pouring Zone 7 | (+18'-9'' to +29'-9'') | Grid G-M/1-3, M/5-7 | A | 2024-08-15
| Sub Structure | GF to 1st floor | L2/335 | 2024-08-13 | 2024-08-13 | level, layout | Check level, layout of stair ST-02 Zone 7 | (+4'-6'' to +16'-6'') | Grid N-Q/5-7 | A | 2024-08-20
| Sub Structure | GF to 1st Floor | L2/336 | 2024-08-15 | 2024-08-13 | Reinforcement | Check formwork and stair st-2 reinforcement and allow for concrete pouring Zone 7 | (+4'-6'' to +16'-6'') | Grid N-Q/5-7 | A | 2024-08-20
| Sub Structure | 1st to 2nd floor | L2/337 | 2024-08-15 | 2024-08-13 | Service lift reinforcement | Check service lift reinforcement and allow for concrete pouring Zone 7 | (+18'-9'' to +29'-9'') | Grid H-J/3-4 | A | 2024-08-20
| Sub Structure | 1st to 2nd floor | L2/338 | 2024-08-15 | 2024-08-13 | column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring Zone 7 | (+18'-9'' to +29'-9'') | Grid N-S/1-7, U/4-6 | A | 2024-08-20
| Sub Structure | GF to 1st Floor | L2/339 | 2024-08-15 | 2024-08-15 | level, layout | Check level, layout of stair ST-02 Zone 7 | (+16'-6'' to +18'-9'') | Grid N-Q/5-7 | A | 2024-08-20
| Sub Structure | 1st to 2nd floor | L2/340 | 2024-08-16 | 2024-08-15 | column reinforcement | Check column (3 Nos) reinforcement and allow for concrete pouring Zone 7 | (+18'-9'' to +29'-9'') | Grid T/1, U/1-3 | A | 2024-08-20
| Sub Structure | GF to 1st Floor | L2/341 | 2024-08-16 | 2024-08-15 | Reinforcement | Check formwork and stair reinforcement and allow for concrete pouring Zone 7 | (+16'-6'' to +18'-9'') | Grid N-Q/5-7 | A | 2024-08-21
| Sub Structure | GF to 1st Floor | L2/342 | 2024-08-18 | 2024-08-18 | level, layout | Check level, layout of stair ST-4 Zone 7 | (+1'-9'' to +10'-6'') | Grid G-H/1-3 | A | 2024-08-21
| Sub Structure | GF to 1st Floor | L2/343 | 2024-08-19 | 2024-08-18 | Reinforcement | Check formwork and stair st-4 reinforcement and allow for concrete pouring Zone 7 | (+1'-9'' to +10'-6'', +1'-9'' to +18'-9'') | Grid G-H/1-3 | A | 2024-08-21
| Sub Structure | 2nd floor | L2/344 | 2024-08-19 | 2024-08-19 | Beam reinforcement | Check beam reinforcement Zone 6 & 7 | (+29'-9'') | Grid N-U/8-12 & R-U/6-8 | A | 2024-08-21
| Sub Structure | 2nd floor | L2/345 | 2024-08-19 | 2024-08-19 | Slab reinforcement | Check slab top & bottom reinforcement Zone 7 | (+29'-9'') | Grid N-U/8-12, R-U/6-8 | A | 2024-08-21
| Sub Structure | 1st to 2nd floor | L2/346 | 2024-08-20 | 2024-08-19 | wall reinforcement | Check lift wall reinforcement & allow for concrete pouring Zone 7 | (+18'-9'' to +29'-9'') | Grid N-Q/5-7 | A | 2024-08-21
| Sub Structure | 2nd floor | L2/347 | 2024-08-21 | 2024-08-21 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 6 & 7 | (+29'-9'') | Grid N-U/8-12, R-U/6-8 | A | 2024-08-28
| Sub Structure | GF to 1st Floor | L2/348 | 2024-08-22 | 2024-08-22 | level, layout | Check level, layout of stair ST-04 Zone 7 | (+10'-6'' to +18'-9'') | Grid G-H/1-3 | A | 2024-08-24
| Sub Structure | 2nd floor | L2/349 | 2024-08-22 | 2024-08-22 | level, layout | Check level, layout of slab & sw-08 & balcony beam Zone 6 & 7 | (+29'-9'') | Grid N-U/8-12, R-U/6-8 | A | 2024-08-24
| Sub Structure | GF to 1st Floor | L2/350 | 2024-08-23 | 2024-08-22 | Reinforcement | Check formwork, reinforcement of stair st-4 & allow for concrete pouring Zone 7 | (+10'-12'' to +18'-9'') | Grid G-H/1-3 | A | 2024-08-24
| Sub Structure | 2nd floor | L2/351 | 2024-08-23 | 2024-08-23 | Beam reinforcement | Check beam reinforcement Zone 6 & 7 | (+29'-9'') | Grid G-R/1-7, R-U/1-6 | A | 2024-08-30
| Sub Structure | 2nd floor | L2/352 | 2024-08-23 | 2024-08-23 | slab formwork | Check slab formwork stair ST-02, 04 Zone 7 | (+29'-9'') | Grid G-H/3, Q-Q/6-7 | A | 2024-08-24
| Sub Structure | 2nd floor | L2/353 | 2024-08-24 | 2024-08-26 | Slab reinforcement | Check top and bottom reinforcement Zone 6 & 7 | (+29'-9'') | Grid G-R/1-7, R-U/1-6 | A | 2024-08-30
| Sub Structure | basement | L2/354 | 2024-08-25 | 2024-08-25 | level, layout | Check level, layout of slab rain harvesting tank Zone 7 | (-13'-3'') | grid L-P/1 | A | 2024-09-07
| Sub Structure | basement | L2/355 | 2024-08-24 | 2024-08-24 | Reinforcement | Check formwork, reinforcement and water stopper of slab rain harvesting Tank Zone 7 | (-13'-3'') | Grid L-T/1 | A | 2024-08-30
| Sub Structure | basement | L2/356 | 2024-08-26 | 2024-08-26 | level, layout | Check level, layout of slab of rain harvesting tank Zone 7 | (-13'-3'') | Grid P-T/1 | A | 2024-09-07
| Sub Structure | 2nd floor | L2/357 | 2024-08-26 | 2024-08-26 | Slab reinforcement | check slab reinforcement and allow for concrete pouring Zone 6 & 7 | (+29'-9'') | Grid G-R/1-7, R-U/1-6 | A | 2024-08-30
| Sub Structure | Basement to GF | L2/358 | 2024-08-26 | 2024-08-26 | Reinforcement | Check UGWT for septic and Rain harvesting walls Zone 1 & 7 | (-13'-3'' to +0;-00'') | Grid F-K/1, L1-T/1 | A | 2024-09-03
| Sub Structure | 1st to 2nd floor | L2/359 | 2024-08-26 | 2024-08-26 | level, layout | Check level, layout of stair ST-02 Zone 7 | (+18'-9' to +29'-9'') | Grid N-Q/5-7 | A | 2024-08-28
| Sub Structure | 1st to 2nd floor | L2/360 | 2024-08-26 | 2024-08-26 | Reinforcement | Check formwork, stair st-2 reinforcement and allow for concrete pouring Zone 7 | (+18'-9' to +29'-9'') | Grid N-Q/5-7 | A | 2024-08-30
| Sub Structure | 2nd floor | L2/361 | 2024-08-27 | 2024-08-27 | level, layout | Check level, layout of slab column, service lift , lift walls & balcony beams Zone 7 | (+29'-9'') | Grid G-Q/1-7, Q-U/1-5 | A | 2024-08-28
| Sub Structure | 2nd to 3rd floor | L2/362 | 2024-08-28 | 2024-08-28 | column reinforcement | Check columns (10 Nos) reinforcement Zone 6 | (+29'-9'' to +40'-9'') | Grid S-U/8-12 | A | 2024-08-30
| Sub Structure | 2nd to 3rd floor | L2/363 | 2024-08-28 | 2024-08-28 | column reinforcement | Check columns (8 Nos) reinforcement & SW-08 Zone 6 | (+29'-9'' to +40'-9'') | Grid N-Q/8-12 | A | 2024-08-30
| Sub Structure | 2nd to 3rd floor | L2/364 | 2024-08-29 | 2024-08-29 | column reinforcement | Check columns (12 Nos) reinforcement Zone 7 | (+29'-9'' to +40'-9'') | Grid P-Q/1-3, R-U/1-7 | A | 2024-09-03
| Sub Structure | 2nd to 3rd floor | L2/365 | 2024-08-29 | 2024-08-29 | column reinforcement | Check columns (10 Nos) reinforcement & allow for concrete pouring Zone 6 | (+29'-9'' to +40'-9'') | Grid S-U/8-12 | A | 2024-09-03
| Sub Structure | 2nd to 3rd floor | L2/366 | 2024-08-30 | 2024-08-30 | lift reinforcement | Check lift wall reinforcement Zone 7 | (+29'-9'' to +40'-9'') | Grid N-Q/5-7 | A | 2024-09-03
| Sub Structure | 2nd to 3rd floor | L2/367 | 2024-08-31 | 2024-08-31 | column reinforcement | Check columns (10 Nos) reinforcement and lift reinforcement Zone 7 | (+29'-9'' to +40'-9'') | Grid N/3, L-M/1-7, K/1, H-J/3-4 | A | 2024-09-03
| Sub Structure | 2nd to 3rd floor | L2/368 | 2024-09-02 | 2024-08-31 | column reinforcement | Check columns (14 Nos), Sw-8 (1 Nos) reinforcement and allow for concrete pouring Zone 87 | (+29'-9'' to +40'-9'') | Grid N-Q/9-12, S-U/3-6, T/1 | A | 2024-09-03
| Sub Structure | basement | L2/369 | 2024-09-02 | 2024-08-31 | Reinforcement | Check septic tank walls reinforcement and water stopper and allow for concrete pouring Zone 7 | (-12'-3'' to +0'-00'') | Grid G-K/1 | A | 2024-09-06
| Sub Structure | 2nd to 3rd floor | L2/370 | 2024-09-02 | 2024-09-01 | Reinforcement | Check columns (11 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (+29'-9'' to +40'-9'') | Grid M-Q/1-3, R&U/1, Q/8, L/3, M/5 | A | 2024-09-06
| Sub Structure | 2nd to 3rd floor | L2/371 | 2024-09-02 | 2024-09-02 | column reinforcement | Check columns (11 Nos) reinforcement Zone 7 | (+29'-9'' to +40'-9'') | Grid G-K/1-7 | A | 2024-09-06
| Sub Structure | 1st to 2nd floor | L2/372 | 2024-09-02 | 2024-09-02 | level,layout | Check level, layout of stair st-4 zone 7 | (+18'-9'' to +29'-9'') | Grid G-H/1-3 | A | 2024-09-03
| Sub Structure | 1st to 2nd floor | L2/373 | 2024-09-03 | 2024-09-02 | Reinforcement | Check stair st-4 reinforcement and allow for concrete pouring Zone 7 | (+18'-9'' to +29'-9'') | Grid G-H/1-3 | A | 2024-09-06
| Sub Structure | 2nd to 3rd floor | L2/374 | 2024-09-03 | 2024-09-02 | column reinforcement | Check columns (8 Nos), Sw-8 (1 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (+29'-9'' to +40'-9'') | Grid H-M/7, H-K/3-5, L/1-5, N/11 | A | 2024-09-06
| Sub Structure | 1st to 2nd floor | L2/375 | 2024-09-05 | 2024-09-03 | Reinforcement | Check formwork and reinforcement of hanging beam & allow for concrete pouring Zone 7 | (+24'-4'' to +29'-9'') | Grid G-H;/1-3 | A | 2024-09-09
| Sub Structure | 2nd to 3rd floor | L2/376 | 2024-09-05 | 2024-09-04 | Reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring Zone 7 | (+29'-9'' to +40'-9'') | Grid G/3-5, H/5, J-K/1 | A | 2024-09-09
| Sub Structure | 2nd to 3rd floor | L2/377 | 2024-09-06 | 2024-09-05 | Reinforcement | Check lift wall reinforcement and allow for concrete pouring Zone 7 | (+29'-9'' to +40'-9'') | Grid N-Q/5-7 | A | 2024-09-07
| Sub Structure | 3rd floor | L2/378 | 2024-09-06 | 2024-09-06 | Reinforcement | Check beam reinforcement Zone 6 & 7 | (+40'-9'') | Grid N-U/8-12, R-U/6-8 | A | 2024-09-10
| Sub Structure | 2nd to 3rd floor | L2/379 | 2024-09-06 | 2024-09-06 | column reinforcement | Check column (3 Nos) reinforcement and allow for concrete pouring Zone 7 | (+29'-9'' to +40'-9'') | Grid G-H/1, G/7 | A | 2024-09-10
| Sub Structure | 3rd floor | L2/380 | 2024-09-07 | 2024-09-07 | Slab reinforcement | Check top and bottom slab reinforcement Zone 6 & 7 | (+40'-9'') | Grid N-U/8-12, R-U/6-8 | A | 2024-09-10
| Sub Structure | 3rd floor | L2/381 | 2024-09-07 | 2024-09-07 | slab formwork | Check slab formwork along stair st-02 Zone 7 | (+40'-9'') | Grid P-Q/6-7 | A | 2024-09-10
| Sub Structure | 2nd to 3rd floor | L2/382 | 2024-09-09 | 2024-09-08 | lift reinforcement | Check lift reinforcement and allow for concrete pouring Zone 7 | (+29'-9'' to +40'-9'') | Grid H-J/3-4 | A | 2024-09-12
| Sub Structure | 3rd floor | L2/383 | 2024-09-09 | 2024-09-09 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring Zone 6 & 7 | (+40'-9'') | Grid N-U/8-12, R-U/6-8 | A | 2024-09-12
| Sub Structure | 2nd to 3rd floor | L2/384 | 2024-09-09 | 2024-09-09 | level, layout | Check level, layout of stair st-2 Zone 7 | (+29'-9'' to +40'-9'') | Grid N-Q/5-7 | A | 2024-09-12
| Sub Structure | 2nd to 3rd floor | L2/385 | 2024-09-09 | 2024-09-09 | Reinforcement | Check formwork, reinforcement of stair st-02 & allow for concrete pouring Zone 7 | (+29'-9'' to +40'-9'') | Grid N-Q/5-7 | A | 2024-09-12
| Sub Structure | 3rd floor | L2/386 | 2024-09-10 | 2024-09-10 | layout | Check slab top level, layout of columns & SW-08 | (+40'-9'') | Grid M-U/8-12 | A | 2024-09-12
| Sub Structure | 3rd to 4th floor | L2/387 | 2024-09-10 | 2024-09-10 | steel fixing | Check steel fixing of columns (5 Nos) Zone 6 | (+40'-9'' to +51'-9'') | Grid U/8-12 | A | 2024-09-12
| Sub Structure | 3rd floor | L2/388 | 2024-09-10 | 2024-09-11 | steel fixing | Check steel fixing of beam Zone 7 | (+40'-9'') | Grid G-U/1-7 | A | 2024-09-16
| Sub Structure | 3rd floor | L2/389 | 2024-09-11 | 2024-09-11 | level, layout | Check level, layout of column, lift wall & balcony Zone 6 & 7 | (+40'-9'') | Grid N-U/5-8 | A | 2024-09-16
| Sub Structure | 3rd to 4th floor | L2/390 | 2024-09-11 | 2024-09-11 | steel fixing | Check steel fixing of columns (8 Nos) Zone 6 | (+40'-9'' to +51'-9'') | Grid Q/8-10, S/8-12 | A | 2024-09-12
| Sub Structure | 3rd to 4th floor | L2/391 | 2024-09-12 | 2024-09-11 | steel fixing | Check steel fixing of columns (10 Nos) and allow for concrete pouring Zone 6 | (+40'-9'' to +51'-9'') | Grid S-U/8-12 | A | 2024-09-16
| Sub Structure | 3rd to 4th floor | L2/392 | 2024-09-12 | 2024-09-12 | steel fixing | Check steel fixing of columns (7 Nos) & SW-08 (02 Nos) Zone 6 | (+40'-9'' to +51'-9'') | Grid N/8-12, Q/8-12, S/7, U/6 | A | 2024-09-16
| Sub Structure | 3rd floor | L2/393 | 2024-09-12 | 2024-09-13 | Steel fixing | Check steel fixing of Slab top and bottom Zone 7 | (+40'-9'') | Grid G-U/1-8 | A | 2024-09-16
| Sub Structure | 3rd to 4th floor | L2/394 | 2024-09-13 | 2024-09-12 | steel fixing | Check steel fixing of columns (10 Nos) and allow to start concrete pouring Zone 6 & 7 | (+40'-9'' to +51'-9'') | Grid N-Q/8-12, U/6, S/7 | A | 2024-09-16
| Sub Structure | 3rd floor | L2/395 | 2024-09-13 | 2024-09-13 | formwork | Check stair st-4 formwork zone 7 | (+40'-2'') | Grid G-H/1-3 | A | 2024-09-20
| Sub Structure | 3rd floor | L2/396 | 2024-09-13 | 2024-09-13 | steel fixing | Check steel fixing of slab and allow for concrete pouring Zone 7 | (++40.0) | Grid G-U/1-7 | A | 2024-09-20
| Sub Structure | basement | L2/397 | 2024-09-13 | 2024-09-13 | steel fixing | Check steel fixing of septic tank wall and allow for concrete pouring Zone 7 | (-11'-9'' to +0.0) | Grid G-K/1 | A | 2024-09-20
| Sub Structure | 3rd to 4th floor | L2/398 | 2024-09-14 | 2024-09-14 | column reinforcement | Check columns (11 Nos) reinforcement Zone 7 | (+40'-9'' to +51'-9'') | Grid N-U/1-5 | A | 2024-09-20
| Sub Structure | 3rd floor | L2/399 | 2024-09-14 | 2024-09-14 | level, layout | Check level, layout of columns main lift service & balcony Zone 7 | (+40'-9'') | Grid G-U/1-5 | A | 2024-09-18
| Sub Structure | 3rd to 4th floor | L2/400 | 2024-09-15 | 2024-09-15 | column reinforcement | Check columns (10 Nos), SW-8 (1 No) reinforcement and allow for concsrete pouring Zone 7 | (+40'-9'' to +51'-9'') | Grid N/3, Q-U/1-5, Q/12 | A | 2024-09-16
| Sub Structure | 3rd to 4th floor | L2/401 | 2024-09-16 | 2024-09-16 | column reinforcement | Columns (20 Nos) and lift wall rienforcement Zone 7 | (+40'-9'' to +51'-9'') | Grid G-M/1-7, N-Q/5-7 | A | 2024-09-20
| Sub Structure | 3rd to 4th floor | L2/402 | 2024-09-16 | 2024-09-16 | column reinforcement | Check columns (10 Nos) and sw-08 (1 Nos) reinforcement and allow for concrete pouring Zone 7 | (+40'-9'' to +51'-9'') | Grid J/1, K-M/1-3, P/1, L-M/5, N/11 | A | 2024-09-20
| Sub Structure | 3rd to 4th floor | L2/403 | 2024-09-18 | 2024-09-18 | lift reinforcement | Check lift reinforcement zone 7 | (+40'-9'' to +51'-9'') | Grid H-J/3-4 | A | 2024-09-20
| Sub Structure | 3rd to 4th floor | L2/404 | 2024-09-19 | 2024-09-18 | Reinforcement | Check column (8 Nos) reinforcement and allow for concrete pouring Zone 7 | (+40'-9'' to +51'-9'') | Grid H-M/7, G-K/5, G/3 | A | 2024-09-24
| Sub Structure | 3rd to 4th floor | L2/405 | 2024-09-19 | 2024-09-19 | Reinforcement | Check columns (3 Nos) reinforcement and allow for concrete pouring Zone 7 | (+40'-9'' to +51'-9'') | Grid G-H/1, G/7 | A | 2024-09-24
| Sub Structure | 4th floor | L2/406 | 2024-09-20 | 2024-09-20 | steel fixing | Check steel fixing of beam Zone 6 & 7 | (+51'-9'') | Grid N-U/5-12 | A | 2024-09-30
| Sub Structure | 2nd to 3rd floor | L2/407 | 2024-09-21 | 2024-09-21 | level, layout | Check level, layout of stair st-04 zone 7 | (+29'-9'' to +40'-9'') | Grid G-H/1-3 | A | 2024-09-24
| Sub Structure | 3rd to 4th floor | L2/408 | 2024-09-23 | 2024-09-21 | Reinforcement | Check lift reinforcement and allow to start concrete pouring Zone 7 | (+40'-9'' to +51'-9'') | Grid N-Q/5-7 | A | 2024-09-30
| Sub Structure | 2nd to 3rd floor | L2/409 | 2024-09-23 | 2024-09-22 | Reinforcement | Check formwork and stair st-4 reinforcement and allow to start concrete work Zone 7 | (+29'-9'' to +40'-9'') | Grid G-H/1-3 | A | 2024-09-26
| Sub Structure | 4th floor | L2/410 | 2024-09-23 | 2024-09-23 | Reinforcement | Check slab top and bottom reinforcement zone 6 & 7 | (+51'-9'') | Grid N-U/6-12 | A | 2024-09-30
| Sub Structure | 4th floor | L2/411 | 2024-09-23 | 2024-09-23 | formwork | Check slab formwork along stair st-2 Zone 7 | (+51'-9'') | Grid P-Q/6-7 | A | 2024-09-26
| Sub Structure | 4th floor | L2/412 | 2024-09-23 | 2024-09-23 | Reinforcement | Check slab reinforcement and allow for concrete pouring Zone 7 | (+51'-9'') | Grid N-U/6-12 | A | 2024-09-26
| Sub Structure | 4th to 5th floor | L2/413 | 2024-09-24 | 2024-09-24 | Reinforcement | Check columns (8 Nos) reinforcement zone 6 & 7 | (+51'-9'' to +62'-9'') | Grid U/8-12, S/7-8, 12 | A | 2024-09-30
| Sub Structure | 4th floor | L2/414 | 2024-09-24 | 2024-09-24 | layout | Check slab level, layout of columns, sw-8 & balcony beam zone 6 & 7 | (+51'-9'') | Grid N-U/6-12 | B | 2024-09-26
| Sub Structure | 3rd to 4th floor | L2/415 | 2024-09-25 | 2024-09-24 | Reinforcement | Check lift reinforcement & allow to start concrete work zone 7 | (+40'-9'' to +51'-9'') | Grid H-J/3-3 | A | 2024-10-02
| Sub Structure | basement | L2/416 | 2024-09-25 | 2024-09-25 | level | Check level sheet before sand filling zone 7 | (-12.52) | Grid G-L/1 | A | 2024-09-30
| Sub Structure | 4th to 5th floor | L2/417 | 2024-09-25 | 2024-09-25 | Reinforcement | Check columns (12 Nos) reinforcement zone 6 & 7 | (+51'-9'' to +62'-9'') | Grid N-Q/8-10, Q/11,12, S/9-11, U/6 | A | 2024-09-30
| Sub Structure | GF | L2/418 | 2024-09-25 | 2024-09-25 | Reinforcement | Check septic tank slab top & bottom reinforcement zone 7 | (+0'-00'') | Grid G-K/1 | A | 2024-09-30
| Sub Structure | 4th to 5th floor | L2/419 | 2024-09-26 | 2024-09-25 | Reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring Zone 6 & 7 | (+51'-9'' to +62'-9'') | Grid S/7-10, U/6-12 | A | 2024-09-30
| Sub Structure | GF | L2/420 | 2024-09-26 | 2024-09-25 | Reinforcement | Check septic tank slab reinforcement and allow for concrete pouring Zone 7 | (+0'-00'') | Grid G-K/1 | A | 2024-09-30
| Sub Structure | GF | L2/421 | 2024-09-26 | 2024-09-25 | level | Check septic tank slab top level zone 7 | (+0'-00'') | Grid G-K/1 | A | 2024-10-02
| Sub Structure | 4th to 5th floor | L2/422 | 2024-09-26 | 2024-09-26 | Reinforcement | Check sw-8 (2 Nos) reinforcement zone 6 | (+51'-9'' to +62'-9'') | Grid N/11, Q/12 | A | 2024-09-30
| Sub Structure | 4th floor | L2/423 | 2024-09-26 | 2024-09-26 | Reinforcement | Check beam reinforcement zone 7 | (+51'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-10-02
| Sub Structure | 4th to 5th floor | L2/424 | 2024-09-27 | 2024-09-26 | Reinforcement | Check columns (10 Nos) and SW-08 (1 Nos) reinforcement and allow to concrete pouring Zone 6 | (+51'-9'' to +62'-9'') | Grid N/8-10, N/12, Q/8-12, S/11-12 | A | 2024-09-30
| Sub Structure | 2nd to 3rd floor | L2/425 | 2024-09-27 | 2024-09-27 | level | check level, layout of stair st-2 zone 7 | (+40'-9'' to +51'-9'') | Grid N-Q/5-7 | A | 2024-10-02
| Sub Structure | 4th floor | L2/426 | 2024-09-27 | 2024-09-27 | slab formwork | Check slab formwork along stair st-04 zone 7 | (+51'-9'') | Grid G-H/2-3 | A | 2024-10-04
| Sub Structure | basement | L2/427 | 2024-09-27 | 2024-09-27 | Primer, membrane | Check vertical primer, membrane on RTW zone 7 | (-13.25' to -2.083'') | Grid G-K/1 | A | 2024-09-30
| Sub Structure | 3rd to 4th floor | L2/428 | 2024-09-28 | 2024-09-27 | Reinforcement | Check formwork and reinforcement of stair st-2 and allow to start concrete pouring zone 7 | (+40'-9'' to +51'-9'') | Grid N-Q/5-7 | A | 2024-10-02
| Sub Structure | 4th to 5th floor | L2/429 | 2024-09-28 | 2024-09-27 | Reinforcement | Check sw-8 (1 No) reinforcement and allow to start concrete pouring zone 6 | (+51'-9'' to +62'-9'') | Grid N/11 | A | 2024-10-02
| Sub Structure | 4th floor | L2/430 | 2024-09-28 | 2024-09-28 | Reinforcement | Check slab top and bottom reinforcement zone 7 | (+51'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-10-04
| Sub Structure | 4th floor | L2/431 | 2024-09-28 | 2024-09-28 | Reinforcement | Check slab reinforcement and allow to start concrete pouring zone 7 | (+51'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-10-02
| Sub Structure | 2nd to 3rd floor | L2/432 | 2024-09-28 | 2024-09-27 | Reinforcement | Check formwork and hanging beam reinforcement and allow to start concrete pouring zone 7 | (+35'-41/2'' to +40'-9'') | Grid G-H/1 | A | 2024-10-02
| Sub Structure | 4th floor | L2/433 | 2024-09-30 | 2024-09-30 | layout | Check slab layout of column service lift & balcony zne 7 | (+51'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-10-02
| Sub Structure | 4th to 5th floor | L2/434 | 2024-09-30 | 2024-09-30 | column reinforcement | Check columns (20 Nos) reinforcement zone 7 | (+51'-9'' to +62'-9'') | Grid N-U/1-5, L-M/1-7, K/1 | A | 2024-10-02
| Sub Structure | 4th to 5th floor | L2/435 | 2024-09-30 | 2024-09-30 | column reinforcement | Check columns (10 Nos) reinforcement and allow to start concrete pouring zone 7 | (+51'-9'' to +62'-9'') | Grid P-U/1-5 | A | 2024-10-02
| Sub Structure | 4th to 5th floor | L2/436 | 2024-10-01 | 2024-10-01 | column reinforcement | Check columns (11 Nos) reinforcement zone 7 | (+51'-9'' to +62'-9'') | Grid G-J/1-7, K/3-7 | A | 2024-10-04
| Sub Structure | 4th to 5th floor | L2/437 | 2024-10-01 | 2024-10-01 | lift reinforcement | Check lift reinforcement zone 7 | (+51'-9'' to +62'-9'') | Grid N-Q/5-7 | A | 2024-10-04
| Sub Structure | 4th to 5th floor | L2/438 | 2024-10-02 | 2024-10-01 | column reinforcement | Check columns (10 Nos) reinforcement & allow for concrete pouring zone 7 | (+51'-9'' to +62'-9'') | Grid K-M/1-5, N/3 | A | 2024-10-04
| Sub Structure | 4th to 5th floor | L2/439 | 2024-10-02 | 2024-10-02 | lift reinforcement | Check lift reinforcement zone 7 | (+51'-9'' to +62'-9'') | Grid H-J/3-3 | A | 2024-10-04
| Sub Structure | 3rd to 4th floor | L2/440 | 2024-10-02 | 2024-10-02 | level,layout | Check level, layout of stair st-4 zone 7 | (+40'-9'' to +51'-9'') | Grid G-H/1-3 | A | 2024-10-04
| Sub Structure | 3rd to 4th floor | L2/441 | 2024-10-03 | 2024-10-02 | Reinforcement | Check formwork and reinforcement of stair st-4 & allow for concrete pouring zone 7 | (+40'-9'' to +51'-9'') | Grid G-H/1-3 | A | 2024-10-04
| Sub Structure | 4th to 5th floor | L2/442 | 2024-10-03 | 2024-10-02 | Reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring zone 7 | (+51'-9'' to +62'-9'') | Grid G-J/1-5, H-M/7 | A | 2024-10-04
| Sub Structure | 5th floor | L2/443 | 2024-10-04 | 2024-10-04 | steel fixing | Check steel fixing beam zone 6 | (+62'-9'') | Grid N-U/7-12 | A | 2024-10-09
| Sub Structure | 4th to 5th floor | L2/444 | 2024-10-05 | 2024-10-04 | lift reinforcement | Check lift wall reinforcement & allow for concrete pouring zone 7 | (+51'-9'' to +62'-9'') | Grid N-Q/5-7 | A | 2024-10-09
| Sub Structure | 4th to 5th floor | L2/445 | 2024-10-07 | 2024-10-05 | column reinforcement | Check column (1 Nos) reinforcement and allow for concrete pouring Zone 7 | (+51'-9'' to +62'-9'') | Grid G/7 | A | 2024-10-09
| Sub Structure | GF | L2/446 | 2024-10-07 | 2024-10-05 | Reinforcement | Check rain harvesting tank wall reinforcement & allow for concrete pouring zone 7 | (-11'-9'' to +0.0) | Grid L-P/1 | A | 2024-10-09
| Sub Structure | 4th floor | L2/447 | 2024-10-07 | 2024-10-05 | formwork | Check slab formwork along stair st-02 Zone 7 | (+62'-9'') | Grid P-Q/6-7 | A | 2024-10-11
| Sub Structure | 5th floor | L2/448 | 2024-10-07 | 2024-10-07 | Reinforcement | Check beam & slab reinforcement zone 6 & 7 | (+62'-9'') | Grid N-U/6-12 | A | 2024-10-09
| Sub Structure | 4th to 5th floor | L2/449 | 2024-10-07 | 2024-10-07 | level, layout | Check level, layout of stair st-2 zone 7 | (+51'-9'' to +62'-9'') | Grid N-Q/5-7 | A | 2024-10-11
| Sub Structure | 4th to 5th floor | L2/450 | 2024-10-08 | 2024-10-07 | Reinforcement | Check formwork, reinforcement of stair st-2 & allow for concrete pouring zone 7 | (+51'-9'' to +62'-9'') | Grid N-Q/5-7 | A | 2024-10-11
| Sub Structure | basement | L2/451 | 2024-10-07 | 2024-10-07 | Primer, membrane | Check vertical primer and membrane zone 7 | (-13.25' to -2.083') | Grid K-T/1-7 | A | 2024-10-11
| Sub Structure | basement | L2/452 | 2024-10-07 | 2024-10-07 | level | check level sheet before sand filling zone 7 | (-13.02') | Grid L-T/1 | A | 2024-10-11
| Sub Structure | basement | L2/453 | 2024-10-08 | 2024-10-07 | Termite proofing | Check termite proofing along RTW zone 7 | (-13'-3'' to 12'-3'') | Grid G-T/1 | A | 2024-10-11
| Sub Structure | basement | L2/454 | 2024-10-08 | 2024-10-07 | compaction | Check compaction backfilling of sand of RTW zone 7 | (-13'-3'' to 12'-3'') | Grid G-T/1 | A | 2024-10-11
| Sub Structure | 5th floor | L2/455 | 2024-10-08 | 2024-10-08 | Reinforcement | Check slab reinforcement and allow for concrete pouring zone 6 & 7 | (+62'-9'') | Grid N-U/6-12 | A | 2024-10-11
| Sub Structure | 5th to 6th floor | L2/456 | 2024-10-09 | 2024-10-09 | column reinforcement | Check columns (12 Nos) reinforcement zone 6 & 7 | (+62'-9'' to +73'-9'') | Grid S-U/6-12 | A | 2024-10-11
| Sub Structure | 5th floor | L2/457 | 2024-10-09 | 2024-10-09 | layout | Check level of slab, layout of columns, sw-8 zone 6 & 7 | (+62'-9'') | Grid N-U/6-12 | A | 2024-10-11
| Sub Structure | 4th to 5th floor | L2/458 | 10-Ot-24 | 2024-10-09 | lift reinforcement | Check lift reinforcement and allow for concrete pouring zone 7 | (+51'-9'' to +62'-9'') | Grid H-J/3-3 | A | 2024-10-11
| Sub Structure | 3rd to 4th floor | L2/459 | 10-Ot-24 | 2024-10-09 | Reinforcement | Check formwork and hanging beam reinforcement and allow for concrete pouring zone 7 | (+46' to +51'-9'') | Grid G-H/1 | A | 2024-10-15
| Sub Structure | 5th to 6th floor | L2/460 | 10-Ot-24 | 10-Ot-24 | column reinforcement | Check columns (8 Nos) and SW-08(2 Nos) reinforcement zone 6 | (+62'-9'' to +73'-9'') | Grid N-Q/8-12 | A | 2024-10-11
| Sub Structure | 5th to 6th floor | L2/461 | 2024-10-11 | 10-Ot-24 | column reinforcement | Check columns (7 Nos) reinforcement and allow for concrete pouring Zone 6 | (+62'-9'' to +73'-9'') | Grid S/8-10, U/8-11 | A | 2024-10-15
| Sub Structure | 5th floor | L2/462 | 2024-10-11 | 2024-10-11 | Beam reinforcement | Check beam rienforcement zone 7 | (+62'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-10-15
| Sub Structure | 5th floor | L2/463 | 2024-10-11 | 2024-10-11 | slab formwork | Check slab formwork along stair st-4 zone 7 | (+62'-9'') | Grid G-H/2-3 | A | 2024-10-15
| Sub Structure | 5th floor | L2/464 | 2024-10-12 | 2024-10-12 | Slab reinforcement | Check slab top and bottom reinforcement zone 7 | (+62'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-10-15
| Sub Structure | 5th floor | L2/465 | 2024-10-12 | 2024-10-12 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring zone 7 | (+62'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-10-24
| Sub Structure | basement | L2/466 | 2024-10-12 | 2024-10-12 | level | check level sheet for sand filling zone 6 | (-17.01') | Grid T/9-12 | A | 2024-10-24
| Sub Structure | basement | L2/467 | 2024-10-12 | 2024-10-12 | level | Check level sheet before sand filling zone 6 | (-16.04') | Grid T/9-12 | A | 2024-10-18
| Sub Structure | 5th to 6th floor | L2/468 | 2024-10-11 | 2024-10-11 | Reinforcement | Check columns (10 Nos) and Sw-8 (1 No) reinforcement & allow for concrete pouring zone 6 | (+62'-9'' to +73'-9'') | Grid S/11-12, U/12, N-Q/9-10, Q/11-12, N/12, S/7 | A | 2024-10-15
| Sub Structure | Basement to GF | L2/469 | 2024-10-12 | 2024-10-12 | Reinforcement | Check reinforcement of rain harvesting tank wall & allow for concrete pouring zone 7 | (-11'-9'' to +0.0) | Grid L-P/1 | A | 2024-10-18
| Sub Structure | basement | L2/470 | 2024-10-12 | 2024-10-12 | Termite proofing | Check termite proofing along RTW zone 7 | (-12'-3'') | Grid G-T/1 | A | 2024-10-18
| Sub Structure | basement | L2/471 | 2024-10-12 | 2024-10-12 | compaction | Check 2nd layer compaction of sand along backside fo RTW zone 7 | (-12'-3'' to 11'-3'') | Grid G-T/1 | A | 2024-10-24
| Sub Structure | basement | L2/472 | 2024-10-12 | 2024-10-12 | Termite proofing | Check termite proofing along RTW zone 7 | (-11'-3'') | Grid G-T/1 | A | 2024-10-18
| Sub Structure | basement | L2/473 | 2024-10-12 | 2024-10-12 | compaction | Check 3rd layer compaction backfilling of sand along backside of RTW zone 7 | (-11'-3'' to 10'-3'') | Grid G-T/1 | A | 2024-10-24
| Sub Structure | 5th floor | L2/474 | 2024-10-14 | 2024-10-13 | level, layout | check level, layout of slab, lift wall & columns zone 7 | (+62'-9'') | Grid G-U/1-5 | A | 2024-10-18
| Sub Structure | basement | L2/475 | 2024-10-14 | 2024-10-14 | compaction | check 4th layer compaction of sand along backside of RTW zone 7 | (-10'-3'' to -9'-3'') | Grid G-T/1 | A | 2024-10-18
| Sub Structure | basement | L2/476 | 2024-10-14 | 2024-10-14 | compaction | Check 5th layer backfilling of sand along backside of RTW zone 7 | (-9'-3'' to -8'-3'') | Grid G-T/1 | A | 2024-10-18
| Sub Structure | basement | L2/477 | 2024-10-14 | 2024-10-14 | compaction | Check 6th layer backfilling of sand along backside of RTW zone 7 | (-8'-3'' to -7'-6'') | Grid G-T/1 | A | 2024-10-18
| Sub Structure | basement | L2/478 | 2024-10-14 | 2024-10-14 | Termite proofing | Check termite proofing along RTW zone 7 | (-10'-3'') | Grid G-T/1 | A | 2024-10-18
| Sub Structure | basement | L2/479 | 2024-10-14 | 2024-10-14 | Termite proofing | Check termite proofing along RTW zone 7 | (-9'-3'') | Grid G-T/1 | A | 2024-10-18
| Sub Structure | basement | L2/480 | 2024-10-14 | 2024-10-14 | Termite proofing | Check termite proofing along RTW zone 7 | (-8'-3'') | Grid G-T/1 | A | 2024-10-18
| Sub Structure | basement | L2/481 | 2024-10-14 | 2024-10-14 | Termite proofing | Check termite proofing along RTW zone 7 | (-7'-6'' | Grid G-T/1 | B | 2024-10-31
| Sub Structure | 5th to 6th floor | L2/482 | 2024-10-14 | 2024-10-14 | steel fixing | Check steel fixing of columns zone 7 | (+62'-9'' to +73'-9'') | Grid G-U/1-5 | A | 2024-10-18
| Sub Structure | 5th to 6th floor | L2/483 | 2024-10-14 | 2024-10-14 | steel fixing | Check steel fixing of columns (3 Nos) & sw-8 zone 6 | (+62'-9'' to +73'-9'') | Grid N-Q/8 ,11 & U/6 | A | 2024-10-18
| Sub Structure | 5th to 6th floor | L2/484 | 2024-10-14 | 2024-10-14 | steel fixing | Check steel fixing of service lift zone 7 | (+62'-9'' to +73'-9'') | Grid H-J/3-4 | A | 2024-10-18
| Sub Structure | 5th to 6th floor | L2/485 | 2024-10-15 | 2024-10-15 | steel fixing | Check steel fixing of main lift zone 7 | (+62'-9'' to +73'-9'') | Grid N-Q/4-7 | A | 2024-10-21
| Sub Structure | 5th to 6th floor | L2/486 | 2024-10-15 | 2024-10-15 | steel fixing | Check steel fixing of columns (8 Nos) & allow for concrete pouring zone 7 | (+62'-9'' to +73'-9'') | Grid L-U/1-5 | A | 2024-10-18
| Sub Structure | 5th to 6th floor | L2/487 | 2024-10-16 | 2024-10-15 | steel fixing | Check steel fixing of columns (8 Nos) and allow for concrete pouring zone 7 | (+62'-9'' to +73'-9'') | Grid N-U/1-5 | A | 2024-10-28
| Sub Structure | 5th to 6th floor | L2/488 | 2024-10-17 | 2024-10-16 | steel fixing | Check steel fixing of columns (7 Nos) and allow for concrete pouring zone 7 | (+62'-9'' to +73'-9'') | Grid G-H/1, K-L/5-7, M/7 | A | 2024-10-24
| Sub Structure | basement | L2/489 | 2024-10-17 | 2024-10-16 | level | Check level sheet before sand filling zone 7 |  | Grid T/1-9 | A | 2024-10-21
| Sub Structure | basement | L2/490 | 2024-10-17 | 2024-10-17 | layer | Check 1st layer compaction backfilling of sand along fron side RWT zone 7 | (-17'-0'' to -16'-0'') | Grid T/1-12 | A | 2024-10-21
| Sub Structure | basement | L2/491 | 2024-10-17 | 2024-10-17 | layer | Check 1st layer compaction backfilling of sand along fron side RWT zone 7 | (-16'-0'' to -15'-0'') | Grid T/1-12 | A | 2024-10-21
| Sub Structure | basement | L2/492 | 2024-10-17 | 2024-10-17 | Termite proofing | Check termite proofing front side along side RWT zone 7 | (-17'-0'') | Grid T/1-12 | A | 2024-10-21
| Sub Structure | basement | L2/493 | 2024-10-17 | 2024-10-17 | Termite proofing | Check termite proofing front side along side RWT zone 7 | (-16'-0'') | Grid T/1-12 | A | 2024-10-21
| Sub Structure | basement | L2/494 | 2024-10-18 | 2024-10-18 | compaction | Check 3rd layer compaction backfilling of sand along front side RWT zone 7 | (-15'-0'' to -14'-0'') | Grid T/1-12 | A | 2024-10-21
| Sub Structure | basement | L2/495 | 2024-10-18 | 2024-10-18 | compaction | Check 4th layer compaction backfilling of sand along front side RWT zone 7 | (-14'-0'' to -13'-0'') | Grid T/1-12 | A | 2024-10-21
| Sub Structure | basement | L2/496 | 2024-10-18 | 2024-10-18 | Termite proofing | Check termite proofing along RWT zone 7 | (-16'-0'' to -13'-0'') | Grid T/1-12 | A | 2024-10-21
| Sub Structure | basement | L2/497 | 2024-10-18 | 2024-10-18 | steel fixing | Check steel fixing of beam zone 6 | (+73'-9'') | Grid N-U/7-12 | A | 2024-10-24
| Sub Structure | 4th to 5th floor | L2/498 | 2024-10-19 | 2024-10-18 | Steel fixing | Check steel fixing of main lift & columns (8 Nos) & allow for concrete pouring zone 7 | (+62'-9'' to +73'-9'') | Grid G-K/1-7, N-Q/4-7 | A | 2024-10-24
| Sub Structure | 6th floor | L2/499 | 2024-10-21 | 2024-10-21 | steel fixing | Check steel fixing of slab top and bottom zone 6 & 7 | (+73'-9'') | Grid N-U/6-12 | A | 2024-10-24
| Sub Structure | 3rd to 4th floor | L2/500 | 2024-10-19 | 2024-10-19 | level, layout | Check level, layout of st-04 zone 7 | (+51'-9'' to +62'-9'') | Grid G-H/1-3 | A | 2024-10-24
| Sub Structure | basement | L2/501 | 2024-10-19 | 2024-10-19 | compaction | Check 5th layer compaction backfilling of sand along fron side RWT zone 7 | (-13'-0'' to -12'-0'') | Grid T/1-12 | A | 2024-10-24
| Sub Structure | basement | L2/502 | 2024-10-19 | 2024-10-19 | compaction | Check 6th layer compaction backfilling of sand along fron side RWT zone 7 | (-12'-0'' to -11'-0'') | Grid T/1-12 | A | 2024-10-24
| Sub Structure | basement | L2/503 | 2024-10-19 | 2024-10-19 | compaction | Check 7th layer compaction backfilling of sand along fron side RWT zone 7 | (-11'-0'' to -10'-0'') | Grid T/1-12 | A | 2024-10-24
| Sub Structure | basement | L2/504 | 2024-10-19 | 2024-10-19 | Termite proofing | Check termite proofing along side RWT zone 7 | (-13'-0'' to -10'-0'') | Grid T/1-12 | A | 2024-10-24
| Sub Structure | GF | L2/505 | 2024-10-19 | 2024-10-19 | steel fixing | Check steel fixing of slab of rain water tank zone 7 | (+0'-00'') | Grid L-Q/1 | A | 2024-10-24
| Sub Structure | basement | L2/506 | 2024-10-19 | 2024-10-19 | primer | Check vertical primer and membrane on RTW zone 6 | (-17'-6'' to -5'-6'') | Grid T/1-12 | A | 2024-10-24
| Sub Structure | 4th to 5th floor | L2/507 | 2024-10-20 | 2024-10-20 | Reinforcement | Check formwork and stair st-4 reinforcement and allow for concrete pouring zone 7 | (+51'-9'' to +62'-9'') | Grid G-H/1-3 | A | 2024-10-24
| Sub Structure | 6th floor | L2/508 | 2024-10-21 | 2024-10-21 | formwork | Check stair st-2 formwork zone 7 | (+73'-9'') | Grid P-Q/6-7 | A | 2024-10-24
| Sub Structure | 6th floor | L2/509 | 2024-10-21 | 2024-10-21 | Slab reinforcement | Check slab rienforcement and allow for concrete pouring zone 6 & 7 | (+73'-9'') | Grid N-U/6-12 | A | 2024-10-24
| Sub Structure | basement | L2/510 | 2024-10-21 | 2024-10-21 | compaction | Check 8th layer compaction of sand along fron side RWT zone 6 & 7 | (-10'-0'' to -9'-0'') | Grid T/1-12 | A | 2024-10-24
| Sub Structure | basement | L2/511 | 2024-10-21 | 2024-10-21 | compaction | Check 9th layer compaction of sand along fron side RWT zone 7 | (-9'-0'' to -8'-0'') | Grid T/1-12 | A | 2024-10-24
| Sub Structure | basement | L2/512 | 2024-10-21 | 2024-10-21 | Termite proofing | Check termite proofing front side RWT zone 6 & 7 | (-10'-0'' to -8'-0'') | Grid T/1-12 | A | 2024-10-24
| Sub Structure | GF | L2/513 | 2024-10-21 | 2024-10-21 | Reinforcement | Check rain tank slab rienforcement and allow for concrete pouring zone 7 | (+0'-00'') | Grid L-P/1 | A | 2024-10-24
| Sub Structure | Basement to GF | L2/514 | 2024-10-21 | 2024-10-21 | Reinforcement | Check rain harvesting tank wall reinforcement and alow for concrete pouring zone 7 | (-11'-9'' to +0'-0'') | Grid P-T/1 | A | 2024-10-24
| Sub Structure | 5th to 6th floor | L2/515 | 2024-10-21 | 2024-10-21 | Reinforcement | Check service lift rienforcement and allow for concrete pouring zone 7 | (+62'-9'' to +73'-9'') | Grid H-J/3-3 | A | 2024-10-24
| Sub Structure | 6th to 7th floor | L2/516 | 2024-10-22 | 2024-10-22 | column reinforcement | Check columns (12 Nos) reinforcement zone 6 & 7 | (+73'-9'' to +84'-9'') | Grid S-U/6-12 | A | 2024-10-31
| Sub Structure | GF | L2/517 | 2024-10-22 | 2024-10-22 | rain tank | Check rain tank above slab zone 7 | (+0'-00'') | Grid L-P/1 | A | 2024-10-24
| Sub Structure | 6th floor | L2/518 | 2024-10-22 | 2024-10-22 | level | Check level of slab & layout of columns & sw-08 zone 6 & 7 | (+73'-9'') | Grid N-U/6-12 | A | 2024-10-24
| Sub Structure | 6th to 7th floor | L2/519 | 2024-10-23 | 2024-10-23 | column reinforcement | Check column (8 Nos) and SW-08 (2 Nos) reinforcement zone 6 | (+73'-9'' to +84'-9'') | Grid N-Q/8-12 | A | 2024-10-31
| Sub Structure | 5th to 6th floor | L2/520 | 2024-10-23 | 2024-10-23 | level, layout | Check level, layout of stair st-2 zone 7 | (+62'-9'' to +73'-9'') | Grid N-Q/5-7 | A | 2024-10-31
| Sub Structure | 6th to 7th floor | L2/521 | 2024-10-23 | 2024-10-23 | column reinforcement | Check columns (9 Nos) and SW-08 (1 No) reinforcement and allow for concrete pouring zone 6 | (+73'-9'' to +84'-9'') | Grid U/8-12, S/8-12, Q/12 | A | 2024-10-31
| Sub Structure | 6th floor | L2/522 | 2024-10-24 | 2024-10-24 | Beam reinforcement | Check beam reinforcement zone 7 | (+73'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-10-31
| Sub Structure | 5th to 6th floor | L2/523 | 2024-10-24 | 2024-10-24 | formwork, reinforcement | Check formwrok, reinforcement of stair st-2 & allow for concrete pouring zone 7 | (+62'-9'' to +73'-9'') | Grid N-Q/5-7 | A | 2024-10-31
| Sub Structure | 6th to 7th floor | L2/524 | 2024-10-24 | 2024-10-24 | column reinforcement | Check columns (6 Nos) and SW-8 (1 Nos) reinforcement & allow for concrete pouring zone 6 | (+73'-9'' to +84'-9'') | Grid U/12, N/8-12, Q/11 | A | 2024-10-31
| Sub Structure | 6th floor | L2/525 | 2024-10-25 | 2024-10-25 | Slab reinforcement | Check slab top and bottom reinforcement zone 7 | (+73'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-10-31
| Sub Structure | 6th floor | L2/526 | 2024-10-25 | 2024-10-25 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring zone 7 | (+73'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-10-31
| Sub Structure | 6th to 7th floor | L2/527 | 2024-10-25 | 2024-10-25 | column reinforcement | Check columns (4 Nos) reinforcement and allow for concrete pouring zone 6 | (+73'-9'' to +84'-9'') | Grid Q/8-10, S/7 | A | 2024-10-31
| Sub Structure | 6th to 7th floor | L2/528 | 2024-10-25 | 2024-10-25 | column reinforcement | Check column (1 Nos) reinforcement and allow for concrete pouring zone 7 | (+73'-9'' to +84'-9'') | Grid U/6 | A | 2024-11-06
| Sub Structure | 6th to 7th floor | L2/529 | 2024-10-26 | 2024-10-26 | column reinforcement | Check columns (23 Nos) reinforcement zone 7 | (+73'-9'' to +84'-9'') | Grid K-M/1-7, N-U/1-5 | A | 2024-10-31
| Sub Structure | 6th floor | L2/530 | 2024-10-26 | 2024-10-26 | level, layout | Check level, layout lift wall & column zone 7 | (+73'-9'') | Grid G-U/1-5 | A | 2024-10-31
| Sub Structure | Basement to GF | L2/531 | 2024-10-28 | 2024-10-26 | Reinforcement | Check rain harvesting tank wall and allow for concrete pouring zone 7 | (-11'-9'' to +0'-00'') | Grid P-T/1 | A | 2024-10-31
| Sub Structure | 4th to 5th floor | L2/532 | 2024-10-28 | 2024-10-26 | Reinforcement | Check formwork and reinforcement of hanging beam & allow for concrete pouring zone 7 | (+57' to +62'-9'') | Grid G-H/1 | A | 2024-10-31
| Sub Structure | 6th to 7th floor | L2/533 | 2024-10-28 | 2024-10-27 | Reinforcement | Check column (7 Nos) reinforcement and allow for concrete pouring zone 7 | (+73'-9'' to +84'-9'') | Grid R-U/1-5 | A | 2024-10-31
| Sub Structure | 6th to 7th floor | L2/534 | 2024-10-28 | 2024-10-28 | Reinforcement | Check columns (8 Nos) & lift wall rienforcement zone 7 | (+73'-9'' to +84'-9'') |  | A | 2024-10-31
| Sub Structure | 6th to 7th floor | L2/535 | 2024-10-28 | 2024-10-28 | Reinforcement | Check columns (10 Nos) reinforcement & allow for concrete pouring zone 7 | (+73'-9'' to +84'-9'') | Grid L/5-7, M-Q/1-7 | A | 2024-10-31
| Sub Structure | 6th to 7th floor | L2/536 | 2024-10-28 | 2024-10-28 | lift reinforcement | Check service lift reinforcement zone 7 | (+73'-9'' to +84'-9'') | Grid H-J/3-3 | A | 2024-10-31
| Sub Structure | GF | L2/537 | 2024-10-28 | 2024-10-28 | steel fixing | Check steel fixing of slab of rain water tank zone 7 | (+0'-0'') | Grid Q-U/1, U/1-3 | A | 2024-10-31
| Sub Structure | 6th to 7th floor | L2/538 | 2024-10-29 | 2024-10-29 | column reinforcement | Check columns (7 Nos) reinforcement and allow for concrete pouring zone 7 | (+73'-9'' to +84'-9'') | Grid H/5, J-K/1-5, L/1-3 | A | 2024-10-31
| Sub Structure | basement | L2/539 | 2024-10-30 | 2024-10-30 | compaction | Check 10th layer compaction backfilling of sand along front side RWT zone 6 & 7 | (-8'-0'' to -7'-3'') | Grid T/1-12 | A | 2024-11-06
| Sub Structure | basement | L2/540 | 2024-10-30 | 2024-10-30 | compaction | Check 11th layer compaction backfilling of sand along front side RWT zone 6 & 7 | (-7'-3'' to -6'-6'') | Grid T/1-12 | A | 2024-10-31
| Sub Structure | basement | L2/541 | 2024-10-30 | 2024-10-30 | Termite proofing | Check termite proofing front side along side RWT zone 6 & 7 | (-8'-0'' to -6'-6'') | Grid T/1-12 | A | 2024-10-31
| Sub Structure | basement | L2/542 | 2024-10-30 | 2024-10-30 | level | Check level of sand filling zone 6 & 7 | (-6.48') | Grid T/1-9 | A | 2024-11-06
| Sub Structure | basement | L2/543 | 2024-10-30 | 2024-10-30 | level | Check level of sand filling zone 6 & 7 | (-6.50') | Grid T/9-12 | A | 2024-11-06
| Sub Structure | basement | L2/544 | 2024-10-30 | 2024-10-30 | Joint treatment | Check joint treatment in RW outer side zone 1 & 7 | (-13'-00'' to +0'-00'') | Grid F-G/1 | A | 2024-11-06
| Sub Structure | GF | L2/545 | 2024-10-31 | 2024-10-30 | Reinforcement | Check slab rain water tank harvesting and allow for concrete pouring zone 7 | (+0'-00'') | Grid Q-U/1, U/1-3 | A | 2024-10-31
| Sub Structure | 6th to 7th floor | L2/546 | 2024-10-31 | 2024-10-30 | Reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring zone 7 | (+73'-9'' to +84'-9'') | Grid G/3-7, H-K/7 | A | 2024-10-31
| Sub Structure | GF | L2/547 | 2024-10-31 | 2024-10-30 | level | Check level of above slab rain tank zone 7 | (+0'-0'') | Grid Q-U/1, U/1-3 | A | 2024-11-06
| Sub Structure | 5th to 6th floor | L2/548 | 2024-10-31 | 2024-10-31 | level | Check level & layout of st-04 zone 7 | (+62'-9'' to +73'-9'') | Grid G-H/1-3 | A | 2024-11-06
| Sub Structure | 5th to 6th floor | L2/549 | 2024-11-01 | 2024-10-31 | Reinforcement | Check formwork and stair st-4 reinforcement & allow to start concrete work zone 7 | (+62'-9'' to +73'-9'') | Grid G-H/1-3 | A | 2024-11-06
| Sub Structure | 6th to 7th floor | L2/550 | 2024-11-01 | 2024-10-31 | Reinforcement | Check lift wall reinforcement and allow for concrete pouring zone 7 | (+73'-9'' to +84'-9'') | Grid N-Q/5-7 | A | 2024-11-06
| Sub Structure | 7th floor | L2/551 | 2024-11-02 | 2024-11-02 | Reinforcement | Check beam reinforcement zone 6 & 7 | (+84'-9'') | Grid N-U/5-12 | A | 2024-11-06
| Sub Structure | 7th floor | L2/552 | 2024-11-02 | 2024-11-02 | steel fixing | Check steel fixing of slab top & bottom zone 6 & 7 | (+84'-9'') | Grid N-U/6-12 | A | 2024-11-06
| Sub Structure | 7th floor | L2/553 | 2024-11-02 | 2024-11-02 | Reinforcement | Check slab reinforcement & allow for concrete pouring zone 6 & 7 | (+84'-9'') | Grid N-U/6-12 | A | 2024-11-06
| Sub Structure | 7th floor | L2/554 | 2024-11-02 | 2024-11-02 | formwork | Check slab formwork along stair st-2 zone 7 | (+84'-9'') | Grid P-Q/6-7 | A | 2024-11-06
| Sub Structure | 6th to 7th floor | L2/555 | 2024-11-04 | 2024-11-02 | column reinforcement | Check columns (2 Nos) and service lift reinforcement and allow for concrete pouring zone 7 | (+73'-9'' to +84'-9'') | Grid G-H/1, H-J/3-3 | A | 2024-11-06
| Sub Structure | 7th to 8th floor | L2/556 | 2024-11-04 | 2024-11-04 | column reinforcement | Check columns (20 Nos) reinforcement zone 6 & 7 | (+84'-9'' to +95'-9'') | Grid N-U/6-12 | A | 2024-11-06
| Sub Structure | 6th floor | L2/557 | 2024-11-04 | 2024-11-04 | level. Layout | Check level & layout of slab of columns , sw-8 zone 6 & 7 | (+84'-9'') | Grid N-U/6-12 | A | 2024-11-06
| Sub Structure | 7th floor | L2/558 | 2024-11-05 | 2024-11-05 | Beam reinforcement | Check beam reinforcement zone 7 | (+84'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-11-09
| Sub Structure | 7th floor to 8th floor | L2/559 | 2024-11-05 | 2024-11-05 | SW-8 reinforcement | Check sw-8 (2 Nos) reinforcement zone 6 | (+84'-9'' to +95'-9'') | Grid N/11, Q/12 | A | 2024-11-06
| Sub Structure | 7th to 8th floor | L2/560 | 2024-11-06 | 2024-11-05 | column reinforcement | Check column (10 Nos) reinforcement and allow for concrete pouring zone 6 & 7 | (+84'-9'' to +95'-9'') | Grid S/9-12, U/6-12 | A | 2024-11-06
| Sub Structure | 6th to 7th floor | L2/561 | 2024-11-06 | 2024-11-06 | level, layout | Check level, layout of stair st-02 zone 7 | (+73'-9'' to +84'-9'') | Grid N-Q/5-7 | A | 2024-11-09
| Sub Structure | 7th floor to 8th floor | L2/562 | 2024-11-07 | 2024-11-06 | column reinforcement | Check column (9 Nos) and sw-8 (1 No) and allow for concrete pouring zone 6 & 7 | (+84'-9'' to +95'-9'') | Grid N/8-10, N/12, Q/8-12, S/8 | A | 2024-11-09
| Sub Structure | 7th floor | L2/563 | 2024-11-07 | 2024-11-07 | Reinforcement | Check slab top and bottom reinforcement zone 7 | (+84'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-11-09
| Sub Structure | 7th floor | L2/564 | 2024-11-07 | 2024-11-07 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring zone 7 | (+84'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-11-09
| Sub Structure | 7th floor | L2/565 | 2024-11-07 | 2024-11-07 | formwork | Check slab formwork along stair st-4 zone 7 | (+84'-9'') | Grid G-H/3-3 | A | 2024-11-09
| Sub Structure | 6th to 7th floor | L2/566 | 2024-11-08 | 2024-11-07 | Reinforcement | Check formwork and reinforcement of stair st-2 and allow for concrete pouring zone 7 | (+73'-9'' to +84'-9'') | Grid N-Q/5-7 | A | 2024-11-09
| Sub Structure | 5th to 6th floor | L2/567 | 2024-11-08 | 2024-11-07 | Reinforcement | Check formwork and reinforcement of hanging beam & allow for concrete pouring zone 7 | (+68'-41/2'' to +73'-9'') | Grid G-H/1 | A | 2024-11-14
| Sub Structure | 7th to 8th floor | L2/568 | 2024-11-08 | 2024-11-07 | Reinforcement | Check column (11 Nos) reinforcement and allow for concrete pouring zone 7 | (+84'-9'' to +95'-9'') | Grid S/7 | A | 2024-11-09
| Sub Structure | 7th to 8th floor | L2/569 | 2024-11-08 | 2024-11-09 | Reinforcement | Check columns (31 Nos) reinforcement zone 7 | (+84'-9'' to +95'-9'') | Grid G-U/1-7 | A | 2024-11-14
| Sub Structure | 7th floor | L2/570 | 2024-11-08 | 2024-11-08 | level, layout | Check level, layout of slab, lift wall & columns zone 7 | (+84'-9'') | Grid G-U/1-5 | A | 2024-11-14
| Sub Structure | Basement to GF | L2/571 | 2024-11-08 | 2024-11-08 | Reinforcement | Check rain UGWT reinforcement for domestic walls and allow for concrete pouring zone 7 | (-11'-9'' to +0'-00'') | Grid T/5-9 | A | 2024-11-14
| Sub Structure | 7th floor to 8th floor | L2/572 | 2024-11-09 | 2024-11-09 | Reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring zone 6 & 7 | (+84'-9'' to +95'-9'') | Grid P-U/1-5, N/11 | A | 2024-11-14
| Sub Structure | 7th floor to 8th floor | L2/573 | 2024-11-10 | 2024-11-10 | Reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring zone 7 | (+84'-9'' to +95'-9'') | Grid K-N/1-5 | A | 2024-11-14
| Sub Structure | 7th floor to 8th floor | L2/574 | 2024-11-11 | 2024-11-11 | lift reinforcement | Check lift wall reinforcement zone 7 | (+84'-9'' to +95'-9'') | Grid N-Q/5-7 | A | 2024-11-14
| Sub Structure | 7th floor to 8th floor | L2/575 | 2024-11-11 | 2024-11-11 | lift reinforcement | Check service lift reinforcement zone 7 | (+84'-9'' to +95'-9'') | Grid H-J/3-3 | A | 2024-11-14
| Sub Structure | 7th floor to 8th floor | L2/576 | 2024-11-11 | 2024-11-11 | column reinforcement | Check columns (5 Nos) reinforcement and allow for concrete pouring zone 7 | (+84'-9'' to +95'-9'') | Grid G-M/7 | A | 2024-11-14
| Sub Structure | 6th to 7th floor | L2/577 | 2024-11-12 | 2024-11-12 | level, layout | Check level, layout of st-04 zone 7 | (+73'-9'' to +84'-9'') | Grid G-H/1-3 | A | 2024-11-18
| Sub Structure | basement | L2/578 | 2024-11-12 | 2024-11-12 | Primer, membrane | Check vertical primer, membrane on RTW zone 7 | (-2.083 to +0'-00'') | Grid G-U/1, T/1-3 | A | 2024-11-18
| Sub Structure | 6th to 7th floor | L2/579 | 2024-11-12 | 2024-11-12 | Reinforcement | Chec k formwork, reinforcement of stair st-04 and allow for concrete pouring zone 4 | (+73'-9'' to +84'-9'') | Grid G-H/1-3 | A | 2024-11-18
| Sub Structure | 7th to 8th floor | L2/580 | 2024-11-11 | 2024-11-11 | Reinforcement | Check column (4 Nos) reinforcement and allow for concrete pouring zone 7 | (+84'-9'' to +95'-9'') | Grid J/1, H/5, G/3-5 | A | 2024-11-18
| Sub Structure | 6th to 7th floor | L2/581 | 2024-11-13 | 2024-11-13 | Reinforcement | Check formwork and stair hanging beam reinforcement and allow for concrete pouring zone 4 | (+79'-41/2 to +84'-9'') | Grid G-H/1 | A | 2024-11-18
| Sub Structure | 7th to 8th floor | L2/582 | 2024-11-14 | 2024-11-14 | Reinforcement | Check lift wall reinforcement and allow for concrete pouring zone 7 | (+84'-9'' to +95'-9'') | Grid N-Q/5-7 | A | 2024-11-22
| Sub Structure | 8th floor | L2/583 | 2024-11-15 | 2024-11-15 | Beam reinforcement | Check beam reinforcement zone 6 & 7 | (+95'-9'') | Grid N-U/5-12 | A | 2024-11-22
| Sub Structure | 8th floor | L2/584 | 2024-11-16 | 2024-11-17 | Steel fixing | Check steel fixing of slab top and bottom zone 6 & 7 | (+95'-9'') | Grid N-U/6-12 | A | 2024-11-28
| Sub Structure | 8th floor | L2/585 | 2024-11-26 | 2024-11-26 | slab formwork | Check slab formwork along stair st-02 zone 6 | (+95'-9'') | Grid P-Q/6-7 | A | 2024-11-28
| Sub Structure | 8th floor | L2/586 | 2024-11-28 | 2024-11-27 | Reinforcement | Check slab reinforcement and allow for concrete ;pouring zone 6 & 7 | (+95'-9'') | Grid N-U/6-12 | A | 2024-11-28
| Sub Structure | 8th to 9th floor | L2/587 | 2024-11-28 | 2024-11-28 | column reinforcement | Check columns (10 Nos) reinforcement zone 6 & 7 | (+95'-9'' to +106'-9'') | Grid U/6-12, S/9-12 | A | 2024-12-02
| Sub Structure | 8th floor | L2/588 | 2024-11-28 | 2024-11-28 | level, layout | Check level, layout of columns, SW-08 zone 6 & 7 | (+95'-9'') | Grid N-U/6-12 | A | 2024-12-02
| Sub Structure | 8th to 9th floor | L2/589 | 2024-11-29 | 2024-11-29 | Reinforcement | Check columns (10 Nos) and SW-8 (2 Nos) reinforcement zone 6 & 7 | (+95'-9'' to +106'-9'') | Grid N-Q/8-12, S/7-8 | A | 2024-12-10
| Sub Structure | 7th to 8th floor | L2/590 | 2024-11-29 | 2024-11-28 | Reinforcement | Check columns (2 Nos) and service lift reinforcement and allow for concrete pouring zone 7 | (+84'-9'' to +95'-9'') | Grid G-H/1, H-J/3-3 | A | 2024-12-02
| Sub Structure | 7th to 8th floor | L2/591 | 2024-11-29 | 2024-11-29 | level, layout | Check level, layout of stair st-02 zone 7 | (+84'-9'' to +95'-9'') | Grid N-Q/5-7 | A | 2024-12-02
| Sub Structure | basement | L2/592 | 2024-11-29 | 2024-11-29 | RW treatment | Check expansion joint treatment in RW inner zone 1 & 7 | (-12'-3'' to +0'-00'') | Grid F-G/1 | A | 2024-12-02
| Sub Structure | 8th to 9th floor | L2/593 | 2024-11-30 | 2024-11-29 | column reinforcement | Check columns (4 Nos) reinforcement and allow to start concrete pouring zone 6 | (+95'-9'' to +106'-9'') | Grid U/9-11, S/9 | A | 2024-12-02
| Sub Structure | 7th to 8th floor | L2/594 | 2024-12-01 | 2024-11-30 | Reinforcement | Check formwork and reinforcement and allow for concrete pouring stair st-02 zone 7 | (+84'-9'' to +95'-9'') | Grid N-Q/5-7 | A | 2024-12-02
| Sub Structure | 8th floor | L2/595 | 2024-12-02 | 2024-12-02 | Beam reinforcement | Check beam reinforcement zone 7 | (+95'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-12-10
| Sub Structure | Basement to GF | L2/596 | 2024-12-03 | 2024-12-02 | UGWT Reinforcement | Check UGWT reinforcement for domestic wall and allow for concrete pouring zone 6 & 7 | (-11'-9'' to +0'-00'') | Grid T/5-9 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/597 | 2024-12-03 | 2024-12-02 | Reinforcement | Check column (6 Nos) and SW-08 (1 No) reinforcement and allow for concrete pouring zone 6 | (+95'-9'' to +106'-9'') | Grid N/10-12, Q/12, S/10-12, U/12 | A | 2024-12-10
| Sub Structure | 8th floor | L2/598 | 2024-12-03 | 2024-12-03 | Reinforcement | Check slab top and bottom reinforcemetn zone 7 | (+95'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-12-10
| Sub Structure | 8th floor | L2/599 | 2024-12-03 | 2024-12-02 | formwork | Check slab formwork along st-04 zone 7 | (+95'-9'') | Grid G-H/3-3 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/600 | 2024-12-04 | 2024-12-03 | Reinforcement | Check column (4 Nos) reinforcement and allow for concrete pouring zone 6 | (+95'-9'' to +106'-9'') | Grid N/8-9, S-U/8 | A | 2024-12-10
| Sub Structure | 8th floor | L2/601 | 2024-12-04 | 2024-12-04 | Reinforcement | Check slab reinforcement and allow for concrete pouring zone 7 | (+95'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/602 | 2024-12-05 | 2024-12-04 | column reinforcement | Check columns (6 Nos) and sw-8 (1 No) reinforcement and allow for concrete pouring zone 6 | (+95'-9'' to +106'-9'') | Grid N-Q/8, Q/10-11, N/11, S/7, U/6 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/603 | 2024-12-05 | 2024-12-05 | column reinforcement | Check column (11 Nos) reinforcement zone 7 | (+95'-9'' to +106'-9'') | Grid N-U/1-5 | A | 2024-12-10
| Sub Structure | 8th floor | L2/604 | 2024-12-05 | 2024-12-05 | level, layout | check level, layout of slab, lift wall & column zone 7 | (+95'-9'') | Grid G-U/1-5 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/605 | 2024-12-06 | 2024-12-06 | Reinforcement | Check columns (10 Nos) reinforcement zone 7 | (+95'-9'' to +106'-9'') | Grid J-K/1, L-M/1-7 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/606 | 2024-12-06 | 2024-12-06 | Reinforcement | Check lift wall reinforcement zone 7 | (+95'-9'' to +106'-9'') | Grid N-Q/5-7 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/607 | 2024-12-06 | 2024-12-06 | Reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring zone 7 | (+95'-9'' to +106'-9'') | Grid Q/1, R-U/1-5 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/608 | 2024-12-07 | 2024-12-07 | Reinforcement | Check columns (10 Nos) reinforcement zone 7 | (+95'-9'' to +106'-9'') | Grid G-H/1-7, K/3-7 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/609 | 2024-12-07 | 2024-12-07 | Reinforcement | Check column (8 Nos) reinforcement and allow for concrete pouring zone 7 | (+95'-9'' to +106'-9'') | Grid G-H/1, L-P/1, M-Q/3 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/610 | 2024-12-09 | 2024-12-09 | lift reinforcement | Check service lift reinforcement zone 7 | (+95'-9'' to +106'-9'') | Grid H-J/3-3 | A | 2024-12-10
| Sub Structure | 7th to 8th floor | L2/611 | 2024-12-09 | 2024-12-09 | level, layout | Check level, layout of st-04 zone 7 | (+84'-9'' to +95'-9'') | Grid G-H/1-3 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/612 | 2024-12-07 | 2024-12-09 | Reinforcement | Check column (8 Nos) reinforcement and allow for concrete pouring zone 7 | (+95'-9'' to +106'-9'') | Grid K-L/3-7, M/5-7 | A | 2024-12-10
| Sub Structure | 8th to 9th floor | L2/613 | 2024-12-10 | 2024-12-09 | Reinforcement | Check lift wall reinforcement and allow for concrete pouring zone 7 | (+95'-9'' to +106'-9'') | Grid N-Q/5-7 | A | 2024-12-10
| Sub Structure | 7th to 8th floor | L2/614 | 2024-12-11 | 2024-12-10 | Reinforcement | Check formwork and reinforcement of stair st-4 and allow for concrete pouring zone 4 | (+84'-9'' to +95'-9'') | Grid G-H/1-3 | A | 2024-12-16
| Sub Structure | Basement to GF | L2/615 | 2024-12-11 | 2024-12-10 | Reinforcement | Check UGWT for domestic wall reinforcement and allow for concrete poring zone 6 | (-11'-9'' to +0'-0'') | Grid T/9-11 | A | 2024-12-19
| Sub Structure | 8th to 9th floor | L2/616 | 2024-12-12 | 2024-12-11 | Reinforcement | Check columns (7 Nos) reinforcement and allow for concrete pouring zone 7 | (+95'-9'' to +106'-9'') | Grid G/3-7, H/5-7, J-K/1 | A | 2024-12-16
| Sub Structure | 9th floor | L2/617 | 2024-12-13 | 2024-12-13 | Reinforcement | Check beam reinforcement zone 6 | (+106'-9'') | Grid N-U/8-12, P-U/5-6 | A | 2024-12-16
| Sub Structure | 9th floor | L2/618 | 2024-12-13 | 2024-12-13 | steel fixing | Check steel fixing of slab top and bottom zone 6 & 7 | (+106'-9'') | Grid N-U/6-12 | A | 2024-12-16
| Sub Structure | 8th to 9th floor | L2/619 | 2024-12-14 | 2024-12-13 | lift reinforcement | Check service lift reinforcement and allow for concrete pouring zone 7 | (+95'-9'' to +106'-9'') | Grid H-J/3-3 | A | 2024-12-16
| Sub Structure | 7th to 8th floor | L2/620 | 2024-12-14 | 2024-12-13 | Reinforcement | check formwork and hanging beam reinforcement and allwo for concrete pouring zone 7 | (+90'-41/2'' to +95'-9'') | Grid G-H/1 | A | 2024-12-16
| Sub Structure | 9th floor | L2/621 | 2024-12-14 | 2024-12-14 | slab formwork | Check slab formwork along st-2 zone 7 | (+106'-9'') | Grid P-Q/6-7 | A | 2024-12-16
| Sub Structure | 9th floor | L2/622 | 2024-12-14 | 2024-12-14 | Slab reinforcement | Check slab reinforcement and allow for concrete pouring zone 6 & 7 | (+106'-9'') | grid N-U/6-12 | A | 2024-12-16
| Sub Structure | 9th to 10th floor | L2/623 | 2024-12-14 | 2024-12-15 | column reinforcement | Check column (10 Nos) reinforcement zone 6 & 7 | (+106'-9'' to +117'-9'') | Grid U/6-12, S/9-12 | A | 2024-12-16
| Sub Structure | 8th floor | L2/624 | 2024-12-15 | 2024-12-15 | level, layout | Check level, layout of columns and sw-8 zone 6 & 7 | (+95'-9'') | Grid N-U;/6-12 | A | 2024-12-16
| Sub Structure | 9th floor | L2/625 | 2024-12-16 | 2024-12-16 | Reinforcement | Check beam reinforcement zone 7 | (+106'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-12-19
| Sub Structure | 9th to 10th floor | L2/626 | 2024-12-16 | 2024-12-16 | Reinforcement | check column (10 Nos) reinforcement and sw-8 (1 No) zone 6 & 7 | (+106'-9'' to +117'-9'') | Grid N-Q/8-12, S/7-8 | A | 2024-12-19
| Sub Structure | 9th to 10th floor | L2/627 | 2024-12-17 | 2024-12-16 | Reinforcement | Check column (10 Nos) and sw-8 (1 No) reinforcement and allow for concrete pouring zone 6 | (+106'-9'' to +117'-9'') | Grid S-U/8-12, Q/12 | A | 2024-12-19
| Sub Structure | 9th floor | L2/628 | 2024-12-17 | 2024-12-16 | slab formwork | Check slab formwork along st-4 zone 7 | (+106'-9'') | Grid G-H/3-3 | A | 2024-12-20
| Sub Structure | 8th to 9th floor | L2/629 | 2024-12-17 | 2024-12-17 | level, layout | Check level, layout of stair st-02 zone 7 | (+84'-9'' to +95'-9'') | Grid N-Q/5-7 | A | 2024-12-20
| Sub Structure | 8th to 9th floor | L2/630 | 2024-12-18 | 2024-12-17 | Reinforcement | Check formwork and reinforcement of stair st-2 and allow for concrete pouring zone 7 | (+95'-9'' to +106'-9'') | Grid N-Q/5-7 | A | 2024-12-19
| Sub Structure | 9th to 10th floor | L2/631 | 2024-12-18 | 2024-12-17 | column reinforcement | Check column (10 Nos) and sw-8 (1 No) reinforcement and allow for concrete pouring zone 6 | (+106'-9'' to +117'-9'') | Grid N-Q/8-11, N/12, S-U/6-7 | A | 2024-12-19
| Sub Structure | 9th floor | L2/632 | 2024-12-18 | 2024-12-18 | Slab reinforcement | Check slab top and bottom reinforcement zone 7 | (+106'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-12-20
| Sub Structure | 9th floor | L2/633 | 2024-12-19 | 2024-12-19 | Reinforcement | Check slab reinforcement and allow for concrete pouring zone 7 | (+106'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2024-12-20
| Sub Structure | 9th to 10th floor | L2/634 | 2024-12-20 | 2024-12-20 | column reinforcement | Check column (7 Nos) reinforcement zone 7 | (+106'-9'' to +117'-9'') | Grid R-U/1-5 | A | 2024-12-23
| Sub Structure | 9th floor | L2/635 | 2024-12-20 | 2024-12-20 | level, layout | Check level, layout of slab lift wall column zone 7 | (+106'-9'') | Grid G-U/1-7 | A | 2024-12-23
| Sub Structure | 9th to 10th floor | L2/636 | 2024-12-21 | 2024-12-21 | column reinforcement | Check columns (24 Nos) reinforcement zone 7 | (+106'-9'' to +117'-9'') | Grid G-Q/1-7, | A | 2024-12-23
| Sub Structure | 9th to 10th floor | L2/637 | 2024-12-21 | 2024-12-22 | lift reinforcement | Check lift wall rienforcement zone 7 | (+106'-9'' to +117'-9'') | Grid N-Q/5-7 | A | 2024-12-23
| Sub Structure | 9th to 10th floor | L2/638 | 2024-12-23 | 2024-12-21 | column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring zone 7 | (+106'-9'' to +117'-9'') | Grid P-U/1-5 | A | 2024-12-31
| Sub Structure | 9th to 10th floor | L2/639 | 2024-12-23 | 2024-12-22 | column reinforcement | check columns (8 Nos) reinforcement and allow for concrete pouring zone 7 | (+106'-9'' to +117'-9'') | Grid L-P/1-7 | A | 2024-12-31
| Sub Structure | 9th to 10th floor | L2/640 | 2024-12-23 | 2024-12-23 | Steel fixing | Check steel fixing of service lift zone 7 | (+106'-9'' to +117'-9'') | Grid H-J/1-5 | A | 2024-12-31
| Sub Structure | 9th to 10th floor | L2/641 | 2024-12-23 | 2024-12-23 | column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring zone 7 | (+106'-9'' to +117'-9'') | Grid G-L/1-7 | A | 2024-12-31
| Sub Structure | basemetn to GF | L2/642 | 2024-12-25 | 2024-12-24 | water tank reinforcement | Check under ground water tank wall reinforcement and allow for concrete pouring zone 6 | (-11'-9'' to +0'-00'') | Grid T/12-14 | A | 2024-12-31
| Sub Structure | 10th floor | L2/643 | 2024-12-26 | 2024-12-26 | steel fixing | Check steel fixing of beam zone 6 & 7 | (+117'-9'') | Grid N-U/5-12 | A | 2024-12-31
| Sub Structure | 9th to 10th floor | L2/644 | 2024-12-27 | 2024-12-26 | Reinforcement | Check lift wall rienforcement and allow for concrete pouring zone 7 | (+106'-9'' to +117'-9'') | Grid N-Q/4-7 | A | 2024-12-31
| Sub Structure | 8th to 9th floor | L2/645 | 2024-12-27 | 2024-12-26 | level, layout | Check level, layout of st-04 Zone 7 | (+95'-9'' to +106'-9'') | Grid G-H/1-3 | A | 2024-12-31
| Sub Structure | 9th to 10th floor | L2/646 | 2024-12-27 | 2024-12-26 | column reinforcement | Check columns (3 Nos) reinforcement and allow for concrete pouring zone 7 | (+106'-9'' to +117'-9'') | Grid G-H/3-5 | A | 2024-12-31
| Sub Structure | 8th to 9th floor | L2/647 | 2024-12-27 | 2024-12-27 | formwork | Check formwork and rienforcement of stair st-04 and allow for concrete pouring zone 4 | (+95'-9'' to +106'-9'') | Grid G-H/1-3 | A | 2024-12-31
| Sub Structure | 10th floor | L2/648 | 2024-12-28 | 2024-12-28 | steel fixing | Check steel fixing of slab top and bottom zone 6 & 7 | (+117'-9'') | Grid N-U/6-12 | A | 2024-12-31
| Sub Structure | 10th floor | L2/649 | 2024-12-29 | 2024-12-29 | slab formwrok | Check slab formwork along st-02 zone 7 | (+117'-9'') | Grid P-Q/6-7 | A | 2024-12-31
| Sub Structure | 10th floor | L2/650 | 2024-12-30 | 2024-12-29 | Slab reinforcement | Check slab rienforcement and allow for concrete pouring zone 6 & 7 | (+117'-9'') | Grid N-U/6-12 | A | 2025-01-02
| Sub Structure | 9th to 10th floor | L2/651 | 2024-12-30 | 2024-12-29 | Reinforcement | Check service lift reinforcement and alow for concrete pouring zone 7 | (+106'-9'' to +117'-9'') | Grid H-J/3-3 | A | 2025-01-02
| Sub Structure | 9th to 10th floor | L2/652 | 2024-12-30 | 2024-12-30 | column reinforcement | Check columns (8 Nos) reinforcement zone 6 | (+117'-9'' to +130'-9'') | Grid U/8-12, S/912 | A | 2025-01-02
| Sub Structure | 10th floor | L2/653 | 2024-12-30 | 2024-12-30 | level | Check level of slab and layout of columns, sw-08 zone 6 & 7 | (+117'--9'') | Grid N-U/6-12 | A | 2025-01-05
| Sub Structure | 10th to 11th floor | L2/654 | 2024-12-31 | 2024-12-30 | column reinforcement | Check columns (10 Nos) reinforcement zone 6 & 7 | (+117'-9'' to +130'-9'') | Grid N/10,12, Q/8-11, S/7-9, U/6 | A | 2025-01-05
| Sub Structure | 9th to 10th floor | L2/655 | 2024-12-31 | 2024-12-31 | level, layout | Check level, layout of stair st-02 zone 7 | (+106'-9'' to +117'-9'') | Grid N-Q/5-7 | A | 2025-01-02
| Sub Structure | 10th to 11th floor | L2/656 | 2024-12-31 | 2024-12-31 | column reinforcement | Check columns (7 Nos) reinforcement and allow for concrete pouring zone 6 | (+117'-9'' to +130'-9'') | grid U/9-12, S/9-11 | A | 2025-01-02
| Sub Structure | 9th to 10th floor | L2/657 | 2025-01-01 | 2025-01-01 | formwork | Check formwork and reinforcement of stair st-02 and allow for concrete pouring zone 7 | (+106'-9'' to +117'-9'') | Grid N-Q/6-7 | A | 2025-01-02
| Sub Structure | 10th floor | L2/658 | 2025-01-01 | 2025-01-01 | Reinforcement | Check beam reinforcement zone 7 | (+117'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2025-01-05
| Sub Structure | 10th to 11th floor | L2/659 | 2025-01-01 | 2025-01-01 | column reinforcement | Check columns (2 Nos) and sw-08 reinforcement zone 6 | (+117'-9'' to +130'-9'') | Grid N/8-9, N/11, Q/12 | A | 2025-01-05
| Sub Structure | 10th to 11th floor | L2/660 | 2025-01-02 | 2025-01-01 | column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring zone 6 | (+117'-9'' to +130'-9'') | Grid N/8-12, Q/8-12, S/12, U/8 | A | 2025-01-05
| Sub Structure | 10th floor | L2/661 | 2025-01-02 | 2025-01-02 | Slab reinforcement | Check slab top and bottom reinforcement zone 7 | (+117'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2025-01-05
| Sub Structure | 10th to 11th floor | L2/662 | 2025-01-03 | 2025-01-02 | Reinforcement | Check columns (2 Nos) and Sw-08 (1 No) reinforcement and allow for concrete pouring zone 6 | (+117'-9'' to +130'-9'') | Grid N-Q/12, S/7 | A | 2025-01-05
| Sub Structure | 10th floor | L2/663 | 2025-01-03 | 2025-01-03 | formwork | Check slab formwork along st-4 zone 7 | (+117'-9'') | Grid G-H/3-3 | A | 2025-01-07
| Sub Structure | 10th floor | L2/664 | 2025-01-03 | 2025-01-03 | Reinforcement | check slab reinforcement and allow for concrete pouring zone 7 | (+117'-9'') | grid G-N/1-7, N-U/1-5 | A | 2025-01-07
| Sub Structure | 10th to 11th floor | L2/665 | 2025-01-04 | 2025-01-04 | Reinforcement | Check columns (31 Nos) reinforcement zone 7 | (+117'-9'' to +130'-9'') | Grid G-H/1-7 | A | 2025-01-07
| Sub Structure | 10th floor | L2/666 | 2025-01-04 | 2025-01-04 | level, layout | Check level, layout of slab lift wall & column zone 7 | (+117'-9'') | Grid G-U/1-7 | A | 2025-01-07
| Sub Structure | 10th to 11th floor | L2/667 | 2025-01-04 | 2025-01-04 | column reinforcement | Check columns (1 Nos) and sw-08 (1 No) reinforcement and allow to start concrete pouring zone 7 & 6 | (+117'-9'' to +130'-9'') | Grid N/11, U/6 | A | 2025-01-07
| Sub Structure | 8th to 9th floor | L2/668 | 2025-01-04 | 2025-01-04 | Reinforcement | Check formwork and hanging beam reinforcement and allow to start concrete pouring zone 7 | (+101'-41/2'' to +106'-9'') | Grid G-H/1 | A | 2025-01-07
| Sub Structure | 10th to 11th floor | L2/669 | 2025-01-06 | 2025-01-06 | Reinforcement | Check lift wall rienforcement zone 7 | (+117'-41/2'') | Grid N-Q/5-7 | A | 2025-01-07
| Sub Structure | 10th to 11th floor | L2/670 | 2025-01-05 | 2025-01-05 | column reinforcement | Check columns (2 Nos) reinforcement and allow to start concrete pouring zone 7 | (+117'-9'' to +130'-9'') | Grid U/1-3 | A | 2025-01-07
| Sub Structure | basement | L2/671 | 2025-01-05 | 2025-01-05 | Reinforcement | Check under ground domestic tank wall reinforcement and allow for concrete pouring zone 6 | (-12'-3'' to +0'-00'') | Grid T/11-12 | A | 2025-01-07
| Sub Structure | 10th to 11th floor | L2/672 | 2025-01-07 | 2025-01-07 | Reinforcement | Check columns (10 Nos) reinforcement | (+117'-9'' to +130'-9'') | Grid M-T/1, N-S/3, S-U/4-5 | A | 2025-01-10
| Sub Structure | 10th to 11th floor | L2/673 | 2025-01-07 | 2025-01-07 | Steel fixing | Check steel fixing of service lift zone 7 | (+117'-9'' to +130'-9'') | Grid H-J/3-3 | A | 2025-01-10
| Sub Structure | 10th to 11th floor | L2/674 | 2025-01-08 | 2025-01-07 | column reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring zone 7 | (+117'-9'' to +130'-9'') | Grid G-L/1, L/3-5, M/3-7 | A | 2025-01-10
| Sub Structure | 10th to 11th floor | L2/675 | 2025-01-09 | 2025-01-08 | column reinforcement | Check column (9 Nos) reinforcement and allow for concrete pouring zone 7 | (+117'-9'' to +130'-9'') | Grid G-K/3-7, L/7 | A | 2025-01-10
| Sub Structure | 9th to 10th floor | L2/676 | 2025-01-10 | 2025-01-10 | level, layout | Check level, layout of st-4 zone 7 | (+106'-9'' to +117'-9'') | Grid G-H/1-3 | A | 2025-01-10
| Sub Structure | 10th to 11th floor | L2/677 | 2025-01-11 | 2025-01-10 | Reinforcement | Check lift wall reinforcement and allow for concrete pouring zone 7 | (+117'-9'' to +130'-9'') | grid N-Q/4-7 | A | 2025-01-10
| Sub Structure | 11th floor | L2/678 | 2025-01-11 | 2025-01-11 | Steel fixing | Check steel fixing of beam zone 6 & 7 | (+140'-9'') | Grid N-U/5-12 | A | 2025-01-15
| Sub Structure | 9th to 10th floor | L2/679 | 2025-01-11 | 2025-01-11 | Reinforcement | Check formwork and reinforcement of stair st-04 and allow for concrete pouring zone 7 | (+106'-9'' to +117'-9'') | Grid G-H/1-3 | A | 2025-01-15
| Sub Structure | 11th floor | L2/680 | 2025-01-13 | 2025-01-13 | Steel fixing | check steel fixing of slab top and bottom zone 6 & 7 | (+130'-9'') | Grid N-U/6-12 | A | 2025-01-15
| Sub Structure | 11th floor | L2/681 | 2025-01-13 | 2025-01-13 | slab formwork | Check slab formwork along st-02 zone 7 | (+130'-9'') | Grid P-Q/6-7 | A | 2025-01-15
| Sub Structure | 11th floor | L2/682 | 2025-01-13 | 2025-01-13 | Slab reinforcement | Check slab reinforcemetn and allow for concrete pouring zone 6 & 7 | (+130'-9'') | Grid N-U/6-12 | A | 2025-01-15
| Sub Structure | 11th floor to top floor | L2/683 | 2025-01-14 | 2025-01-14 | column reinforcement | Check column (20 Nos) & sw-08 (2 Nos) reinforcement zone 6 & 7 | (+117'-9'' to +130'-9'') | Grid N-U/6-12 | A | 2025-01-15
| Sub Structure | 11th floor | L2/684 | 2025-01-14 | 2025-01-14 | level | Check level of slab & layout of columns , sw-08 zone 6 & 7 | (+130'-9'') | Grid N-U/6-12 | A | 2025-01-15
| Sub Structure | 10th to 11th floor | L2/685 | 2025-01-15 | 2025-01-14 | Reinforcement | Check service lift rienforcement and allow for concrete pouring zone 7 | (+117'-9'' to +130'-9'') | Grid H-J/3-3 | A | 2025-01-15
| Sub Structure | 9th to 10th floor | L2/686 | 2025-01-15 | 2025-01-14 | Reinforcement | Check formwork and reinforcement of hanging beam and allow for concrete pouring zone 7 | (+112'-41/2'' to +117'-9'') | Grid G-H/1 | A | 2025-01-15
| Sub Structure | GF | L2/687 | 2025-01-15 | 2025-01-15 | Reinforcement | Check UGWT reinforcement above slab zone 7 | (+0'-00'') | Grid U/3-10 | A | 2025-01-15
| Sub Structure | Ground floor | L2/688 | 2025-01-16 | 2025-01-15 | Reinforcement | Check UGWT reinforcement and allow for concrete pouring zone 6 & 7 | (+0'-00'') | Grid U/3-9 | A | 2025-01-17
| Sub Structure | Top floor | L2/689 | 2025-01-16 | 2025-01-15 | Reinforcement | Check columns (10 Nos) reinforcement and allow for concrete pouring zone 6 | (+117'-9'' to +130'-9'') | Grid S-U/8-12 | A | 2025-01-17
| Sub Structure | Ground floor | L2/690 | 2025-01-16 | 2025-01-16 | level, layout | Check level, layout of UGWT of slab zone 6 & 7 | (+0'-00'') | Grid U/3-9 | A | 2025-01-17
| Sub Structure | 11th floor to top floor | L2/691 | 2025-01-17 | 2025-01-16 | Reinforcement | Check columns (2 Nos) and Sw-08 (1 Nos) reinforcement and allow for concrete pouring zone 6 | (+130'-9'' to +145'-9'') | Grid S-U/12, Q/12 | A | 2025-01-17
| Sub Structure | 11th floor | L2/692 | 2025-01-17 | 2025-01-17 | Reinforcement | Check beam reinforcement zone 7 | (+130'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2025-01-20 |  |  |  |  | 2025-01-17
| Sub Structure | 10th to 11th floor | L2/693 | 2025-01-17 | 2025-01-17 | level, layout | Check level, layout of stair st-02 zone 7 | (+117'-9'' to +130'-9'') | Grid N-Q/5-7 | A | 2025-01-20
| Sub Structure | 10th floor to 11th floor | L2/694 | 2025-01-18 | 2025-01-17 | Reinforcement | Check stair st-2 reinforcement and allow to start concrete pouring zone 7 | (+117'-9'' to +130'-9'') | Grid N-Q/6-7 | A | 2025-01-20
| Sub Structure | 11th floor to top floor | L2/695 | 2025-01-18 | 2025-01-17 | Reinforcement | Check columns (8 Nos) and sw-8 (1 No) reinforcement and allow for concrete pouring zone 6 | (+130'-9'' to +145'-9'') | Grid S-U/11, N/11, Q/10-11 | A | 2025-01-20
| Sub Structure | 11th floor | L2/696 | 2025-01-18 | 2025-01-18 | Reinforcement | Check slab top and bottom reinforcement zone 7 | (+130'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2025-01-20
| Sub Structure | 11th floor | L2/697 | 2025-01-18 | 2025-01-18 | formwork | Check slab formwork along st-4 zone 7 | (+130'-9'') | Grid G-H/3-3 | A | 2025-01-20
| Sub Structure | 11th floor | L2/698 | 2025-01-18 | 2025-01-18 | Reinforcement | Check slab reinforcement and allow for concrete pouring zone 7 | (+130'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2025-01-22
| Sub Structure | 11th floor to top floor | L2/699 | 2025-01-18 | 2025-01-18 | Reinforcement | Check columns (8 Nos) and sw-08 (1 No) & columns (2 Nos) and reinforcement and allow for concrete pouring zone 6 | (+130'-9'' to +145'-9'') | Grid N/8-10, N/12, Q/8-9, S-U/6-7, N/11, Q/10-11 | A | 2025-01-22
| Sub Structure | 10th floor to 11th floor | L2/700 | 2025-01-20 | 2025-01-19 | Reinforcement | Check lift wall reinforcement and allow for concrete pouring zone 7 | (+117'-9'' to +130'-9'') | Grid N-Q/4-7 | A | 2025-01-22
| Sub Structure | 11th floor to top floor | L2/701 | 2025-01-20 | 2025-01-20 | Reinforcement | Check column (31 Nos) reinforcement zone 7 | (+130'-9'' to +145'-9'') | Grid G-H/1-7 | A | 2025-01-22
| Sub Structure | 11th floor | L2/702 | 2025-01-20 | 2025-01-20 | level, layout | Check level, layout of slab, lift wall & columns zone 7 | (+130'-9'') | Grid G-U/1-7 | A | 2025-01-22
| Sub Structure | 11th floor to top floor | L2/703 | 2025-01-21 | 2025-01-20 | Reinforcement | Check columns (8 Nos) and sw-8 (1 No) reinforcement and allow for concrete pouring zone 6 | (+130'-9'' to +145'-9'') | Grid N/8-10, N/12, Q/8-9, S-U/6-7, Q/12 | A | 2025-01-22
| Sub Structure | basement | L2/704 | 2025-01-22 | 2025-01-21 | Reinforcement | Check under ground reinforcement for domestic tank wall and allow for concrete pouring zone 6 & 8 | (-11'-9'' to +0'-00'') | Grid T/11-12 | A | 2025-01-22
| Sub Structure | 11th floor to top floor | L2/705 | 2025-01-22 | 2025-01-21 | Reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | Grid Q-T/1-5, U/3-4 | A | 2025-01-22
| Sub Structure | 11th floor to top floor | L2/706 | 2025-01-22 | 2025-01-22 | Reinforcement | Check lift wall rienforcement zone 7 | (+130'-9'' to +145'-9'') | Grid N-Q/5-7 | A | 2025-01-27
| Sub Structure | 11th floor to top floor | L2/707 | 2025-01-22 | 2025-01-22 | Reinforcement | Check columns (8 Nos) and (2 Nos) reinforcement and allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | Grid P-U/1-5 | A | 2025-01-27
| Sub Structure | 11th floor to top floor | L2/708 | 2025-01-22 | 2025-01-22 | steel fixing | check steel fixing of service lift zone 7 | (+130'-9'' to +145'-9'') | Grid H-J/3-3 | A | 2025-01-27
| Sub Structure | Ground floor | L2/709 | 2025-01-23 | 2025-01-23 | Reinforcement | Check UGWT Reinforcement zone 6 | (+0'-00'') | Grid U/10-12 | A | 2025-01-29
| Sub Structure | Ground floor | L2/710 | 2025-01-24 | 2025-01-23 | Reinforcement | Check UGWT reinforcement and allow for concrete pouring zone 6 & 8 | (+0'-00'') | Grid U/.9-12 | A | 2025-01-27
| Sub Structure | 11th floor to top floor | L2/711 | 2025-01-24 | 2025-01-23 | Reinforcement | Check column (3 Nos) and (2 Nos) reinforcement and allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | Grid M-N/1-3, P/1, U/1 | A | 2025-01-27
| Sub Structure | Ground floor | L2/712 | 2025-01-24 | 2025-01-24 | level | Check level of UGWT zone 6 & 8 | (+0'-00'') | Grid U/9-12 | A | 2025-01-27
| Sub Structure | 11th floor to top floor | L2/713 | 2025-01-24 | 2025-01-24 | Reinforcement | Check column (7 Nos) and (3 Nos) reinforcement and allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | grid G-H/1, K-L/1, L/3, M/5-7, M-N/1-3 | A | 2025-01-27
| Sub Structure | 11th floor to top floor | L2/714 | 2025-01-27 | 2025-01-27 | Reinforcement | Check column (1 No) and (7 No) reinforcement and allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | Grid J/1, K/3, L/5, G-H/1, K-L/1, L/3, M/5-7 | A | 2025-01-29
| Sub Structure | 11th floor to top floor | L2/715 | 2025-01-28 | 2025-01-27 | Reinforcement | check lift wall reinforcement and allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | Grid N-Q/5-7 | A | 2025-01-29
| Sub Structure | 11th floor to top floor | L2/716 | 2025-01-28 | 2025-01-27 | Reinforcement | Check columns (10 Nos) reinforcemetn and allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | Grid G-K/5-7, L/7, J/1, K/3, L/5 | A | 2025-01-29
| Sub Structure | Top floor | L2/717 | 2025-01-28 | 2025-01-28 | Steel fixing | Check steel fixing zone 6 & 7 | (+145'-9'') | Grid N-U/5-12 | A | 2025-01-31
| Sub Structure | 10th to 11th floor | L2/718 | 2025-01-29 | 2025-01-29 | level, layout | Check level, layout of stair st-04 zone 7 | (+117'-9'' to +130'-9'') | Grid G-H/1-3 | A | 2025-01-31
| Sub Structure | 10th to 11th floor | L2/719 | 2025-01-30 | 2025-01-29 | Reinforcement | check formwork and stair st-4 reinforcement and allow for concrete pouring zone 7 | (+117'-9'' to +130'-9'') | Grid G-H/1-3 | A | 2025-01-31
| Sub Structure | 11th to top floor | L2/720 | 2025-01-30 | 2025-01-29 | Reinforcement | Check columns (8 Nos) reinforcement and allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | Grid G-K/5-7, L/7, G/3 | A | 2025-01-31
| Sub Structure | 11th to top floor | L2/721 | 2025-01-30 | 2025-01-29 | Reinforcement | Check beam rienforcement and allow for concrete pouring zone 6 | (+145'-9'') | Grid P-T/12 | A | 2025-01-31
| Sub Structure | Top floor | L2/722 | 2025-01-31 | 2025-01-31 | slab formwork | Check slab formwork along st-.02 zone 7 | (+145'-9'') | Grid P-Q/6-7 | A | 2025-02-05
| Sub Structure | top floor | L2/723 | 2025-01-31 | 2025-01-31 | Reinforcement | Check slab top and bottom and parapet wall rienforcement zone 6 & 7 | (+145'-9'') | Grid N-U/6-12 | A | 2025-02-05
| Sub Structure | Top floor | L2/724 | 2025-01-31 | 2025-01-31 | Reinforcement | Check slab rienforcement and allow for concrete pouring zone 6 & 7 | (+145'-9'') | Grid N-U/6-12 | A | 2025-02-05
| Sub Structure | Top floor | L2/725 | 2025-02-01 | 2025-02-01 | layout | check level of slab and layout of parapet wall, columns & bracket beam nib zone 6 & 7 | (+145'-9'') | Grid N-U/6-12 | A | 2025-02-05
| Sub Structure | 11th floor to top floor | L2/726 | 2025-02-03 | 2025-02-01 | Reinforcement | Check lift reinforcement and allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | Grid H-J/3-3 | A | 2025-02-05
| Sub Structure | Top floor | L2/727 | 2025-02-03 | 2025-02-03 | Reinforcement | Check beam rienforcement zone 7 | (+145'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2025-02-05
| Sub Structure | Top floor | L2/728 | 2025-02-03 | 2025-02-03 | Reinforcement | Check parapet wall rienforcement zone 6 | (+145'-9'' to +149'-6'') | Grid N/8-12, N-P/12, U/6-12, T-U/12 | A | 2025-02-05
| Sub Structure | 11th floor to top floor | L2/729 | 2025-02-04 | 2025-02-04 | level, layout | Check level, layout of stair st-02 zone 7 | (+130'-9'' to +145'-9'') | Grid N-Q/6-7 | A | 2025-02-05
| Sub Structure | 11th floor to top floor | L2/730 | 2025-02-05 | 2025-02-04 | formwork | Check formwork and rienforcement of stair st-02 & allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | Grid N-Q/6-7 | A | 2025-02-08
| Sub Structure | 11th floor | L2/731 | 2025-02-05 | 2025-02-04 | formwork | Check fomwork and hanging beam rienforcement and allow for concrete pouring zone 7 | (+125'-41/2'' to +130'-9'') | Grid G-H/1 | A | 2025-02-08
| Sub Structure | Top floor | L2/732 | 2025-02-05 | 2025-02-05 | Slab reinforcement | check slab top and bottom reinforcement zone 7 | (+145'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2025-02-08
| Sub Structure | Top floor | L2/733 | 2025-02-05 | 2025-02-05 | formwork | Check slab formwork along st-04 zone 7 | (+145'-9'') | Grid G-H/3-3 | A | 2025-02-08
| Sub Structure | Top floor | L2/734 | 2025-02-05 | 2025-02-05 | Reinforcement | Check slab reinforcement and allow for concrete pouring zone 7 | (+145'-9'') | Grid G-N/1-7, N-U/1-5 | A | 2025-02-08
| Sub Structure | basement | L2/735 | 2025-02-07 | 2025-02-06 | Reinforcement | Check Ground septic tank wall reinforcement and allow for concrete pouring zone 1 | (-11'-9'' to +0'-00'') | Grid F-G/1 | A | 2025-02-11
| Sub Structure | Top floor | L2/736 | 2025-02-07 | 2025-02-07 | level | Check level of slab and layout of parapet wall, columns + service lift zone 6 & 7 | (+145'-9'') | Grid G-N/1-7, P-U/1-5 | A | 2025-02-08
| Sub Structure | Mummty to top floor | L2/737 | 2025-02-07 | 2025-02-07 | Reinforcement | Check parapet wall, columns (4 Nos) & service lift reinforcement zone 7 | (+145'-9'' to +149'-6'') (+145'-9'' to +159'-00'') | Grid G-J/1-3, J-U/1, U/1-5, G/1-5, G-N/7 | A | 2025-02-08
| Sub Structure | Top floor | L2/738 | 2025-02-10 | 2025-02-08 | Reinforcement | Check parapet wall reinforcement & allow for concrete pouring zone 6 | (+145'-9'' to +149'-6'') | Grid U/6-12, T-U/12 | A | 2025-02-13
| Sub Structure | top floor to mummty | L2/739 | 2025-02-10 | 2025-02-08 | Reinforcement | Check column (1 Nos) reinforcement and allow for concrete pouring zone 7 | (+145'-9'' to +159'-00'') | Grid J/1 | A | 2025-02-13
| Sub Structure | top floor to mummty | L2/740 | 2025-02-10 | 2025-02-09 | Reinforcement | check column (1 No) reinforcement and allow for concrete pouring zone 7 | (+145'-9'' to +159'-00'') | Grid G/3 | A | 2025-02-13
| Sub Structure | top floor to mummty | L2/741 | 2025-02-10 | 2025-02-10 | Reinforcement | Check lift wall reinforcement zone 7 | (+145'-9'' to +159'-00''), (+165'-2'') | Grid N-Q/5-7 | A | 2025-02-13
| Sub Structure | top floor to mummty | L2/742 | 2025-02-11 | 2025-02-10 | Reinforcement | check lift reinforcement and allow for concrete pouring zone 7 | (+145'-9'' to +159'-0'') | Grid H-J/3-3 | A | 2025-02-11
| Sub Structure | top floor to mummty | L2/743 | 2025-02-11 | 2025-02-11 | layout | Check OHWT layout and FSS tank zone 6 | (+145'-9'') | Grid N-Q/7-8 | A | 2025-02-13
| Sub Structure | top floor to mummty | L2/744 | 2025-02-11 | 2025-02-10 | Reinforcement | Check column (1 No) reinforcement and allow for concrete pouring zone 7 | (+145'-9'' to +159'-0'') | Grid H/1 | A | 2025-02-11
| Sub Structure | top floor | L2/745 | 2025-02-11 | 2025-02-11 | Reinforcement | Check column (1 No) reinforcement and allow for concrete pouring zone 7 | (+145'-9'' to +159'-0'') | Grid G/1 | A | 2025-02-14
| Sub Structure | top floor | L2/746 | 2025-02-11 | 2025-02-11 | Reinforcement | check parapet wall reinforcement and allow for concrete pouring zone 7 | (+145'-9'' to +149'-6'') | Grid N-U/1 | A | 2025-02-14
| Sub Structure | basement | L2/747 | 2025-02-13 | 2025-02-12 | Reinforcement | check septic tank wall reinforcement and allow for concrete pouring zone 7 | (-11'-9'' to +0'-0'') | Grid F-G/1 | A | 2025-02-13
| Sub Structure | 11th to top floor | L2/748 | 2025-02-15 | 2025-02-14 | level, layout | Check level, layout of stair st-04 zone 7 | (+130'-9'' to +145'-9'') | Grid G-H/1-3 | A | 2025-02-15
| Sub Structure | 11th to top floor | L2/749 | 2025-02-15 | 2025-02-14 | formwork | Check formwork and steel fixing of stair st-04 & allow for concrete pouring zone 7 | (+130'-9'' to +145'-9'') | Grid G-H/1-3 | A | 2025-02-14
| Sub Structure | Top floor | L2/750 | 2025-02-15 | 2025-02-14 | Reinforcement | Check reinforcement of parapet wall & allow for concrete pouring zone 7 | (+145'-9'' to +149'-6'') | Grid J-N/1 | A | 2025-02-20
| Sub Structure | Top floor | L2/751 | 2025-02-17 | 2025-02-17 | layout | Check layout of Genset beam zone 7 | (+145'-9'') | Grid J-N/1-3 | A | 2025-02-19
| Sub Structure | Top floor | L2/752 | 2025-02-18 | 2025-02-17 | formwork | Check formwork and hanging beam reinforcement and allwo for concrete pouring zone 7 | (+138'-41/2'' to +145'-9'') | Grid G-H/1 | A | 2025-02-19
| Sub Structure | Top floor | L2/753 | 2025-02-18 | 2025-02-18 | Reinforcement | check Genset beam reinforcement zone 7 | (+146'-3'') | Grid J-N/1-3 | A | 2025-02-27
| Sub Structure | Mummty to top floor | L2/754 | 2025-02-18 | 2025-02-18 | Reinforcement | Check Mummty beam reinforcement zone 7 | (+159'-00'') | Grid G-J/1-3, | A | 2025-02-27
| Sub Structure | Mummty to top floor | L2/755 | 2025-02-19 | 2025-02-19 | Reinforcement | check Mummty slab reinforcement zone 7 | (+159'-00'') | Grid G-J/1-3 | A | 2025-02-27
| Sub Structure | basement | L2/756 | 2025-02-20 | 2025-02-20 | Reinforcement | Check ramp wall reinforcement zone 7 | (+0'-00'') | Grid G-N/7, N/7-12 | OP
| Sub Structure | Top floor | L2/757 | 2025-02-21 | 2025-02-20 | Reinforcement | Check parapet wall reinforcement and allow for concrete pouring zone 7 | (+145'-9'' to +149'-6'') | Grid U/1-6, U-U/1 | A | 2025-02-27
| Sub Structure | Top floor | L2/758 | 2025-02-22 | 2025-02-22 | Reinforcement | Check service lift mummty slab reinforcement and allwo for concrete pouring zone 7 | (+159'-00'') | Grid G-J/1-3 | A | 2025-02-27
| Sub Structure | Top floor | L2/759 | 2025-02-22 | 2025-02-22 | Reinforcement | Check parapet wall reinforcement and allow for concrete pouring zone 6 | (+145'-9'' to +149'-6'') | Grid N/9-12, N-P/12 | A | 2025-02-27
| Sub Structure | Top floor | L2/760 | 2025-02-22 | 2025-02-22 | Reinforcement | Check lift wall reinforcement and allow for concrete pouring zone 7 | (+145'-9'' to +159'-0'') | Grid N-Q/5-7 | A | 2025-02-27
| Sub Structure | Top floor | L2/761 | 2025-02-22 | 2025-02-22 | level | Check level of mummty slab & layout of service lift zone 7 | (+159'-00'') | Grid G-J/1-3 | A | 2025-03-04
| Sub Structure | Top floor | L2/762 | 2025-02-26 | 2025-02-26 | Reinforcement | Check parapet wall reinforcement and allow for concrete pouring zone 7 | (+145'-9'' to +149'-6'') | Grid G-N/7, G/5-7 | A | 2025-02-27
| Sub Structure | Top floor | L2/763 | 2025-02-27 | 2025-02-27 | Reinforcement | Check OHWT & FSS Tank reinforcement zone 6 | (+147'-3'') | Grid N-Q/7-8 | A | 2025-03-06
| Sub Structure | Top floor | L2/764 | 2025-03-03 | 2025-03-03 | Reinforcement | check mummty beam reinforcement zone 7 | (+159'-00'') | Grid N-Q/5-7 | A | 2025-03-03
| Sub Structure | Mummty to top floor | L2/765 | 2025-03-04 | 2025-03-04 | Reinforcement | check Mummty slab reinforcement zone 7 | (+159'-00'') | Grid N-Q/5-7 | A | 2025-03-04
| Sub Structure | Mummty to top floor | L2/766 | 2025-03-05 | 2025-03-05 | Reinforcement | Check Mummty slab reinforcement and allow for concrete pouring zone 7 | (+159'-00'') | Grid N-Q/5-7 | A | 2025-03-06
| Sub Structure | Mummty to top floor | L2/767 | 2025-03-06 | 2025-03-06 | level, layout | Check level of Mummty slab & layout of machine room wall zone 7 | (+159'-00'') | Grid N-Q/5-7 | A | 2025-03-13
| Sub Structure | Mummty to top floor | L2/768 | 2025-03-07 | 2025-03-06 | Reinforcement | Check machine room wall reinforcement and allow for concrete pouring zone 7 | (+159'-00'') | Grid H-J/3-3 | A | 2025-03-12
| Sub Structure | Mummty to top floor | L2/769 | 2025-03-07 | 2025-03-06 | Reinforcement | Check parapet reinforcement and allow for concrete p;ouring zone 7 | (+160'-00'') | Grid G-J/1-3 | A | 2025-03-12
| Sub Structure | SOG Area | L2/770 | 2025-03-07 | 2025-03-07 | Reinforcement | Check reinforcement and thermopore of expansion joint toe and allow for concrete pouring SOG Area | (+0'-00'') | Grid G/1-7, Q-U/12,15, G/26 | A | 2025-03-12
| Sub Structure | 1st to 5th floor | L2/771 | 2025-03-10 | 2025-03-10 | housekeeping | Chexck complete housekeeping of with stair st-02 and st-04 zone 6 & 7 | (+18'-9'' to +62'-9'') |  | A | 2025-03-13
| Sub Structure | Ground floor | L2/772 | 2025-03-12 | 2025-03-11 | Reinforcement | check reinforcement and thermopore of expansion joint toe and allow for concrete pouring SOG Area | (+0'-00'') | Grid G/22-26, G/7-10, G/11-20, N-Q/12-15 | A | 2025-03-13
| Sub Structure | Top floor | L2/773 | 2025-03-12 | 2025-03-12 | Reinforcement | Check OHWT & FSS walls reinforcement zone 6 | (+147'-3'' to +159'-00'') | Grid N-Q/7-8 | A | 2025-03-14
| Sub Structure | Top floor | L2/774 | 2025-03-13 | 2025-03-12 | Reinforcement | Check machine room reinforcement zone 7 | (+165'-2'') | Grid H-J/3-3 | A | 2025-03-15
| Sub Structure | Top floor | L2/775 | 2025-03-15 | 2025-03-13 | Reinforcement | Check machine room reinforcement and allow for concrete pouring zone 7 | (+159' to +165'-2'') | Grid N-Q/5-6 | A | 2025-03-15
| Sub Structure | SOG Area | L2/776 | 2025-03-15 | 2025-03-14 | Reinforcement | Check reinforcement and thermopore of expansion joint Toe and allow for concrete pouring SOG Area | (+0'-0'' to +1'-9'') | Grid N-Q/12,15 | A | 2025-03-15
| Sub Structure | Top floor | L2/777 | 2025-03-17 | 2025-03-15 | Reinforcement | Check machine room slab reinforcement and allow for concrete pouring zone 7 | (+165'-2'') | Grid H-J/3-3 | A | 2025-03-18
| Sub Structure | Ground floor | L2/778 | 2025-03-17 | 2025-03-15 | Reinforcement | Check reinforcement and thermopore of ramp wall & allow for concrete pouring SOG Area | (+0'-00'') | Grid N/7-12, G-N/7 | A | 2025-03-18
| Sub Structure | top floor | L2/779 | 2025-03-17 | 2025-03-17 | level | Check level of machine room slab | (+165'-2'') | Grid H-J/3-3 | A | 2025-03-21
| Sub Structure | 11th floor | L2/780 | 2025-03-17 | 2025-03-17 | housekeeping | Check housekeeping of Tower with stairs st-02 & St-04 | (+73'-9'' to +130'-9'') |  | A | 2025-03-19
| Sub Structure | Top floor | L2/781 | 2025-03-18 | 2025-03-17 | Reinforcement | check machine room slab reinforcement and allow for concrete pouring zone 7 | (+165'-2'') | Grid N-Q/5-5 | A | 2025-03-18
| Sub Structure | Top floor | L2/782 | 2025-03-18 | 2025-03-18 | level | Check level for machine room slab & layout of parapet wall zone 7 | (+165'-2'') | Grid N-Q/5-5 | A | 2025-03-21
| Sub Structure | Mummty to top floor | L2/783 | 2025-03-20 | 2025-03-19 | Reinforcement | check parapet wall of machine room of service lift & lift wall & lift mummty parapet reinforcement and allow for concrete zone 7 | (+159'-00'' to +160' to 00'') & +165'-2'') | Grid H-J/3-3, N-Q/5-5 | A | 2025-03-21
| Sub Structure | Top floor | L2/784 | 2025-04-09 | 2025-04-08 | Reinforcement | Check OHWT & FSS Tank base slab reinforcement and water stopper and allow for concrete pouring zone 6 | (+147'-3'') | Grid N-Q/7-8 | A | 2025-04-14
| Sub Structure | Top floor | L2/785 | 2025-04-09 | 2025-04-09 | level | Check OHWT & FSS tank base slab level zone 6 | (+147'-3'') | Grid N-Q/7-8 | A | 2025-05-16
| Sub Structure | Top floor | L2/786 | 2025-05-12 | 2025-05-12 | Reinforcement | Check Genset slab reinforcement zone 7 | (+148'-3'') | Grid J-L/1-3 | A | 2025-05-12
| Sub Structure | Top floor | L2/787 | 2025-05-13 | 2025-05-12 | Reinforcement | Check Genset slab & beam reinforcement and allow for concrete pouring zone 7 | (+148'-3'') | Grid J-L/1-3 | A | 2025-05-12
| Sub Structure | Top floor | L2/788 | 2025-05-13 | 2025-05-13 | level | Check level genset slab zone 7 | (+148'-3'') | Grid J-L/1-3 | A | 2025-05-13
| Sub Structure | Ground floor | L2/789 | 2025-05-13 | 2025-05-13 | Reinforcement | Check Deck slab & steps reinforcement zone 8 SOG |  |  | A | 2025-05-13
| Sub Structure | Ground floor | L2/790 | 2025-05-13 | 2025-05-14 | Reinforcement | Check deck slab & steps reinforcement & allow for concrete pouring zone 8 SOG |  | Grid L-M/19-20, M/15-20 | A | 2025-05-13
| Sub Structure | Ground floor | L2/791 | 2025-05-14 | 2025-05-14 | Reinforcement | Check deck slab & steps reinforcement zone 8 SOG |  | Grid J-L/19-20 | A | 2025-05-14
| Sub Structure | Ground floor | L2/792 | 2025-05-14 | 2025-05-14 | level | Check level of deck slab & steps zone 8 SOG area |  | Grid L-M/19-20, M/15-20 | A | 2025-05-14
| Sub Structure | Top floor | L2/793 | 2025-05-20 | 2025-05-19 | Reinforcement | Check OHWT & FSS reiforcement and FSS walls and allow for concrete pouring zone 6 | (+147'-3'' to +159'-00'') | Grid N-Q/7-8 | A | 2025-05-19
| Sub Structure | Ground floor | L2/794 | 2025-05-20 | 2025-05-19 | Reinforcement | check Deck slab & steps reinforcement and allow for concrete pouring zone 8 SOG Area | (+1'-9'') | Grid J-L/18-19 | A | 2025-05-20
| Sub Structure | Ground floor | L2/795 | 2025-05-20 | 2025-05-20 | level | Check deck slab level zone 8 SOG area | (+1'-9'') | Grid J-L/18-19 | A | 2025-05-21
| Sub Structure | Top flooor | L2/796 | 2025-05-22 | 2025-05-22 | Reinforcement | Check OHWT & FSS reinforcement zone 6 | (+159'-00'') | Grid N-Q/7-8 | A | 2025-05-22
| Sub Structure | Ground floor | L2/797 | 2025-05-23 | 2025-05-23 | Reinforcement | Check Deck slab & steps reinforcement zone 8 SOG Area | (+1'-9'') | Grid M-N/10-12 | A | 2025-05-22
| Sub Structure | Top floor | L2/798 | 2025-05-26 | 2025-05-24 | Reinforcement | check OHWT & FSS reinforcement and allow for concrete pouring zone 6 | (+159'-00'') | Grid N-Q/7-8 | A | 2025-05-24
| Sub Structure | Ground floor | L2/799 | 2025-05-26 | 2025-05-25 | Reinforcement | check Deck slab & steps reinforcement and allow for concrete pouring zone 8 SOG Area | (+1'-9'') | Grid M-N/10-12 | A | 2025-05-26
| Sub Structure | Top floor | L2/800 | 2025-05-26 | 2025-05-26 | level | check OHWT & FSS level zone 6 | (+159'-00'') | Grid N-Q/7-8 | A | 2025-05-26
| Sub Structure | Ground floor | L2/801 | 2025-05-26 | 2025-05-26 | level | check deck slab & steps level zone 8 SOG area | (+1'-9'') | Grid M-N/10-12 | A | 2025-05-26
| Sub Structure | Top floor | L2/802 | 2025-05-27 | 2025-05-26 | Reinforcement | check OHWT & FSS reinforcement and allow for concrete pouring zone 6 | (+159' to +160') | Grid N-Q/7-8 | A | 2025-05-26
| Sub Structure | Ground floor | L2/803 | 2025-05-28 | 2025-05-28 | Reinforcement | check reinforcement of deck slab & steps zone 8 SOG Area | (+1'-9'') | Grid J-M/7-8 | A | 2025-05-29
| Sub Structure | Ground floor | L2/804 | 2025-05-29 | 2025-05-28 | Reinforcement | check deck slab reinforcement and allow for concrete pouring zone 8 SOG Area | (+1'-9'') | Grid J-M/7-8, M-N/8 | A | 2025-05-29
| Sub Structure | Ground floor | L2/805 | 2025-05-29 | 2025-05-28 | Reinforcement | check ramp wall reinforcement and allow for concrete pouring zone 8 SOG Area | (+1'-9'') | Grid G-K/7-8 | A | 2025-05-29
| Sub Structure | Ground floor | L2/806 | 2025-05-29 | 2025-05-29 | level | check deck slab level zone 8 SOG Area | (+1'-9'') | Grid J-M/7-8, M-N/8 | A | 2025-05-31
| Sub Structure | Ground floor | L2/807 | 2025-06-03 | 2025-06-02 | Reinforcement | check flat slab reinforcement and allow for concrete pouring zone 8 SOG Area | (+1'-9'') | Grid G-J/7-8 | A | 2025-06-02
| Sub Structure | Ground floor | L2/808 | 2025-06-03 | 2025-06-03 | level | check flat slab level & ramp slab zone 8 SOG Area | (+1'-9'') | Grid G-J/7-8 | A | 2025-06-03
| Sub Structure |  | L2/809
| Sub Structure |  | L2/810
| Sub Structure |  | L2/811
| Sub Structure |  | L2/812
| Sub Structure |  | L2/813
| Sub Structure |  | L2/814
| Sub Structure |  | L2/815
| Sub Structure |  | L2/816
| Sub Structure |  | L2/817
| Sub Structure |  | L2/818
| Sub Structure |  | L2/819
| Sub Structure |  | L2/820
| Sub Structure |  | L2/821
| Sub Structure |  | L2/822
| Sub Structure |  | L2/823
| Sub Structure |  | L2/824
| Sub Structure |  | L2/825
| Sub Structure |  | L2/826
| Sub Structure |  | L2/827
| Sub Structure |  | L2/828
| Sub Structure |  | L2/829
| Sub Structure |  | L2/830
| Sub Structure |  | L2/831
| Sub Structure |  | L2/832
| Sub Structure |  | L2/833
| Sub Structure |  | L2/834
| Sub Structure |  | L2/835
| Sub Structure |  | L2/836
| Sub Structure |  | L2/837
| Sub Structure |  | L2/838
| Sub Structure |  | L2/839
| Sub Structure |  | L2/840
| Sub Structure |  | L2/841
| Sub Structure |  | L2/842
| Sub Structure |  | L2/843
| Sub Structure |  | L2/844
| Sub Structure |  | L2/845
| Sub Structure |  | L2/846
| Sub Structure |  | L2/847
| Sub Structure |  | L2/848
| Sub Structure |  | L2/849
| Sub Structure |  | L2/850
| Sub Structure |  | L2/851
| Sub Structure |  | L2/852
| Sub Structure |  | L2/853
| Sub Structure |  | L2/854
| Sub Structure |  | L2/855
| Sub Structure |  | L2/856
| Sub Structure |  | L2/857
| Sub Structure |  | L2/858
| Sub Structure |  | L2/859
| Sub Structure |  | L2/860
| Sub Structure |  | L2/861
| Sub Structure |  | L2/862
| Sub Structure |  | L2/863
| Sub Structure |  | L2/864
| Sub Structure |  | L2/865
| Sub Structure |  | L2/866
| Sub Structure |  | L2/867
| Sub Structure |  | L2/868
| Sub Structure |  | L2/869
| Sub Structure |  | L2/870
| Sub Structure |  | L2/871
| Sub Structure |  | L2/872
| Sub Structure |  | L2/873
| Sub Structure |  | L2/874
| Sub Structure |  | L2/875
| Sub Structure |  | L2/876
| Sub Structure |  | L2/877
| Sub Structure |  | L2/878
| Sub Structure |  | L2/879
| Sub Structure |  | L2/880
| Sub Structure |  | L2/881
| Sub Structure |  | L2/882
| Sub Structure |  | L2/883
| Sub Structure |  | L2/884
| Sub Structure |  | L2/885
| Sub Structure |  | L2/886
| Sub Structure |  | L2/887
| Sub Structure |  | L2/888
| Sub Structure |  | L2/889
| Sub Structure |  | L2/890
| Sub Structure |  | L2/891
| Sub Structure |  | L2/892
| Sub Structure |  | L2/893
| Sub Structure |  | L2/894
| Sub Structure |  | L2/895
| Sub Structure |  | L2/896
| Sub Structure |  | L2/897
| Sub Structure |  | L2/898
| Sub Structure |  | L2/899
| Sub Structure |  | L2/900
| Sub Structure |  | L2/901
| Sub Structure |  | L2/902
| Sub Structure |  | L2/903
| Sub Structure |  | L2/904
| Sub Structure |  | L2/905
| Sub Structure |  | L2/906
| Sub Structure |  | L2/907
| Sub Structure |  | L2/908
| Sub Structure |  | L2/909
| Sub Structure |  | L2/910
| Sub Structure |  | L2/911
| Sub Structure |  | L2/912
| Sub Structure |  | L2/913
| Sub Structure |  | L2/914
| Sub Structure |  | L2/915
| Sub Structure |  | L2/916
| Sub Structure |  | L2/917
| Sub Structure |  | L2/918
| Sub Structure |  | L2/919
| Sub Structure |  | L2/920
| Sub Structure |  | L2/921
| Sub Structure |  | L2/922
| Sub Structure |  | L2/923
| Sub Structure |  | L2/924
| Sub Structure |  | L2/925
| Sub Structure |  | L2/926
| Sub Structure |  | L2/927
| Sub Structure |  | L2/928
| Sub Structure |  | L2/929
| Sub Structure |  | L2/930
| Sub Structure |  | L2/931
| Sub Structure |  | L2/932
| Sub Structure |  | L2/933
| Sub Structure |  | L2/934
| Sub Structure |  | L2/935
| Sub Structure |  | L2/936
| Sub Structure |  | L2/937
| Sub Structure |  | L2/938
| Sub Structure |  | L2/939
| Sub Structure |  | L2/940
| Sub Structure |  | L2/941
| Sub Structure |  | L2/942
| Sub Structure |  | L2/943
| Sub Structure |  | L2/944
| Sub Structure |  | L2/945
| Sub Structure |  | L2/946
| Sub Structure |  | L2/947
| Sub Structure |  | L2/948
| Sub Structure |  | L2/949
| Sub Structure |  | L2/950
| Sub Structure |  | L2/951
| Sub Structure |  | L2/952
| Sub Structure |  | L2/953
| Sub Structure |  | L2/954
| Sub Structure |  | L2/955
| Sub Structure |  | L2/956
| Sub Structure |  | L2/957
| Sub Structure |  | L2/958
| Sub Structure |  | L2/959
| Sub Structure |  | L2/960
| Sub Structure |  | L2/961
| Sub Structure |  | L2/962
| Sub Structure |  | L2/963
| Sub Structure |  | L2/964
| Sub Structure |  | L2/965
| Sub Structure |  | L2/966
| Sub Structure |  | L2/967
| Sub Structure |  | L2/968
| Sub Structure |  | L2/969
| Sub Structure |  | L2/970
| Sub Structure |  | L2/971
| Sub Structure |  | L2/972
| Sub Structure |  | L2/973
| Sub Structure |  | L2/974
| Sub Structure |  | L2/975
| Sub Structure |  | L2/976
| Sub Structure |  | L2/977
| Sub Structure |  | L2/978
| Sub Structure |  | L2/979
| Sub Structure |  | L2/980
| Sub Structure |  | L2/981
| Sub Structure |  | L2/982
| Sub Structure |  | L2/983
| Sub Structure |  | L2/984
| Sub Structure |  | L2/985
| Sub Structure |  | L2/986
| Sub Structure |  | L2/987
| Sub Structure |  | L2/988
| Sub Structure |  | L2/989
| Sub Structure |  | L2/990
| Sub Structure |  | L2/991
| Sub Structure |  | L2/992
| Sub Structure |  | L2/993
| Sub Structure |  | L2/994
| Sub Structure |  | L2/995
| Sub Structure |  | L2/996
| Sub Structure |  | L2/997
| Sub Structure |  | L2/998
| Sub Structure |  | L2/999
| Sub Structure |  | L2/1000
| Sub Structure |  | L2/1001
| Sub Structure |  | L2/1002
| Sub Structure |  | L2/1003
| Sub Structure |  | L2/1004
| Sub Structure |  | L2/1005
| Sub Structure |  | L2/1006
| Sub Structure |  | L2/1007
| Sub Structure |  | L2/1008
| Sub Structure |  | L2/1009
| Sub Structure |  | L2/1010
| Sub Structure |  | L2/1011
| Sub Structure |  | L2/1012
| Sub Structure |  | L2/1013
| Sub Structure |  | L2/1014
| Sub Structure |  | L2/1015
| Sub Structure |  | L2/1016
| Sub Structure |  | L2/1017
| Sub Structure |  | L2/1018
| Sub Structure |  | L2/1019
| Sub Structure |  | L2/1020
| Sub Structure |  | L2/1021
| Sub Structure |  | L2/1022
| Sub Structure |  | L2/1023
| Sub Structure |  | L2/1024
| Sub Structure |  | L2/1025
| Sub Structure |  | L2/1026
| Sub Structure |  | L2/1027
| Sub Structure |  | L2/1028
| Sub Structure |  | L2/1029
| Sub Structure |  | L2/1030
| Sub Structure |  | L2/1031
| Sub Structure |  | L2/1032
| Sub Structure |  | L2/1033
| Sub Structure |  | L2/1034
| Sub Structure |  | L2/1035
| Sub Structure |  | L2/1036
| Sub Structure |  | L2/1037
| Sub Structure |  | L2/1038
| Sub Structure |  | L2/1039
| Sub Structure |  | L2/1040
| Sub Structure |  | L2/1041
| Sub Structure |  | L2/1042
| Sub Structure |  | L2/1043
| Sub Structure |  | L2/1044
| Sub Structure |  | L2/1045
| Sub Structure |  | L2/1046
| Sub Structure |  | L2/1047
| Sub Structure |  | L2/1048
| Sub Structure |  | L2/1049
| Sub Structure |  | L2/1050
| Sub Structure |  | L2/1051
| Sub Structure |  | L2/1052
| Sub Structure |  | L2/1053
| Sub Structure |  | L2/1054
| Sub Structure |  | L2/1055
| Sub Structure |  | L2/1056
| Sub Structure |  | L2/1057
| Sub Structure |  | L2/1058
| Sub Structure |  | L2/1059
| Sub Structure |  | L2/1060
| Sub Structure |  | L2/1061
| Sub Structure |  | L2/1062
| Sub Structure |  | L2/1063
| Sub Structure |  | L2/1064
| Sub Structure |  | L2/1065
| Sub Structure |  | L2/1066
| Sub Structure |  | L2/1067
| Sub Structure |  | L2/1068
| Sub Structure |  | L2/1069
| Sub Structure |  | L2/1070
| Sub Structure |  | L2/1071
| Sub Structure |  | L2/1072
| Sub Structure |  | L2/1073
| Sub Structure |  | L2/1074
| Sub Structure |  | L2/1075
| Sub Structure |  | L2/1076
| Sub Structure |  | L2/1077
| Sub Structure |  | L2/1078
| Sub Structure |  | L2/1079
| Sub Structure |  | L2/1080
| Sub Structure |  | L2/1081
| Sub Structure |  | L2/1082
| Sub Structure |  | L2/1083
| Sub Structure |  | L2/1084
| Sub Structure |  | L2/1085
| Sub Structure |  | L2/1086
| Sub Structure |  | L2/1087
| Sub Structure |  | L2/1088
| Sub Structure |  | L2/1089
| Sub Structure |  | L2/1090
| Sub Structure |  | L2/1091
| Sub Structure |  | L2/1092
| Sub Structure |  | L2/1093
| Sub Structure |  | L2/1094
| Sub Structure |  | L2/1095
| Sub Structure |  | L2/1096
| Sub Structure |  | L2/1097
| Sub Structure |  | L2/1098
| Sub Structure |  | L2/1099
| Sub Structure |  | L2/1100
| Sub Structure |  | L2/1101
| Sub Structure |  | L2/1102
| Sub Structure |  | L2/1103
| Sub Structure |  | L2/1104
| Sub Structure |  | L2/1105
| Sub Structure |  | L2/1106
| Sub Structure |  | L2/1107
| Sub Structure |  | L2/1108
| Sub Structure |  | L2/1109
| Sub Structure |  | L2/1110
| Sub Structure |  | L2/1111
| Sub Structure |  | L2/1112
| Sub Structure |  | L2/1113
| Sub Structure |  | L2/1114
| Sub Structure |  | L2/1115
| Sub Structure |  | L2/1116
| Sub Structure |  | L2/1117
| Sub Structure |  | L2/1118
| Sub Structure |  | L2/1119
| Sub Structure |  | L2/1120
| Sub Structure |  | L2/1121
| Sub Structure |  | L2/1122
| Sub Structure |  | L2/1123
| Sub Structure |  | L2/1124
| Sub Structure |  | L2/1125
| Sub Structure |  | L2/1126
| Sub Structure |  | L2/1127
| Sub Structure |  | L2/1128
| Sub Structure |  | L2/1129
| Sub Structure |  | L2/1130

## IIL I Tower IR
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) IIL-CSL | [5 empty] | Fully Approved (A) |  | 226
[9 empty] | Approved with comments (B) |  | 34
[9 empty] | Rejected ( R) |  | 3 |  | As of : |  | 2025-12-19
[9 empty] | Open/Pending (OP) |  | 2
[9 empty] | Total |  | 265
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR closing Date | Pour Card No. | Concrete Qty (m3) | Attachment | Remarks
1 | Sub Structure | Basement | IT/1 | 2022-09-17 |  | Retaining wall | Inspection of retaining wall, starter |  | Grid F-G/7-8 | A | 2022-09-20 |  |  | E:\Soft IRs\IIL\I Tower\1.pdf
2 | Sub Structure | Basement | IT/2 | 2022-09-26 |  | Formwork | Inspection of columns, formwork |  | Grid 7/F | A | 2022-10-05 |  |  | E:\Soft IRs\IIL\I Tower\2.pdf
3 | Sub Structure | Basement | IT/3 | 2022-09-27 |  | Wall starter | Inspection of retaining wall starter formwork |  | Grid 7-8, 12-3 | A | 2022-10-05 |  |  | E:\Soft IRs\IIL\I Tower\3.pdf
4 | Sub Structure | Basement | IT/4 | 2022-09-30 |  | Formwork | Inspection of retaining wall formwork before concrete |  | Grid A-F/G-1 | A | 2022-10-05 |  |  | E:\Soft IRs\IIL\I Tower\4.pdf
5 | Sub Structure | Basement | IT/5 | 2022-09-30 |  | Formwork | Inspection of retaining wall formwork after concrete |  | Grid A-F/G-1 | A | 2022-10-06 |  |  | E:\Soft IRs\IIL\I Tower\5.pdf
6 | Sub Structure | Basement | IT/6 | 2022-10-04 |  | Retaining wall | Inspection of retaining wall, starter |  | Grid 12-13, 15-16 | A | 2022-10-06 |  |  | E:\Soft IRs\IIL\I Tower\6.pdf
7 | Sub Structure | Basement | IT/7 | 2022-10-04 |  | Formwork | Inspection of formwork of Columns |  | Grid 8-A & 8-F | A | 2022-10-06 |  |  | E:\Soft IRs\IIL\I Tower\7.pdf
8 | Sub Structure | Basement | IT/7A | 2022-10-07 |  | Retaining wall | Inspection of retaining wall formwork before concrete |  | Grid btw 1, Grid 10 btw 11 | A | 2022-10-10 |  |  | E:\Soft IRs\IIL\I Tower\7A.pdf
9 | Sub Structure | Basement | IT/8 | 2022-10-08 |  | Formwork | Inspection of columns formwork before concrete C20, C21 and C22 |  | Grid 8-B & 8-D & 9-F | A | 2022-10-12 |  |  | E:\Soft IRs\IIL\I Tower\8.pdf
10 | Sub Structure | Basement | IT/9 | 2022-10-09 |  | Formwork | Inspection of columns formwork after concrete C19, C20, C21 & C22 |  | Grid 8-A, 8-F, 8-B & 8-D, 9-F | A | 2022-10-10 |  |  | E:\Soft IRs\IIL\I Tower\9.pdf
11 | Sub Structure | Basement | IT/10 | 2022-10-09 |  | Retaining wall | Inspection of retaining wall formwork after concrete |  | Grid btw 1, grid 10 btw 11 | A | 2022-10-09 |  |  | E:\Soft IRs\IIL\I Tower\10.pdf
12 | Sub Structure | Basement | IT/11 | 2022-10-10 |  | Retaining wall | Inspection of retaining wall formwork starter |  | Grid 15 btw 16 to Grid 20 | A | 2022-10-12 |  |  | E:\Soft IRs\IIL\I Tower\11.pdf
13 | Sub Structure | Basement | IT/12 | 2022-10-15 |  | Column formwork | Columns formwork and shear walls before concrete |  | Grid 9D, 10F, 11F, 10D, 11D, 11B, 11A, Grid 8 btw 9D, 8 btw 9B | A | 2022-10-18 |  |  | E:\Soft IRs\IIL\I Tower\12.pdf
14 | Sub Structure | Basement | IT/13 | 2022-10-17 |  | Column formwork | Columns formwork and shear walls after concrete |  | Grid 9D, 10F, 11F, 10D, 11D, 11B, 11A, Grid 8 btw 9D, 8 btw 9B | A | 2022-10-18 |  |  | E:\Soft IRs\IIL\I Tower\13.pdf
15 | Sub Structure | Basement | IT/14 | 2022-10-19 |  | Retaining wall | Inspection of retaining wall starter formwork Zone 3 |  | Grid 20 to Grid F | A | 2022-10-24 |  |  | E:\Soft IRs\IIL\I Tower\14.pdf
16 | Sub Structure | Basement | IT/15 | 2022-10-21 |  | Slab formwork | Inspection of Slab formwork for Zone 1 |  | Grid A to F 1-4 | A | 2023-03-14 |  |  | E:\14.Soft IRs\IIL\I Tower\15.pdf
17 | Sub Structure | Basement | IT/16 | 2022-10-26 |  | Slab formwork layout | Inspection of slab formwork layout & level Zone 1 Grid 4 to 8 A to F |  | Grid 4 to 8 A to F | A | 2023-03-14 |  |  | E:\14.Soft IRs\IIL\I Tower\16.pdf
18 | Sub Structure | Basement | IT/17 | 2022-10-28 |  | Starter | Inspection of starter for Zone 1 retaining wall |  | Grid F to G | A | 2022-10-08 |  |  | E:\14.Soft IRs\IIL\I Tower\17.pdf
19 | Sub Structure | Basement | IT/18 | 2022-10-31 |  | Core wall | Inspection of core wall Zone 1 |  | Zone 1 | A | 2023-04-07 |  |  | E:\14.Soft IRs\IIL\I Tower\18.pdf
20 | Sub Structure | Basement | IT/19 | 2022-10-31 |  | Column formwork | Inspection of columns formwork |  | Grid 11 to 16, Grid F to G | R | 2023-05-11 |  |  | E:\14.Soft IRs\IIL\I Tower\19.pdf
21 | Sub Structure | Basement | IT/20 | 2022-11-01 |  | Core wall | Inspection of core wall after pouring |  | Zone 1 | R | 2023-05-11 |  |  | E:\14.Soft IRs\IIL\I Tower\20.pdf
22 | Sub Structure | Basement | IT/21 | 2022-11-01 |  | Column work | Inspection of columns after pouring |  | Grid G to 11 | A | 2022-10-08 |  |  | E:\14.Soft IRs\IIL\I Tower\21.pdf
23 | Sub Structure | Basement | IT/22 | 2022-11-02 |  | Formwork | Inspection of formwork Zone 2 Retaining wall |  | Zone 2 | R | 2022-11-14
24 | Sub Structure | Basement | IT/23 | 2022-11-07 |  | RTW Inspection | Inspection of formwork retaining wall Zone 1 F to G |  | Grid F to G | A | 2023-04-07
25 | Sub Structure | Basement | IT/24 | 2022-11-07 |  | Slab formwork | Inspection of slab formwork layout and level Zone 1 |  | Grid 8 to btw 10-11 | A | 2023-03-14
26 | Sub Structure | Basement | IT/25 | 2022-11-08 |  | Slab formwork | Inspection of slab formwork layout and level |  | Grid F to G | A | 2023-04-07
27 | Sub Structure | Basement | IT/26 | 2022-11-08 |  | Formwork | Inspection of Formwork retaining wall Zone 1 F to G after concrete |  | Grid 1 F to G | A | 2023-03-14
28 | Sub Structure | Basement | IT/27 | 2022-11-08 |  | Shoring | Inspection of Shoring Zone 1 |  | Grid A to G | A | 2023-04-07
29 | Sub Structure | Basement | IT/28 | 2022-11-09 |  | Retaining wall | Inspection of retaining wall Zone 2 |  | Grid center of 10 & 11 to grid center of 16 & 17 | A | 2023-04-07
30 | Sub Structure | Basement | IT/29 | 2022-11-09 |  | Columns formwork | Inspection of column formwork |  | Grid 12B, 13A, 13B, 14A, 14B, 14D, 15B, 15D, 16B, 16D, 16F | A | 2023-04-07
31 | Sub Structure | Basement | IT/30 | 2022-11-14 |  | slab formwork | Inspection of slab formwork Zone 1 |  | Grid 1 to center of 10 to 11, A to G | A | 2022-11-22
32 | Sub Structure | Basement | IT/31 | 2022-11-15 |  | RW Formwork | Inspection of formwork after pouring Zone 2 Retaining wall |  | Grid A to F, center of 10,11 to 16,17 | A | 2022-11-22
33 | Sub Structure | Basement | IT/32 | 2022-11-19 |  | Slab | Inspection of slab Zone 1 |  | Grid 3 to center of 10 to 11, B to F | A | 2022-11-22
34 | Sub Structure | Basement | IT/33 | 2022-11-21 |  | Columns formwork | Inspection of columns formwork Zone 2 |  | Grid A11, F14, A15, A16 | A | 2022-11-30
35 | Sub Structure | Basement | IT/34 | 2022-11-21 |  | RW Inspection | Inspection of RW formwork Zone 2 |  | Zone 2 | A | 2022-12-02
36 | Sub Structure | Basement | IT/35 | 2022-11-22 |  | Starter formwork | Inspection of starter formwork RW Zone 4 |  | Grid F to M | A | 2022-12-02
37 | Sub Structure | Basement | IT/36 | 2022-11-23 |  | Formwork after concrete | Inspection of formwork after concrete columns Zone 2 |  | Grid A12, F14, A15, A16 | A | 2023-03-14
38 | Sub Structure | Basement | IT/37 | 2022-11-25 |  | Column formwork | Inspection of column formwork Zone 2 |  | Grid 11 to 16, F to G | A | 2023-03-14
39 | Sub Structure | Basement | IT/38 | 2023-06-21 |  | RW Formwork | Inspection of RW formwork Zone 5 before concrete SOG Area |  | Grid 13 btw 14-15 to U | A | 2023-07-12
40 | Sub Structure | Basement | IT/39 | 2022-11-25 |  | RW Formwork | Inspection of RW formwork Zone 2 |  | Zone 2 | A | 2022-12-02
41 | Sub Structure | Basement | IT/40 | 2022-11-29 |  | Slab formwork | Inspection of slab formwork Zone 2 |  | Grid 11 to center of 16 & 17, A to G | A | 2023-04-07
42 | Sub Structure | Basement | IT/41 | 2022-11-26 |  | Column formwork | Inspection of column formwork after concrete Zone 2 |  | Grid 11 to 16, F to G, 12G, 13G, 14G, 15G, 16G | A | 2022-12-02
43 | Sub Structure | Basement | IT/42 | 2022-12-01 |  | Columns formwork | Inspection of column formwork |  | Grid B-F, 17-23 | A | 2023-03-14
44 | Sub Structure | Basement | IT/43 | 2022-12-02 |  | Columns formwork | Inspection of column formwork and shear wall Zone 3 |  | Grid B-F, 17-23 | A | 2022-12-07
45 | Sub Structure | Basement | IT/44 | 2022-12-02 |  | RW Formwork | Inspection of retaining wall formwork Zone 3 |  | Grid B-F, 17-23 | A | 2022-12-07
46 | Sub Structure | Basement | IT/45 | 2022-12-03 |  | RW Formwork | Inspection of retaining wall formwork Zone 3 |  | Grid B-F, 17-23 & A | A | 2022-12-07
47 | Sub Structure | Basement | IT/46
48 | Sub Structure | Basement | IT/47 | 2022-12-03 |  | Column formwork | Inspection of column formwork Zone 3 |  | Grid 23A, 25A, 26A | A | 2022-12-07
49 | Sub Structure | Basement | IT/48 | 2022-12-03 |  | columns formwork 3 | Inspection of column formwork 3 before concrete Zone 3 |  | Grid A-E/19-26 | A | 2022-12-13
50 | Sub Structure | Basement | IT/49 | 2022-12-05 |  | Shoring, formwork | Inspection of shoring and formwork stability Zone 2 |  | Grid 11-16 | A | 2022-12-13
51 | Sub Structure | Basement | IT/50 | 2022-12-05 |  | Pouring | Final inspection before pouring Zone 2 |  | Grid 11-17 | A | 2022-12-13
52 | Sub Structure | Basement | IT/51 | 2022-12-05 |  | Pouring | Inspection of Z3 column before pouring Zone 3 |  | Grid 19-26, D-F/ | A | 2022-12-13
53 | Sub Structure | Basement | IT/52 | 2022-12-07 |  | Pouring | Inspection of Z3 column after concrete pouring Zone 3 |  | Grid 17-26, A-F | A | 2022-12-13
54 | Sub Structure | Basement | IT/53 | 2022-12-08 |  | Pouring | Inspection of Zone 3 column before pouring Zone 3 |  | Grid 18-26 | A | 2022-12-13
55 | Sub Structure | Basement | IT/54 | 2022-12-08 |  | Pouring | Inspection of Zone 3 column after pouring |  | Grid G, 18-26 | A | 2022-12-13
56 | Sub Structure | Basement | IT/55 | 2022-12-10 |  | Pouring | Inspection of Zone 1 column before pouring Zone 1 |  | Grid 1-4, A-F | A | 2022-12-13
57 | Sub Structure | Basement | IT/56 | 2022-12-09 |  | Concrete | Inspection of Zone 3 RW before concrete |  | Grid A-G | A | 2022-12-13
58 | Sub Structure | Basement | IT/57 | 2022-12-10 |  | RW | Inspection of RW after concrete |  | Grid A-G | A | 2022-12-21
59 | Sub Structure | Basement | IT/58 | 2022-12-11 |  | Pouring | Inspection of Zone 1 column after pouring |  | Grid 1-4, A-F | A | 2022-12-13
60 | Sub Structure | Basement | IT/59 | 2022-12-12 |  | Core wall | Inspection of Core wall before pouring |  | Grid 17-18, A-B | A | 2022-12-21
61 | Sub Structure | Basement | IT/60 | 2022-12-12 |  | Core wall | Inspection of Core wall after pouring |  | Grid 17-18, A-B | A | 2022-12-21
62 | Sub Structure | Basement | IT/61 | 2022-12-13 |  | slab | Inspection of slab for layout and level Zone 3 |  | Grid 16/17 to 24, F-G/24-26, A to F, B to A | A | 2022-12-20
63 | Sub Structure | Basement | IT/62 | 2022-12-13 |  | Column | Inspection of Z1 GF column before concrete |  | Grid 3-8, A-F | A | 2022-12-21
64 | Sub Structure | Basement | IT/63 | 2022-12-14 |  | Column | Inspection of Z1 GF column after concrete |  | Grid 3-8, A-F | A | 2022-12-21
65 | Sub Structure | Basement | IT/64 | 2022-12-16 |  | columns | Inspection of formwork before concrete |  | Grid 1-8 and A-F | A | 2022-12-18
66 | Sub Structure | Basement | IT/65 | 2022-12-16 |  | Columns | Inspection of formwork after concrete |  | Grid 1-8, A-F | A | 2022-12-17
67 | Sub Structure | Basement | IT/66 | 2022-12-17 |  | Columns | Inspection of formwork before concrete |  | Grid 2-8, B-F | A | 2022-12-18
68 | Sub Structure | Basement | IT/67 | 2022-12-17 |  | Columns | Inspection of formwork after concrete |  | Grid 2-8, B-F | A | 2022-12-18
69 | Sub Structure | Basement | IT/68 | 2022-12-18 |  | Slab | Inspection of slab formwork layout and level before concrete Zone 3 |  | Grid A to F, Btw 16,17 to 24 | A | 2022-12-27
70 | I Tower | Ground | IT/69 | 2022-12-18 |  | columns | Inspection of column formwork Zone 1 GF before concrete |  | Grid C20 to C24 | A | 2022-12-20
| I Tower | Ground | IT/70 A | 2022-12-18 |  | Column | Inspection of column formwork Zone 1 GF after concrete |  | Grid 1 to 10 and A to F | A | 2022-12-20
72 | I Tower | Ground | IT/71 | 2022-12-19 |  | SW | Inspection of shear wall formwork lower portion before concrete GF |  | Grid btw 8 to 9, A to E | A | 2022-12-20
73 | I Tower | Ground | IT/72 | 2022-12-19 |  | SW | Inspection of shear wall formwork lower portion after concrete Z1 GF |  | Grid btw 8 to 9 A to E | A | 2022-12-20
74 | Sub Structure | Basement | IT/73 | 2022-12-20 |  | Starter | Inspection of starter formwork of RTW |  | Grid 14 to 19-20 | A | 2022-12-28
75 | Sub Structure | Basement | IT/74 | 2022-12-20 |  | Shoring | Inspection of shoring stability for slab Zone 3 |  | Grid A to B btw 16/17, 26 | A | 2022-12-27
76 | I Tower | Ground | IT/75 | 2022-12-21 |  | columns | Inspection of column formwork before concrete Zone 1 GF |  | Grid C21, C24, C22 | A | 2022-12-27
77 | I Tower | Ground | IT/76 | 2022-12-21 |  | columns | Inspection of column formwork after concrete Zone 1 GF |  | Grid C21, C24, C22 | A | 2022-12-27
78 | I Tower | Ground | IT/77 | 2022-12-22 |  | SW | Inspection of Shear wall formwork before concrete Zone 1GF |  | Grid btw 8 to 9 A to E | A | 2022-12-28
79 | I Tower | Ground | IT/78 | 2022-12-22 |  | SW | Inspection of shear wall formwork 2nd height after concrete Zone 1 GF |  | Grid btw 8 to 9 A to F | A | 2022-12-28
80 | I Tower | Ground | IT/79 | 2022-12-23 |  | Column | Inspection of column formwork 1st height before concrete Zone 2 GF |  | Grid 11A, 11B, 11D, 11F, 12F | A | 2022-12-27
81 | I Tower | Ground | IT/80 | 2022-12-23 |  | Column | Inspection of column formwork 1st height after concrete Zone 2 GF |  | Grid 11A, 11B, 11D, 11F | A | 2022-12-27
82 | I Tower | Ground | IT/81 | 2022-12-23 |  | Core wall | Inspection of formwork core wall before concrete Zone 1 GF |  | Grid 9-10, A to C | A | 2022-12-30
83 | I Tower | Ground | IT/82 | 2022-12-23 |  | Core wall | Inspection of formwork Core wall after concrete Zone 1 GF |  | Grid 9-10, A to C | A | 2022-12-30
84 | Sub Structure | Basement | IT/83 | 2022-12-23 |  | Shoring | Inspection of shoring stability Zone 3 basement slab |  | Grid btw 16/17 to 24 & A to F | A | 2022-12-27
85 | I Tower | Ground | IT/84 | 2022-12-26 |  | Slab | Inspection of slab formwork layout , level |  | Grid 1 to 8 A to F | A | 2022-12-30
86 | I Tower | Ground | IT/85 | 2022-12-26 |  | Column | Inspection of columns formwork before concrete Zone 2 GF |  | Grid 12A, 12B, 12D, 12F, 13A, 13B, 13D, 13F, 14A, 14B, 14D, 11A, 11B, 11D, 11F | A | 2022-12-27
87 | I Tower | Ground | IT/86 | 2022-12-26 |  | Columns | Inspection of columns formwork after concrete Zone 2 GF |  | Grid 12A, 12B, 12D, 12F, 13A, 13B, 13D, 13F, 14A, 14B, 14D, 11A, 11B, 11D, 11F | A | 2022-12-27
88 | I Tower | Ground | IT/87 | 2022-12-28 |  | Columns | Inspection of columns formwork before concrete Zone 2 GF 1st and 2nd height |  | Grid 15B, 15D, 15F, 14F, 12A, 12B12D, 12F, 13A, 13B, 13D, 13F | A | 2022-12-30
89 | I Tower | Ground | IT/88 | 2022-12-28 |  | Columns | Inspection of columns formwork after concrete Zone 2 GF |  | Grid 12A, 12B, 12D, 12F, 14F | A | 2023-01-02
90 | I Tower | Ground | IT/89 | 2022-12-30 |  | Slab | Inspection of slab formwork Zone 1 GF before concrete |  | Grid 8 to center of 10/11 & A to F | A | 2023-01-02
91 | I Tower | Ground | IT/90 | 2022-12-30 |  | Core wall | Inspection of core wall 2nd height before concrete Zone 1 GF |  | Grid 9-10 & A to C | A | 2023-01-02
92 | I Tower | Ground | IT/91
93 | I Tower | Ground | IT/92 | 2022-12-30 |  | Columns formwork | Inspection of columns formwork before concrete Zone 2 GF |  | Grid 16A, 15A, and 14A, 14B, 14D | A | 2023-01-01
94 | I Tower | Ground | IT/93
95 | I Tower | Ground | IT/94 | 2023-01-01 |  | Columns formwork | Inspection of columns formwork before concrete Zone 2 GF |  | Grid 16B, 16D and 16A, 15A, 15B, 15D, 15F | A | 2023-01-02
96 | I Tower | Ground | IT/95
97 | I Tower | Ground | IT/96 | 2023-01-01 |  | SW formwork | Inspection of formwork shear wall before concrete SW1, SW2 Zone 3 |  | Grid 17F | A | 2023-01-02
98 | I Tower | Ground | IT/97
99 | I Tower | Ground | IT/98 | 2023-01-02 |  | Columns formwork | Inspection of formwork of columns Zone 3 GF before concrete |  | Grid 19A, 21B, 21S, 18D, 18F, 17D, and 17F, 16F and 16B, 16D | A | 2023-01-02
100 | I Tower | Ground | IT/99
101 | I Tower | Ground | IT/100 | 2023-01-03 |  | SW formwork | Inspection of SW formwork before concrete Zone 2 - 3 |  | Grid 16F, 17D, 18D, & 18F, 19F 21D, 21B, 23A, 21A | A | 2023-01-10
102 | I Tower | Ground | IT/101
103 | I Tower | Ground | IT/102 | 2023-01-05 |  | Columns formwork | Inspection of columns formwork before concrete |  | Grid 19B, 19D, 23B, 23D, 23F, 18F, 19A, 19F, 21A, 21B, 21D, 23A | A | 2023-01-05
104 | I Tower | Ground | IT/103 | 2023-01-05 |  | Columns formwork | Inspection of columns formwork after concrete |  | Grid 19B, 19D, 23B, 23D, 23F, 18F, 19A, 19F, 21A, 21B, 21D, 23A | OP
105 | I Tower | Ground | IT/104 | 2023-01-05 |  | Shoring | Inspection of shoring stability GF Zone 1 |  | Grid 1-10/11, A to F | OP
106 | I Tower | Ground | IT/105 | 2023-01-06 |  | Slab | Inspection of slab formwork layout and level Zone 2 GF |  | Grid A to F, center 10/11-15 | A | 2023-01-07
107 | I Tower | Ground | IT/106 | 2023-01-07 |  | Columns formwork | Inspection of columns formwork before concrete Zone 3 GF |  | Grid 24B, 24D, 24F and 19B, 19D, 23B, 23D, 23F | A | 2023-01-07
108 | I Tower | Ground | IT/107 | 2023-01-09 |  | Columns formwork | Inspection of columns formwork before concrete Zone 3 GF |  | Grid 25A, 26A, 26B, 26 B/C, 26D, 26D/E, 26F, 23Fand 24B | A | 2023-01-10
109 | I Tower | Ground | IT/108 | 2023-01-10 |  | Slab formwork | Inspection of slab formwork layout and level Zone 2 GF |  | Grid A to F, center 15 to bw 16/17, 17 & balcony formwork 13-16 | A | 2023-01-20
110 | I Tower | Ground | IT/109 | 2023-01-14 |  | Core wall | Inspection of core wall Zone 3 GF |  | Grid 17-18 & A-B | A | 2023-01-17
111 | I Tower | 1st Floor | IT/110 | 2023-01-16 |  | Column Formwork | Inspection of column formwork Zone 1 1st Floor before concrete |  | Grid 1A, 1B, 1C, 1E, 1F, 2A, 4A, 3B | A | 2023-01-17
112 | I Tower | 2nd Floor | IT/111 | 2023-01-19 |  | Columns Formwork | Inspection of formwork columns Zone 1 1st floor before concrete |  | Grid 3d, 3f, 6A, 6B, 6D, 6F, 8D, 8F | A | 2023-01-20
113 | I Tower | Ground | IT/112 | 2023-01-21 |  | Core Wall | Inspection of core wall Zone 3 GF Formwork before concrete 2nd height |  | Grid 17-18, A-B | A | 2023-02-02
114 | I Tower | Ground | IT/113 | 2023-01-21 |  | Slab formwork | Inspection of slab formwork Zone 3 GF Layout, level |  | Grid A-F/16-17, Balcony 17-21 and A-F | B | 2023-02-02
115 | I Tower | Ground | IT/114 | 2023-01-26 |  | Canopy formwork | Inspection of canopy formwork 5 nos Zone 1 GF |  | Grid 1 to 10-11 and A to F | A | 2023-02-02
116 | I Tower | Ground | IT/115 | 2023-01-26 |  | Canopy formwork | Inspection of canopy formwork 5 nos Zone 3 GF |  | Grid 16-17 to 26 and A to F | A | 2023-02-02
117 | I Tower | 1st Floor | IT/116 | 2023-01-26 |  | Columns formwork | Inspection of columns formwok 1st Floor Zone 1 before concrete |  | Grid 8A, 8B, 9D, 9F, 10D, 10F SW1, SW2 Grid 8-9 and B-E | A | 2023-02-02
118 | I Tower | 2nd Floor | IT/117 | 2023-01-27 |  | Columns formwork | Inspection of columns formwork 1st Floor Zone 2 before concrete |  | Grid 11F, 11D, 11B, 11A, 12A, 12B, 12D, 12F, 13D, 13F, 14F | A | 2023-02-02
119 | I Tower | 1st Floor | IT/118 | 2023-02-04 |  | FF Formwork | Inspection of core wall Zone 1 FF formwork before concrete |  | Grid 9-10 & A - B | B | 2023-02-06
120 | I Tower | 1st Floor | IT/119 | 2023-02-04 |  | Column formwork | Inspection of formwork columns Zone 2 1st floor before concrete |  | Grid 13-16 to A-F | A | 2023-02-06
121 | I Tower | 2nd Floor | IT/120 | 2023-02-04 |  | Slab formwork | Inspection of slab formwork 1st floor Zone 1 Layout and level |  | Grid 1 to 10-11 and A to F | A | 2023-02-22
122 | I Tower | 1st Floor | IT/121 | 2023-02-07 |  | Column formwork | Inspection of column formwork before concrete 1st Floor Zone 2 |  | Grid 16 to B-F | A | 2023-02-15
123 | I Tower | 1st Floor | IT/122 | 2023-02-10 |  | Slab formwork | Inspection of slab formwork F1st Floor Layout and level Zone 1 1st floor |  | Grid 10-11 to 16-17 | A | 2023-03-01
124 | I Tower | 1st Floor | IT/123 | 2023-02-10 |  | Columns formwork | Inspection of formwork columns 1st Floor Zone 3 before concrete |  | Grid 24-26 and A-F | A | 2023-02-15
125 | I Tower | 1st Floor | IT/124 | 2023-02-13 |  | Columns formwork | Inspection of formwork columns Zone 3 1st Floor |  | Grid 21-25 and A-F | A | 2023-02-15
126 | I Tower | 1st Floor | IT/125 | 2023-02-13 |  | Columns formwork | Inspection of columns formwok Zone 3 1st Floor before concrete |  | Grid 17-19 and A-F | A | 2023-02-15
127 | I Tower | 1st Floor | IT/126 | 2023-02-16 |  | Core wall formwork | Inspection of formwork core wall zone 3 1st floor before concrete |  | Grid 17-18 to A-B | B | 2023-02-22
128 | I Tower | 1st floor | IT/127 | 2023-02-17 |  | Slab shoring | Inspection of slab shoring for undisturbed striking Zone 1 1st floor |  | Grid 1 to 10-11 and A-F | A | 2023-03-01
129 | I Tower | 2nd floor | IT/128 | 2023-02-17 |  | Columns formwork | Inspection of columns formwork before concrete 2nd floor Zone 1 |  | Grid 1-3 & A-F | A | 2023-02-22
130 | I Tower | 2nd floor | IT/129 | 2023-02-18 |  | Column formwork | Inspection of columns formwork before concrete 2nd Floor Zone 1 |  | Grid 4-10 & A-F | A | 2023-02-22
131 | I Tower | 1st floor | IT/130 | 2023-02-18 |  | Slab formwork | Inspection of slab formwork 1st floor Zone 3 |  | Grid 16-17 to 26 | A | 2023-03-01
132 | I Tower | 2nd floor | IT/131 | 2023-02-20 |  | Shear wall formwork | Inspection of shear wall formwork before concrete 2nd floor Zone 1 |  | Grid b/w 8-9 | A | 2023-03-01
133 | I Tower | 2nd floor | IT/132 | 2023-02-20 |  | Columns formwork | Inspection of columns formwork before concrete 2nd floor Zone 2 |  | Grid 11-12 & A-F | A | 2023-03-01
134 | I Tower | 2nd floor | IT/133 | 2023-02-23 |  | Slab formwork | Inspection of slab formwork before concrete layout and level SF Zone 1 |  | Grid 1 to 10-11 and A-F | A | 2023-03-03
135 | I Tower | 2nd Floor | IT/134 | 2023-02-27 |  | Corewall formwork | Inspection of core wall Zone 1 Second floor formwork before concrete |  | Grid 9-10 & A-B | B | 2023-03-01
136 | I Tower | 2nd Floor | IT/135 | 2023-02-27 |  | Column formwork | Inspection of column formwork before concrete 2nd Floor Zone 2 |  | Grid 13-16 & B-F | A | 2023-03-01
137 | I Tower | 2nd Floor | IT/136 | 2023-02-27 |  | Column Formwork | Inspection of columns formwork before concrete Zone 2 & 3 2nd Floor |  | Grid 13-17 & A-F | A | 2023-03-01
138 | I Tower | 2nd Floor | IT/137 | 2023-03-01 |  | Columns formwork | Inspection of columns formwork before concrete 2nd Floor Zone 3 |  | Grid 18-26 & A-F | A | 2023-03-01
139 | I Tower | 2nd Floor | IT/138 | 2023-03-03 |  | Slab formwork | Inspection of slab formwork SF Zone 2 |  | Grid 10-11 to 16-17 | A | 2023-03-08
140 | I Tower | 3rd Floor | IT/139 | 2023-03-06 |  | Column Formwork | Inspection of columns formwork before concrete 3rd Floor Zone 1 |  | Grid 1-2 & A-F | A | 2023-03-08
142 | I Tower | 3rd Floor | IT/140 | 2023-03-06 |  | Columns formwork | Inspection of columns formwork before concrete 3rd Floor Zone 1 |  | Grid 3-8 & A-F | A | 2023-03-08
143 | I Tower | 3rd Floor | IT/141 | 2023-03-06 |  | Columns formwork | Inspection of column formwork before concrete 3rd Floor Zone 1 |  | Grid 8/9-10 & B-F | A | 2023-03-08
144 | I Tower | 2nd Floor | IT/142 | 2023-03-06 |  | Slab formwork | Inspection of slab formwork Z3 SF, Layout and level |  | Grid 16-17 to 26 | A | 2023-03-13
145 | I Tower | 2nd Floor | IT/143 | 2023-03-07 |  | Core wall formwork | Inspection of core wall formwork 1st floor Zone 3 |  | Grid 17-18 to A-B | A | 2023-03-13
146 | I Tower | 3rd Floor | IT/144 | 2023-03-09 |  | Slab formwork | Inspection of slab formwork 3rd floor Zone 1 |  | Grid 1 to 10-11 | A | 2023-03-20
147 | I Tower | 3rd Floor | IT/145 | 2023-03-11 |  | Corewall | Inspection of Core wall 3rd Floor Zone 1 before concrete |  | Grid 9-10 & A-B | A | 2023-03-13
148 | I Tower | 3rd Floor | IT/146 | 2023-03-09 |  | Column formwork | Inspection of columns formwork before concrete 3rd floor Zone 2 |  | Grid 11-12 & A-F | A | 2023-03-13
149 | I Tower | 3rd Floor | IT/147 | 2023-03-10 |  | Column formwork | Inspection Column formwork before concrete 3rd Floor Zone 2 |  | Grid 13-14 & A-F | A | 2023-03-13
150 | I Tower | 3rd Floor | IT/148 | 2023-03-11 |  | Column formwork | Inspection of column formwork before concrete 3rd floor Zone 2 |  | Grid 15-16 & A-F | A | 2023-03-13
151 | I Tower | 3rd Floor | IT/149 | 2023-03-13 |  | Column Formwork | Inspection of columns formwork before concrete Zone 3 |  | Grid 17-21 & A-F | A | 2023-03-20
152 | I Tower | 3rd Floor | IT/150 | 2023-03-14 |  | Slab formwork | Inspection of slab formwork 3rd floor Zone 2, layout and level |  | Gride 10-11 to 16-17 | A | 2023-03-22
153 | I Tower | 3rd Floor | IT/151 | 2023-03-14 |  | Column and SW formwork | Inspection of columns and shear wall formwork before concrete Zone 3 |  | Grid 23-26 & A-F + SW 18-19 | A | 2023-03-20
154 | I Tower | 3rd floor | IT/152 | 2023-03-17 |  | Slab formwork | Inspection of slab formwork Zone 3 3rd floor |  | Grid 16-17 to 26 | A | 2023-03-28
155 | I Tower | 3rd Floor | IT/153 | 2023-03-18 |  | Core wall formwork | Inspection of core wall formwork Zone 3 before concrete |  | Grid 17-18 to A-B | B | 2023-03-22
156 | I Tower | 4th floor | IT/154 | 2023-03-18 |  | Columns formwork | Inspection of column formwork and shear wall before concrete Zone 1 |  | Grid 1-10 & a-f + 2 Nos SW Grid 8-9 | A | 2023-03-28
157 | I Tower | 4th floor | IT/155 | 2023-03-21 |  | Column formwork | Inspection of columns formwork 4th Floor Zone 2 |  | Grid 11-12 & A-F | A | 2023-03-28
158 | I Tower | 4th floor | IT/156 | 2023-03-22 |  | Core wall formwork | Inspection of core wall formwork before concrete Zone 4 |  | Grid 9-10 & A-B | B | 2023-03-28
159 | I Tower | 4th floor | IT/157 | 2023-03-22 |  | Slab formwork | Inspection of slab formwork Zone 1 4th floor before concrete |  | Grid 1 to 10-11 | B | 2023-04-03
160 | I Tower | 4th floor | IT/158 | 2023-03-22 |  | Column Formwork | Inspection of columns formwork Zone 2 (16 Nos) |  | Grid 13-16 & A-F | A | 2023-03-28
161 | I Tower | 4th floor | IT/159 | 2023-03-25 |  | Column formwork | Inspection of columns formwork Zone 3 (174 Nos) |  | Grid 17-26 & A-F | A | 2023-03-28
162 | I Tower | 4th floor | IT/160 | 2023-03-28 |  | Column formwork | Inspection of column formwork (5 Nos) Zone 3 |  | Grid 17-26 & SW2 Grid 18-19 | A | 2023-03-28
163 | I Tower | 4th floor | IT/161 | 2023-03-28 |  | Slab formwork | Inspection of slab formwork Zone 2 , layout and level |  | Grid 10-11 to 16-17 | A | 2023-04-07
164 | I Tower | 5th Floor | IT/162 | 2023-03-30 |  | Column formwork | Inspection of columns formwork Zone 1 (8 Nos) |  | Grid 1-4 & A-F | A | 2023-04-03
165 | I Tower | 3rd Floor | IT/163 | 2023-03-31 |  | Slab formwork | Inspection of slab formwork Zone 3, layout and level |  | Grid 16-17 to 26 | A | 2023-04-07
166 | I Tower | 4th floor | IT/164 | 2023-03-31 |  | Core wall formwork | Inspection of core wall formwork Zone 3 before concrete |  | Grid 17-18 to A-B | B | 2023-04-03
167 | I Tower | 5th Floor | IT/165 | 2023-04-07 |  | Columns formwork | Inspection of columns formwork Zone 1 (14 Nos) |  | Grid 3-10 & A-F | A | 2023-04-10
168 | I Tower | 5th Floor | IT/166 | 2023-04-07 |  | Columns formwork | Inspection of columns formwork Zone 2 (6 Nos) |  | Grid 11-12 & B-F | A | 2023-04-10
169 | I Tower | 5th Floor | IT/167 | 2023-04-07 |  | SW formwork | Inspection of SW formwork Zone 1 |  | Grid 8/9-10 & B-F | A | 2023-04-10
170 | I Tower | 5th Floor | IT/168 | 2023-04-10 |  | Column formwork | Inspection of columns formwork Zone 5 (18 Nos) |  | Grid 11-16 & A-F | A | 2023-04-14
171 | I Tower | 4th floor | IT/169
172 | I Tower | 5th Floor | IT/170 | 2023-04-13 |  | Slab formwork | Inspection of slab formwork Zone 1, layout, level before concrete |  | Grid 1 to 10-11 | A | 2023-04-19
173 | I Tower | 6th Floor | IT/171 | 2023-04-16 |  | Slab formwork | Inspection of slab formwork Zone 1 (+73.75') |  | Grid 1 & 10 to 11 | A | 2023-05-08
174 | I Tower | 6th floor | IT/172 | 2023-04-29 |  | Slab formwork | Inspection of slab formwork Zone 2 | (+73.75') | Grid 10 to 11 & 16 to 17 | A | 2023-05-08
175 | I Tower | 5th Floor | IT/173 | 2023-04-30 |  | Columns formwork | Inspection of columns formwork Zone 3 |  | Grid 17 to 18 | A | 2023-05-08
176 | I Tower | 5th Floor | IT/174 | 2023-05-01 |  | Columns formwork | Inspection of columns formwork Zone 3 (5 Nos) columns Zone 3 |  | Grid 19 to 21 | A | 2023-05-08
177 | I Tower | 5th Floor | IT/175 | 2023-05-01 |  | Shear wall formwork | Inspection of shear wall formwork Zone 3 (2 Nos) before concrete |  | Grid 18 to 19 | A | 2023-05-08
178 | I Tower | 5th Floor | IT/176 | 2023-05-02 |  | Columns formwork | Inspection of columns formwork Zone 3 (11 Nos) before concrete Zone 3 |  | Grid 21-26 to F-G | A | 2023-05-08
179 | I Tower | 5th Floor | IT/177 | 2023-05-06 |  | Slab formwork | Inspection of slab formwork Zone |  | Grid 16-17 to 26 | A | 2023-05-17
180 | I Tower | 5th Floor | IT/178 | 2023-05-06 |  | Core wall formwork | Inspection of core wall formwork Zone 3 before concrete Zone 3 |  | Grid 17-18 to A-B | B | 2023-05-08
181 | I Tower | Basement | IT/179 | 2023-05-06 |  | RW Starter | Inspection of RW Starter Zone 8 |  | Grid 12-15 and U onwards | A | 2023-05-08
182 | I Tower | 6th Floor | IT/180 | 2023-05-07 |  | Column formwork | Inspection of columns formwork Zone 6 |  | Grid 1-3 to A-F | B | 2023-05-17
183 | I Tower | 6th Floor | IT/181 | 2023-05-09 |  | Columns formwork | Inspection of columns formwork Zone 1 2 Nos shear wall and 14 Nos columns |  | Grid 4-10 to A-F | B | 2023-05-17
184 | I Tower | 6th Floor | IT/182 | 2023-05-13 |  | Core wall formwork | Inspection of core wall formwork before concrete Zone 1 |  | Grid 9-10 & A-B | A | 2023-05-16
185 | I Tower | 6th Floor | IT/183 | 2023-05-13 |  | Column formwork | Inspection of column formwork Zone 2 (8 Nos) before concrete |  | Grid 11-12 to A-F | B | 2023-05-16
186 | I Tower | 6th Floor | IT/184 | 2023-05-14 |  | Slab formwork | Inspection of slab formwork Zone 1, layout, level |  | Grid 1 to 10-11 | A | 2023-05-23
187 | I Tower | Basement | IT/185 | 2023-05-15 |  | Columns formwork | Inspection of columns formwork Zone 2 6th Floor before concrete (8 Nos) |  | Grid 13-14 to A-F | A | 2023-05-23
188 | I Tower | 6th Floor | IT/186 | 2023-05-17 |  | Column formwork | Inspection of columns formwork Zone 2 before concrete |  | Grid 15-16 to A-F | A | 2023-05-23
189 | I Tower | 6th Floor | IT/187 | 2023-05-19 |  | Column formwork | Inspection of column formwork Zone 3 (20 Nos) before concrete |  | Grid 17-26 to A-F | A | 2023-05-30
190 | I Tower | 6th Floor | IT/188 | 2023-05-22 |  | Slab formwork | Inspection of slab formwork Zone 2 layout, level |  | Grid 10-11 to 16-17 | A | 2023-05-30
191 | I Tower | 6th Floor | IT/189 | 2023-05-22 |  | Column formwork | Inspection of columns formwork Zone 3 2 Nos column 2 No sW |  | Grid 18-19 to B-F | A | 2023-05-26
192 | I Tower | 6th Floor | IT/190 | 2023-05-29 |  | CW formwork | Inspection of CW formwork Zone 3 before concrete |  | Grid 17-18 to A-B | A | 2023-06-16
193 | I Tower | 6th Floor | IT/191 | 2023-05-29 |  | slab formwork | Inspection of slab formowork Zone 3, layout , level |  | Grid 16-17 to 26 | A | 2023-06-16
194 | I Tower | 7th Floor | IT/192 | 2023-06-08 |  | Column formwork | Inspection of columns formwork Zone 3 (22 Nos columns 2 Nos SW) before concrete |  | Grid 17-26 to A-F | A | 2023-06-16
195 | I Tower | 7th Floor | IT/193 | 2023-06-12 |  | CW formwork | Inspection of CW formwork Zone 3 before concrete |  | Grid 17-18 to A-B | A | 2023-06-16
196 | I Tower | 7th Floor | IT/194 | 2023-06-13 |  | Slab formwork | Inspection of slab formwork Zone 3, laout and level |  | Grid 16-17 to 26 | A | 2023-07-12
197 | I Tower | 7th Floor | IT/195 | 2023-06-15 |  | columns formwork | Inspection of columns formwork Zone 2 (24 Nos) before concrete |  | Grid 11-16 to A-F | A | 2023-07-12
198 | I Tower | 7th Floor | IT/196 | 2023-07-03 |  | Column formwork | Inspection of columns formwork Zone 1 before concrete |  | Grid 1-10 and A-F | A | 2023-07-27
199 | I Tower | 7th floor | IT/197 | 2023-07-12 |  | Slab formwork | Inspection of slab formwork Zone 2 layout, level |  | Grid 10-11 to 16-17 | A | 2023-07-27
200 | I Tower | 7th Floor | IT/198 | 2023-07-12 |  | SW formwork | Inspection of SW formwork Zone 1 (2 Nos) 7th Floor before concrete |  | Grid 8-9 and B-E | A | 2023-07-27
201 | I Tower | 7th Floor | IT/199 | 2023-05-15 |  | CW formwork | Inspection of core wall formwork Zone 1 |  | Grid 9-10 & A-B | A | 2023-07-27
202 | I Tower | 8th Floor | IT/200 | 2023-07-18 |  | columns formwork | Inspection of columns formwork Zone 3 (18 Nos) before concrete |  | Grid 19-26 to A-F | A | 2023-07-27
203 | I Tower | 7th Floor | IT/201 | 2023-07-21 |  | Slab formwork | Inspection of slab formwork Zone 1, layout, level before concrete |  | Grid 1 to 10-11 | B | 2023-08-09
204 | I Tower | 8th Floor | IT/202 | 2023-07-24 |  | Column formwork | Inspection of column formwork Zone 3 before concrete |  | Grid 17-19 to B-F | A | 2023-07-27
205 | I Tower | 8th Floor | IT/203 | 2023-07-31 |  | CW formwork | Inspection of Core wall formwork Zone 3 before concrete |  | Grid 17-18 to A-B | B | 2023-08-16
206 | I Tower | 8th Floor | IT/204 | 2023-07-31 |  | Slab formwork | Inspection of slab formwork Zone 3 before concrete |  | Grid 17-18 to A-B | B | 2023-08-16
207 | I Tower | 8th Floor | IT/205 | 2023-07-31 |  | Column formwork | Inspection of columns formwork (11 Nos) Zone 2 before concrete |  | Grid 13-16 and A-F | A | 2023-08-16
208 | I Tower | 8th Floor | IT/206 | 2023-08-03 |  | column formwork | Inspection of column formwork Zone 2 before concrete |  | Grid 11 to 16, A to F | A | 2023-08-16
209 | I Tower | 8th Floor | IT/207 | 2023-08-07 |  | slab formwork | Inspection of slab formwork Zone 2, layout, leve |  | Grid 10-11 to 16-17 | A | 2023-08-16
210 | I Tower | 8th Floor | IT/208 | 2023-08-07 |  | Column Formwork | Inspection of columns (12 Nos) formwork Zone 1 before concrete |  | Grid 6-10 and A-F | A | 2023-08-16
211 | I Tower | 8th Floor | IT/209 | 2023-08-09 |  | Column Formwork | Inspection of columns (10 Nos) formwork and 2 Nos SW Zone 1 |  | Grid 1-9 and A-F | A | 2023-08-16
212 | I Tower | 9th Floor | IT/210 | 2023-08-12 |  | Column Formwork | Inspection of columns (10 Nos) formwork Zone 3 before concrete |  | Grid 23-26 and A-F | A | 2023-08-18
213 | I Tower | 8th Floor | IT/211 | 2023-08-12 |  | CW formwork | Inspection of CW formwork before concrete Zone 1 |  | Grid 9-10 & A-B | A | 2023-08-18
214 | I Tower | 9th Floor | IT/212 | 2023-08-15 |  | Column Formwork | Inspection of 8 Nos column formwork Zone 3 before concrete |  | Grid 19-21 and A-F | A | 2023-08-18
215 | I Tower | 8th Floor | IT/213 | 2023-08-17 |  | slab formwork | Inspection of slab formwork Zone 1, layout, level before concrete |  | Grid 1 to 10-11 | A | 2023-09-01
216 | I Tower | 9th Floor | IT/214 | 2023-08-18 |  | columns formwork | Inspection of 4 nos columns formwork and 2 nos Shear wall Zone 3 before concrete |  | Grid 19-17 and B-F | A | 2023-09-01
217 | I Tower | 9th Floor | IT/215 | 2023-08-21 |  | Column Formwork | Inspection of columns (8 Nos) formwork Zone 2 before concrete |  | Grid 13-16 and A-F | A | 2023-08-28
218 | I Tower | 9th Floor | IT/216 | 2023-08-22 |  | column formwork | Inspection of 8 nos columns formwork Zone 2 before concrete |  | Grid 13-14 and A-F | A | 2023-08-28
219 | I Tower | 9th Floor | IT/217 | 2023-08-22 |  | CW formwork | Inspection of CW formwork Zone 3 before concrete |  | Grid 17-18 to A-B | A | 2023-09-01
220 | I Tower | 9th Floor | IT/218 | 2023-08-23 |  | slab formwok | Inspection of slab formwork Zone 3, layout, level |  | Grid 17-26 to A-B | B | 2023-09-06
221 | I Tower | 9th Floor | IT/219 | 2023-08-23 |  | column formwork | Inspection of columns formwork Zone 2 before concrete |  | Grid 11-12 and A-F | A | 2023-08-28
222 | I Tower | 9th Floor | IT/220 | 2023-08-31 |  | Column Formwork | Inspection of columns (6 Nos) formwork Zone 1 |  | Grid 8-10 and D-F | A | 2023-09-06
223 | I Tower | 9th Floor | IT/221 | 2023-09-01 |  | column formwork | Inspection of (11 Nos) columns formwork before concrete |  | Grid 1-6 and A-F | A | 2023-09-13
224 | I Tower | 9th Floor | IT/222 | 2023-09-02 |  | slab formwork | Inspection of slab formwork Zone 2, layout, level |  | Grid 10-11 to 16-17 | B | 2023-09-15
225 | I Tower | 9th Floor | IT/223 | 2023-09-03 |  | column formwork | Inspection of columns formwork (5 Nos) before concrete |  | Grid 1 & 8-9 and A-F | A | 2023-09-13
226 | I Tower | 9th Floor | IT/224 | 2023-09-04 |  | CW formwork | Inspection of CW formwork before concrete Zone 1 |  | Grid 9-10 & A-B | A | 2023-09-13
227 | I Tower | 9th Floor | IT/225 | 2023-09-06 |  | column formwork | Inspection of column formwork before concrete |  | Grid 8-9 and B-E | A | 2023-09-13
228 | I Tower | 9th Floor | IT/226 | 2023-09-10 |  | Slab formwork | Inspection of slab formwork Zone 1, layout and level |  | Grid 1 to 10-11 | B | 2023-09-15
229 | I Tower | 10th Floor | IT/227 | 2023-09-12 |  | column formwork | Inspection of (12 nos) column formwork Zone 2 before concrete |  | Grid 13-11 and A-F | A | 2023-09-15
230 | I Tower | 10th Floor | IT/228 | 2023-09-14 |  | Column Formwork | Inspection of (12 nos) column formwork Zone 2 before concrete |  | Grid 14-16 and A-F | A | 2023-09-15
231 | I Tower | 10th Floor | IT/229 | 2023-09-18 |  | column formwork | Inspection of (4 Nos) columns formwork Zone 3 before concrete |  | Grid 17-18 and E-D | A | 2023-09-20
232 | I Tower | 10th Floor | IT/230 | 2023-09-20 |  | Column Formwork | Inspection of (12 No) column formwork Zone 1 before concrete |  | Grid 1-6 and A-F | A | 2023-09-22
233 | I Tower | 10th Floor | IT/231 | 2023-09-21 |  | CW formwork | Inspection of CW formwork Zone 3 before concrete |  | Grid 17-18 and A-B | B | 2023-09-27
234 | I Tower | 10th Floor | IT/232 | 2023-09-21 |  | Slab formwork | Inspection of Slab formwork Zone 2, layout, level |  | Grid 10-11 and 16-17 | B | 2023-09-27
235 | I Tower | 10th Floor | IT/233 | 2023-09-22 |  | Column Formwork | Inspection of Columns (10 Nos) formwork and SW (2 Nos) before concrete |  | Grid 6-9 and A-F | A | 2023-09-27
236 | I Tower | 10th Floor | IT/234 | 2023-09-23 |  | Column Formwork | Inspection of columns (6 Nos) formwork before concrete |  | Grid 23-26 and A-B | A | 2023-09-27
237 | I Tower | 10th Floor | IT/235 | 2023-09-25 |  | CW formwork | Inspection of CW formwork before concrete Zone 1 |  | Grid 9-10 & A-B | A | 2023-09-27
238 | I Tower | 10th Floor | IT/236 | 2023-09-25 |  | Column SW formwork | Inspection of columns (2 Nos) and SW (2 Nos) formwork Zone 3 before concrete |  | Grid 18-19 and B-F | A | 2023-10-04
239 | I Tower | 10th Floor | IT/237 | 2023-09-26 |  | Slab formwork | Inspection of slab formwork Zone 1 before concrete |  | Grid 1 to 10-11 | B | 2023-10-04
240 | I Tower | 10th Floor | IT/238 | 2023-10-03 |  | slab formwork | Inspection of slab formwork Zone 3, laout, level |  | Grid 17-26 & A-F | B | 2023-10-11
241 | I Tower | 11th Floor | IT/239 | 2023-11-18 | 2023-11-19 | Column Formwork | Inspection of columns (9 Nos) formwork Zone 1 before concrete |  | Grid 1-3 & A-F | A | 2023-11-20
242 | I Tower | 11th Floor | IT/240 | 2023-11-20 | 2023-11-20 | Column Formwork | Inspection of (7 Nos) columns formwork and (5 Nos) 1st height formwork Zone 1 |  | Grid 1-8 & A-F | A | 2023-11-25
243 | I Tower | 11th Floor | IT/241 | 2023-11-24 | 2023-11-25 | Column Formwork | Inspection of columns (7 Nos) formwork Zone 1 before concrete |  | Grid 1-8 & A-F | A | 2023-11-28
244 | I Tower | 11th Floor | IT/242 | 2023-11-25 | 2023-11-25 | Column Formwork | Inspection of columns (3 Nos), SW-01 formwork Zone 1 before concrete |  | Grid 8-9 & A-F | A | 2023-11-28
245 | I Tower | 11th Floor | IT/243 | 2023-11-27 | 2023-11-27 | Column Formwork | Inspection of columns (5 Nos) and SW (01 Nos) formwork Zone 1 before concrete |  | Grid 8-10 & A-F | B | 2023-11-28
246 | I Tower | 11th Floor | IT/244 | 2023-11-27 | 2023-11-27 | Column Formwork | Inspection of columns (4 Nos) formwork Zone 2 before concrete |  | Grid 11 & A-F | A | 2023-11-28
247 | I Tower | 11th Floor | IT/245 | 2023-11-28 | 2023-11-28 | Column Formwork | Inspection of column (1 No), SW (SW-01) formwork Zone 1 before concrete |  | Grid 8-9 & B-C | B | 2023-11-29
248 | I Tower | 11th Floor | IT/246 | 2023-11-29 | 2023-11-29 | column, sw formwork | Inspection of columns (4 Nos) and SW formwork Zone 1 before concrete |  | Grid 8-10 & B-F | A | 2023-11-30
249 | I Tower | 11th Floor | IT/247 | 2023-11-29 | 2023-11-29 | Column Formwork | Inspection of columns (2 Nos) 2nd height and (4 Nos) 1st height formwork Zone 2 |  | Grid 11-12 & A-F | A | 2023-11-30
250 | I Tower | 11th Floor | IT/248 | 2023-11-29 | 2023-11-30 | CW formwork | Inspection of CW formwork before concrete (+145'-9'') |  | Grid 9-10 & A-B | B | 2023-12-05
251 | I Tower | 11th Floor | IT/249 | 2023-11-30 | 2023-11-30 | Column Formwork | Inspection of columns (6 Nos) formwork Zone 2 before concrete |  | Grid 11-12 & A-F | A | 2023-12-04
252 | I Tower | 11th Floor | IT/250 | 2023-12-01 | 2023-12-01 | Column Formwork | Inspection of columns (4 Nos) formwork Zone 2 before concrete |  | Grid 13 & A-F | A | 2023-12-05
253 | I Tower | 11th Floor | IT/251 | 2023-12-02 | 2023-12-02 | slab formwork | Inspection of slab formwork Zone 1 (+145'-9''), layout, level |  | Grid 1 to 10-11 | B | 2023-12-18
254 | I Tower | 11th Floor | IT/252 | 2023-12-04 | 2023-12-04 | Column formwork | Inspection of columns (4 Nos) formwork Zone 2 before concrete |  | Grid 13-14 & A-F | A | 2023-12-05
255 | I Tower | 11th Floor | IT/253 | 2023-12-05 | 2023-12-05 | CW formwork | Inspection of CW formwork 2nd height before concrete |  | Grid 9-10 & A-B | B | 2023-12-08
256 | I Tower | 11th Floor | IT/254 | 2023-12-07 | 2023-12-07 | Column formwork | Inspection of columns (8 Nos) 1st height formwork Zone 2 before concrete |  | Grid 15-16 & A-F | A | 2023-12-11
257 | I Tower | 11th Floor | IT/255 | 2023-12-11 | 2023-12-11 | column formwork | Inspection of columns (8 Nos) formwork Zone 2 before concrete |  | Grid 14-15 & A-F | A | 2023-12-18
258 | I Tower | 11th Floor | IT/256 | 2023-12-11 | 2023-12-12 | Column formwork | Inspection of columns (4 Nos) formwork Zone 3 before concrete |  | Grid 17-18 & D-F | A | 2023-12-18
259 | I Tower | 11th Floor | IT/257 | 2023-12-12 | 2023-12-12 | Column formwork | Inspection of columns (4 Nos) formwork Zone 2 before concrete |  | Grid 16 & A-F | A | 2023-12-18
260 | I Tower | 11th Floor | IT/258 | 2023-12-26 | 2023-12-26 | Slab formwork | Inspection of Slab formwork Zone 2 layout, level | (+145'-9'') | Grid 10-11 and 16-17 | B | 2024-01-03
261 | I Tower | 11th Floor | IT/259 | 2023-12-28 | 2023-12-28 | Column formwork | Inspection of columns (8 Nos) formwork Zone 3 before concrete |  | Grid 19-21 & A-F | A | 2024-01-03
| I Tower | 11th Floor | IT/260 | 2024-01-01 | 2024-01-01 | CW formwork | Inspection of CW formwork Zone 3 before concrete |  | Grid 17-18 & A-B | B | 2024-01-09
| I Tower | 11th Floor | IT/261 | 2024-01-01 | 2024-01-02 | Column formwork | Inspection of columns formwork (8 Nos) before concrete Zone 3 |  | Grid 17-19 & A-F | A | 2024-01-03
| I Tower | 11th Floor | IT/262 | 2023-01-02 | 2023-01-02 | SW formwork | Inspection of SW (2 Nos) formwork zone 3 before concrete |  | Grid 18-19 & A-E | A | 2024-01-03
| I Tower | 11th Floor | IT/263 | 2024-01-04 | 2024-01-04 | column, sw formwork | Inspection of sw (2 Nos) and columns (4 Nos) formwork before concrete |  | Grid 18-21 & A-D | A | 2024-01-09
| I Tower | 11th Floor | IT/264 | 2024-01-04 | 2024-01-05 | Column formwork | Inspection of columns (10 Nos) formwork before concrete |  | Grid 23-26 & A-F | A | 2024-01-09
| I Tower | 11th Floor | IT/265 | 2024-01-08 | 2024-01-07 | Column formwork | Inspection of columns (10 Nos) fomrwork before concrete Zone 3 |  | Grid 23-26 & A-F | A | 2024-01-17
| I Tower | 11th Floor | IT/266 | 2024-01-09 | 2024-01-10 | CW formwork | Inspection of CW formwork Zone 3 before concrete |  | Grid 17-18 to A-B | B | 2024-01-17
| I Tower | 11th Floor | IT/267 | 2024-01-15 | 2024-01-16 | Slab formwork | Inspection of slab formwork Zone 3 level, layout |  | Grid 17 & A to F | B | 2024-01-24
| I Tower | 11th Floor | IT/268 | 2024-02-14 | 2024-02-15 | PW | Inspection of Parapet wall formwork Zone 1 (+145'-9'') layout , level | (+145'-9'') | Grid 1-9 & C to F | B | 2024-02-19
| I Tower | 11th Floor | IT/269 | 2024-02-23 | 2024-02-23 | PW formwork | Inspection of PW formwork Zone 2, level , layout | (+145'-9'') | Grid 10 to 16 & A to F | A | 2024-02-26 |  |  |  |  | v
| I Tower | 11th Floor | IT/270 | 2024-02-29 | 2024-02-29 | PW formwork | Inspection of Parapet wall formwork Zone 3, layout, level | (+145'-9" | Grid 17-26 & F | A | 2024-03-06
| I Tower | 11th Floor | IT/271 | 2024-03-09 | 2024-03-10 | PW formwork | Inspection of PW formwork Zone 3, layout, level |  | Grid 20-26 & A-F | B | 2024-03-18
| I Tower | 11th Floor | IT/272 | 2024-03-20 | 2024-03-20 | PW formwork | Inspection of PW formwork Zone 2 (+145'-9'') layout, level | (+145'-9'') | Grid 11-16 & A-F | B | 2024-03-26
| I Tower | 11th Floor | IT/273
| I Tower | 11th Floor | IT/274
| I Tower | 11th Floor | IT/275
| I Tower | 11th Floor | IT/276
| I Tower | 11th Floor | IT/277
| I Tower | 11th Floor | IT/278
| I Tower | 11th Floor | IT/279
| I Tower | 11th Floor | IT/280
| I Tower | 11th Floor | IT/281
| I Tower | 11th Floor | IT/282
| I Tower | 11th Floor | IT/283
| I Tower | 11th Floor | IT/284
2022-12-19

## IIL L1 Tower IR
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (L1 Tower) IIL-CSL | [5 empty] | Fully Approved (A) |  | 119
[9 empty] | Approved with comments (B) |  | 54
[9 empty] | Rejected ( R) |  | 1 |  | As of : | 2025-12-19
[9 empty] | Open/Pending (OP) |  | 2
[9 empty] | Total |  | 176
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR closing Date | Pour Card No. | Concrete Qty (m3) | Status
1 | Sub Structure | Basement | L1-T/01 | 2023-03-28 |  | RW formwork | Inspection of RW formwork Zone 4 |  | Grid G to L after 26 | A | 2023-04-03
2 | Sub Structure | Basement | L1-T/02 | 2023-03-29 |  | Column formwork | Inspection of columns formwork Zone 4 before concrete (11 Nos) |  | Grid 22-26 and G-R | A | 2023-04-03
3 | Sub Structure | Basement | L1-T/03 | 2023-03-31 |  | Column formwork | Inspection of columns formwork Zone 4 before concrete (14 Nos) |  | Grid 22-26 and K-U | A | 2023-04-03
4 | Sub Structure | Basement | L1-T/04 | 2023-04-01 |  | Column formwork | Inspection of columns formwork Zone 4 Basement before concrete (8 Nos) |  | Grid 20-21 and H-M | A | 2023-04-06
5 | Sub Structure | Basement | L1-T/05 | 2023-04-07 |  | RW formwork | Inspection of RW formwork Zone 4 |  | Grid L to T after 26 | A | 2023-04-10
6 | Sub Structure | Basement | L1-T/06 | 2023-04-07 |  | Column formwork | Inspection of columns formwork Zone 4 &5 before concrete |  | Grid 15-22 and G-U | A | 2023-04-10
7 | Sub Structure | Basement | L1-T/07 | 2023-04-07 |  | RW formwork | Inspection of RW formwork Zone 4 |  | Grid L to T after T till end | A | 2023-04-10
8 | Sub Structure | Basement | L1-T/08 | 2023-04-10 |  | Column formwork | Inspection of column formwork before concrete Zone 5 |  | Grid 15-19, Q-S | A | 2023-04-14
9 | Sub Structure | Basement | L1-T/09 | 2023-04-10 |  | RW formwork | Inspection of RW Formwork Zone 4 |  | Grid 22-26 after U | A | 2023-04-14
10 | Sub Structure | Basement | L1-T/10 | 2023-04-10 |  | CW formwork | Inspection of CW formwork before concrete Zone 4 |  | Grid H-J and 23-24 | A | 2023-04-14
11 | Sub Structure | Basement | L1-T/11 | 2023-04-16 |  | Slab formwork | Inspection of slab formwork Zone 4 down part basement floor |  | Grid G-U & 23 to 26 | A | 2023-05-08
| Sub Structure | Basement | L1-T/12 | 2023-05-02 |  | RW formwork | Inspection of RW Basement Zone 6 |  | Grid 16-17 to 20-21 & S | A | 2023-05-08
12 | Sub Structure | Basement | L1-T/13 | 2023-05-05 |  | Slab formwork | Inspection of Slab formwork Zone 4 uppaart Floor layout level |  | Grid G-U & 20-26 | A | 2023-05-17
13 | Sub Structure | Basement | L1-T/14 | 2023-05-10 |  | Slab formwork | Inspection of slab formwork Zone 5 down part basement floor, |  | Grid N-U, 15-26 | A | 2023-05-23
14 | Sub Structure | Basement | L1-T/15 | 2023-05-12 |  | RW Formwork | Inspection of RW formwork Zone 4 |  | Grid after U & 15-17 | A | 2023-05-17
15 | Sub Structure | Basement | L1-T/16 | 2023-05-17 |  | Lift CW formwork | Inspection of Lift CW formwork Zone 4 basement before concrete |  | Grid N-Q and 20-22 | B | 2023-05-23
16 | Sub Structure | Basement | L1-T/17 | 2023-05-19 |  | Slab formwork | Inspection of slab formwork Zone 4 & 5 up part basement floor |  | Grid N-S & 15-26 | B | 2023-05-26
17 | Sub Structure | Basement | L1-T/18 | 2023-05-16 |  | Column formwork | Inspection of column formwork Zone 5 Basement floor before concrete |  | Grid 15-19 and N-Q | B | 2023-05-15
18 | Sub Structure | Basement | L1-T/19 | 2023-05-27 |  | Column formwork | Inspection of column formwork 1st height Zone 4 before concrete |  | Grid 20-26 and G-M | A | 2023-05-30
19 | Sub Structure | Basement | L1-T/20 | 2023-05-27 |  | Column formwork | Inspection of column formwork 2nd height Zone 4 before concrete |  | Grid 20-26 and G-M | A | 2023-05-30
20 | Sub Structure | Basement | L1-T/21 | 2023-05-30 |  | Column formwork | Inspection of columns formwork Zone 4 before concrete (9 Nos) |  | Grid 20-26 and G-M | A | 2023-06-16
21 | Sub Structure | Basement | L1-T/22 | 2023-05-30 |  | Column formwork | Inspection of columns formwork Zone 4 before concrete (4 Nos) |  | Grid 20-26 and G-M | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/23 | 2023-05-30 |  | CW formwork | Inspection of Service CW formwork Zone 4 before concrete (1 Nos) |  | Grid H-J and 23-24 | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/24 | 2023-06-01 |  | Service lift formwork | Inspection of service lift formwork Zone 4 |  | upper portion | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/25 | 2023-06-04 |  | Slab formwork | Inspection of slab formwork Zone 4 before cW, layout, level |  | Grid G-M & 20-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/26 | 2023-06-02 |  | Column formwork | Inspection of columns formwork Zone 4 & 5 before concrete (7 Nos) |  | Grid 18-26 and Q-U | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/27 | 2023-06-03 |  | Column formwork | Inspection of columns formwork Zone 4 before concrete (8 Nos) |  | Grid 20-26 and N-S | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/28 | 2023-06-04 |  | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid N-Q and 20-22 | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/29 | 2023-06-04 |  | Column formwork | Inspection of columns formwork (6 Nos) Zone 4 & 5 before concrete |  | Grid 15-26 and U | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/30 | 2023-06-06 |  | Column formwork | Inspection of columns formwork Zone 5 before concrete |  | Grid 15-19 and N-U | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/31 | 2023-06-08 |  | Column formwork | Inspection of columns formwork 3 Nos 2nd height 10 Nos Zone 5 GF before concrete |  | Grid 15-19 and N-U | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/32 | 2023-06-08 |  | CW formwork | Inspection of CW Formwork Zone 4 2nd height before concrete |  | Grid N-Q and 20-22 | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/33 | 2023-06-10 |  | Slab formwork | Inspection of slab formwork Zone 4 remaining part, layout, level |  | Grid N-U & 20-26 | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/34 | 2023-06-08 |  | Column formwork | Inspection of columns formwork (4 Nos) 1st height Zone 5 before concrete |  | Grid 15-18 and S | A | 2023-06-16
| Sub Structure | Ground floor | L1-T/35 | 2023-06-11 |  | Column formwork | Inspection of columns formwork (4 Nos) 2nd height Zone 5 before concrete |  | Grid 15-18 and S | A | 2023-06-16
| Sub Structure | 1st floor | L1-T/36 | 2023-06-16 |  | Columns formwork | Inspection of columns formwork (7 Nos) before concrete |  | Grid 1-7 and G-M | A | 2023-07-12
| Sub Structure | Ground floor | L1-T/37 | 2023-06-19 |  | Slab formwork | Inspection of slab formwork Zone 5, Layout, level |  | Grid M-U and 8-12 | B | 2023-07-12
| Sub Structure | 1st floor | L1-T/38 | 2023-07-03 |  | Column formwork | Inspection of column formwork Zone 4 before concrete |  | Grid 1-7 and G-M | B | 2023-07-27
| Sub Structure | 1st floor | L1-T/39 | 2023-07-10 |  | CW formwork | Inspection of Service CW formwork Zone 4 before concrete (1 Nos) |  | Grid H-J and 23-24 | B | 2023-07-27
| Sub Structure | 1st floor | L1-T/40 | 2023-07-10 |  | Column formwork | Inspection of columns formwork Zone 4 (9 Nos) before concrete |  | Grid 22-26 and S-M | A | 2023-07-27
| Sub Structure | 1st Floor | L1-T/41 | 2023-07-13 |  | Column formwork | Inspection of columns formwork Zone 4 & 5 (9 Nos) before concrete |  | Grid 19-26 and G-U | A | 2023-07-27
| Sub Structure | 1st Floor | L1-T/42 | 2023-07-12 |  | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid N-Q and 20-22 | B | 2023-07-27
| Sub Structure | 1st Floor | L1-T/43 | 2023-07-15 |  | Slab formwork | Inspection of slab formwork Zone 4 layout and level |  | Grid G-S & 20-26 | A | 2023-08-16
| Sub Structure | Ground floor | L1-T/44
| Sub Structure | 1st floor | L1-T/45 | 2023-07-15 |  | Column formwork | Inspection of columns formwork Zone 4 before concrete (8 NOS) |  | Grid 18-21 and N-U | A | 2023-01-02
| Sub Structure | Ground floor | L1-T/46 | 2023-07-18 |  | Column formwork | Inspection of columns formwork (12 Nos) before concrete |  | Grid 15-17 and N-U | A | 2023-07-27
| Sub Structure | 2nd Floor | L1-T/47 | 2023-07-31 |  | Column formwork | Inspection of columns formwork (14 Nos) Zone 4 before concrete |  | Grid G to N, 3 to 7 | A | 2023-08-16
| Sub Structure | 2nd Floor | L1-T/48 | 2023-08-02 |  | Column formwork | Inspection of columns (7 Nos) formwork Zone 4 before concrete |  | Grid G to N, 26 | A | 2023-08-16
| Sub Structure | 2nd Floor | L1-T/49 | 2023-08-02 |  | CW Service | Inspection of Service CW formwork Zone 4 before concrete |  | Grid H-J and 23-24 | A | 2023-08-16
| Sub Structure | 1st Floor | L1-T/50 | 2023-08-03 |  | Slab formwork | Inspection of slab formwork Zone 5 layout, level |  | Grid N-U, 15-26 | A | 2023-08-16
| Sub Structure | 2nd Floor | L1-T/51 | 2023-08-04 |  | Column formwork | Inspection of columns (3 Nos) formwork Zone 4 before concrete |  | Grid P-Q, 24-26 | A | 2023-08-16
| Sub Structure | 2nd Floor | L1-T/52 | 2023-08-05 |  | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid N-Q and 20-22 | B | 2023-08-16
| Sub Structure | 2nd Floor | L1-T/53 | 2023-08-16 |  | Slab formwork | Inspection of slab formwork Zone 4 , layout and level |  | Grid G-S & 20-26 | A | 2023-09-01
| Sub Structure | 2nd Floor | L1-T/54 | 2023-08-21 |  | Column formwork | Inspection of columns formwork Zone 5 (11 Nos) before concrete |  | Grid 15-17 and N-U | A | 2023-08-28
| Sub Structure | 3rd floor | L1-T/55 | 2023-08-25 |  | Column formwork | Inspection of columns formwork (12 Nos) before concrete |  | Grdi 20-26 and G-L | A | 2023-09-01
| Sub Structure | 3rd floor | L1-T/56 | 2023-08-26 |  | Column formwork | Inspection of columns formwork (7 Nos) Zone 4 before concrete |  | Grid 20-26 and G-M | A | 2023-09-06
| Sub Structure | 3rd floor | L1-T/57 | 2023-08-26 |  | lift formwork | Inspection of lift formwork Zone 4 before concrete |  | Grid H-J and 23-24 | A | 2023-09-01
| Sub Structure | 3rd Floor | L1-T/58 | 2023-08-31 |  | slab formwork | Inspection of slab formwork Zone 4 layout and level |  | Grid G-M & 20-26 | B | 2023-09-13
| Sub Structure | 3rd Floor | L1-T/59 | 2023-09-02 |  | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid N-Q and 20-22 | A | 2023-09-13
| Sub Structure | 2nd Floor | L1-T/60 | 2023-09-06 |  | Column formwork | Inspection of columns formwork Zone 5 (15 Nos) before concrete |  | Grid 17-26 and N-U | A | 2023-09-15
| Sub Structure | 4th Floor | L1-T/61 | 2023-09-11 |  | Column formwork | Inspection of (8 Nos) column formwork Zone 4 before concrete |  | Grid 20-22 and G-L | A | 2023-09-15
| Sub Structure | 2nd Floor | L1-T/62 | 2023-09-13 |  | slab formwork | Inspection of slab formwork Zone 5 layout and level |  | Grid N-U & 15-26 | A | 2023-09-20
| Sub Structure | 4th Floor | L1-T/63 | 2023-09-26 |  | Column formwork | Inspection of columns formwork (8 Nos0 Zone 4 before concrete |  | Grid 19-26 and K-M | A | 2023-10-02
| Sub Structure | 4th Floor | L1-T/64 | 2023-09-27 |  | CW formwork | Inspection of CW formwork service Zone 4 before concrete |  | Grid H-J and 23-24 | A | 2023-10-02
| Sub Structure | 4th floor | L1-T/65 | 2023-09-28 |  | Column formwork | Inspection of columns (4 Nos) formwork before concrete |  | Grid 23-26 and G-J | A | 2023-10-02
| Sub Structure | 3rd Floor | L1-T/66 | 2023-10-02 |  | Column formwork | Inspection of columns formwork (23 Nos) Zone 5 before concrete |  | Grid 16-26 & N-U | A | 2023-10-06
| Sub Structure | 3rd Floor | L1-T/67 | 2023-10-04 |  | Column formwork | Inspection of columns formwork Zone 5 before concrete |  | Grid 16-15 & N-U | A | 2023-10-06
| Sub Structure | 4th Floor | L1-T/68 | 2023-10-04 |  | Slab formwork | Inspection of slab formwork Zone 4, layout, level |  | Grid G-M & 20-26 | A | 2023-10-11
| Sub Structure | 3rd Floor | L1-T/69 | 2023-10-07 |  | Slab formwork | Inspection of slab formwork Zone 5 layout and level |  | Grid N-U & 15-26 | B | 2023-10-18
| Sub Structure | 5th Floor | L1-T/70 | 2023-10-13 |  | Column formwork | Inspection of columns (12 Nos) formwork Zone 4 before concrete |  | Grid 20-24 and G-L | B | 2023-10-18
| Sub Structure | 5th Floor | L1-T/71 | 2023-10-14 |  | Column formwork | Inspection of columns (8 Nos) formwork Zone 4 before concrete |  | Grid 20-26 and G-M | A | 2023-10-18
| Sub Structure | 5th Floor | L1-T/72 | 2023-10-15 |  | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid H-J and 23-24 | B | 2023-10-18
| Sub Structure | 4th Floor | L1-T/73 | 2023-10-16 |  | Column formwork | Inspection of column (15 Nos) formwork Zone 5 before concrete |  | Grid 18-15 & N-U | A | 2023-10-18
| Sub Structure | 4th Floor | L1-T/74 | 2023-10-25 | 2023-10-24 | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid N-Q and 20-22 | B | 2023-10-27
| Sub Structure | 4th Floor | L1-T/75 | 2023-10-19 |  | Column formwork | Inspection of (15 Nos) formwork Zone 5 |  | Grid 26-15 & N-U | A | 2023-10-18
| Sub Structure | 5th Floor | L1-T/76 | 2023-10-19 | 2023-10-19 | Slab formwork | Inspection of slab formwork Zone 4 layout and level |  | Grid G-M & 20-26 | A | 2023-10-24
| Sub Structure | 4th Floor | L1-T/77 | 2023-10-21 | 2023-10-21 | Column formwork | Inspection of column formwrok (3 Nos) Zone 4 & 5 before concrete |  | Grid 24-26 & N-Q | A | 2023-10-24
| Sub Structure | 4th Floor | L1-T/78 | 2023-10-23 | 2023-10-23 | Slab formwork | Inspection of slab formwork Zone 5 layout and level |  | Grid N-U & 15-26 | B | 2023-10-28
| Sub Structure | 6th Floor | L1-T/79 | 2023-10-29 | 2023-10-29 | column formwork | Inspection of column formwork (6 Nos) Zone 4 before concrete |  | Grid 20-26 & K-M | B | 2023-10-31
| Sub Structure | 5th Floor | L1-T/80 | 2023-10-30 | 2023-10-30 | Column formwork | Inspection of columns (16 Nos) formwork Zone 5 before concrete |  | Grid 15-18 & N-U | A | 2023-10-31
| Sub Structure | 5th Floor | L1-T/81 | 2023-10-31 | 2023-10-31 | Column formwork | Inspection of column (4 Nos) formwork Zone 5 before concrete |  | Grid 19 & N-U | A | 2023-11-08
| Sub Structure | 5th Floor | L1-T/82 | 2023-10-31 | 2023-11-01 | Column formwork | Inspection of column (13 Nos) formwork zone 5 before concrete |  | Grid 20-26 & N-U | B | 2023-11-02
| Sub Structure | 6th Floor | L1-T/83 | 2023-10-31 | 2023-10-30 | column formwork | Inspection of column (6 Nos) formwork Zone 4 before concrete |  | Grid 20-26 & L-G | A | 2023-11-08
| Sub Structure | 6th Floor | L1-T/84 | 2023-10-31 | 2023-11-01 | Column formwork | Inspection of columns (6 Nos) formwork Zone 4 before concrete |  | Grid 20-26 & G-J | A | 2023-11-18
| Sub Structure | 6th Floor | L1-T/85 | 2023-10-31 | 2023-11-01 | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid H-J & 23-24 | A | 2023-11-02
| Sub Structure | 5th Floor | L1-T/86 | 2023-11-02 | 2023-11-03 | CW formwork | Inspection of CW formwork Zone 4 & 5 before concrete |  | Grid N-Q and 22 btw 23-24 | B | 2023-11-06
| Sub Structure | 5th Floor | L1-T/87 | 2023-11-04 | 2023-11-05 | Slab formwork | Inspection of slab formwork Zone 4 & 5 layout and level |  | Grid N-U & 15-26 | B | 2023-11-10
| Sub Structure | 6th Floor | L1-T/88 | 2023-11-11 | 2023-11-11 | Column formwork | Inspection of columns (4 Nos) formwork Zone 4 before concrete |  | Grid 26 & T-U, G-H | A | 2023-11-13
| Sub Structure | 6ht Floor | L1-T/89 | 2023-11-12 | 2023-11-12 | Column formwork | Inspection of columns (7 Nos) formwork Zone 4 before concrete |  | Grid N-U, 26-26 | A | 2023-11-13
| Sub Structure | 6th Floor | L1-T/90 | 2023-11-12 | 2023-11-12 | slab formwork | Inspection of slab formwork Zone 4 layout and level |  | Grid G-U btw 20-26 | B | 2023-11-20
| Sub Structure | 6th Floor | L1-T/91 | 2023-11-13 | 2023-11-13 | Column formwork | Inspection of columns (24 Nos) formwork Zone 5 before concrete |  | Grid N-U & 15-23 | A | 2023-11-14
| Sub Structure | 6th Floor | L1-T/92 | 2023-11-15 | 2023-11-15 | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid 22 btw 23 to 20 | A | 2023-11-17
| Sub Structure | 6th Floor | L1-T/93 | 2023-11-16 | 2023-11-16 | Slab formwork | Check slab formwork Zone 4 & 5 layout and level |  | Grid N-U & 15-26 | B | 2023-11-28
| Sub Structure | 7th Floor | L1-T/94 | 2023-11-20 | 2023-11-20 | Column formwork | Inspection fo columns (10 Nos) formwork Zone 4 before concrete |  | Grid 20-26 & G-L | A | 2023-11-21
| Sub Structure | 7th Floor | L1-T/95 | 2023-11-20 | 2023-11-21 | Column formwork | Inspection of columns (6 Nos) formwork Zone 4 before concrete |  | Grid 20-26 & G-L | A | 2023-11-21
| Sub Structure | 7th Floor | L1-T/96 | 2023-11-22 | 2023-11-23 | CW formwork | Inspection of CW formwork service Zone 4 before concrete Zone 4 |  | Grid H-J and 23-24 | B | 2023-11-23
| Sub Structure | 7th Floor | L1-T/97 | 2023-11-23 | 2023-11-23 | Column formwork | Inspection of columns (8 Nos) formwork Zone 4 before concrete |  | Grid 20-26 & G-L | B | 2023-11-29
| Sub Structure | 7th Floor | L1-T/98 | 2023-11-24 | 2023-11-25 | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid 22 btw 23 to 20 & N to Q | B | 2023-11-29
| Sub Structure | 7th Floor | L1-T/99 | 2023-11-28 | 2023-11-28 | Slab formwork | Inspection of slab formwork Zone 4, level, layout (+95'-9'') |  | Grid G-R & 20-26 | B | 2023-12-18
| Sub Structure | 7th Floor | L1-T/100 | 2023-12-01 | 2023-12-01 | Column formwork | Inspection of columns formwork Zone 4 before concrete Zone 4 |  | Grid 19-24 & N-S | A | 2023-12-05
| Sub Structure | 7th Floor | L1-T/101 | 2023-12-02 | 2023-12-02 | Column formwork | Inspection of columns (10 Nos) formwork Zone 4 & 5 before concrete Zone 4 & 5 |  | Grid 18-26 & N-U | A | 2023-12-05
| Sub Structure | 7th Floor | L1-T/102 | 2023-12-04 | 2023-12-04 | Column formwork | Inspection of columns (12 Nos) formwork Zone 5 before concrete |  | Grid 15-17 & N-U | A | 2023-12-05
| Sub Structure | 7th Floor | L1-T/103 | 2023-12-05 | 2023-12-05 | Ducts opening | Inspection of Ducts openings size and location Zone 4 |  | Grid G-R & 20-26 | OP
| Sub Structure | 7th Floor | L1-T/104 | 2023-12-09 | 2023-12-08 | slab formwork | Inspection of slab formwork Zone 4 & 5 layout and level |  | Grid N-U & 15-26 | B | 2023-12-22
| Sub Structure | 8th Floor | L1-T/105 | 2023-12-11 | 2023-12-11 | Column formwork | Inspection of columns (10 Nos) formwork Zone 4 before concrete |  | Grid 20-22 & G-M | A | 2023-12-18
| Sub Structure | 8th Floor | L1-T/106 | 2023-12-12 | 2023-12-12 | Column formwork | Inspection of columns (6 Nos) formwork Zone 4 before concrete |  | Grid 24-26 & G-N | A | 2023-12-18
| Sub Structure | 8th Floor | L1-T/107 | 2023-12-13 | 2023-12-13 | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid H-J and 23-24 | A | 2023-12-18
| Sub Structure | 8th Floor | L1-T/108 | 2023-12-13 | 2023-12-13 | Column formwork | Inspection of columns (9 Nos) formwork Zone 4 before concrete |  | Grid 26 & G-R | A | 2023-12-18
| Sub Structure | 7th Floor | L1-T/109 | 2023-12-16 | 2023-12-16 | CW formwork | Inspection of CW formwork Zone 4 before concrete |  | Grid 22 btw 23 to 20 & N to Q | B | 2023-12-22
| Sub Structure | 8th Floor | L1-T/110 | 2023-12-19 | 2023-12-19 | Slab formwork | Inspection of slab formwork Zone 4, layout and level |  | Grid G-R & 20-26 | B | 2023-12-27
| Sub Structure | 8th Floor | L1-T/111 | 2023-12-19 | 2023-12-19 | Column formwork | Inspection of columns (4 Nos) formwork Zone 4 before concrete |  | Grid 19-24 & S-T | A | 2023-12-22
| Sub Structure | 8th Floor | L1-T/112 | 2023-12-20 | 2023-12-20 | Column formwork | Inspection of columns (12 Nos) formwork Zone 5 before concrete |  | Grid 18-26 & N-U | A | 2023-12-22
| Sub Structure | 8th Floor | L1-T/113 | 2023-12-21 | 2023-12-21 | Column formwork | Inspection of columns (12 Nos) formwork Zone 5 before concrete |  | Grid 15-17 & N-U | A | 2023-12-22
| Sub Structure | 7th Floor | L1-T/114 | 2023-12-28 | 2023-12-28 | slab formwork | Inspection of slab formwork Zone 4 & 5 layout, level | (+106'-9'') | Grid N-U & 15-26 | B | 2024-01-09
| Sub Structure | 9th Floor | L1-T/115 | 2023-12-29 | 2023-12-29 | Column formwork | Inspection of columns (10 Nos) formwork Zone 4 before concrete | (+106'-9'') | Grid 20-22 & G-M | A | 2024-01-03
| Sub Structure | 9th Floor | L1-T/116 | 2023-12-30 | 2023-12-30 | Column formwork | Inspection of columns (8 Nos) Zone 4 before concrete | (+106'-9'') | Grid 24-26 & G-Q | A | 2024-01-03
| Sub Structure | 9th Floor | L1-T/117 | 2024-01-01 | 2024-01-01 | Column formwork | Inspection of columns (7 Nos) formwork Zone 4 before concrete | (+106'-9'') | Grid 22-26 & G-R | A | 2024-01-03
| Sub Structure | 9th Floor | L1-T/118 | 2024-01-01 | 2024-01-01 | CW formwork | Inspection of CW formwork Service Zone 4 before concrete |  | Grid H-J and 23-24 | A | 2024-01-03
| Sub Structure | Courtyard | L1-T/119 | 2024-01-01 | 2024-01-02 | Tank Wall fomrowkr | Inspection of Tank Wall formwork (1 Nos) courtyard non tower area |  | Grid 12-15 & after U | A | 2024-01-03
| Sub Structure | 9th Floor | L1-T/120 | 2024-01-01 | 2024-01-01 | Column formwork | Inspection of columns (2 Nos) formwork Zone 4 before concrete | (+106'-9'') | Grid 26 & G-H | A | 2024-01-03
| Sub Structure | 9th Floor | L1-T/121 | 2024-01-03 | 2024-01-04 | CW formwork | Inspection of CW formwork Zone 4 before concrete | (+106'-9'') | Grid 23 to 20 & N to Q | B | 2024-01-09
| Sub Structure | 9th Floor | L1-T/122 | 2024-01-04 | 2024-01-05 | slab formwork | Inspection of slab formwork Zone 4 layout, level | (+117'-9'') | Grid G-R & 20-26 | B | 2024-01-17
| Sub Structure | 9th Floor | L1-T/123 | 2024-01-05 | 2024-01-05 | Column formwork | Inspection of columns (7 Nos) formwork Zone 4 before concrete | (+106'-9'') | Grid 19-26 & N-T | A | 2024-01-09
| Sub Structure | 9th Floor | L1-T/124 | 2024-01-06 | 2024-01-07 | Column formwork | Inspection of column (15 Nos) formwork Zone 5 before concrete | (+106'-9'') | Grid 16-26 & N-U | A | 2024-01-09
| Sub Structure | 9th Floor | L1-T/125 | 2024-01-09 | 2024-01-09 | Column formwork | Inspection of columns (6 Nos) formwork Zone 5 before concrete | (+106'-9'') | Grid 15-16 & N-U | A | 2024-01-17
| Sub Structure | 10th Floor | L1-T/126 | 2024-01-11 | 2024-01-11 | slab formwork | Inspection of slab formwork Zone 4 & 5 level, layout | (+117'-9'') | Grid N-U & 15-26 | B | 2024-01-24
| Sub Structure | 10th Floor | L1-T/127 | 2024-01-11 | 2024-01-11 | Column formwork | Inspection of columns (12 Nos) formwork before concrete | (+117'-9'') | Grid 20-24 & G-N | B | 2024-01-17
| Sub Structure | 10th Floor | L1-T/128 | 2024-01-13 | 2024-01-13 | SL formwork | Inspection of Service lift formwork Zone 4 before concrete | (+117'-9'') | Grid H-J, 23-24 | A | 2024-01-17
| Sub Structure | 10th Floor | L1-T/129 | 2024-01-13 | 2024-01-13 | Column formwork | Inspection of column formwork Zone 4 before concrete | (+117'-9'') | Grid 20-26 & G-T | A | 2024-01-17
| Sub Structure | 10th Floor | L1-T/130
| Sub Structure | 10th Floor | L1-T/131 | 2024-01-14 | 2024-01-15 | CW formwork | Inspection of CW formwork Zone 4 before concrete | (+117'-9'') | Grid N-Q and 20-23 | B | 2024-01-17
| Sub Structure | 10th Floor | L1-T/132 | 2024-01-14 | 2024-01-14 | Column formwork | Inspection of columns (6 Nos) formwork before concrete Zone 4 | (+117'-9'') | Grid 26 & G-R | A | 2024-01-17
| Sub Structure | 10th Floor | L1-T/133 | 2024-01-17 | 2024-01-17 | Slab formwork | Inspection of slab formwork Zone 4 before concrete | (+130'-9'') | Grid G-R and 19-26 | B | 2024-01-24
| Sub Structure | 10th Floor | L1-T/134 | 2024-01-20 | 2024-01-20 | Column formwork | Inspection of columns (6 Nos) formwork Zone 4 before concrete | (+117'-9'') | Grid 19-24 & S-N | A | 2024-01-24
| Sub Structure | 10th Floor | L1-T/135 | 2024-01-21 | 2024-01-21 | Column formwork | Inspection of column (10 Nos) formwork Zone 5 before concrete | (+117'-9'') | Grid 18-26 & U-S | A | 2024-01-24
| Sub Structure | 10th Floor | L1-T/136 | 2024-01-23 | 2024-01-23 | Column formwork | Inspection of columns formwork (8 Nos) Zone 5 before concrete | (+117'-9'') | Grid 16-17 & U-N | A | 2024-01-24
| Sub Structure | 10th Floor | L1-T/137 | 2024-01-24 | 2024-01-24 | Column formwork | Inspection of columns (4 Nos) formwork Zone 5 before concrete | (+117'-9'') | Grid 15-16 & U-N | A | 2024-01-30
| Sub Structure | 11th Floor | L1-T/138 | 2024-01-26 | 2024-01-26 | Column formwork | Inspection of columns (10 Nos) formwork Zone 4 before concrete |  | Grid 20-26 & G-M | A | 2024-01-30
| Sub Structure | 10th Floor | L1-T/139 | 2024-01-26 | 2024-01-26 | Slab formwork | Inspection of slab formwork Zone 5 before concrete | (+130'-9'') | Grid U-N and 15-26 | B | 2024-02-06
| Sub Structure | 11th Floor | L1-T/140 | 2024-01-27 | 2024-01-27 | Column formwork | Inspection of columns (10 Nos) formwork Zone 4 before concrete | (+130'-9'') | Grid 20-26 & G-M | A | 2024-01-30
| Sub Structure | 11th Floor | L1-T/141 | 2024-01-27 | 2024-01-27 | Column formwork | Inspection of columns (8 Nos) formwork before concrete Zone 4 | (+130'-9'') | Grid 20-26 & G-M | A | 2024-01-30
| Sub Structure | 11th Floor | L1-T/142 | 2024-01-27 | 2024-01-28 | lift formwork | Inspection of lift formwork Zone 4 before concrete | (+117'-9'') | Grid 20-26 & G-M | A | 2024-01-30
| Sub Structure | 11th Floor | L1-T/143 | 2024-01-30 | 2024-01-30 | Column formwork | Inspection of columns (8 Nos) formwork Zone 4 before concrete | (+145'-9'') | Grid 20-26 & G-M | B | 2024-02-01
| Sub Structure | 11th Floor | L1-T/144 | 2024-01-30 | 2024-01-30 | lift formwork | Inspection of service lift formwork before concrete Zone 4 | (+117'-9'') | Grid 20-26 & G-M | A | 2024-02-06
| Sub Structure | 11th Floor | L1-T/145 | 2024-02-01 | 2024-02-01 | Column formwork | Inspection of columns (2 Nos) formwork Zone 4 before concrete | (+145'-9'') | Grid 19-26 & G-S | B | 2024-02-06
| Sub Structure | 11th Floor | L1-T/146 | 2024-02-01 | 2024-02-02 | CW formwork | Inspection of CW formwork Zone 4 before concrete | (+130'-9'') | Grid N-Q and 20-23 | B | 2024-02-06
| Sub Structure | 11th Floor | L1-T/147 | 2024-02-02 | 2024-02-02 | Column formwork | Inspection of columns (6 Nos) formwork before concrete Zone 4 |  | Grid 19-24 & N-S | A | 2024-02-06
| Sub Structure | 11th Floor | L1-T/148 | 2024-02-03 | 2024-02-03 | Slab formwork | Check slab formwork before concrete | (+145'-9'') | Grid G-R and 19-26 | B | 2024-02-15
| Sub Structure | 11th Floor | L1-T/149 | 2024-02-03 | 2024-02-04 | CW formwork | Inspection of CW formwork before concrete Zone 4 |  | Grid N-Q and 20-23 | B | 2024-02-06
| Sub Structure | 11th Floor | L1-T/150 | 2024-02-03 | 2024-02-03 | Column formwork | Inspection of columns (6 Nos) formwork before concrete Zone 5 | (+130'-9'') | Grid 19-26 & T-U | A | 2024-02-06
| Sub Structure | 11th Floor | L1-T/151 | 2024-02-05 | 2024-02-05 | Column formwork | Inspection of columns (13 Nos) Zone 4 and 5 before concrete | (+130'-9'') | Grid 19-26 & G-U | A | 2024-02-06
| Sub Structure | 11th Floor | L1-T/152 | 2024-02-06 | 2024-02-06 | Column formwork | Inspection of columns (8 Nos) formwork before concrete Zone 5 | (+130'-9'') | Grid 17-18 & N-U | A | 2024-02-06
| Sub Structure | 10th Floor | L1-T/153
| Sub Structure | 10th Floor | L1-T/154
| Sub Structure | 10th Floor | L1-T/155
| Sub Structure | Basement | L1-T/156 | 2024-02-12 | 2024-02-12 | TW formwork | Inspection of TW formwork Zone 4 | (0'-0'') | Grid 25 & after U | A | 2024-02-15
| Sub Structure | Basement | L1-T/157 | 2024-02-12 | 2024-02-12 | Slab formwork | Inspection of Tank Slab formwork Zone 5 | (0'-0'') | Grid 16-22 after U | A | 2024-02-17
| Sub Structure | 10th Floor | L1-T/158 | 2024-02-14 | 2024-02-14 | Slab formwork | Inspection of slab formwork Zone 5 before conrete | (+145'-9'') | Grid U-N, 15-16 | B | 2024-02-27
| Sub Structure | Basement | L1-T/159 | 2024-02-19 | 2024-02-19 | Ramp formwork | Inspection of ramp formwork Zone 5 | (-13'-3'' to 0'-0'') | Grid 5 btw 6 & 12 | A | 2024-02-26
| Sub Structure | Basement | L1-T/160 | 2024-02-19 | 2024-02-20 | Fuel Tank | Inspection of Tank wall formwork non tower area | (0'-00'') | Grid 25-26 & P-T | B | 2024-02-27
| Sub Structure | Basement | L1-T/161 | 2024-02-24 | 2024-02-24 | formwork | Inspection of upstand beam ramp before concrete | (-13'-3'' to 0'-0'')) | Grid 5 btw 6 & 12 | A | 2024-03-06
Courtyard
| Sub Structure | Courtyard | Cy/01 | 2023-10-09 |  | column formwork | Inspection of column formwork (12 Nos) Zone 8 non tower area |  | Grid 15-18 & M-K | A | 2023-10-11
| Sub Structure | Courtyard | Cy/02 | 2023-10-11 |  | column formwork | Inspection of column formwork before concrete Zone 8 |  | Grid 15-19 & M-G | B | 2023-10-18
| Sub Structure | Courtyard | Cy/03 | 2023-10-12 |  | column formwork | Inspection of column formwork (7 Nos) Zone 8 non tower area |  | Grid 15-13 & N-S | A | 2023-10-18
| Sub Structure | Courtyard | Cy/04 | 2023-10-15 |  | column formwork | Inspection of column formwork (4 Nos) Zone 8 Non tower area |  | Grid 14 & G-K | A | 2023-10-18
| Sub Structure | Courtyard | Cy/05 | 2023-10-23 | 2023-10-17 | column formwork | Inspection of column formwork (4 Nos) Zone 8 Non tower area |  | Grid 13-15 & G-U | A | 2023-10-24
| Sub Structure | Courtyard | Cy/06 | 2023-10-18 |  | slab, beam formwork | Inspection of slab and beam formwork and layout Zone 8 non tower area |  | Grid 13-20 & G-M | B | 2023-10-18
| Sub Structure | Courtyard | Cy/07 | 2023-10-19 | 2023-10-19 | column formwork | Inspection of column formwork (2 Nos) Zone 8 non tower area |  | Grid 13 & M-L | A | 2023-10-24
| Sub Structure | Courtyard | Cy/08 | 2023-10-22 | 2023-10-23 | column formwork | Inspection of column formwork (13 Nos) Zone 8 non tower area |  | Grid 10-12 & G-M | B | 2023-10-24
| Sub Structure | Courtyard | Cy/09 | 2023-10-24 | 2023-10-24 | column formwork | Inspection of column formwork (10 Nos) Zone 8 non tower area |  | Grid 8-9 & G-M | B | 2023-10-27
| Sub Structure | Courtyard | Cy/10 | 28-Ot-23 | 28-Ot-23 | slab formwork | Inspection of slab and beam formwork and layout Zone 8 non tower area |  | Grid 8,6,9,14 & G-N | B | 2023-11-02
| Sub Structure | Courtyard | Cy/11 | 2023-11-01 | 2023-11-02 | tank wall | Inspection of Tank wall formwork (1 Nos) Zone 8 courtyard non tower area |  | Grid 12-15 after U | B | 2023-11-13
| Sub Structure | Courtyard | Cy/12 | 2023-11-04 | 2023-11-05 | Tank wall | Inspection of tank wall formwork (1 Nos) Zone 8 courtyard non tower area |  | Grid 12-15 & U | A | 2023-11-13
| Sub Structure | Courtyard | Cy/13 | 2023-11-08 | 2023-11-08 | Slab formwork | Inspection of slab and beam formwork and layout Zone 8 non tower area |  | Grid 12-15 & L-U | B | 2023-11-13
| Sub Structure | Courtyard | Cy/14 | 2023-12-19 | 2023-12-19 | slab, beam formwork | Inspection of partial slab and beam formwork & layout Zone 8 courtyard area |  | Grid 7-8/9 & G-N | B | 2023-12-27
| Sub Structure | Courtyard | Cy/15
| Sub Structure | Courtyard | Cy/16 | 2024-01-19 | 2024-01-20 | TW | Inspection of tank wall formwork Zone 8 courtyard (0'-0'') non tower area | (0'-0'') | Grid 15-18 after U | B | 2024-01-24
| Sub Structure | Courtyard | Cy/17 | 2024-01-24 | 2024-01-24 | Tank wall | Inspection of tank wall formwork Zone 8 courtyard (0'-0'') non tower area |  | Grid 17 btw 18-25 & U | B | 2024-01-30
| Sub Structure | Tank wall | Cy/18 | 2024-02-03 | 2024-02-03 | Tank wall | Inspection of TW formwork Zone 5 courtyard | (0'-0'') | Grid 17-25 and after U | B | 2024-02-06
| Sub Structure | Courtyard | Cy/19
| Sub Structure | Courtyard | Cy/20
| Sub Structure | Courtyard | Cy/21
| Sub Structure | Courtyard | Cy/22
| Sub Structure | Courtyard | Cy/23
| Sub Structure | Courtyard | Cy/24
| Sub Structure | Courtyard | Cy/25
| Sub Structure | Courtyard | Cy/26
| Sub Structure | Courtyard
Snag List
| Sub Structure | Basement | 1 | 2023-11-21 | 2023-11-21 | Snag summary | Inspection of snag summary basement |  |  | B | 2023-10-04
| Sub Structure | Basement | 1 | 2023-11-15 | 2023-11-15 | Snag summary | Inspection of snag list I Tower Basement |  |  | OP
| Sub Structure | GF | 2 | 2023-12-26 | 2023-12-26 | Snag list | Inspection of snag list summary GF & 1st Floor |  |  | R | 2024-01-03
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
| Sub Structure | Basement
2023-08-02

## GE I Tower
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 954
[9 empty] | Approved with comments (B) |  | 333
[9 empty] | Rejected ( R) |  | 82
[9 empty] | Open/Pending (OP) |  | 32
[9 empty] | Total |  | 1401
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | 1st Floor | IT/1 | 2023-12-26 | 2023-12-26 | brick work | Check layout and allow to start the brick masonry work |  | Grid A-F/1 | A | 2024-01-17
2 | Sub Structure | 2nd Floor | IT/2 | 2023-12-31 | 2023-12-31 | brick work | Check layout and allow to start the brick masonry work |  | Grid A-F/1, A-F/26, A/1-26, F/1-26 | A | 2024-01-17
3 | Sub Structure | 3rd Floor | IT/3 | 2024-01-08 | 2024-01-09 | brick work | Check the layout and allow to start brick masonry on external sides of building |  | Grid A-F/1, A-F/26, A/1-26, F/1-26 | A | 2024-01-17
4 | Sub Structure | Basement | IT/4
5 | Sub Structure | 1st Floor | IT/5 | 2024-01-08 | 2024-01-09 | masonry work | Check the masonry brick of external sides of building |  | Grid A-F/1, A-F/26, A/1-26, F/1-26 | B | 2024-01-24
6 | Sub Structure | 5th Floor | IT/6 | 2024-01-09 | 2024-01-10 | layout | Check the layout of brick and allow the brick work |  | Grid A-F/1-26 | A | 2024-01-17
7 | Sub Structure | 1st Floor | IT/7 | 2024-01-10 | 2024-01-11 | formwork | Check formwork of vertical band and allow for concrete work |  | Grid F/9-10 | A | 2024-01-24
8 | Sub Structure | 4th Floor | IT/8 | 2024-01-11 | 2024-01-12 | layout | Check layout and allow to start brick work Zone 1 on external sides |  | Grid 1-9/A-F | A | 2024-01-17
9 | Sub Structure | 1st Floor | IT/9 | 2024-01-12 | 2024-01-13 | concrete work | Check the formwork of vertical band & allow to start the concrete work |  | Grid F/11-12 | B | 2024-01-24
10 | Sub Structure | 2nd Floor | IT/10 | 2024-01-12 | 2024-01-13 | brick work | Check the complete brick work of external sies |  | Grid A-F/1-26 | B | 2024-01-24
11 | Sub Structure | 1st Floor | IT/11 | 2024-01-15 | 2024-01-16 | vertical formwork | Check vertical formwork and allow to start the concrete work |  | Grid F/6-8 | R | 2024-01-24
12 | Sub Structure | 3rd Floor | IT/12 | 2024-01-15 | 2024-01-16 | masonry work | Check brick masonry work Zone 1 on external sides of building |  | Grid A-F/1-9 | B | 2024-01-24
13 | Sub Structure | 4th Floor | IT/13 | 2024-01-15 | 2024-01-16 | layout | Check the layout and allow to start brick masonry on external sides of building |  | Grid A-F/1-26 | A | 2024-01-30
14 | Sub Structure | 3rd Floor | IT/14 | 2024-01-16 | 2024-01-17 | masonry work | Check the brick masonry bwork Zone 3 on external sides |  | Grid A-F/18-26 | B | 2024-01-24
15 | Sub Structure | 5th Floor | IT/15 | 2024-01-16 | 2024-01-17 | masonry work | Check the brick masonry bwork Zone 1 on external sides |  | Grid A-F/1-9 | B | 2024-01-24
16 | Sub Structure | 6th Floor | IT/16 | 2024-01-16 | 2024-01-17 | masonry work | Check layout and allow to start the brick masonry work Zone 1 |  | Grid A-F/1-9 | A | 2024-01-24
17 | Sub Structure | 1st Floor | IT/17 | 2024-01-16 | 2024-01-17 | formwork | Check vertical band formwork and allow to start the concrete work |  | Grid F/13-14 | A | 2024-01-24
18 | Sub Structure | 1st Floor | IT/18 | 2024-01-18 | 2024-01-18 | reinforcement | Check reinforcement and allow to start formwork of vertical |  | Grid F/15-16 | A | 2024-01-24
19 | Sub Structure | 1st Floor | IT/19 | 2024-01-19 | 2024-01-19 | formwork | Check vertical band formwork and allow to start the concrete work |  | Grid F/15-16 | A | 2024-01-24
20 | Sub Structure | 2nd Floor | IT/20 | 2024-01-19 | 2024-01-19 | formwork | Check reinforcement and formwork of beam/slab and allow to start the work | (30') | Grid F/9-10, 11-12, 13-14 | A | 2024-01-24
21 | Sub Structure | 1st Floor | IT/21 | 2024-01-20 | 2024-01-21 | formwork | Check formwork vertical band and allow to start the concrete work |  | Grid F/6-8 | B | 2024-01-24
22 | Sub Structure | 1st Floor | IT/22 | 2024-01-22 | 2024-01-23 | formwork | Check vertical band formwork and allow to start the concrete work |  | Grid F/17-18, C-E/1 | A | 2024-01-24
23 | Sub Structure | 7th Floor | IT/23 | 2024-01-22 | 2024-01-23 | layout | Check the layout and allow to start brick masonry of external sides of building |  | Grid A-F/1-26 | A | 2024-01-24
24 | Sub Structure | 8th Floor | IT/24 | 2024-01-24 | 2024-01-25 | layout | Check layout and allow to start the brick masonry of external sides of building |  | Grid A-F/1-26 | A | 2024-01-30
25 | Sub Structure | 2nd Floor | IT/25 | 2024-01-24 | 2024-01-25 | vertical layout | Check vertical layout band | (+30') | Grid F/6-21 | OP
26 | Sub Structure | 1st Floor | IT/26 | 2024-01-24 | 2024-01-25 | formwork | Check formwork of FB3, SEC 3b--3B & allow to start the concrete work | (+19') | Grid F/6-12 | A | 2024-01-30
27 | Sub Structure | 1st Floor | IT/27 | 2024-01-24 | 2024-01-25 | vertical formwork | Check vertical formwork and allow to start the concrete work | (+19') | Grid F/19-21 | A | 2024-01-30
28 | Sub Structure | 2nd Floor | IT/28 | 2024-01-24 | 2024-01-25 | vertical reinforcement | Check vertical reinforcement and allow to start the formwork | (+30') | Grid F/6-21 | R | 2024-01-25
29 | Sub Structure | 2nd Floor | IT/29 | 2024-01-25 | 2024-01-24 | reinforcement | Check formwork and reinforcement of beam & allow to start the concrete work | (+30') | Grid F/6-8, 15-16, 17-18, 19-21 | A | 2024-02-15
30 | Sub Structure | 3rd Floor | IT/30 | 2024-01-25 | 2024-01-26 | brick work | Check brick masonry work Zone 2 |  | Grid A-F/9-18 | B | 2024-01-30
31 | Sub Structure | 4th Floor | IT/31 | 2024-01-25 | 2024-01-26 | brick work | Check the brick masonry work | (+52') | Grid A-F/1-26 | B | 2024-01-30
32 | Sub Structure | 5th Floor | IT/32 | 2024-01-25 | 2024-01-26 | brick work | Kindly brick masonry work Zone 3 |  | Grid A-F/18-26 | B | 2024-01-30
33 | Sub Structure | 2nd Floor | IT/33 | 2024-01-27 | 2024-01-27 | reinforcement | Check vertical reinforcement and allow to start the formwork | (+30') | Grid F/9-14 | A | 2024-01-30
34 | Sub Structure | 2nd Floor | IT/34 | 2024-01-27 | 2024-01-28 | formwork | Check vertical formwork and allow to start the concrete work | (+30') | Grid F/9-14 | A | 2024-01-30
35 | Sub Structure | 2nd Floor | IT/35 | 2024-01-29 | 2024-01-29 | reinforcement | Check vertical band reinforcement and allow to start the formwork | (+30') | Grid F/6-8, 15-16 | A | 2024-02-17
36 | Sub Structure | 2nd Floor | IT/36 | 2024-01-29 | 2024-01-30 | formwork | Check formwork and allow to start the concrete work | (+30') | Grid F/6-8, 15-16, | A | 2024-02-06
37 | Sub Structure | 1st Floor | IT/37 | 2024-01-29 | 2024-01-30 | reinforcement | Check reinforcement and allow to start the formwork | (+19'') | Grid F/6-21 | A | 2024-02-02
38 | Sub Structure | 1st floor | IT/38 | 2024-01-29 | 2024-01-30 | formwork | Check formwork and allow to start concrete work | (+19') | Grid F/13-21 | B | 2024-02-06
39 | Sub Structure | 1st Floor | IT/39 | 2024-01-30 | 2024-01-30 | reinforcement | Check reinforcement and allow to start ehe formwork | (+19.00) | Grid F/8-9 | A | 2024-02-15
40 | Sub Structure | 1st floor | IT/40 | 2024-01-30 | 2024-01-30 | formwork | Check formwork and allow to start the concrete work | (+19') | Grid F/8-9 | B | 2024-02-06
41 | Sub Structure | 1st Floor | IT/41 | 2024-01-30 | 2024-01-31 | vertical reinforcement | Check vertical band reinforcement and allow to start the formwork | (+19') | Grid A-B/1, C-E/26 | A | 2024-02-02
42 | Sub Structure | 1st Floor | IT/42 | 2024-01-30 | 2024-01-31 | vertical reinforcement | Check vertical band formwork and allow to start the concrete work | (+19') | Grid A-B/1, C-E/26 | B | 2024-02-06
43 | Sub Structure | 2nd Floor | IT/43 | 2024-01-30 | 2024-01-31 | vertical reinforcement | Check vertical band reinforcement and allow to start the formwork | (+30') | Grid F/17-21 | A | 2024-02-02
44 | Sub Structure | 2nd Floor | IT/44 | 2024-01-30 | 2024-01-31 | vertical reinforcement | Check vertical band reinforcement and allow to start the formwork | (+30') | Grid F/17-21 | A | 2024-02-06
45 | Sub Structure | 3rd Floor | IT/45 | 2024-01-30 | 2024-01-31 | layout | Check layout and allow to start brick masonry on external sides of building |  | Grid A-F/1-26 | A | 2024-02-06
46 | Sub Structure | 5th Floor | IT/46 | 2024-01-01 | 2024-02-02 | masonry work | Check the brick masonry work Zone 2 |  | Grid A-F/9-18 | B | 2024-02-06
47 | Sub Structure | 6th Floor | IT/47 | 2024-01-01 | 2024-02-02 | masonry work | Check the brick masonry work Zone | (+74') | Grid A-F/1-26 | B | 2024-02-06
48 | Sub Structure | 7th Flor | IT/48 | 2024-01-01 | 2024-02-02 | masonry work | Check the brick masonry work Zone | (+85') | Grid A-F/1-26 | B | 2024-02-06
49 | Sub Structure | 2nd Floor | IT/49 | 2024-01-01 | 2024-02-02 | reinforcement | Check formwork and reinforcement of beams / slab and allow to start the concrete work | (+30') | Grid A-E/1, A-E/26 | A | 2024-02-15
50 | Sub Structure | 2nd Floor | IT/50 | 2024-02-03 | 2024-02-03 | reinforcement | Check reinforcement and formwork of beam/slab and allow to start the concrete | (+40.75'') | Grid F/6-10,C-E/1 | A | 2024-02-19
51 | Sub Structure | 10th Floor | IT/51 | 2024-01-03 | 2024-01-03 | masonry work | Check layout and allow to start the masonry work on external sides |  | Grid A-F/1-26 | A | 2024-02-06
52 | Sub Structure | 3rd Floor | IT/52 | 2024-02-09 | 2024-02-09 | reinforcement | Check reinforcement and formwork and allow to start the concrete work | (+40.75'') | Grid F/6-10, A-E/1 | A | 2024-02-17
53 | Sub Structure | 3rd Floor | IT/53 | 2024-02-10 | 2024-02-10 | concrete work | Check reinforcement and formwork and allow to start the concrete work | (+40.75) | Grid F/6-10 | B | 2024-02-15
54 | Sub Structure | 3rd Floor | IT/54 | 2024-02-10 | 2024-02-12 | slab reinforcement | Check slab and beam reinforcement and allow to start the formwork Zone 2 | (+40.75) | Grid F/11-16 | B | 2024-02-15
55 | Sub Structure | 4th Floor | IT/55 | 2024-01-12 | 2024-01-13 | reinforcement | Check vertical reinforcement and allow to start the formwork | (+51.75') | Grid F/6-10 | A | 2024-02-15
56 | Sub Structure | 4th Floor | IT/56 | 2024-01-12 | 2024-01-13 | formwork | Check vertical formwork and allow to start the concrete work | (+51.75') | Grid F/6-10 | B | 2024-02-17
57 | Sub Structure | 8th Floor | IT/57 | 2024-01-12 | 2024-01-13 | masonry work | Check brick masonry work | (+96') | Grid A-F/1-26 | B | 2024-02-19
58 | Sub Structure | 9th Floor | IT/58 | 2024-01-12 | 2024-01-13 | masonry work | Check brick masonry work of external sides | (+107'-0) | Grid A-F/1-26 | B | 2024-02-19
59 | Sub Structure | 3rd floor | IT/59 | 2024-02-14 | 2024-02-15 | vertical formwork | Check vertical formwork bends & allow to start the concrete work | (+40.75') | Grid F/11-16 | B | 2024-02-19
60 | Sub Structure | 3rd Floor | IT/60 | 2024-02-15 | 2024-02-16 | slab reinforcement | Check formwork and slab reinforcement Zone 3 | (+40.75) | Grid F/17-21 | A | 2024-02-19
61 | Sub Structure | 4th Floor | IT/61 | 2024-02-15 | 2024-02-15 | reinforcement | Check vertical band reinforcement and allow to start the formwork | (+51.75) | Grid F/11-12 | A | 2024-02-17
62 | Sub Structure | 4th Floor | IT/62 | 2024-02-15 | 2024-02-16 | formwork | Check vertical bends formwork and allow to start the concrete work | (+51.75) | Grid F/11-12 | B | 2024-02-19
63 | Sub Structure | 11th Floor | IT/63 | 2024-02-15 | 2024-02-16 | layout | Check layout and allow to start the brick work Zone 1 |  | Grid A-F/1-10 | A | 2024-02-19
64 | Sub Structure | 3rd Floor | IT/64 | 2024-02-16 | 2024-02-17 | beam formwork | Check beam formwork and allow to start the reinforcement Zone 2 | (+40.75) | Grid F/11-16 | B | 2024-02-27
65 | Sub Structure | 3rd Floor | IT/65 | 2024-02-16 | 2024-02-17 | reinforcement | Check vertical bends reinforcement and allow to start the formwork | (+40.75) | Grid F/17-21 | A | 2024-02-27
66 | Sub Structure | 5th Floor | IT/66 | 2024-02-19 | 2024-02-19 | slab/beam formwork | Check slab/beam formwork and allow to start the reinforcement Zone 1 | (+62.75') | Grid F/6-10 | A | 2024-03-06
67 | Sub Structure | 4th Floor | IT/67 | 2024-02-19 | 2024-02-20 | vertical reinforcement | Check vertical band reinforcement and allow to start formwork | (+51.75) | Grid F/13-21 | A | 2024-02-27
68 | Sub Structure | 4th Floor | IT/68 | 2024-02-19 | 2024-02-20 | vertical bends | Check vertical bends formwork and allow to start the concrete work | (+51.75) | Grid F/13-16 | A | 2024-02-27
69 | Sub Structure | 3rd floor | IT/69 | 2024-02-21 | 2024-02-21 | reinforcement | Check beam reinforcement and allow to start the formwork Zone 3 | (+40.75) | Grid F/17-21 | B | 2024-02-27
70 | Sub Structure | 3rd floor | IT/70 | 2024-02-21 | 2024-02-21 | formwork | Check beam formwork and allow to start the concrete work Zone 3 | (+40.75) | Grid F/17-21 | R | 2024-04-02
71 | Sub Structure | 5th Floor | IT/71 | 2024-02-21 | 2024-02-22 | reinforcement | Check vertical reinforcement and allow to start the formwork | (+62.75) | Grid F/6-10 | A | 2024-02-26
72 | Sub Structure | 5th Floor | IT/72 | 2024-02-21 | 2024-02-22 | formwork | Check vertical bends formwork and allow to start the concrete work | (+62.75) | Grid F/6-10 | B | 2024-03-06
73 | Sub Structure | 4th Floor | IT/73 | 2024-02-22 | 2024-02-22 | vertical formwork | Check vertical bends formwork and allow to start the concrete work | (+51.75') | Grid F/17-18, | B | 2024-02-27
74 | Sub Structure | 10ht Floor | IT/74 | 2024-02-22 | 2024-02-23 | mosonry work | Check brick masonry work | (+118.00) | Grid A-F/1-26 | B | 2024-03-06
75 | Sub Structure | 5th Floor | IT/75 | 2024-02-23 | 2024-02-23 | slab formwork | Check slab formwork and allow to start the reinforcement Zone 2 | (+62.75') | Grid F/11-12 | B | 2024-02-27
76 | Sub Structure | 5th Floor | IT/76 | 2024-02-23 | 2024-02-23 | slab reinforcement | Check slab reinforcement and allow to start the concrete work Zone 2 | (+62.75) | Grid F/11-12 | A | 2024-02-27
77 | Sub Structure | 5th Floor | IT/77 | 2024-02-23 | 2024-02-24 | slab reinforcement | Check slab / beams formwork and allow to start the concrete work Zone 2 | (+62.75) | Grid F/12-14 | B | 2024-02-26
78 | Sub Structure | 5th Floor | IT/78 | 2024-02-23 | 2024-02-24 | slab reinforcement | Check slab/beams reinforcement and allow to start the concrete work Zone 2 | (+62.75) | Grid F/12-14 | A | 2024-03-05
79 | Sub Structure | 4th Floor | IT/79 | 2024-02-24 | 2024-02-25 | reinforcement | Check vertical band reinforcement and allow to start the formwork | (+51.75) | Grid F/19-21 | A | 2024-03-06
80 | Sub Structure | 5th Floor | IT/80 | 2024-03-01 | 2024-03-01 | brick work | Check layout and allow to start the brick masonry work Zone 1 | (+63.00) | Grid A-F/1-9 | B | 2024-03-06
81 | Sub Structure | 1st Floor | IT/81 | 2024-02-28 | 2024-02-28 | level layout | Check layout and allow to start the brick work Zone 1 | (+19.00) | Grid A-F/1-9 | A | 2024-03-06
82 | Sub Structure | 5th Floor | IT/82 | 2024-03-26 | 2024-03-26 | reinforcement | Check vertical reinforcement and allow to start the formwork | (+62.75) | Grid F/11-14 | A | 2024-03-06
83 | Sub Structure | 5th Floor | IT/83 | 2024-02-26 | 2024-02-26 | vertical formwork | Check vertical bends formwork and allow to stat the concrete work | (+62.75) | Grid F/11-12 | B | 2024-03-06
84 | Sub Structure | 5th Floor | IT/84 | 2024-02-26 | 2024-02-26 | slab reinforcement | Check formwork and slab/beam reinforcement and allow to start the reinforcement Zone 2 | (+62.75) | Grid F/14-16 | A | 2024-03-08
85 | Sub Structure | 5th Floor | IT/85 | 2024-02-26 | 2024-02-26 | slab reinforcement | Check slab/beam reinforcement and allow to start the concrete work Zone 2 | (+62.75) | Grid F/14-16 | A | 2024-03-06
86 | Sub Structure | 5th Floor | IT/86 | 2024-02-28 | 2024-02-28 | vertical bends formwork | Check vertical bends formwork and allow to start the concrete work | (+62.75) | Grid F/13-14 | B | 2024-03-06
87 | Sub Structure | 4th Floor | IT/87 | 2024-02-29 | 2024-02-29 | vertical formwork | Check vertical bends formwork and allow to start the concrete work | (+51.75) | Grid F/19-21 | A | 2024-03-06
88 | Sub Structure | 1st Floor | IT/88 | 2024-02-29 | 2024-02-29 | layout | Check layout and allow to start the brick work Zone 2 | (+19.00) | Grid A-F/9-17 | B | 2024-03-06
89 | Sub Structure | 1st Floor | IT/89 | 2024-02-29 | 2024-02-29 | layout | Check layout and allow to start brick work Zone 3 | (+19.00) | Grid A-F/18-26 | A | 2024-03-06
90 | Sub Structure | 5th Floor | IT/90 | 2024-02-26 | 2024-03-01 | reinforcement | Check vertical bends reinforcement and allow to start the formwork | (+62.75) | Grid F/15-16 | A | 2024-03-06
91 | Sub Structure | 5th Floor | IT/91 | 2024-03-01 | 2024-03-01 | vertical bends | Check vertical bends formwork and allow to start the concrete work | (+62.75) | Grid F/15-16 | B | 2024-03-06
92 | Sub Structure | 5th Floor | IT/92 | 2024-03-01 | 2024-03-01 | formwork | Check besms formwork and allow to start the concrete work Zone 1 | (+62.75) | Grid F/6-10 | B | 2024-03-06
93 | Sub Structure | 6th Floor | IT/93 | 2024-02-26 | 2024-03-01 | reinforcement | Check bertical bends reinforcement and allow to start the formwork | (+73.75) | Grid F/6-10 | A | 2024-03-06
94 | Sub Structure | 6ht Floor | IT/94 | 2024-03-04 | 2024-03-04 | formwork | Check vertical bends formwork and allow to start the concrete work | (+73.75) | Grid F/6-10 | A | 2024-03-06
95 | Sub Structure | 5th Floor | IT/95 | 2024-03-04 | 2024-03-04 | formwork | Check slab/beams formwork and allow to start the reinforcement Zone 3 | (+62.75) | Grid F/17-21 | A | 2024-03-06
96 | Sub Structure | 5th Floor | IT/96 | 2024-03-04 | 2024-03-04 | reinforcement | Check slab/beams reinforcement and allow to start the concrete work Zone 3 | (+62.75) | Grid F/17-21 | A | 2024-03-06
97 | Sub Structure | 6ht Floor | IT/97 | 2024-03-04 | 2024-03-04 | reinforcement | Check vertical bends reinforcement and allow to start the formwork | (+73.75) | Grid F/9-12 | A | 2024-03-06
98 | Sub Structure | 6th Floor | IT/98 | 2024-03-06 | 2024-03-06 | vertical formwork | Check formwork and vertical bends and allow to start the concrete work | (+73.75) | Grid F/11-14 | B | 2024-03-06
99 | Sub Structure | 5th Floor | IT/99 | 2024-03-05 | 2024-03-05 | reinforcement | Check vertical bends reinforcement and allow to start the formwork | (+62.75) | Grid F/17-21 | A | 2024-03-06
100 | Sub Structure | 5th Floor | IT/100 | 2024-03-06 | 2024-03-06 | vertical formwork | Check vertical bends formwork and start the concrete work | (+62.75') | Grid F/17-21 | B | 2024-03-08
101 | Sub Structure | 2nd Floor | IT/101 | 2024-03-13 | 2024-03-13 | masonry work | Check layout and layout to start the internal brick work Zone 1 | (+30.00) | Grid A-F/1-9 | B | 2024-03-18
102 | Sub Structure | 5th Floor | IT/102 | 2024-03-07 | 2024-03-07 | beam formwork | Check beam formwork and allow to start the concrete work Zone 2 | (+62.75) | Grid F/11-14 | B | 2024-03-15
103 | Sub Structure | 6th Floor | IT/103 | 2024-03-07 | 2024-03-07 | reinforcement | Check vertical reinforcement and allow to start the formwork | (+84.75) | Grid F/6-8 | A | 2024-03-15
104 | Sub Structure | 7th Floor | IT/104 | 2024-03-08 | 2024-03-08 | vertical bends formwork | Check vertical bends formwork and allow to start the concrete work | (+84.75) | Grid F/6-8 | A | 2024-03-15
105 | Sub Structure | 7th Floor | IT/105 | 2024-03-09 | 2024-03-09 | reinforcement | Check vertical bends reinforcement and allow to start the formwork | (+84.75) | Grid F/9-10 | A | 2024-03-15
106 | Sub Structure | 7th Floor | IT/106 | 2024-03-09 | 2024-03-09 | formwork | Check vertical bends formwork and allow to start the concrete work | (+84.75) | Grid F/9-10 | B | 2024-03-15
107 | Sub Structure | 6th Floor | IT/107 | 2024-03-09 | 2024-03-09 | reinforcement | Check vertical bends reinforcement and allow to start the formwork | (+73.75) | Grid F/17-18 | A | 2024-03-15
108 | Sub Structure | 6th Floor | IT/108 | 2024-03-09 | 2024-03-09 | formwork | Check vertical bends formwork and allow to start the concrete work | (+73.75) | Grid F/17-18 | B | 2024-03-13
109 | Sub Structure | 7th Floor | IT/109 | 2024-03-09 | 2024-03-10 | reinforcement | Check vertical bends formwork and allow to start the formwork | (+84.75) | Grid F/11-14 | A | 2024-03-18
110 | Sub Structure | 7th Floor | IT/110 | 2024-03-09 | 2024-03-10 | formwork | Check vertical bends formwork and allow to start the concrete work | (+84.75) | Grid F/11-14 | B | 2024-03-18
111 | Sub Structure | 7th Floor | IT/111 | 2024-03-11 | 2024-03-11 | reinforcement | Check vertical bends formwork & allow to start the formwork |  | Grid F/15-16 | A | 2024-03-14
112 | Sub Structure | 7th Floor | IT/112 | 2024-03-11 | 2024-03-11 | formwork | Check vertical bends formwork and allow to start the concrete work | (+84.75) | Grid F/15-16 | B | 2024-03-13
113 | Sub Structure | 6th Floor | IT/113 | 2024-03-11 | 2024-03-11 | reinforcement | Check vertical bends reifnrocement and allow to start the formwork | (+73.75) | Grid F/19-21 | A | 2024-03-15
114 | Sub Structure | 5th Floor | IT/114 | 2024-03-11 | 2024-03-11 | beam formwork | Check beam formwork and allow to start the concrete work Zone 2 | (+62.75) | Grid F/14-16 | B | 2024-03-13
115 | Sub Structure | 6th Floor | IT/114A | 2024-03-11 | 2024-03-11 | formwork | Check vertical bends formwork and allow to start the concrete work | (+73.75) | Grid F/19-21 | A | 2024-03-13
116 | Sub Structure | 2nd floor | IT/115 | 2024-03-16 | 2024-03-16 | layout | Check layout and allow to start the internal brick masonry work | (+30.0) | Grid C-F/8-13 | B | 2024-03-18
117 | Sub Structure | 7th Floor | IT/116 | 2024-03-12 | 2024-03-12 | reinforcement | Check vertical bends reinforcement and allow to start the formwork | (+84.75) | Grid F/17-18 | A | 2024-03-22
118 | Sub Structure | 7th Floor | IT/117 | 2024-03-12 | 2024-03-12 | formwork | Check vertical bends formwork and allow to start the concrete work | (+84.75) | Grid F/17-18 | B | 2024-03-18
119 | Sub Structure | 1st Floor | IT/118 | 2024-03-16 | 2024-03-16 | reinforcement | Check reinforcement of RCC Lintels (14 Nos) and allow to start the concrete work | (+19.0'') |  | A | 2024-03-22
120 | Sub Structure | 2nd Floor | IT/119 | 2024-03-18 | 2024-03-18 | layout | Check layout and allow to start internal brick masonry | (+30.00') | Grid C-F/12-19 | B | 2024-03-22
121 | Sub Structure | 1st floor | IT/120 | 2024-03-17 | 2024-03-17 | Lintel reinforcement | Check RCC Lintels reinforcement and allow to start the concrete work | (+19.00'') | Grid A/110 | A | 2024-03-22
122 | Sub Structure | 1st floor | IT/121 | 2024-03-20 | 2024-03-20 | Lintel reinforcement | Check RCC Lintels Zone 3 | (+19.00'') | Grid A/110 | A | 2024-05-04
123 | Sub Structure | 1st Floor | IT/122 | 2024-03-25 | 2024-03-25 | Lintel reinforcement | Check RCC lintels reinforcement and allow to start the concrete work | (+19.00'') | Grid A/110 | A | 2024-04-02
124 | Sub Structure | 2nd Floor | IT/123 | 2024-03-27 | 2024-03-28 | reinforcement | Check RCC Lintels reinforcement and allow to start the concret work Zone 1 | (+30.00) | Grid A/111 | A | 2024-04-02
125 | Sub Structure | 11th Floor | IT/124 | 2024-03-28 | 2024-03-28 | brick work | Check completed external brick masonry work | (+131.00) | Grid A-F/1-26 | OP
126 | Sub Structure | 1st Floor | IT/125 | 2024-03-28 | 2024-03-29 | masonry work | Check internal brick masonry work | (+19.00) | Grid A-F/1-9 | B | 2024-04-05
127 | Sub Structure | 1st Floor | IT/126 | 2024-03-28 | 2024-03-29 | masonry work | Check internal brick masonry work | (+19.00) | Grid A-C/10-17, C-F/16-19 | B | 2024-04-22
128 | Sub Structure | 1st Floor | IT/127 | 2024-03-28 | 2024-03-29 | masonry work | Check internal brick masonry work | (+19.00) | Grid A-F/19-26 | B | 2024-04-05
129 | Sub Structure | 2nd Floor | IT/128 | 2024-03-28 | 2024-03-29 | masonry work | Check internal brick masonry work | (+30.00) | Grid D-F/8-17 | A | 2024-06-14
130 | Sub Structure | 2nd Floor | IT/129 | 2024-03-28 | 2024-03-28 | masonry work | Check layout and allow to start brick masonry work Zone 2 | (+30.00) | Grid A-C/10-13 | B | 2024-04-02
131 | Sub Structure | 2nd Floor | IT/130 | 2024-03-30 | 2024-04-01 | layout | Check layout and allow to start internal brick masonry Zone 3 | (+30.00) | Grid A-F/18-26 | B | 2024-04-22
132 | Sub Structure | 2nd floor | IT/131 | 2024-04-03 | 2024-04-04 | brick work | Check internal brick masonry work Zone 2 | (+30.00) | Grid C-F/8-19, A-C/11-13 | A | 2024-06-14
133 | Sub Structure | 3rd floor | IT/132 | 2024-04-03 | 2024-04-04 | brick work | Check layout for internal brick masonry Zone 3 | (+41.00) | Grid A-F/18-26 | B | 2024-04-22
| Sub Structure | 2nd Floor | IT/133 | 2024-04-04 | 2024-04-05 | Lintel reinforcement | Check RCC Lintel reinforcement Zone 2 | (+30.00) | Grid A/111 | A | 2024-05-04
| Sub Structure | 3rd Floor | IT/134 | 2024-04-17 | 2024-04-18 | brick work | Check layouts for internal brick masonry Zone 1 | (+41.00) | Grid A-F/1-9 | B | 2024-05-04
| Sub Structure | 3rd Floor | IT/135 | 2024-04-17 | 2024-04-18 | brick work | Check layouts for internal brick masonry Zone 2 | (+41.00) | Grid C-F/8-15 | B | 2024-05-04
| Sub Structure | 4th floor | IT/136 | 2024-04-22 | 2024-04-23 | brick work | Check layout of internal brick masonry work Zone 1 | (+52.00) | Grid A-F/1-9 | B | 2024-05-16
| Sub Structure | 3rd Floor | IT/137 | 2024-04-22 | 2024-04-22 | brick work | check layout of internal brick masonry work Zone 2 | (+52.00) | Grid A-C/12-17 | B | 2024-05-04
| Sub Structure | 2nd floor | IT/138 | 2024-04-22 | 2024-04-22 | brick work | check layout of internal brick masonry work Zone 2 | (+52.00) | Grid A-C/10-17, C-F/14-18 | B | 2024-05-04
| Sub Structure | 4th Floor | IT/139 | 2024-04-27 | 2024-04-27 | brick work | check layout of internal brick work Zone 2 | (+52.00) | Grid A-C/10-17 | B | 2024-05-04
| Sub Structure | 3rd Floor | IT/140 | 2024-04-29 | 2024-04-30 | Lintel reinforcement | Check RCC lintel reinforcement Zone 2 | (+41.00) | Grid A/112 | A | 2024-05-04
| Sub Structure | 2nd floor | IT/141 | 2024-05-02 | 2024-05-03 | brick work | Check internal brick masonry Zone 1/3 | (+30.0) | Grid A-F/1-8, 19-26 | A | 2024-06-14
| Sub Structure | 2nd floor | IT/142 | 2024-05-02 | 2024-05-03 | brick work | Check internal brick masonry work Zone 2 | (+30.0) | Grid A-C/10-17, C-F/16-19 | A | 2024-06-14
| Sub Structure | 6th Floor | IT/143 | 2024-05-03 | 2024-05-03 | vertical formwork | Check vertical band formwork and allow to start the concrete work Zone 3 |  | Grid F/19-21 | B | 2024-05-16
| Sub Structure | 7th Floor | IT/144 | 2024-05-03 | 2024-05-03 | vertical formwork | Check vertical band formwork and allow to start the concrete work Zone 3 |  | Grid F/17-18 | A | 2024-05-16
| Sub Structure | 4th Floor | IT/145 | 2024-05-03 | 2024-05-04 | layout | Check layout of internal brick masonry Zone 3 | (+52.0) | Grid A-F/18-26 | B | 2024-05-15
| Sub Structure | 3rd floor | IT/146 | 2024-05-08 | 2024-05-09 | slab formwork | Check slab formwork and slab/beams and allow to start concrete work Zone 1 | (+40.75) | Grid C-E/1 | A | 2024-05-16
| Sub Structure | 5th Floor | IT/147 | 2024-05-08 | 2024-05-08 | brick work | Check layout for internal brick masonry and allow to start brick work | (+63.0) | Grid C-F/14-19 | B | 2024-05-16
| Sub Structure | 4th Floor | IT/148 | 2024-05-08 | 2024-05-08 | brick work | Check layout for internal brick work and allow to start brick work | (+52.0) | Grid C-F/9-13 | B | 2024-05-16
| Sub Structure | 2nd floor | IT/149 | 2024-05-09 | 2024-05-09 | formwork | Check vertical band formwork and allow to start concrete work | (+30.0) | Grid C-E/26 | B | 2024-05-15
| Sub Structure | 5th Floor | IT/150 | 2024-05-10 | 2024-05-10 | brick work | Check layout for internal brick work and alow to start brick work | (+63.0) | Grid C-F/9-15 | B | 2024-05-21
| Sub Structure | 3rd Floor | IT/151 | 2024-05-11 | 2024-05-11 | brick work | check internal brick masonry work | (+41.0) | Grid C-F/13-19 | B | 2024-06-14
| Sub Structure | 3rd Floor | IT/152 | 2024-05-11 | 2024-05-11 | brick work | Check internal brick masonry work | (+41.0) | Grid A-C/10-17 | B | 2024-06-14
| Sub Structure | 3rd Floor | IT/153 | 2024-05-11 | 2024-05-11 | brick work | Check internal brick masonry work | (+41.0) | Grid A-F/18-26 | B | 2024-06-14
| Sub Structure | 7th Floor | IT/154 | 2024-05-11 | 2024-05-11 | vertical reinforcement | Check vertical reinforcement and allow to start the formwork | (+84.75) | Grid F/19-21 | A | 2024-05-16
| Sub Structure | 7th Floor | IT/155 | 2024-05-11 | 2024-05-11 | vertical bends | Check vertical bends formwork and allow to start the concrete work | (+84.75) | Grid F/19-21 | B | 2024-05-15
| Sub Structure | 5th Floor | IT/156 | 2024-05-11 | 2024-05-11 | internal brick work | Check layout for internal brick masonry and allow to start brick work | (+63.0) | Grid A-C/10-14 | B | 2024-05-15
| Sub Structure | 5th floor | IT/157 | 2024-05-13 | 2024-05-13 | brick work | Check layout for internal brick work and allow to start brick work | (+63.0) | Grid A-F/18-23 | B | 2024-05-15
| Sub Structure | 4th Floor | IT/158 | 2024-05-13 | 2024-05-13 | brick work | Check layout for internal brick work and allow to start brick work | (+52.0) | Grid C-F/12-19 | B | 2024-05-21
| Sub Structure | 2nd Floor | IT/159 | 2024-05-13 | 2024-05-14 | RCC Lintels | Check RCC Lintels reinforcement Zone 3 | (+30.0) | Grid A/111 | A | 2024-05-21
| Sub Structure | 3rd Floor | IT/160 | 2024-05-13 | 2024-05-14 | RCC Lintels | Check RCC Lintels reinforcement Zone 3 | (+41.0) | Grid A/112 | A | 2024-05-21
| Sub Structure | 3rd Floor | IT/161 | 2024-05-13 | 2024-05-14 | RCC Lintels | Check RCC Lintels reinforcement Zone 3 | (+41.0) | Grid A/112 | A | 2024-05-15
| Sub Structure | 3rd Floor | IT/162 | 2024-05-14 | 2024-05-14 | vertical reinforcement | Check vertical bends reinforcement | (+40.75) | Grid C-E/1 | A | 2024-05-15
| Sub Structure | 3rd Floor | IT/163 | 2024-05-14 | 2024-05-14 | vertical formwork | Check vertical bends formwork and allow to start concrete work | (+40.75) | Grid C-E/1 | B | 2024-05-15
| Sub Structure | 6th Floor | IT/164 | 2024-05-16 | 2024-05-17 | brick work | Check layout for internal brick work and allow to start brick work Zone 1 | (+74.00) | Grid A-F/1-9 | B | 2024-05-22
| Sub Structure | 3rd Floor | IT/165 | 2024-05-16 | 2024-05-17 | slab formwork | Check slab/beam formwork and allow to start reinforcement in Zone 3 | (+40.75) | Grid C-E/26 | A | 2024-05-22
| Sub Structure | 3rd Floor | IT/166 | 2024-05-16 | 2024-05-17 | slab formwork | Check slab/beam formwork & allow to start concrete work Zone 3 | (+40.75) | Grid C-E/26 | A | 2024-05-22
| Sub Structure | 8th Floor | IT/167 | 2024-05-15 | 2024-05-15 | slab formwork | Check slab/beam formwork and allow to start reinforcement Zone 3 | (+95.75) | Grid F/17-18 | A | 2024-05-22
| Sub Structure | 8th Floor | IT/168 | 2024-05-15 | 2024-05-15 | slab formwork | Check slab/beam reinforcement and allow to start concrete work Zone 3 | (+95.75) | Grid F/17-18 | A | 2024-05-22
| Sub Structure | 4th Floor | IT/169 | 2024-05-18 | 2024-05-18 | band reinforcement | Check vertical bands reinforcement and allow to start formwork | (+51.75) | Grid C-E/1 | A | 2024-05-22
| Sub Structure | 4th Floor | IT/170 | 2024-05-18 | 2024-05-18 | vend formwork | Check vertical bends formwork and allow to start concrete work | (+51.75) | Grid C-E/1 | B | 2024-05-22
| Sub Structure | 8th Floor | IT/171 | 2024-05-18 | 2024-05-18 | vertical band | Check vertical bends reinforcement and allow to start formwork | (+95.75) | Grid F/17-18 | A | 2024-05-22
| Sub Structure | Basement | IT/172
| Sub Structure | 3rd Floor | IT/173 | 2024-05-20 | 2024-05-20 | RCC Lintels | Check RCC Lintels reinforcement and allow to start concrete work | (+52.0) | Grid A/113 | A | 2024-05-22
| Sub Structure | 6th Floor | IT/174 | 2024-05-20 | 2024-05-20 | brick work | Check layout for internal brick work and allow to start brick work Zone 2 | (+74.0) | Grid A-C/10-17 | B | 2024-05-29
| Sub Structure | 5th Floor | IT/175 | 2024-05-23 | 2024-05-23 | RCC Lintels | Check RCC Lintels reinforcement and allow to start concrete work | (+63.0) | Grid A/114 | A | 2024-05-29
| Sub Structure | 8th Floor | IT/176 | 2024-05-22 | 2024-05-22 | slab/beam formwork | Check slab/beam formwork and allow to start reinforcement Zone 3 | (+95.75) | Grid F/18-21 | A | 2024-05-29
| Sub Structure | 8th Floor | IT/177 | 2024-05-22 | 2024-05-22 | slab/beam formwork | Check slab/beam formwork and allow to start reinforcement Zone 3 | (+95.75) | Grid F/18-21 | A | 2024-05-29
| Sub Structure | 4th Floor | IT/178 | 2024-05-24 | 2024-05-24 | vertical reinforcement | Check vertical bands reinforcement and allow to start formwork | (+51.75) | Grid C-E/26 | A | 2024-05-29
| Sub Structure | 4th Floor | IT/179 | 2024-05-24 | 2024-05-24 | vertical formwork | Check vertical bands formwork and allow to start concrete work | (+51.75) | Grid C-E/26 | B | 2024-05-29
| Sub Structure | 8th Floor | IT/180 | 2024-05-24 | 2024-05-24 | vertical reinforcement | Check vertical bands reinforcement and allow to start formwork | (+95.75) | Grid F/19-21 | A | 2024-05-29
| Sub Structure | 8th Floor | IT/181 | 2024-05-24 | 2024-05-24 | vertical formwork | Check vertical bands formwork and allow to start concrete work | (+95.75) | Grid F/19-21 | A | 2024-05-29
| Sub Structure | 1st floor | IT/182 | 2024-05-24 | 2024-05-25 | brick work | Check layout and allow to start brick work, electrical, services & garbage rooms | (+19.0) | Grid B-C/8-9, A-C/10-11, A-C/16-17, B-C/18-19 | B | 2024-06-03
| Sub Structure | 2nd floor | IT/183 | 2024-05-24 | 2024-05-25 | brick work | Check layout & allow to start brick work, electrical, services & garbage rooms | (+30.0) | Grid B-C/8-9, A-C/10-11, A-C/16-17, B-C/18-19 | B | 2024-06-03
| Sub Structure | 4th Floor | IT/184 | 2024-05-24 | 2024-05-25 | brick work | Check internal brick masonry work | (+52.0) | Grid A-F/1-9, A-C/10-17 | A | 2024-06-14
| Sub Structure | 4th Floor | IT/185 | 2024-05-24 | 2024-05-25 | brick work | Check internal brick masonry work | (+52.0) | Grid A-F/18-26 | B | 2024-06-14
| Sub Structure | 5th Floor | IT/186 | 2024-05-25 | 2024-05-25 | slab/beam formwork | Check slab/beam formwork and allow to start reinforcement Zone 1 | (+62.75) | Grid C-E/1 | A | 2024-05-29
| Sub Structure | 5th Floor | IT/187 | 2024-05-25 | 2024-05-25 | Slab/beam reinforcement | Check slab/beam reinforcement and allow to start concrete work Zone 1 | (+62.75) | Grid C-E/1 | A | 2024-05-29
| Sub Structure | Basement | IT/188 | 2024-05-25 | 2024-05-25 | brick work | Check layout and allow to start brick work on external sides at Ground floor | (+02.0) | Grid B-F/3, B/3-9 | B | 2024-05-29
| Sub Structure | 6th Floor | IT/189 | 2024-05-27 | 2024-05-27 | brick work | Check layout for internal brick work and allow to start brick work Zone 2 | (+74.0) | Grid C-F/8-19, | B | 2024-06-05
| Sub Structure | 6th Floor | IT/190 | 2024-05-27 | 2024-05-28 | brick work | Check layout for internal brick work and allow to start brick work Zone 3 | (+74.0) | Grid A-F/18-26 | B | 2024-06-05
| Sub Structure | Basement | IT/191
| Sub Structure | 8th Floor | IT/192 | 2024-05-25 | 2024-05-25 | vertical reinforcement | Check vertical reinforcement and allow to start formwork | (+95.75) | Grid F/19-21 | A | 2024-05-29
| Sub Structure | 8th Floor | IT/193 | 2024-05-25 | 2024-05-25 | vertical formwork | Check vertical bends formwork and allow to start concrete work | (+95.75) | Grid F/19-21 | B | 2024-06-01
| Sub Structure | 9th Floor | IT/194 | 2024-05-25 | 2024-05-25 | vertical reinforcement | Check vertical reinforcement and allow to start formwork | (+106.75) | Grid F/17-18 | A | 2024-05-29
| Sub Structure | 9th Floor | IT/195 | 2024-05-25 | 2024-05-25 | vertical formwork | Check vertical bends formwork and allow to start concrete work | (+106.75) | Grid F/17-18 | B | 2024-06-01
| Sub Structure | 5th floor | IT/196 | 2024-05-27 | 2024-05-27 | vertical reinforcement | Check vertical bands reinforcement and allow to start formwork | (+62.75) | Grid 1/C-E | A | 2024-06-14
| Sub Structure | 5th Floor | IT/197 | 2024-05-27 | 2024-05-27 | vertical formwork | Check vertical bends formwork and allow to start concrete work | (+62.75) | Grid C-E/1 | B | 2024-06-05
| Sub Structure | 9th Floor | IT/198 | 2024-05-27 | 2024-05-28 | vertical reinforcement | Check vertical bands reinforcement and allow to start formwork | (+106.75) | Grid F/19-21 | A | 2024-06-03
| Sub Structure | 9th Floor | IT/199 | 2024-05-27 | 2024-05-28 | vertical formwork | Check vertical bands formwork and allow to start concrete work | (+106.75) | Grid F/19-21 | B | 2024-06-03
| Sub Structure | 5th Floor | IT/200 | 2024-05-29 | 2024-05-29 | slab/beam formwork | Check slab/beam formwork and allow to start reinforcement Zone 3 | (+62.75) | Grid C-E/26 | B | 2024-06-03
| Sub Structure | 5th Floor | IT/201 | 2024-05-29 | 2024-05-29 | slab reinforcement | Check slab/beam reinforcement and allow to start concrete work Zone 3 | (+62.75) | Grid C-E/26 | A | 2024-06-05
| Sub Structure | 8th floor | IT/202 | 2024-06-12 | 2024-06-12 | slab/beam formwork | Check slab/beam formwork and allow to start reinforcement Zone 1 | (+84.75) | Grid F/6-10 | B | 2024-06-14
| Sub Structure | 8th Floor | IT/203 | 2024-05-29 | 2024-05-29 | slab reinforcement | Check slab/beam reinforcement and allow to start concrete work Zone 1 | (+84.75) | Grid F/6-10 | A | 2024-06-05
| Sub Structure | 3rd Floor | IT/204 | 2024-05-29 | 2024-05-30 | layout | Check layout and allow to start brick work of electrical, serv ices & garbage rooms | (+41.0)_ | Grid B-C/8-9, A-C/10-11, A-C/16-17, B-C/18-19 | B | 2024-06-01
| Sub Structure | 4th Floor | IT/205 | 2024-05-29 | 2024-05-30 | layout | Check layout and allow to start brick work of electrical, serv ices & garbage rooms | (+52.0) | Grid B-C/8-9, A-C/10-11, A-C/16-17, B-C/18-19 | B | 2024-06-01
| Sub Structure | 5th Floor | IT/206 | 2024-05-30 | 2024-05-29 | brick work | Check layout and allow to start brick work of electrical, services & garpabe rooms | (+63.0) | Grid B-C/8-9, A-C/10-11, A-C/16-17, B-C/18-19 | B | 2024-06-07
| Sub Structure | 10th Floor | IT/207 | 2024-05-29 | 2024-05-29 | reinforcement | Check vertical bends reinforcement and allow to start formwork | (+117.75) | Grid F/17-18 | A | 2024-06-01
| Sub Structure | 10th Floor | IT/208 | 2024-05-30 | 2024-05-30 | vertical formwork | Check vertical bends formwork and allow for start concrete work | (+117.75) | Grid F/.17-18 | B | 2024-06-01
| Sub Structure | Basement | IT/209 | 2024-05-30 | 2024-05-30 | brick work | Check layout & allow to start brick work | (+02.0) | Grid B-F/18-24 | B | 2024-06-07
| Sub Structure | 6th floor | IT/210 | 2024-05-31 | 2024-05-31 | vertical reinforcement | Check vertical bands reinforcement and allow to start formwork | (+73.75) | Grid C-E/1 | A | 2024-06-01
| Sub Structure | 6th floor | IT/211 | 2024-05-31 | 2024-05-31 | vertical reinforcement | Check vertical bands formwork and allow to start concrete work | (+73.75) | Grid C-E/1 | B | 2024-06-01
| Sub Structure | 5th Floor | IT/212 | 2024-05-31 | 2024-05-31 | vertical reinforcement | Check vertical bands reinforcement and allow to start formwork | (+62.75) | Grid C-E/26 | A | 2024-06-01
| Sub Structure | 5th Floor | IT/213 | 2024-05-31 | 2024-05-31 | vertical formwork | Check vertical bands formwork and allow to start concrete work | (+62.75) | Grid C-E/26 | B | 2024-06-07
| Sub Structure | 7th Floor | IT/214 | 2024-06-01 | 2024-06-01 | internal brick work | Check layout for internal brick work and allow to start brick work Zone 1 | (+85.0) | Grid A-F/4-9 | B | 2024-06-07
| Sub Structure | 8th Floor | IT/215 | 2024-06-01 | 2024-06-01 | slab/beam formwork | Check slab/beam formwork and allow to start reinforcement Zone 2 | (+84.75) | Grid F/15-16 | B | 2024-06-07
| Sub Structure | 8th Floor | IT/216 | 2024-06-01 | 2024-06-01 | Slab/beam reinforcement | Check slab/beam reinforcement and allow to start concrete work Zone 2 | (+84.75) | Grid F/15-16 | A | 2024-06-07
| Sub Structure | 5th floor | IT/217 | 2024-06-03 | 2024-06-03 | brick work | Check internal brick work | (+63.0) | Grid A-F/1-17 | A | 2024-06-27
| Sub Structure | Ground floor | IT/218 | 2024-06-03 | 2024-06-03 | brick work | Check layout and allow to start brick work on external sides of building | (+2.0) | Grid B-F/8-9 | B | 2024-06-07
| Sub Structure | 7th Floor | IT/219 | 2024-06-03 | 2024-06-03 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+84.75) | Grid C-E/1 | A | 2024-06-07
| Sub Structure | 7th Floor | IT/220 | 2024-06-03 | 2024-06-03 | formwork | Check vertical bands formwork and allow to start concrete work | (+84.75) | Grid C-E/1 | A | 2024-06-07
| Sub Structure | 7th Floor | IT/221 | 2024-06-04 | 2024-06-04 | brick work | Check layout for internal brick work and allow to start brick work Zone 2 | (+85.0) | Grid A-C/10-17 | B | 2024-06-07
| Sub Structure | 8th Floor | IT/222 | 2024-06-03 | 2024-06-03 | slab/beam formwork | Check slab/beam formwork and allow to start reinforcement Zone 2 | (+84.75) | Grid F/13-14 | B | 2024-06-07
| Sub Structure | 8th Floor | IT/223 | 2024-06-03 | 2024-06-03 | Slab/beam reinforcement | Check slab/beam reinforcement and allow to start concrete work Zone 2 | (+84.75) | Grid F/13-14 | A | 2024-06-07
| Sub Structure | 8th Floor | IT/224 | 2024-06-05 | 2024-06-05 | vertical reinforcement | Check vertical bands reinforcement & allow to start formwork | (+95.75) | Grid F/11-16 | A | 2024-06-07
| Sub Structure | 8th Floor | IT/225 | 2024-06-05 | 2024-06-05 | vertical formwork | Check vertical bends formwork and allow to start concrete work | (+95.75) | Grid F/13-14 | B | 2024-06-07
| Sub Structure | 6th floor | IT/226 | 2024-06-05 | 2024-06-05 | RCC Lintels | Check RCC lintels reinforcement & allow for start concrete work | (+74.0) |  | A | 2024-06-12
| Sub Structure | 8th floor | IT/227 | 2024-06-12 | 2024-06-13 | formwork | Check vertical bends formwork and allow to start concrete work | (+95.75) | Grid F/11-12 | A | 2024-06-14
| Sub Structure | 6th Floor | IT/228 | 2024-06-06 | 2024-06-06 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+73.75) | Grid C-E/26 | A | 2024-06-12
| Sub Structure | 6th Floor | IT/229 | 2024-06-06 | 2024-06-06 | vertical bands formwork | Check vertical bands formwork and allow to start concrete work | (+73.75) | Grid C-E/26 | B | 2024-06-07
| Sub Structure | 8th Floor | IT/230 | 2024-06-06 | 2024-06-07 | formwork | Check vertical bends formwork and allow to start concrete work | (+95.75) | Grid F/15-16 | B | 2024-06-12
| Sub Structure | 7th Floor | IT/231 | 2024-06-07 | 2024-06-07 | brick work | Check layout for internal brick work and allow to start brick work Zone 1 | (+85.0) | Grid A-F/1-5 | B | 2024-06-12
| Sub Structure | 10th Floor | IT/232 | 2024-06-07 | 2024-06-07 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+11.75) | Grid F/19-21 | A | 2024-06-12
| Sub Structure | Basement | IT/233 | 2024-06-07 | 2024-06-07 | formwork | Check vertical bands formwork and allow to start concrete work | (+117.75) | Grid F/19-21 | B | 2024-06-12
| Sub Structure | 11th floor | IT/234 | 2024-06-07 | 2024-06-07 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+131.75) | Grid F/17-18 | A | 2024-06-12
| Sub Structure | 11th floor | IT/235 | 2024-06-07 | 2024-06-08 | formwork | Check vertical formwork and allow to start concrete work | (+131.75) | Grid F/17-18 | B | 2024-06-12
| Sub Structure | 8th floor | IT/236 | 2024-06-08 | 2024-06-08 | slab formwork | Check slab/beam formwork and allow to start reinforcement Zone 2 | (+84.75) | Grid F/11-12 | B | 2024-06-12
| Sub Structure | 8th floor | IT/237 | 2024-06-08 | 2024-06-08 | slab formwork | Check slab/beam formwork and allow to start reinforcement Zone 2 | (+84.75) | Grid F/11-12 | A | 2024-06-12
| Sub Structure | 7th floor | IT/238 | 2024-06-08 | 2024-06-08 | vertical bands reinforcement | Check vertical bands reinforcement and allow to start formwork | (+84.75) | Grid C-E/26 | A | 2024-06-14
| Sub Structure | 7th floor | IT/239 | 2024-06-08 | 2024-06-09 | formwork | Check vertical bands formwork and allow to start concrete work | (+84.75) | Grid C-E/26 | B | 2024-06-12
| Sub Structure | 7th floor | IT/240 | 2024-06-11 | 2024-06-11 | brick work | Check internal brick work and allow to start brick work Zone 2 | (+85.0) | Grid C-F/8-13 | B | 2024-06-12
| Sub Structure | basement | IT/241 | 2024-06-13 | 2024-06-13 | RTW reinforcement | Check RTW reinforcement and water stopper and allow for concrete pouring Zone 7 |  | Grid Q-T/1 | B | 2024-06-14
| Sub Structure | 11th floor | IT/242 | 2024-06-10 | 2024-06-10 | formwork | Check vertical bands formwork and allow to start concrete work | (+131.75) | Grid F/19-21 | B | 2024-06-12
| Sub Structure | 5th floor | IT/243 | 2024-06-11 | 2024-06-11 | brick work | Check brick masonry work | (+63.0) | Grid A-F/17-26 | B | 2024-06-14
| Sub Structure | 6th floor | IT/244 | 2024-06-11 | 2024-06-11 | brick work | Check internal brick work | (+74.0) | Grid A-F/1-17 | B | 2024-06-14
| Sub Structure | 7th floor | IT/245 | 2024-06-11 | 2024-06-12 | Lintel reinforcement | Check RCC lintel reiforcement | (+85.0) |  | A | 2024-06-14
| Sub Structure | GF | IT/246 | 2024-06-12 | 2024-06-13 | brick work | Check brick work | (2.0') | Grid B-F/3-9 | B | 2024-06-14
| Sub Structure | GF | IT/247 | 2024-06-12 | 2024-06-13 | brick work | Check brick work | (2.0') | Grid B-F/19-26 | B | 2024-06-14
| Sub Structure | 8th Floor | IT/248 | 2024-06-13 | 2024-06-13 | reinforcement | Check vertical bands reinforcement & allow to start formwork | (+95.75) | Grid F/6-10 | B | 2024-06-14
| Sub Structure | 8th Floor | IT/249 | 2024-06-13 | 2024-06-13 | formwork | check vertical bands formwork and allow to start concrete work | (+95.75) | Grid F/9-10 | B | 2024-07-01
| Sub Structure | 8th Floor | IT/250 | 2024-07-01 | 2024-07-01 | formwork | check vertical bands formwork and allow to start concrete work | (+95.75) | Grid F/9-8 | A | 2024-07-01
| Sub Structure | 9th Floor | IT/251 | 2024-07-01 | 2024-07-01 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+106.75) | Grid F/13-14 | A | 2024-07-02
| Sub Structure | 9th Floor | IT/252 | 2024-07-01 | 2024-07-01 | formwork | Check vertical bands formwork and allow to start concrete work | (+106.75) | Grid F/13-14 | B | 2024-07-02
| Sub Structure | 7th floor | IT/253 | 2024-06-25 | 2024-06-26 | brick work | Check layout for internal brick work and allow to start brick work Zone 2 | (+85.0) | Grid C-F/12-19 | A | 2024-07-01
| Sub Structure | 8th floor | IT/254 | 2024-06-27 | 2024-06-27 | layout | Check internal brick layout and allow to start brick work Zone 3 | (+96.0) | Grid A-F/17-26 | B | 2024-07-01
| Sub Structure | GF | IT/255 | 2024-07-03 | 2024-07-03 | layout | Check layout and allow to start brick on external sides | (+02.0) | Grid A-F/10-17 | B | 2024-07-04
| Sub Structure | GF | IT/256 | 2024-06-28 | 2024-06-28 | layout | Check layout & allow to start brick masonry on external sides of building | (+02.00) | Grid A-F/10-17 | B | 2024-07-04
| Sub Structure | 8th floor | IT/257 | 2024-06-29 | 2024-06-29 | layout | Check layout for internal brick work and allow to start brick work Zone 2 | (+96.0) | Grid C-F/12-19 | B | 2024-07-02
| Sub Structure | 9th floor | IT/258 | 2024-07-01 | 2024-07-01 | brick work | Check internal brick work and allow to start brick work Zone 1 | (+107.00) | Grid A-F/9-11 | B | 2024-07-02
| Sub Structure | 9th floor | IT/259 | 2024-07-02 | 2024-07-02 | reinforcement | Check vertical bands reinforcement & allow to start formwork | (+106.75) | Grid F/11-12 | B | 2024-07-02
| Sub Structure | 9th floor | IT/260 | 2024-07-03 | 2024-07-03 | formwork | Check vertical bands formwork and allow to start concrete work | (+106.75) | Grid F/11-12 | B | 2024-07-04
| Sub Structure | 9th floor | IT/261 | 2024-07-04 | 2024-07-04 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+106.75) | Grid F/15-16 | A | 2024-07-04
| Sub Structure | 9th floor | IT/262 | 2024-07-04 | 2024-07-04 | formwork | Check vertical bands formwork and allow to start concrete work | (+106.75) | Grid F/15-16 | B | 2024-07-04
| Sub Structure | 8th floor | IT/263 | 2024-07-04 | 2024-07-04 | slab/beam formwork | Check slab/beam formwork and allow to start reinforcement Zone 1 | (+95.75) | Grid C-E/1 | B | 2024-07-04
| Sub Structure | 8th floor | IT/264 | 2024-07-04 | 2024-07-04 | slab/beam formwork | Check slab/beam formwork and allow to start concrete work Zone 1 | (+95.75) | Grid C-E/1 | A | 2024-07-04
| Sub Structure | 9th floor | IT/265 | 2024-07-05 | 2024-07-06 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+106.75) | Grid F/9-10 | A | 2024-07-10
| Sub Structure | 9th floor | IT/266 | 2024-07-05 | 2024-07-06 | formwork | Check vertical bands formwork and allow to start concrete work | (+106.75) | Grid F/9-10 | B | 2024-07-18
| Sub Structure | 2nd floor | IT/267 | 2024-07-05 | 2024-07-06 | screeding | Check sceeding in apartment and allow to start concrete work | (+30.0) | Grid C-F/14-17 | B | 2024-07-23
| Sub Structure | 1st floor | IT/268 | 2024-07-09 | 2024-07-09 | screeding | Check levels for screeding in apartment & allow to start concrete work | (+19.0) | Grid A-F/1-9 | B | 2024-07-30
| Sub Structure | 1st floor | IT/269 | 2024-07-10 | 2024-07-10 | screeding | Check level for screeding and allow to start concrete work | (+19.0) | Grid A-F/8-13 | A | 2024-07-30
| Sub Structure | 1st floor | IT/270 | 2024-07-10 | 2024-07-10 | screeding | Check level for screeding and allow to start concrete work | (+19.0) | Grid B-D/3-15 | B | 2024-07-30
| Sub Structure | 8th floor | IT/271 | 2024-07-10 | 2024-07-10 | layout | Check layout for internal brick work and allow to start brick work Zone 1 | (+96.0) | Grid A-C/1-9 | B | 2024-07-18
| Sub Structure | 8th floor | IT/272 | 2024-07-10 | 2024-07-10 | brick work | Check layout for internal brick work and allow to start brick work Zone 2 | (+96.0) | Grid C-F/8-13 | B | 2024-07-18
| Sub Structure | 8th floor | IT/273 | 2024-07-10 | 2024-07-10 | Lintel reinforcement | Check RCC Lintels reinforcement and allow to start concrete work | (+96.0) |  | A | 2024-07-11
| Sub Structure | 1st floor | IT/274 | 2024-07-11 | 2024-07-11 | screening | Check levels for screeding in apartment and allow to start concrete work | (+19.0) | Grid A-F/12-17 | B | 2024-07-30
| Sub Structure | 1st floor | IT/275 | 2024-07-14 | 2024-07-14 | screening | Check levels for screeding in apartment and allow to start concrete work | (+19.0) | Grid A-F/12-17 | B | 2024-07-30
| Sub Structure | 1st floor | IT/276 | 2024-07-13 | 2024-07-13 | screening | Check levels for screeding in apartment and allow to start concrete work | (+19.0) | Grid B-F/15-24 | B | 2024-07-30
| Sub Structure | 7th floor | IT/277 | 2024-07-13 | 2024-07-13 | layout | Check layout for internal brick work and allow to start brick work Zone 3 | (+85.0) | Grid A-C/17-26 | A | 2024-07-20
| Sub Structure | 1st Floor | IT/278 | 2024-07-15 | 2024-07-15 | screeding | Check levels for screeding in apartment and allow to start concrete work | (+19.0) | Grid A-C/24-26 | B | 2024-07-30
| Sub Structure | 8th floor | IT/279 | 2024-07-18 | 2024-07-18 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+95.75) | Grid C-E/1 | A | 2024-07-19
| Sub Structure | 8th floor | IT/280 | 2024-07-23 | 2024-07-23 | formwork | Check vertical bands formwork and allow to start concrete work | (+95.75) | Grid C-E/1 | B | 2024-08-05
| Sub Structure | Basement | IT/281
| Sub Structure | 9th floor | IT/282 | 2024-07-18 | 2024-07-18 | vertical formwork | Check vertical bands formwork and allow to start concrete work | (+106.75) | Grid F/6-8 | B | 2024-07-20
| Sub Structure | 10th floor | IT/283 | 2024-07-19 | 2024-07-19 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+117.75) | Grid F/11-14 | A | 2024-07-19
| Sub Structure | 2nd floor | IT/284 | 2024-07-20 | 2024-07-20 | screeding | Check level for screeding in apartment 201 to 206 and allow to start concrete | (+30.0) | Grid A-F/1-11 | B | 2024-07-23
| Sub Structure | 2nd floor | IT/285 | 2024-07-20 | 2024-07-20 | screeding | Check level for screeding in corridor & allow to start concrete work | (+30.0) | Grid C-F/3-11 | A | 2024-07-23
| Sub Structure | 10th floor | IT/286 | 2024-07-21 | 2024-07-21 | formwork | Check vertical bands formwork & allow to start concrete work | (+117.75) | Grid F/11-14 | B | 2024-07-23
| Sub Structure | 9th floor | IT/287 | 2024-07-22 | 2024-07-22 | internal brick work | Check layout for internal brick work and allow to start brick work Zone 3 | (+107.00) | Grid A-F/18-26 | A | 2024-07-23
| Sub Structure | 7th floor | IT/288 | 2024-07-22 | 2024-07-22 | internal brick work | Check layout for internal brick work and allow to start brick work Zone 3 | (+85.00) | Grid C-F/18-26 | OP
| Sub Structure | 2nd floor | IT/289 | 2024-07-22 | 2024-07-22 | screeding | Check level for screeding in apartment 205,207,208 & 210 & allow to start concrete work | (+30.0) | Grid A-F/10-15 | A | 2024-07-26
| Sub Structure | 10th floor | IT/290 | 2024-07-23 | 2024-07-23 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (++117.75) | Grid F/6-10 | A | 2024-07-26
| Sub Structure | 10th floor | IT/291 | 2024-07-24 | 2024-07-24 | formwork | Check vertical bends formwork and allow to start concrete work | (++117.75) | Grid F/9-10 | B | 2024-07-26
| Sub Structure | 2nd floor | IT/292 | 2024-07-24 | 2024-07-24 | screeding | Check screeding in apartment 209 & 214 and allow to start concrete work | (+30.0) | Grid A-F/14-19 | A | 2024-07-26
| Sub Structure | 2nd floor | IT/293 | 2024-07-24 | 2024-07-24 | screeding | Check level for screeding and allow to start concrete work | (+30.0) | Grid B-D/10-17 | A | 2024-07-26
| Sub Structure | 10th floor | IT/294 | 2024-07-25 | 2024-07-25 | reinforcement | Check vertical bands reinforcement & allow to start the formwork | (+117.75) | Grid F/15-16 | A | 2024-07-30
| Sub Structure | 10th floor | IT/295 | 2024-07-25 | 2024-07-25 | formwork | Check vertical columns formwork and allow to start concrete work | (+117.75) | Grid F/15-16 | B | 2024-07-26
| Sub Structure | 10th floor | IT/296 | 2024-07-25 | 2024-07-25 | formwork | Check formwork of vertical band & allow to start concrete work | (+117.75) | Grid F/6-8 | B | 2024-07-26
| Sub Structure | 9th floor | IT/297 | 2024-07-27 | 2024-07-27 | brick work | Check layout for internal brick work and allow to start brick work | (+107.00) | Grid A-C/10-17 | A | 2024-07-30
| Sub Structure | 2nd floor | IT/298 | 2024-07-28 | 2024-07-28 | screeding | Check level for screeding and allow to start concrete work | (+30.0) | Grid B-F/17-24 | A | 2024-07-31
| Sub Structure | 2nd floor | IT/299 | 2024-07-28 | 2024-07-28 | screeding | Check level for screeding and allow to start concrete work | (+30.0) | Grid A-F/18-26 | B | 2024-07-31
| Sub Structure | 11th floor | IT/300 | 2024-07-29 | 2024-07-29 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+131.75) | Grid F/8-10 | A | 2024-07-31
| Sub Structure | 11th floor | IT/301 | 2024-07-29 | 2024-07-29 | formwork | Check vertical bands formwork and allow to start concrete work | (+131.75) | Grid F/8-10 | B | 2024-07-31
| Sub Structure | 11th floor | IT/302 | 2024-07-29 | 2024-07-29 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+131.75) | Grid F/13-14 | A | 2024-07-31
| Sub Structure | 11th floor | IT/303 | 2024-07-30 | 2024-07-30 | formwork | Check vertical bands formwork and allow to start concrete work | (+131.75) | Grid F/13-14 | A | 2024-07-31
| Sub Structure | 1st Floor | IT/304 | 2024-07-30 | 2024-07-30 | screeding | Check level for screeding and allow to start concrete work | (+19.00) | Grid A-C/24-26 | A | 2024-07-31
| Sub Structure | 11th floor | IT/305 | 2024-07-30 | 2024-07-30 | reinforcement | Check vertical bands reinforcement & allow to start formwork | (+131.0) | Grid F/11-12 | A | 2024-08-03
| Sub Structure | 9th floor | IT/306 | 2024-07-31 | 2024-07-31 | layout | Check layout for internal brick work and allow to start brick work | (+107.0) | Grid B-F/8-15 | A | 2024-08-03
| Sub Structure | 2nd floor | IT/307 | 2024-10-08 | 2024-10-08 | level layout | Check level screeding flooring in apartment 205,207,208,210 | (+30.0) | Grid A-F/10-15 | B | 2024-10-11
| Sub Structure | 11th floor | IT/308 | 2024-08-02 | 2024-08-02 | reinforcement | Check vertical bands reinforcement and allow to start formwork | (+131.75) | Grid F/15-16 | A | 2024-08-03
| Sub Structure | 11th floor | IT/309 | 2024-08-02 | 2024-08-02 | formwork | Check vertical bands formwork and allow to start concrete work | (+131.75) | Grid F/15-16 | B | 2024-08-03
| Sub Structure | 10th floor | IT/310 | 2024-08-02 | 2024-08-02 | brick work | Check layout for internal brick wrok and allow to start brick work | (+118.0) | Grid A-F/1-9 | A | 2024-08-03
| Sub Structure | 10th floor | IT/311 | 2024-08-04 | 2024-08-04 | brick work | Check layout for internal brick work and allow to start brick work Zone 1 | (+118.0) | Grid A-C/10-17 | A | 2024-08-05
| Sub Structure | 2nd floor | IT/312 | 2024-10-08 | 2024-10-08 | screed level | Check level of screed flooring in apartment 209,214,corridor | (+30.0) | Grid A-F/10-19 | B | 2024-10-11
| Sub Structure | 2nd floor | IT/313 | 2024-08-15 | 2024-08-15 | screed level | Check level of screed flooring in apartment 211,213,215,216, coordior | (+30.0) | Grid A-F/17-26 | B | 2024-10-21
| Sub Structure | 1st floor | IT/314 | 2024-08-15 | 2024-08-15 | screed level | Check level of screed flooring in apartment 102,115 | (+19.0) | Grid B-F/1-4, B-F/23-26 | OP
| Sub Structure | 10th floor | IT/315 | 2024-08-05 | 2024-08-05 | layout | Check layout for internal brick work and allow to start brick work Zone 3 | (+118.0) | Grid A-F/17-26 | A | 2024-08-07
| Sub Structure | 11th floor | IT/316 | 2024-08-07 | 2024-08-06 | reinforcement | Check reinforcement of columns & allow to start formwork | -131.75 | Grid F/6-8 | A | 2024-08-13
| Sub Structure | 11th floor | IT/317 | 2024-08-06 | 2024-08-06 | formwork | Check vertical formwork and allow to start concrete work | (+131.0) | Grid F/6-8 | A | 2024-08-07
| Sub Structure | Basement | IT/318 | 2024-08-07 | 2024-08-07 | layout | Check layout for internatl brick work and allow to start brick work Zone 3 | (+118) | Grid B-F/8-13 | A | 2024-08-07
| Sub Structure | 9th floor | IT/319 | 2024-08-08 | 2024-08-08 | RCC Lintels | Check reinforcement of RCC Lintels | (+107.0) |  | A | 2024-08-13
| Sub Structure | 10th floor | IT/320 | 2024-08-08 | 2024-08-08 | RCC Lintels | Check reinforcement of RCC Lintels | (+118.0) |  | A | 2024-08-13
| Sub Structure | 9th floor | IT/321 | 2024-08-10 | 2024-08-10 | brick work | Check layout for internal brick work and allow to start brick work | (+107.0) | Grid C-F/14-19 | A | 2024-08-20
| Sub Structure | 10th floor | IT/322 | 2024-08-10 | 2024-08-10 | brick work | Check layout for internal brick work and allow to start work Zone 2 | (+118.0) | Grid C-F/12-19 | A | 2024-08-20
| Sub Structure | 8th floor | IT/323 | 2024-08-12 | 2024-08-12 | column reinforcement | Check vertical band reinforcement and allow to start formwork | (+95.75) | Grid C-E/26 | A | 2024-08-15
| Sub Structure | 9th floor | IT/324 | 2024-08-12 | 2024-08-12 | vertical reinforcement | Check vertical band reinforcement and allow to start formwork | (+106.75) | Grid C-E/0 | A | 2024-08-15
| Sub Structure | 9th floor | IT/325 | 2024-08-12 | 2024-08-12 | vertical formwork | Check vertical band formwork and allow to start concrete work | (+106.75) | Grid C-E/1 | A | 2024-08-15
| Sub Structure | 3rd floor | IT/326 | 2024-08-13 | 2024-08-13 | screeding | Check level for screeding and allow to start concrete work | (+41.0) | Grid A-F/12-19 | A | 2024-08-20
| Sub Structure | 3rd floor | IT/327 | 2024-08-13 | 2024-08-13 | screeding | Check level for screeding and allow to start concrete work | (+41.0) | Grid A-F/18-26 | B | 2024-08-20
| Sub Structure | 3rd floor | IT/328 | 2024-08-13 | 2024-08-13 | screeding | Check level for screeding and allow to start concrete work | (+41.0) | Grid B-F/13-24 | A | 2024-08-20
| Sub Structure | 6th floor | IT/329 | 2024-08-15 | 2024-08-15 | brick work | Check internal brick work | (+74.0) | Grid A-F/17-26 | B | 2024-08-21
| Sub Structure | 7th floor | IT/330 | 2024-08-15 | 2024-08-15 | brick work | Check internal brick work | (+85.0) | Grid A-F/1-26 | B | 2024-08-21
| Sub Structure | 8th floor | IT/331 | 2024-08-15 | 2024-08-15 | brick work | Check internal brick work | (+96.0) | Grid A-F/1-26 | B | 2024-09-03
| Sub Structure | 8th floor | IT/332 | 2024-08-15 | 2024-08-15 | formwork | Check vertical formwork and allow to start concrete work | (+95.75) | Grid C-E/26 | B | 2024-08-21
| Sub Structure | 8th floor | IT/333 | 2024-08-15 | 2024-08-15 | reinforcement | Check horizontal reinforcement and allow to start formwork | (+95.75) | Grid F/12-13 | A | 2024-08-19
| Sub Structure | 8th floor | IT/334 | 2024-08-15 | 2024-08-15 | formwork | Check horizontal band formwork and allow to start concrete work | (+95.75) | Grid F/12-13 | B | 2024-08-21 |  |  |  | 2024-08-15
| Sub Structure | 10th floor | IT/335 | 2024-08-16 | 2024-08-16 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+117.75) | Grid C-E/01 | A | 2024-08-19
| Sub Structure | 10th floor | IT/336 | 2024-08-17 | 2024-08-17 | formwork | Check vertical band formwork and allow to start concrete work | (+117.75) | Grid C-E/1 | A | 2024-08-21
| Sub Structure | 3rd floor | IT/337 | 2024-08-17 | 2024-08-17 | screeding | Check screeding in apartments and allow to start concrete work | (+41.0) | Grid A-F/10-15 | A | 2024-08-21
| Sub Structure | 3rd floor | IT/338 | 2024-08-18 | 2024-08-18 | screeding | Check screeding in apartments & allow to start concrete work | (+41.0) | Grid A-F/1-9 | B | 2024-08-21
| Sub Structure | 11th floor | IT/339 | 2024-08-21 | 2024-08-21 | layout | Check layout for internal brick work and allow to start brick work Zone 2 | (+132.0) | Grid A-F/10-17 | A | 2024-08-24
| Sub Structure | 3rd floor | IT/340 | 2024-08-20 | 2024-08-20 | level layout | Check level for screeding in apartments and allow tostart concrete work | (+41.0) | Grid C-F/8-13 | A | 2024-08-24
| Sub Structure | 3rd floor | IT/341 | 2024-08-20 | 2024-08-20 | level, | Check level for screeding & allow to start concrete work | (+41.0) | Grid B-F/3-13 | A | 2024-08-24
| Sub Structure | 9th floor | IT/342 | 2024-08-21 | 2024-08-21 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+106.75) | Grid C-E/26 | A | 2024-08-24
| Sub Structure | 9th floor | IT/343 | 2024-08-22 | 2024-08-22 | formwork | Check vertical band formwork and allow to start concrete work | (+106.75) | Grid C-E/26 | A | 2024-08-24
| Sub Structure | 11th floor | IT/344 | 2024-08-22 | 2024-08-22 | reinforcement | Check vertical band reinforcement & allow to start formwork | (+131.75) | Grid C-E/01 | A | 2024-08-28
| Sub Structure | 11th floor | IT/345 | 2024-08-22 | 2024-08-22 | formwork | Check vertical band formwork and allow to start concret work | (+131.75) | Grid C-E/01 | B | 2024-08-24
| Sub Structure | 11th floor | IT/346 | 2024-08-23 | 2024-08-22 | layout | Check layout for internal brick work and allow to start brick work | (+132.0) | Grid A-F/1-9 | A | 2024-08-24
| Sub Structure | 11th floor | IT/347 | 2024-08-24 | 2024-08-24 | layout | Check layout for internal brick work and allow to start brick work | (+132.0) | Grid A-F/18-23 | A | 2024-08-28
| Sub Structure | 4th floor | IT/348 | 2024-08-28 | 2024-08-28 | screeding | Check screeding for level points zone 3 and allow to start concrete work | (+52.0) | Grid A-F/19-26 | A | 2024-08-30
| Sub Structure | 4th floor | IT/349 | 2024-08-26 | 2024-08-26 | screeding | Check level point for screeding Zone 3 & allow to start concrete work | (+52.0) | Grid C-F/18-26 | A | 2024-08-30
| Sub Structure | 10th floor | IT/350 | 2024-08-29 | 2024-08-29 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+117.75) | Grid C-E/26 | A | 2024-09-06
| Sub Structure | 10th floor | IT/351 | 2024-08-29 | 2024-08-29 | formwork | Check vertical band formwork and allow to start concrete work | (+117.75) | Grid C-E/26 | A | 2024-09-03
| Sub Structure | 4th floor | IT/352 | 2024-08-29 | 2024-08-29 | screeding | Check level for screeding and allow to start concrete work | (+52.0) | Grid A-F/14-19 | A | 2024-09-03
| Sub Structure | 4th floor | IT/353 | 2024-08-30 | 2024-08-30 | screeding | Check level for screeding and allow to start concrete work | (+52.0) | Grid A-F/12-17 | A | 2024-09-03
| Sub Structure | 4th floor | IT/354 | 2024-08-30 | 2024-08-30 | screeding | Check level for screeding and allow to start concrete work | (+52.0) | Grid A-F/12-18 | A | 2024-09-03
| Sub Structure | 3rd floor | IT/355 | 2024-10-11 | 2024-10-11 | screeding | Check level for screeding in apartment and corridor | (+41.0) | Grid A-F/14-26 | B | 2024-10-21
| Sub Structure | 3rd floor | IT/356 | 2024-10-11 | 2024-10-11 | screeding | Check level for screeding in apartment and corridor | (+41.0) | Grid A-D/12-18 | B | 2024-10-21
| Sub Structure | 3rd floor | IT/357 | 2024-10-11 | 2024-10-11 | screeding | Check level for screeding in apartment, electrial room & Garbage room | (+41.0) | Grid A-F/1-15 | B | 2024-10-21
| Sub Structure | 3rd floor | IT/358 | 2024-10-11 | 2024-10-11 | screeding | Check level for screeding in apartment, corridor | (+41.0) | Grid A-F/13-13 | B | 2024-10-21
| Sub Structure | 4th floor | IT/359 | 2024-08-31 | 2024-08-31 | screeding | Check level for screeding in apartments & corridor | (+52.0) | Grid A-F/18-26 | B | 2024-10-21
| Sub Structure | 11th floor | IT/360 | 2024-09-02 | 2024-09-02 | layout | Check layout for internal brick work and allow to start brick work | (+132.0) | Grid B-F/1-4, C-F/14-17 | A | 2024-09-09
| Sub Structure | 4th floor | IT/361 | 2024-09-01 | 2024-09-01 | level | Check level for sceeding and allow to start concrete work | (+52.0) | Grid A-F/1-9 | A | 2024-09-06
| Sub Structure | 4th floor | IT/362 | 2024-09-01 | 2024-09-01 | level | Check level for screeding and allow to start concrete work | (+52.0) | Grid B-F/3-7 | A | 2024-09-06
| Sub Structure | 11th floor | IT/363 | 2024-09-02 | 2024-09-02 | layout | Check layout for internal brick work and allow to start brick work | (+132.0) | Grid A-F/22-26 | A | 2024-09-09
| Sub Structure | 4th floor | IT/364 | 2024-09-02 | 2024-09-02 | level | Check level for screeding and allow to start concrete work | (+52.0) | Grid B-F/1-4, A-F/8-13 | A | 2024-09-06
| Sub Structure | 4th floor | IT/365 | 2024-09-02 | 2024-09-02 | level | Check level for screeding and allow to start concrete work | (+52.0) | Grid A-D/7-12 | A | 2024-09-06
| Sub Structure | 4th floor | IT/366 | 2024-10-15 | 2024-10-15 | level | Check level for screeding | (+52.0) | Grid A-F/12-19 | B | 2024-10-24
| Sub Structure | 4th floor | IT/367 | 2024-10-15 | 2024-10-15 | level | Check leve for screeding | (+52.0) | Grid A-F/1-9 | B | 2024-10-21
| Sub Structure | 1st floor | IT/368 | 2024-09-07 | 2024-09-07 | formwork | Check vertical band formwork and allow to start concrete work | (+18.75) | Grid A/6-8 | A | 2024-09-18
| Sub Structure | 1st floor | IT/369 | 2024-09-07 | 2024-09-07 | formwork | Check vertical band formwork and allow to start concrete work | (+18.75) | Grid A/11-12 | A | 2024-09-18
| Sub Structure | 1st floor | IT/370 | 2024-09-07 | 2024-09-07 | level | Check screeding level | (+19.0) | Grid A-F/12-19 | B | 2024-09-10
| Sub Structure | 1st floor | IT/371 | 2024-09-09 | 2024-09-09 | screeding | Check level for screeding | (+19.0) | Grid A-F/10-18 | B | 2024-09-16
| Sub Structure | 1st floor | IT/372 | 2024-09-09 | 2024-09-09 | formwork | Check vertical band formwork and allow to start concrete work | (+18.75) | Grid A/2-4 | A | 2024-09-18
| Sub Structure | 1st floor | IT/373 | 2024-09-10 | 2024-09-10 | formwork | Check vertical band formwork and allow to stat concrete work | (+18.75) | Grid A/13-14 | A | 2024-09-18
| Sub Structure | Top floor | IT/374 | 2024-09-10 | 2024-09-10 | reinforcement | Check horizontal band reinforcement and allow to start formwork | (+146.0) | Grid F/6-10, F/11-14 | A | 2024-09-12
| Sub Structure | 11th floor | IT/375 | 2024-09-10 | 2024-09-10 | reinforcement | Check vertical band reinforcement & allow to start formwork | (+131.75) | Grid C-E/26 | A | 2024-09-12
| Sub Structure | 5th floor | IT/376 | 2024-09-10 | 2024-09-11 | screeding | Check screeding and allow to stat concrete work | (+63.0) | Grid A-F/18-26 | A | 2024-09-18
| Sub Structure | 5th floor | IT/377 | 2024-09-10 | 2024-09-11 | screeding | Check screeding and allow to start concrete work | (+63.0) | Grid B-F/18-24 | A | 2024-09-18
| Sub Structure | 1st floor | IT/378 | 2024-09-11 | 2024-09-11 | screeding | Check level for screeding flooring in apartments | (+19.0) | Grid A-F/18-26 | B | 2024-09-16
| Sub Structure | 1st floor | IT/379 | 2024-09-11 | 2024-09-11 | reinforcement | Check vertical band reinforcement & allow to start formwork | (+18.75) | Grid A/15-16 | A | 2024-09-12
| Sub Structure | 2nd floor | IT/380 | 2024-09-11 | 2024-09-11 | formwork | Check leftover slab/beam formwork in balcony & allow to start concrete work | (+29.75) | Grid A/6-8, A/11-12 | A | 2024-09-18
| Sub Structure | 11th floor | IT/381 | 2024-09-11 | 2024-09-11 | formwork | Check vertical band formwork and allow to start concrete work | (+131.75) | Grid C-E/26 | A | 2024-09-18
| Sub Structure | Basement | IT/382
| Sub Structure | 1st floor | IT/383 | 2024-09-13 | 2024-09-13 | formwork | Check vertical band formwork and allow to start concrete work | (+18.75) | Grid A/15-16 | A | 2024-09-20
| Sub Structure | Top floor | IT/384 | 2024-09-13 | 2024-09-13 | formwork | Check slab formwork and allow to start concrete work | (+146.0) | Grid F/6-10 | A | 2024-09-20
| Sub Structure | 1st floor | IT/385 | 2024-09-14 | 2024-09-14 | reinforcement | Check vertical band reinforcement & allow to start formwork | (+18.75) | Grid A/19-21, A/23-25 | A | 2024-09-18
| Sub Structure | 5th floor | IT/386 | 2024-09-14 | 2024-09-14 | level | check level for screeding | (+63.0) | Grid A-F/18-26 | B | 2024-09-18
| Sub Structure | 9th floor | IT/387 | 2024-09-24 | 2024-09-24 | brick work | Check internal brick work | (+107.00) | Grid A-F/1-26 | B | 2024-10-04
| Sub Structure | 10th floor | IT/388 | 2024-09-24 | 2024-09-24 | brick work | Check internal brick work | (+118.0) | Grid A-F/1-26 | B | 2024-10-04
| Sub Structure | 2nd floor | IT/389 | 2024-09-15 | 2024-09-15 | formwork | Check leftover slab/beam formwork in balcony to start concrete work | (+29.75) | Grid A/2-4, A/13-14 | A | 2024-09-20
| Sub Structure | top floor | IT/390 | 2024-09-16 | 2024-09-16 | formwork | Check slab formwork, beam & bottom of horizontal band & allow to start rienforcement | (+146.0) | Grid F/11-14 | A | 2024-09-20
| Sub Structure | top floor | IT/391 | 2024-09-16 | 2024-09-16 | reinforcement | Check slab, beam reinforcement and allow to start concrete work | (+146.0) | Grid F/11-14 | A | 2024-09-24
| Sub Structure | 1st floor | IT/392 | 2024-09-16 | 2024-09-16 | formwork | Check vertical band formwork & allow to start concrete work | (+18.75) | Grid A/19-21 | A | 2024-09-20
| Sub Structure | 2nd floor | IT/393 | 2024-09-16 | 2024-09-16 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+29.75) | Grid A/6-8, A/11-12 | A | 2024-09-24
| Sub Structure | 1st floor | IT/394 | 2024-09-16 | 2024-09-16 | formwork | Check vertical band formwork and allow to start concrete work | (+18.75) | Grid A/23-25 | A | 2024-09-20
| Sub Structure | 4th floor | IT/395 | 2024-10-15 | 2024-10-15 | level | Check level for screeding | (+52.0) | Grid B-F/1-4, A-F/7-13 | B | 2024-10-21
| Sub Structure | 2nd floor | IT/396 | 2024-09-18 | 2024-09-18 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+29.75) | Grid A/2-4 | A | 2024-09-30
| Sub Structure | 2nd floor | IT/397 | 2024-09-18 | 2024-09-18 | formwork | Check vertical band formwork and allow to start concrete work | (+29.75) | Grid A/11-12 | A | 2024-09-24
| Sub Structure | 2nd floor | IT/398 | 2024-09-18 | 2024-09-18 | formwork | Check leftover slab/beam formwork in balcony & allow to start concrete work | (+29.75) | Grid A/15-16 | A | 2024-09-24
| Sub Structure | 2nd floor | IT/399 | 2024-09-19 | 2024-09-19 | formwork | Check vertical band formwork and allow to start concrete work | (+29.75) | Grid A/2-4, 6-8 | A | 2024-09-24
| Sub Structure | 5th floor | IT/400 | 2024-09-19 | 2024-09-19 | screeding | Check screeding in apartments and allow to start concrete work | (+63.0) | Grid A-F/10-19 | A | 2024-09-24
| Sub Structure | 5th floor | IT/401 | 2024-09-19 | 2024-09-19 | screeding | Check screeding in corridor & allow to start concrete work | (+63.0) | Grid A-D/10-18 | A | 2024-09-24
| Sub Structure | 2nd floor | IT/402 | 2024-09-19 | 2024-09-19 | vertical | Check vertical band formwork and allow to start concrete work | (+29.75) | Grid A/13-14 | B | 2024-09-30
| Sub Structure | 2nd floor | IT/403 | 2024-09-19 | 2024-09-19 | slab/beam formwork | Check slab / beam formwork in balcony & allow to start concrete work | (+29.75) | Grid A/19-21, A/23-25 | A | 2024-09-30
| Sub Structure | 5th floor | IT/404 | 2024-09-21 | 2024-09-21 | level | Check level for screeding in apartments | (+63.0) | Grid A-F/10-19 | B | 2024-10-09
| Sub Structure | 2nd floor | IT/405 | 2024-09-20 | 2024-09-21 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+29.75) | Grid A/15-16 | A | 2024-09-30
| Sub Structure | 2nd floor | IT/406 | 2024-09-20 | 2024-09-21 | reinforcement | Check vertical rienforcement and allow to start formwork | (+29.75) | Grid A/19-21 | A | 2024-09-30
| Sub Structure | 2nd floor | IT/407 | 2024-09-20 | 2024-09-21 | formwork | Check vertical band formwork and allow to start concrete work | (+29.75) | Grid A/15-21 | A | 2024-09-30
| Sub Structure | 2nd floor | IT/408 | 21-Sep-245 | 2024-09-22 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+29.75) | Grid A/23-25 | A | 2024-09-30
| Sub Structure | 2nd floor | IT/409 | 2024-09-21 | 2024-09-22 | formwork | Check vertical band formwork and allow to start concrete work | (+29.75) | Grid A/23-25 | A | 2024-09-26
| Sub Structure | 5th floor | IT/410 | 2024-09-21 | 2024-09-22 | screeding | Check level point for screediong | (+63.0) | Grid A-F/1-12 | A | 2024-09-30
| Sub Structure | 5th floor | IT/411 | 2024-09-21 | 2024-09-22 | screeding | Check level point for screediong | (+63.0) | Grid B-F/4-12 | A | 2024-09-30
| Sub Structure | top floor | IT/412 | 2024-09-21 | 2024-09-22 | formwork | Check horizontal formwork and allow to start concrete work | (+146.0) | Grid F/6-10 | A | 2024-09-26
| Sub Structure | 5th floor | IT/413 | 2024-09-24 | 2024-09-24 | screeding | Check level for screeding | (+63.0) | Grid A-F/1-12 | B | 2024-10-09
| Sub Structure | 3rd floor | IT/414 | 2024-09-24 | 2024-09-24 | formwork | Check leftover slab/beam formwork and allow to start reinforcement zone 1 & 2 | (+40.75) | Grid A/2-4, A/6-8, A/11-12, A/13-14 | A | 2024-10-04
| Sub Structure | 3rd floor | IT/415 | 2024-09-25 | 2024-09-25 | reinforcement | Check leftover slab/beam reinforcement and allow to start concrete work | (+40.75) |  | A | 2024-10-02
| Sub Structure | Top roof | IT/416 | 2024-09-25 | 2024-09-25 | formwork | Check lift & stair formwork & shear wall zone 1 | (+146.0) | Grid A-B/9-10 | B | 2024-10-02
| Sub Structure | 3rd floor | IT/417 | 2024-09-26 | 2024-09-26 | reinforcement | Check leftover slab/beam reinforcement and allow to start concrete work zone 2 | (+40.75) | Grid A/11-12, A/13-14 | A | 2024-09-30
| Sub Structure | 11th floor | IT/418 | 2024-09-26 | 2024-09-26 | reinforcement | Check RCC lintel reinforcement and allow to start concrete work | (+131.00) |  | A | 2024-09-30
| Sub Structure | 3rd floor | IT/419 | 2024-09-27 | 2024-09-27 | reinforcement | Check vertical band reinforcement & allow to start formwork | (+40.75) | Grid A/2-4, A/6-8 | A | 2024-09-30
| Sub Structure | Top floor | IT/420 | 2024-09-28 | 2024-09-28 | formwork | Check horizontal band & allow to start concrete work | (+146.0) | Grid F/11-14 | A | 2024-10-04
| Sub Structure | 3rd floor | IT/421 | 2024-09-28 | 2024-09-28 | formwork | Check vertical band formwork and allow to start concrete work | (+40.75) | Grid A/2-4, A/6-8 | A | 2024-10-04
| Sub Structure | 6th floor | IT/422 | 2024-09-28 | 2024-09-28 | level | Check level for screeding in apartments | (+74.0) | Grid A-F/3-12 | A | 2024-10-09
| Sub Structure | 3rd floor | IT/423 | 2023-10-01 | 2023-10-01 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+40.75) | Grid A/11-12, A/13-14 | A | 2024-10-04
| Sub Structure | 11th floor | IT/424 | 2023-10-01 | 2023-10-01 | brick work | Check internal brick work | (+131.0) | Grid A-F/1-26 | B | 2024-10-09
| Sub Structure | Basement | IT/425
| Sub Structure | 3rd floor | IT/426 | 2024-10-01 | 2024-10-01 | formwork | Check vertical band formwork and allow to start concrete work | (+40.75) | Grid A/11-12, A/13-14 | A | 2024-10-09
| Sub Structure | 3rd floor | IT/427 | 2024-10-01 | 2024-10-02 | formwork | Check slab/beam formwork & allow to start reinforcement zone 2 & 3 | (+40.75) | Grid A/15-16, A/19-21, A/23-25 | A | 2024-10-04
| Sub Structure | 6th floor | IT/428 | 2024-10-01 | 2024-10-02 | level | Check level point for screeding in appartments | (+74.0) | Grid A-F/18-26 | B | 2024-10-09
| Sub Structure | 6th floor | IT/429 | 2024-10-03 | 2024-10-03 | level | check level for screeding | (+74.0) | Grid A-F/3-12 | B | 2024-10-09
| Sub Structure | 3rd floor | IT/430 | 2024-10-02 | 2024-10-02 | formwork | Check vertical band formwork and allow to start concrete work | (+40.75) | Grid A/11-13 | A | 2024-10-09
| Sub Structure | 3rd floor | IT/431 | 2024-10-03 | 2024-10-03 | reinforcement | Check levtover reinforcement and allow to start concrete work zone 2-3 | (+40.75) | Grid A/15-16, A/19-21, A/23-25 | A | 2024-10-09
| Sub Structure | 6th floor | IT/432 | 2024-10-04 | 2024-10-04 | level | check level for screeding zone 2 & 3 | (+74.0) | Grid A-C/10-12, A-F/18-26 | B | 2024-10-09
| Sub Structure | 6th floor | IT/433 | 2024-10-04 | 2024-10-04 | level | Check screeidng level in apartments | (+74.0) | Grid A-F/14-17, A-C/22-26 | A | 2024-10-18
| Sub Structure | top floor | IT/434 | 2024-10-04 | 2024-10-04 | plaster work | Check plumb points and allow for plaster work on external side zone 1 & 2 | (+19.0 to +146) | Grid F/6-8, F/9-10 | A | 2024-10-09
| Sub Structure | 6th floor | IT/435 | 2024-10-05 | 2024-10-05 | level | Chek screeding level in apartments | (+74.0) | Grid B-F/1-4, A-F/10-15, C-F/16-19 | A | 2024-10-18
| Sub Structure | 3rd floor | IT/436 | 2024-10-05 | 2024-10-05 | reinforcement | Check vertical band reinforcement & allow to start formwork | (+40.75) | Grid A/15-16, A/19-21, A/23-25 | A | 2024-10-09
| Sub Structure | 3rd floor | IT/437 | 2024-10-07 | 2024-10-07 | formwork | Check vertical band formwork and allow to start concrete work | (+40.75) | Grid A/15-16, A/19-21 | A | 2024-10-11
| Sub Structure | 6th floor | IT/438 | 2024-10-07 | 2024-10-07 | level | Check level for screeding zone 2 | (+74.0) | Grid A-F/14-17, A-C/22-26 | B | 2024-10-21
| Sub Structure | top floor | IT/439 | 11-Oct-234 | 2024-10-12 | slab fomrwork | Check slab formwork and allow to start reinforcement | (+146.0) | Grid A/14-16, A/17-21 | B | 2024-10-15
| Sub Structure | Top floor | IT/440 | 11-Oct-234 | 2024-10-12 | slab formwork | Check slab, beam & bottom of horizontal band and allow to start concrete work | (+146.0) | Grid A/14-16, A/17-21 | A | 2024-10-24
| Sub Structure | 4th floor | IT/441 | 2024-10-07 | 2024-10-07 | formwork | Check leftover slab / beam formwrok & allow to start concrete work | (+51.75) | Grid A/2-4, A/6-8 | A | 2024-10-11
| Sub Structure | 4th floor | IT/442 | 2024-10-08 | 2024-10-08 | formwork | Check leftover formwork in balcony & allow to start concrete work | (+51.75) | Grid A/11-12, A/13-14 | A | 2024-10-24
| Sub Structure | 3rd floor | IT/443 | 2024-10-08 | 2024-10-08 | formwork | Check vertical band formwork and allow to start concrete work | (+40.75) | Grid A/23-25 | A | 2024-10-11
| Sub Structure | top floor | IT/444 | 2024-10-10 | 2024-10-11 | formwork | Check swimming pool formwork zone 2 | (+146'-6'') | Grid A-F/11-15 | B | 2024-10-18
| Sub Structure | 6th floor | IT/445 | 2024-10-10 | 2024-10-10 | screeding | Check screeding level in apartments & corridor | (+74.00) | Grid B-F/1-4, A-F/10-15, C-F/16-19 | B | 2024-10-21
| Sub Structure | 7th floor | IT/446 | 2024-10-09 | 2024-10-09 | level | Check level for screeding | (+85.0) | Grid A-F/14-26 | A | 2024-10-21
| Sub Structure | 2nd floor | IT/447 | 2024-10-10 | 2024-10-10 | screeding | Check screeding level in appartments and corridor | (+30.0) | Grid A-F/1-12, C-F/14-17 | B | 2024-10-21
| Sub Structure | 7th floor | IT/448 | 2024-10-15 | 2024-10-15 | screeding | Check screeding level in apartments & corridor | (+85.00) | Grid A-F/14-17, A-C/22-26 | B | 2024-10-24
| Sub Structure | 4th floor | IT/449 | 2024-10-16 | 2024-10-16 | slab formwork | Check slab / beam formwork in balcony & allow to start concrete work | (+51.75) | Grid A/19-21, A/23-25 | A | 2024-10-21
| Sub Structure | 7th floor | IT/450 | 2024-10-16 | 2024-10-16 | screeding | Check screeidng level in apartments | (+85.0) | Grid A-F/12-15, B-F/23-26 | A | 2024-10-24
| Sub Structure | 7th floor | IT/451 | 2024-10-17 | 2024-10-18 | screeding | Check screeding | (+85.0) | Grid A-F/16-24 | B | 2024-10-24
| Sub Structure | 4th floor | IT/452 | 2024-10-17 | 2024-10-17 | reinforcement | Check vertical band reinforcement & allow to start formwork | (+51.75) | Grid A/2-4, A/6-8, A/11-12, A/13-14, A/15-16 | A | 2024-10-24
| Sub Structure | 4th floor | IT/453 | 2024-10-21 | 2024-10-21 | formwork | Check vertical band formwork and allow to start concrete work | (+51.75) | Grid A/2-4 | A | 2024-10-24
| Sub Structure | 7th floor | IT/454 | 2024-10-18 | 2024-10-18 | screeding | Check level for screeding in apartments | (+85.0) | Grid A-F/12-15, B-F/23-26 | B | 2024-10-24
| Sub Structure | top floor | IT/455 | 2024-10-21 | 2024-10-21 | formwork | Check columns (2 Nos) formwork zone 2 | (+146.0) | Grid A/11, B/11 | A | 2024-10-24
| Sub Structure | 4th floor | IT/456 | 2024-10-22 | 2024-10-22 | formwork | Check vertical band formwork and allow to start concrete work | (+51.75) | Grid A/6-8 | A | 2024-10-31
| Sub Structure | 7th floor | IT/457 | 2024-10-22 | 2024-10-22 | level | Check level for screeding | (+85.0) | Grid A-C/1-13 | A | 2024-10-31
| Sub Structure | 4th floor | IT/458 | 2024-10-22 | 2024-10-22 | formwork | Check vertical band formwork and allow to start concrete work | (+51.75) | Grid A/11-12 | A | 2024-10-31
| Sub Structure | Top floor | IT/459 | 2024-10-23 | 2024-10-23 | formwork | Check mumty roof slab formwork and bea zone 1 & 2 | (+159.0) | Grid A-C/8-12 | B | 2024-11-28
| Sub Structure | 7th floor | IT/460 | 2024-10-26 | 2024-10-26 | level | Check level for screeding | (+85.0) | Grid A-F/1-13 | A | 2024-10-31
| Sub Structure | 1st floor | IT/461 | 2024-10-26 | 2024-10-26 | plumb points | Check plumb points and allow for plaster work | (+19 to +146) | Grid F/11-12 | A | 2024-10-28
| Sub Structure | 4th floor | IT/462 | 2024-10-28 | 2024-10-28 | formwork | Check vertical band formwork and allow to start concrete work | (+51.75) | Grid A/13-14, A/15-16 | A | 2024-11-06
| Sub Structure | 7th floor | IT/463 | 2024-10-28 | 2024-10-28 | level | Check level for screeding | (+85.0) | Grid A-F/1-9, A-D/10-14 | B | 2024-10-31
| Sub Structure | top floor | IT/464 | 2024-10-28 | 2024-10-28 | plaster work | Check plaster work on external side | (+19.0 to +148.5) | Grid F/6-10 | A | 2024-10-28
| Sub Structure | 4th floor | IT/465 | 2024-10-29 | 2024-10-29 | formwork | Check vertical band formwork and allow to start concrete work | (+51.75) | Grid A/19-21, A/23-25 | B | 2024-11-06
| Sub Structure | 4th floor | IT/466 | 2024-10-29 | 2024-10-29 | reinforcement | Check vertical band reinforcement and allow to start formowrk | (+51.75) | Grid A/19-21, A/23-25 | A | 2024-10-31
| Sub Structure | 7th floor | IT/467 | 2024-11-03 | 2024-11-03 | screeding | Check level for screeding in apartments | (+85.0) | Grid A-F/1-3 | B | 2024-11-06
| Sub Structure | top floor | IT/468 | 2024-11-01 | 2024-11-01 | formwork | Check horizontal band formwork and allow to start concrete work | (+146.0) | Grid F/17-21 | A | 2024-11-06
| Sub Structure | 8th floor | IT/469 | 2024-11-02 | 2024-11-02 | level | Check level for screeding in apartments | (+96.0) | Grid A-F/18-26 | A | 2024-11-09
| Sub Structure | 8th floor | IT/470 | 2024-11-06 | 2024-11-06 | level | Check level points for screeding in apartments | (+96.01 | Grid A-F/14-26 | A | 2024-11-14
| Sub Structure | 8th floor | IT/471 | 2024-11-04 | 2024-11-04 | level | check level for screeding in apartments | (+96.0) | Grid A-F/18-26 | B | 2024-11-09
| Sub Structure | Top floor | IT/472 | 2024-11-05 | 2024-11-05 | formwork | Check internal wall of kids pool formwork zone 1 | (+146'-6'') | Grid C-F/10-12 | A | 2024-11-06
| Sub Structure | 5th floor | IT/473 | 2024-11-06 | 2024-11-06 | reinforcement | Check reinforcement and formwork of leftover slab/beam & allow to start concrete work | (+62.75) | Grid A/19-21, A/23-25 | A | 2024-11-14
| Sub Structure | 5th floor | IT/474 | 2024-11-07 | 2024-11-07 | reinforcement | Check reinforcement and formwork of bottom nib of horizontal band and allow to concrete | (+62.75) | Grid A/11-12, A/13-14, A/15-16 | A | 2024-11-14
| Sub Structure | 5th floor | IT/475 | 2024-11-07 | 2024-11-07 | reinforcement | Check reinforcement and formwork of bottom nib of horizontal band & allow to start concrete | (+62.75) | Grid A/2-4, A/6-8 | A | 2024-11-14
| Sub Structure | 2nd floor | IT/476 | 2024-11-07 | 2024-11-07 | reinforcement | Check reinforcement & formwork of leftover slab & allow to start concrete work | (+29.75) | Grid A-B/1, | A | 2024-11-14
| Sub Structure | 1st floor | IT/477 | 2024-11-07 | 2024-11-07 | reinforcement | Check reinforcement and allow for formwork | (+18.75) | Grid A-B/26 | A | 2024-11-09
| Sub Structure | 8th floor | IT/478 | 2024-11-08 | 2024-11-08 | screeding | Check level for screeding in apartment | (+9+6.0) | Grid A-F/15-26 | B | 2024-11-14
| Sub Structure | 8th floor | IT/479 | 2024-11-08 | 2024-11-09 | screeding | Check screeding level | (+96.0) | Grid A-F/12-17 | A | 2024-12-02
| Sub Structure | 8th floor | IT/480 | 2024-11-11 | 2024-11-11 | screeding | Check screeding level points in apartments |  | Grid B-D/12-14 | A | 2024-11-22
| Sub Structure | 9th floor | IT/481 | 2024-11-11 | 2024-11-11 | screeding | Check screeding level | (+107.0) | Grid A-F/1-9 | A | 2024-11-28
| Sub Structure | 5th floor | IT/482 | 2024-11-12 | 2024-11-12 | reinforcement | Check reinforcement and formwork of leftover slab/beam & allow to start concrete work | (+62.75) | Grid A/15-16 | B | 2024-11-22
| Sub Structure | 1st floor | IT/483 | 2024-11-12 | 2024-11-12 | formwork | Check vertical band formwork and allow to start concrete work | (+18.75) | Grid A-B/26 | A | 2024-11-22
| Sub Structure | 5th floor | IT/484 | 2024-11-12 | 2024-11-12 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+62.75) | Grid A/19-21, A/24-26 | A | 2024-11-18
| Sub Structure | 5th floor | IT/485 | 2024-11-12 | 2024-11-12 | formwork | Check vertical band formwork and allow to start concrete work | (+62.75) | Grid A/19-21, A/23-25 | A | 2024-11-22
| Sub Structure | 5th floor | IT/486 | 2024-11-12 | 2024-11-12 | reinforcement | chck reinforcement and leftover slab / beam formwork and allow to start concrete work z-2 | (+62.75) | Grid A/13-14 | A | 2024-11-22
| Sub Structure | 2nd floor | IT/487 | 2024-11-12 | 2024-11-12 | reinforcement | Check vertical band reinforcement and allow for concrete pouring | (+29.75) | Grid A-B/1 | A | 2024-11-18
| Sub Structure | 8th floor | IT/488 | 2024-11-12 | 2024-11-13 | level | Check screeding level | (+96.0) | Grid A-C/1-9, C-F/8-11 | A | 2024-11-28
| Sub Structure | 8th floor | IT/489 | 2024-11-15 | 2024-11-15 | level | Check screeding level in apartments & corridor | (+96.0) | Grid A-F/10-15 | B | 2024-11-22
| Sub Structure |  | IT/490
| Sub Structure | 9th floor | IT/491 | 2024-11-13 | 2024-11-14 | screeding | Check screeding level in apartment | (+107.0) | Grid A-F/8-13 | A | 2024-12-10
| Sub Structure | Top floor | IT/492 | 2024-11-14 | 2024-11-14 | formwork | Check beam formwork at roof slab zone 1 & 2 | (+159.0) | Grid A-C/8-12 | A | 2024-11-18
| Sub Structure | 5th floor | IT/493 | 2024-11-14 | 2024-11-14 | reinforcement | Check reinforcement and leftover formwork & allow to start concrete work zone 2 | (+62.75) | Grid A/11-12 | A | 2024-11-22
| Sub Structure | 2nd floor | IT/494 | 2024-11-14 | 2024-11-14 | formwork | Check vertical band formwork and allow to start concrete work | (+29.75) | Grid A-B/1 | A | 2024-11-22
| Sub Structure | 5th floor | IT/495 | 2024-11-15 | 2024-11-15 | reinforcement | check formwork and reinforcement slab /beam & allow to start concrete work zone 2 | (+62.75) | Grid A/2-4, A/6-8 | A | 2024-12-02
| Sub Structure | 2nd floor | IT/496 | 2024-11-14 | 2024-11-14 | reinforcement | Check reinforcement and formwork of leftover slab/beam & allow to start concrete work | (+29.75) | Grid A-B/26 | A | 2024-11-22
| Sub Structure | 5th floor | IT/497 | 2024-11-15 | 2024-11-15 | reinforcement | Check vertical band reinforcement and allow for concrete pouring | (+62.75) | Grid A/13-14, A/15-16 | A | 2024-11-18
| Sub Structure | 5th floor | IT/498 | 2024-11-15 | 2024-11-16 | formwork | Check vertical band formwork and allow to start concrete work | (+62.75) | Grid A/15-16 | A | 2024-12-02
| Sub Structure |  | IT/499
| Sub Structure | 9th floor | IT/500 | 2024-11-15 | 2024-11-16 | level | Check screeding level | (+107.0) | B-F/1-10 | B | 2024-11-28
| Sub Structure | 5th floor | IT/501 | 2024-11-16 | 2024-11-16 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+62.75) | Grid A/11-12 | A | 2024-11-18
| Sub Structure | 8th floor | IT/502 | 2024-11-16 | 2024-11-16 | screeding | Check screeding level in apartments and corridor | (+96.0) | Grid B-F/1-4, C-F/4-9, C-F/10-13, C-F/4-13 | A | 2024-12-02
| Sub Structure | 5th floor | IT/503 | 2024-11-16 | 2024-11-16 | screeding | Check vertical band formwork and allow to start concrete work | (+62.75) | Grid A/13-14 | A | 2024-11-22
| Sub Structure | 11th floor | IT/504 | 2024-11-29 | 2024-11-29 | formwork | Check core lift wall formwork and allow to start concrete work | (+146.0) | Grid A-B/17-18 | B | 2024-12-16
| Sub Structure | 8th floor | IT/505 | 2025-11-18 | 2024-11-25 | screeding | Check screeding level in apartments | (+96.0) | Grid A-C/1-9, C-F/8-11 | B | 2024-11-28
| Sub Structure | 8th floor | IT/506 | 2024-11-27 | 2024-11-27 | screeding | Check screeding level in apartments and corridor | (+96.0) | Grid A-F/10-15 | B | 2024-12-02
| Sub Structure | 5th floor | IT/507 | 2024-11-27 | 2024-11-27 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+62.75) | Grid A/2-4, 6-8 | A | 2024-11-28
| Sub Structure | 5th floor | IT/508 | 2024-11-28 | 2024-11-28 | formwork | Check vertical band formwork and allow to start concrete work | (+62.75) | Grid A/11-12 | A | 2024-12-10
| Sub Structure | 8th floor | IT/509 | 2024-11-28 | 2024-11-29 | level | Check level for screeding | (+96.0) | Grid A-F/12-17 | B | 2024-12-10
| Sub Structure | 8th floor | IT/510 | 2024-11-29 | 2024-11-28 | level | Check screeding level in apartment & corridor | (+96.0) | Grid B-F/1-4, C-F/4-9, C-F/10-13, C-F/4-13 | B | 2024-12-10
| Sub Structure | 9th floor | IT/511 | 2024-11-28 | 2024-11-28 | level | Check level for screeding | (+107.0) | Grid A-F/8-13 | B | 2024-12-10
| Sub Structure | 2nd floor | IT/512 | 2024-11-29 | 2024-11-29 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+30.0) | Grid A-B/26 | A | 2024-12-02
| Sub Structure | 3rd floor | IT/513 | 2024-11-30 | 2024-11-30 | reinforcement | Check reinforcement and formwork leftover slab and allow to start concrete work | (+41.0) | Grid A-B/1 | A | 2024-12-10
| Sub Structure | 6th floor | IT/514 | 2024-11-29 | 2024-11-29 | reinforcement | Check reinforcement and formwork of leftover slab & allow to start concrete work | (+73.75) | Grid A/23-25 | A | 2024-12-10
| Sub Structure | 2nd floor | IT/515 | 2024-12-01 | 2024-12-01 | formwork | Chck vertical band formwork and allow to start concrete work | (+30.0) | Grid A-B/26 | A | 2024-12-10
| Sub Structure | 5th floor | IT/516 | 2024-12-01 | 2024-12-01 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid A/6-8 | A | 2024-12-10
| Sub Structure | 5th floor | IT/517 | 2024-12-02 | 2024-12-02 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid A/2-6 | A | 2024-12-10
| Sub Structure | 3rd floor | IT/518 | 2024-12-02 | 2024-12-02 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+41.0) | Grid A-B/1 | A | 2024-12-02
| Sub Structure | 6th floor | IT/519 | 2024-12-02 | 2024-12-02 | reinforcement | Check reinforcement and formwork and allow to start concrete work | (+73.0) | Grid A/19-21 | B | 2024-12-10
| Sub Structure | 8th floor | IT/520 | 2024-12-02 | 2024-12-03 | screeding | check screeding level in apartments | (+96.0) | Grid C-F/10-12 | A | 2024-12-10
| Sub Structure | 6th floor | IT/521 | 2024-12-03 | 2024-12-03 | reinforcement | Check reinforcement and formwork leftover slab & allow to start concrete work | (+73.75) | Grid A/15-16 | A | 2024-12-10
| Sub Structure | 6th floor | IT/522 | 2024-12-03 | 2024-12-03 | reinforcement | Check rienforcement and leftover formwork and allow to start concrete work | (+73.75) | Grid A/13-14 | A | 2024-12-10
| Sub Structure | 6th floor | IT/523 | 2024-12-04 | 2024-12-04 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+73.75) | Grid A/19-25 | A | 2024-12-04
| Sub Structure | 3rd floor | IT/524 | 2024-12-04 | 2024-12-04 | formwork | Check vertical band formwork and allow to start concrete work | (+40.75) | Grid A-B/01 | A | 2024-12-10
| Sub Structure | 9th floor | IT/525 | 2024-12-04 | 2024-12-04 | screeding | Check screeding level in apartment and corridor | (+107.00) | Grid A-F/18-26 | A | 2024-12-10
| Sub Structure | 6th floor | IT/526 | 2024-12-04 | 2024-12-04 | reinforcement | Check rinforcement and formwork slab and allow to start concrete wrok | (+73.75) | Grid A/2-4 | B | 2024-12-10
| Sub Structure | 6th floor | IT/527 | 2024-12-05 | 2024-12-05 | reinforcement | Check reinforcement and formwork of leftover slab & allow to start concrete work | (+73.75) | Grid A/6-8 | A | 2024-12-10
| Sub Structure | 6th floor | IT/528 | 2024-12-05 | 2024-12-05 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+73.75) | Grid A/19-25 | A | 2024-12-05
| Sub Structure | 6th floor | IT/529 | 2024-12-05 | 2024-12-05 | formwork | Check vertical band formwork and allow to start concrete work | (+73.75) | Grid A/23-25 | A | 2024-12-10
| Sub Structure | 6th floor | IT/530 | 2024-12-06 | 2024-12-06 | formwork | Check vertical band formwork and allow to start concrete work | (+73.75) | Grid A/19-21 | B | 2024-12-10
| Sub Structure | 9th floor | IT/531 | 2024-12-06 | 2024-12-06 | screeding | Check screeding level in apartments | (+107.0) | Grid A/16-18, 23-26 | A | 2024-12-10
| Sub Structure | 6th floor | IT/532 | 2024-12-06 | 2024-12-07 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+73.75) | Grid A/13-16 | A | 2024-12-07
| Sub Structure | 9th floor | IT/533 | 2024-12-07 | 2024-12-07 | screeding | check screeding level in apartments | (+107.0) | Grid A-F/12-17 | A | 2024-12-16
| Sub Structure | Mummty floor | IT/534 | 2024-12-07 | 2024-12-07 | column formwork | Check column (2 Nos) and pick column and allow to start concrete |  | Grid A-B/16 | A | 2024-12-16
| Sub Structure | 9th floor | IT/535 | 2024-12-09 | 2024-12-09 | screeding | Check screeding level in apartment | (+107.0) | Grid A-F/18-26 | A | 2024-12-10
| Sub Structure | 9th floor | IT/536 | 2024-12-09 | 2024-12-09 | screeding | Check screeding level in apartment | (+107.0) | Grid A-F/16-18, 23-26 | A | 2024-12-10
| Sub Structure | 6th floor | IT/537 | 2024-12-09 | 2024-12-09 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+73.75) | Grid A/2-8 | A | 2024-12-09
| Sub Structure | 3rd floor | IT/538 | 2024-12-09 | 2024-12-09 | reinforcement | check reinforcement and formwork of leftover slab and allow to start concrete | (+39.75) | Grid A-B/26 | A | 2024-12-16
| Sub Structure | 4th floor | IT/539 | 2024-12-09 | 2024-12-09 | reinforcement | check reinforcement and formwork of leftover slab and allow to start concrete | (+51.75) | Grid A-B/01 | A | 2024-12-16
| Sub Structure | 6th floor | IT/540 | 2024-12-09 | 2024-12-09 | formwork | Check vertical bend formwork and allow to start concrete work | (+73.75) | Grid A/13-16 | A | 2024-12-16
| Sub Structure | top floor | IT/541 | 2024-12-12 | 2024-12-12 | formwork | Check top roof kids pool formwork |  | Grid D-F/15-17 | A | 2025-02-10
| Sub Structure | 6th floor | IT/542 | 2024-12-09 | 2024-12-09 | reinforcement | check rienforcement and formwork of leftover slab & allow to start concrete work | (+73.75) | Grid A/11-12 | A | 2024-12-16
| Sub Structure | 9th floor | IT/543 | 2024-12-09 | 2024-12-09 | screeding | Check level for screeding in apartments | (+107.0) | Grid A-F/10-14 | A | 2024-12-16
| Sub Structure | 4th floor | IT/544 | 2024-12-10 | 2024-12-10 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+51.75) | Grid A-B/01 | A | 2024-12-10
| Sub Structure | 9th floor | IT/545 | 2024-12-10 | 2024-12-10 | screeding | Check screeding level in apartments | (+107.0) | Grid A-F/12-17 | B | 2024-12-16
| Sub Structure | 8th floor | IT/546 | 2024-12-10 | 2024-12-10 | screeding | Check screeding level in apartment | (+96.0) | Grid C-F/10-13 | A | 2024-12-10
| Sub Structure | 6th floor | IT/547 | 2024-12-11 | 2024-12-11 | formwork | Check vertical bend formwork and allow to start concrete | (+73.75) | Grid A/2-8 | A | 2024-12-16
| Sub Structure |  | IT/548
| Sub Structure | 4th floor | IT/549 | 2024-12-11 | 2024-12-11 | formwork | Check vertical bend formwrok and allow to start concrete work | (+51.75) | Grid A-B/1 | A | 2024-12-16
| Sub Structure | 6th floor | IT/550 | 2024-12-12 | 2024-12-12 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+72.75) | Grid A/11-12 | B | 2024-12-16
| Sub Structure | 5th floor | IT/551 | 2024-12-12 | 2024-12-12 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+62.75) | Grid A-B/1 | B | 2024-12-12
| Sub Structure | 6th floor | IT/552 | 2024-12-13 | 2024-12-13 | formwork | Check vertical bend formwork and allow to start concrete work | (+73.75) | Grid A/11-12 | A | 2024-12-19
| Sub Structure | 5th floor | IT/553 | 2024-12-13 | 2024-12-13 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+62.75) | Grid A-B/1 | B | 2024-12-16
| Sub Structure | 5th floor | IT/554 | 2024-12-13 | 2024-12-13 | formwork | Check vertical bend formwork and allow to start concrete work | (+62.75) | Grid A-B/1 | A | 2024-12-19
| Sub Structure | 9th floor | IT/555 | 2024-12-15 | 2024-12-15 | screeding | Check screeding level in apartment | (+107.0) | Grid A-F/10-14 | B | 2024-12-16
| Sub Structure | 7th floor | IT/556 | 2024-12-15 | 2024-12-15 | reinforcement | check reinforcement and formwork of leftover slab and allow to start concrete | (+84.75) | Grid A/2-4, 11-12 | A | 2024-12-16
| Sub Structure | 7th floor | IT/557 | 2024-12-15 | 2024-12-15 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete work | (+84.75) | Grid A/6-8 | A | 2024-12-19
| Sub Structure | 6th floor | IT/558 | 2024-12-15 | 2024-12-15 | reinforcement | check rienforcement and formwork of leftover slab & allow to start concrete work | (+74.75) | Grid A-B/1 | A | 2024-12-16
| Sub Structure | 6th floor | IT/559 | 2024-12-16 | 2024-12-16 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+73.75) | Grid A-B/1 | A | 2024-12-16
| Sub Structure | 6th floor | IT/560 | 2024-12-17 | 2024-12-17 | formwork | Check vertical band formwork and allow to start concrete work | (+73.75) | Grid A-B/1 | A | 2024-12-19
| Sub Structure | 7th floor | IT/561 | 2024-12-16 | 2024-12-16 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+84.75) | Grid A/2-8 | A | 2024-12-16
| Sub Structure | top roof mummty | IT/562 | 2024-12-17 | 2024-12-17 | formwork | check formwork of slab & allow to start concrete work | (+159.0) | Grid A-B/15-19 | B | 2024-12-31
| Sub Structure | 7th floor | IT/563 | 2024-12-17 | 2024-12-18 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+84.75) | Grid A/11-12 | A | 2024-12-23
| Sub Structure | top floor | IT/564 | 2025-01-13 | 2025-01-13 | plaster work | Check plaster work on external sides | (+19.0 to +148.5) | Grid F/11-16 | A | 2025-01-19
| Sub Structure | top floor | IT/564 R03 | 2025-06-28 | 2025-06-28 | plaster work | Check plaster work on external sides | (+19.0 to +148.5) | Grid F/11-16 | R | 2025-06-28
|  | top floor | IT/564 R04 | 2025-06-30 | 2025-06-30 | plaster work | Check plaster work on external sides | (+19.0 to +148.5) | Grid F/11-16 | A | 2025-07-07
| Sub Structure | 7th floor | IT/565 | 2024-12-17 | 2024-12-17 | formwork | Check vertical bend formwork and allow to start concrete work | (+84.75) | Grid A/2-4 | A | 2024-12-23
| Sub Structure | 7th floor | IT/566 | 2024-12-18 | 2024-12-18 | formwork | Check vertical bend formwork and allow to start concrete | (+84.75) | Grid A/11-12 | A | 2024-12-23
| Sub Structure | 7th floor | IT/567 | 2024-12-18 | 2024-12-18 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete work | (+84.75) | Grid A/13-16 | A | 2024-12-23
| Sub Structure | 7th floor | IT/568 | 2024-12-18 | 2024-12-18 | reinforcement | Check reinforcement and formwork of leftover slab & allow to start concrete work | (+84.75) | Grid A-B/1 | R | 2024-12-23
| Sub Structure | 7th floor | IT/569 | 2024-12-19 | 2024-12-18 | reinforcement | check vertical bend rienforcement and allow to start formwork | (+84.75) | Grid A/6-8 | R | 2024-12-19
| Sub Structure | 3rd floor | IT/570 | 2024-12-19 | 2024-12-19 | reinforcement | check vertical bend rienforcement and allow to start formwork | (+40.75) | Grid A-B/26 | A | 2024-12-23
| Sub Structure | 7th floor | IT/571 | 2024-12-19 | 2024-12-19 | reinforcement | Check vertical bend reinforcement and allow to start formowrk | (+84.75) | Grid A/13-14 | A | 2024-12-23
| Sub Structure | 7th floor | IT/572 | 2024-12-21 | 2024-12-21 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+84.75) | Grid A/15-16 | A | 2024-12-23
| Sub Structure | 7th floor | IT/573 | 2024-12-19 | 2024-12-19 | reinforcement | check vertical bend rienforcement and allow to start formwork | (+84.75) | Grid A-B/1 | A | 2024-12-23
| Sub Structure | 7th floor | IT/574 | 2024-12-19 | 2024-12-19 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+84.75) | Grid A/19-21 | A | 2024-12-23
| Sub Structure | 7th flor | IT/575 | 2024-12-19 | 2024-12-20 | reinforcement | Check reinforcement and formwork of leftover slab & allow to start concre work | (+84.75) | Grid A/23-25 | A | 2024-12-23
| Sub Structure | 7th floor | IT/576 | 2024-12-19 | 2024-12-20 | formwork | Check formwork of vertical bend and allow to start concrete work | (+84.75) | Grid A/6-8, 13-14 | A | 2024-12-23
| Sub Structure | 7th floor | IT/577 | 2024-12-19 | 2024-12-20 | formwork | Check vertical bend formwork and allow to start concrete work | (+84.75) | Grid A-B/1 | A | 2024-12-23
| Sub Structure | 1st to 2nd floor | IT/578 | 2024-12-20 | 2024-12-20 | plaster work | Check plumb points and allwo for plaster work on internal sides of façade | (+19.0) | Grid U/15-16 | R | 2024-12-23
| Sub Structure |  | IT/579
| Sub Structure | 1st floor | IT/580 | 2025-01-01 | 2025-01-01 | brick work | Check brick work on internal side of façade work | (+19.0) | Grid A-F/2-25 | A | 2025-01-18
| Sub Structure | 7th floor | IT/581 | 2024-12-21 | 2024-12-21 | formwork | Check vertical bend formwork and allow to start concrete work | (+84.75) | Grid a/15-16 | A | 2024-12-23
| Sub Structure | 7th floor | IT/582 | 2024-12-21 | 2024-12-21 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+84.75) | Grid A/23-25 | A | 2024-12-23
| Sub Structure | 8th floor | IT/583 | 2024-12-21 | 2024-12-21 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+95.75) | Grid A-B/1 | A | 2024-12-23
| Sub Structure | 8th floor | IT/584 | 2024-12-23 | 2024-12-23 | reinforcement | Check vertical bend rienforcement and allow to start formwork | (+95.75) | Grid A-B/1 | A | 2024-12-24
| Sub Structure | 7th floor | IT/585 | 2024-12-23 | 2024-12-23 | reinforcement | check vertical bend reinforcement and allow to start formwork | (+84.75) | Grid A/19-21 | A | 2024-12-24
| Sub Structure | 7th floor | IT/586 | 2024-12-23 | 2024-12-23 | formwork | Check vertical bend formwork and allow to start concrete work | (+84.75) | Grid A/23-25 | A | 2024-12-31
| Sub Structure | 7th floor | IT/587 | 2024-12-23 | 2024-12-24 | formwork | check vertical bend formwork and allow to start concrete work | (+84.75) | Grid A/19-21 | A | 2024-12-31
| Sub Structure | 8th floor | IT/588 | 2024-12-21 | 2024-12-21 | reinforcement | Check rienforcement and formwork of bottom nib of horizontal band & allow to start concrete work zone 1 & 2 | (+96.0) | Grid A/2-4, A/11-12 | A | 2024-12-31
| Sub Structure | 8th floor | IT/589 | 2024-12-24 | 2024-12-24 | formwork | Check vertical bend formwork and allow to start concrete work | (+96.75) | Grid A-B/1 | B | 2024-12-31
| Sub Structure | 8th floor | IT/590 | 2024-12-25 | 2024-12-25 | formwork | Check reinforcement and formwork of leftover slab and allow to start concrete work | (+95.75) | Grid A/2-4, 11-12 | A | 2025-01-02
| Sub Structure | GF | IT/591 | 2024-12-26 | 2024-12-26 | formwork | Check ramp wall formwork and allow to start concrete work |  | Grid A/9-10, 17-18 | A | 2024-12-31
| Sub Structure | 3rd floor | IT/592 | 2024-12-27 | 2024-12-27 | formwork | Check vertical bend formwork and allow to start concrete work | (+41.75) | Grid A-B/26 | A | 2024-12-31
| Sub Structure | 9th floor | IT/593 | 2024-12-27 | 2024-12-27 | formwork | Check reinforcement and formwork of leftover slab and allow to start concrete | (+106.75) | Grid A-B/1 | A | 2024-12-31
| Sub Structure | 8th floor | IT/594 | 2024-12-27 | 2024-12-27 | formwork | Check reinforcement and formwork of nib beam and allow to start concrete | (+95.75) | Grid U/6-8,13-14,15-16 | A | 2024-12-31
| Sub Structure | 8th floor | IT/595 | 2024-12-28 | 2024-12-28 | reinforcement | Check vertical bend reinforcement and allow to startformwork | (+96.0) | Grid A/2-4 | A | 2024-12-31
| Sub Structure | 8th floor | IT/596 | 2024-12-28 | 2024-12-28 | formwork | Check vertical bend formwork and allow to start concrete work | (+95.75) | Grid A/2-4 | B | 2025-01-05
| Sub Structure | 9th floor | IT/597 | 2024-12-28 | 2024-12-28 | reinforcement | Check vertical bend rienforcement and allow to start formwork | (+107.0) | Grid A-B/1 | A | 2024-12-31
| Sub Structure | 9th floor | IT/598 | 2024-12-29 | 2024-12-29 | formwork | Check vertical band formwork and allow to start concrete | (+107.0) | Grid A-B/1 | A | 2025-01-07
| Sub Structure | 8th floor | IT/599 | 2024-12-30 | 2024-12-30 | formwork | Check vertical bend formwork and allow to start concrete work | (+96.0) | Grid A/11-12 | A | 2025-01-07
| Sub Structure | 8th floor | IT/600 | 2024-12-30 | 2024-12-30 | reinforcement | check rienforcement and formwork of leftover slab and allow to start concrete | (+96.0) | Grid A/6-8 | A | 2025-01-02
| Sub Structure | 8th floor | IT/601 | 2024-12-31 | 2024-12-31 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+96.0) | Grid A/13-14 | A | 2025-01-02
| Sub Structure | 8th floor | IT/602 | 2024-12-31 | 2024-12-31 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+96.0) | Grid A/15-16 | A | 2025-01-07
| Sub Structure | 8th floor | IT/603 | 2024-12-31 | 2024-12-31 | reinforcement | Check reinforcement and formwork of nib beam and allow to start concrete | (+95.75) | Grid A/19-21, 23-25 | A | 2025-01-02
| Sub Structure | Top floor | IT/604 | 2024-12-31 | 2024-12-31 | formwork | Check parapet wall formwork and allow to start concrete work | (+146.0) | Grid A/1-8 | B | 2025-01-07
| Sub Structure | 2nd floor | IT/605 | 2025-01-01 | 2025-01-01 | brick work | Check brick work on internal side of façade work | (+30.0) | Grid A-F/2-25 | A | 2025-01-18
| Sub Structure | 9th floor | IT/606 | 2025-01-01 | 2025-01-02 | reinforcement | Check rienforcement and formwork of leftover slab & allow to start concrete work | (+107.0) | Grid A/2-4,11-12 | B | 2025-01-03
| Sub Structure | 9th floor | IT/607 | 2025-01-01 | 2025-01-02 | reinforcement | Check vertical bend rienforcement and allow to start formwork | (+107.0) | Grid A/6-8 | R | 2025-01-02
| Sub Structure | 8th floor | IT/608 | 2025-01-02 | 2025-01-02 | formwork | Check vertical band formwork and allow to start concrete work | (+96.0) | Grid A/6-8 | A | 2025-01-07
| Sub Structure | 10th floor | IT/609 | 2025-01-03 | 2025-01-03 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+118.0) | Grid A-B/1 | A | 2025-01-07
| Sub Structure | 4th floor | IT/610 | 2025-01-07 | 2025-01-07 | reinforcement | check rienforcement and formwork of leftover slab and allow to start concrete | (+52.0) | Grid A-B/26 | B | 2025-01-11
| Sub Structure | 8th floor | IT/611 | 2025-01-02 | 2025-01-02 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+96.0) | Grid A/13-14 | A | 2025-01-03
| Sub Structure | 8th floor | IT/612 | 2025-01-03 | 2025-01-03 | formwork | Check vertical band formwork and allow to start concrete wrok | (+96.0) | Grid A/13-14 | A | 2025-01-11
| Sub Structure | 8th floor | IT/613 | 2025-01-03 | 2025-01-03 | reinforcement | Check vertical bend reinforcement and allow to start formwork | (+96.0) | Grid A/15-16 | A | 2025-01-05
| Sub Structure | 10th floor | IT/614 | 2025-01-03 | 2025-01-03 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+118.0) | Grid A-B/1 | A | 2025-01-05
| Sub Structure | 8th floor | IT/615 | 2025-01-03 | 2025-01-03 | formwork | Check vertical band formwork and allow to start concrete work | (+96.0) | Grid A/15-16 | A | 2025-01-11
| Sub Structure | 8th floor | IT/616 | 2025-01-03 | 2025-01-03 | reinforcement | check rienforcement and formwork of leftover slab and allow to start concrete | (+96.0) | Grid A/19-21 | A | 2025-01-11
| Sub Structure | 8th floor | IT/617 | 2025-01-06 | 2025-01-06 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+96.0) | Grid A/23-25 | A | 2025-01-11
| Sub Structure | Mummty floor | IT/618 | 2024-12-29 | 2024-12-29 | formwork | Check beam formwork and allow to start concrete | (+159.0) | Grid A-B/15-19 | B | 2024-12-30
| Sub Structure | top floor | IT/619 | 2024-12-31 | 2024-12-31 | formwork | Check parapet wall formwork and allow to start concrete work | (+146.0) | Grid A-C/1 | B | 2025-01-07
| Sub Structure | 9th floor | IT/620 | 2025-01-05 | 2025-01-05 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+107.0) | Grid A/6-8 | B | 2025-01-17
| Sub Structure | 9th floor | IT/621 | 2025-01-07 | 2025-01-07 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+107.0) | Grid A/11-12 | B | 2025-01-09
| Sub Structure | 9th floor | IT/622 | 2025-01-06 | 2025-01-06 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+107.0) | Grid A/13-14 | A | 2025-01-11
| Sub Structure | 9th floor | IT/623 | 2025-01-07 | 2025-01-07 | formwork | Check vertical band formwork and allow to start concrete | (+107.0) | Grid A/11-12 | B | 2025-01-11
| Sub Structure | 10th floor | IT/624 | 2025-01-07 | 2025-01-07 | formwork | Check vertical band formwork and allow to start concrete | (+118.0) | Grid A-B/1 | A | 2025-01-11
| Sub Structure | 8th floor | IT/625 | 2025-01-07 | 2025-01-08 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+96.0) | Grid A/19-21 | A | 2025-01-09
| Sub Structure | 9th floor | IT/626 | 2025-01-07 | 2025-01-08 | reinforcement | Check leftover slab rienforcement and formwork and allow to start concrete work | (+107.0) | Grid A/15-16 | A | 2025-01-11
| Sub Structure | 5th floor | IT/627 | 2025-01-07 | 2025-01-07 | reinforcement | check reinforcement and formwork of beam and allow to start concrete | (+63.0) | Grid F/12-13 | B | 2025-01-11
| Sub Structure | 8th floor | IT/628 | 2025-01-08 | 2025-01-08 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+96.0) | Grid A/23-25 | B | 2025-01-15
| Sub Structure | 8th floor | IT/629 | 2025-01-09 | 2025-01-09 | formwork | Check vertical band formwork and allow to start concrete work | (+96.0) | Grid A/19-21 | A | 2025-01-17
| Sub Structure | 9th floor | IT/630 | 2025-01-09 | 2025-01-09 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+107.0) | Grid A/2-4 | A | 2025-01-09
| Sub Structure | 10th floor | IT/631 | 2025-01-10 | 2025-01-11 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+118.0) | Grid A/11-12 | A | 2025-01-17
| Sub Structure | 8th floor | IT/632 | 2025-01-10 | 2025-01-11 | formwork | Check vertical band formwork and allow to start concrete | (+96.0) | Grid A/23-25 | B | 2025-01-17
| Sub Structure | 9th floor | IT/633 | 2025-01-10 | 2025-01-10 | formwrok | Check vertical band formwrok and allow to start concrete | (+107.0) | Grid A/2-4 | B | 2025-01-17
| Sub Structure | 9th floor | IT/634 | 2025-01-14 | 2025-01-14 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+107.0) | Grid A/6-8 | A | 2025-01-15
| Sub Structure | 5th floor | IT/635 | 2025-01-11 | 2025-01-11 | reinforcement | check reinforcement and formwork of beam and allow for concrete pouring | (+63.0) | Grid F/14-15 | B | 2025-01-22
| Sub Structure | 9th floor | IT/636 | 2025-01-14 | 2025-01-14 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+107.0) | Grid A/13-14 | B | 2025-01-17
| Sub Structure | 9th floor | IT/637 | 2025-01-14 | 2025-01-14 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+107.0) | Grid A/19-21 | A | 2025-01-17
| Sub Structure | Top floor | IT/638 | 2025-01-14 | 2025-01-14 | formwork | Check genertator pad formwork and allow to start concrete work | (+146.0) | Grid A-B/1-8 | A | 2025-02-10
| Sub Structure | 10th flooor | IT/639 | 2025-01-13 | 2025-01-13 | formwork | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid A/6-8 | B | 2025-01-17
| Sub Structure | 10th floor | IT/640 | 2025-01-15 | 2025-01-15 | formwork | Check reinforcement and formwork of leftover slab and allow to start concrete | (+118.0) | Grid A/2-4 | B | 2025-01-17
| Sub Structure | 11th floor | IT/641 | 2025-01-15 | 2025-01-15 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+131.0) | Grid A-B/1 | A | 2025-01-22
| Sub Structure | 4th floor | IT/642 | 2025-01-15 | 2025-01-15 | reinforcement | Check rienforcement and formwork of leftover slab and allow to start concrete | (+52.0) | Grid A-B/26 | A | 2025-01-15
| Sub Structure | 9th floor | IT/643 | 2025-01-15 | 2025-01-16 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+107.0) | Grid A/15-16 | A | 2025-01-17
| Sub Structure | 9th floor | IT/644 | 2025-01-17 | 2025-01-17 | formwork | Check vertical band formwork and allow to start concrete work | (+107.0) | Grid A/15-16 | A | 2025-01-22
| Sub Structure | 10th floor | IT/645 | 2025-01-18 | 2025-01-18 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+118.0) | Grid A/19-21 | A | 2025-01-19
| Sub Structure | 10th floor | IT/646 | 2025-01-18 | 2025-01-18 | formwork | Check slab leftover formwork and allow to start concrete work | (+118.0) | Grid A/6-8 | A | 2025-01-22
| Sub Structure | 1st floor to top floor | IT/647 | 2025-01-18 | 2025-01-18 | plaster work | Check plaster work on external side | (+19.0 to +146.0) | Grid F/17-21 | A | 2025-01-19
| Sub Structure | 1st floor to top floor | IT/647 R01 | 2025-06-28 | 2025-06-28 | plaster work | Check plaster work on external side | (+19.0 to +146.0) | Grid F/17-21 | R | 2025-06-28
|  | 1st floor to top floor | IT/647 R02 | 2025-06-30 | 2025-06-30 | plaster work | Check plaster work on external side | (+19.0 to +146.0) | Grid F/17-21 | A | 2025-07-07
| Sub Structure | 10th floor | IT/648 | 2025-01-19 | 2025-01-19 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+118.0) | Grid A/23-25 | A | 2025-01-22
| Sub Structure | top floor | IT/649 | 2025-02-07 | 2025-02-07 | formwork | Check ramp slab formwork and allow to start concrete work |  | Grid C/10-12 | A | 2025-02-08
| Sub Structure |  | IT/650 | 2025-01-20 | 2025-01-20 | formwork | Check lift wall & allow to start concrete Mummty level |  | Grid A/9-10 | B | 2025-01-22
| Sub Structure | 11th floor | IT/651 | 2025-01-21 | 2025-01-21 | formwork | Check vertical band formwork and allow to start concrete work |  | Grid A-B/1 | A | 2025-01-29
| Sub Structure | 9th floor | IT/652 | 2025-01-22 | 2025-01-22 | formwork | Check vertical band formwork and allow to start concrete work | (+107.0) | Grid A/19-21 | B | 2025-01-29
| Sub Structure | 4th floor | IT/653 | 2025-01-22 | 2025-01-22 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid A-B/26 | A | 2025-01-29
| Sub Structure | 10th floor | IT/654 | 2025-01-22 | 2025-01-22 | reinforcement | Check reinforcement and formwork of leftover slab & allow to start concrete work | (+118.0) | Grid A/13-14, 15-16 | A | 2025-01-29
| Sub Structure | 10th floor | IT/655 | 2025-01-22 | 2025-01-23 | reinforcement | check vertical band rienforcement and allow to start formwork | (+118.0) | Grid A/6-8 | A | 2025-01-24
| Sub Structure | 10th floor | IT/656 | 2025-01-27 | 2025-01-27 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+118.0) | Grid A/2-4 | A | 2025-01-28
| Sub Structure | 9th floor | IT/657 | 2025-01-24 | 2025-01-24 | formwork | Check vertical band formwork and allow to start concrete work | (+107.0) | Grid A/23-25 | A | 2025-02-05
| Sub Structure | top floor | IT/658 | 2025-01-24 | 2025-01-24 | formwork | Check over head water tank formwork |  | Grid A-B/18-19 | A | 2025-02-08
| Sub Structure | 10th floor | IT/659 | 2025-01-25 | 2025-01-25 | formwork | Check leftover slab formwork & allow to start concrete work | (+118.0) | Grid A/19-21 | A | 2025-02-05
| Sub Structure | top floor | IT/660 | 2025-01-25 | 2025-01-25 | formwork | Check lift slab formwork at mummty level |  | Grid A/9-10 | A | 2025-02-10
| Sub Structure | 10th floor | IT/661 | 2025-01-27 | 2025-01-27 | formwork | Check vertical band formwork and allow to start concrete work | (+131.0) | Grid A/6-8 | A | 2025-02-05
| Sub Structure | 10th floor | IT/662 | 2025-01-27 | 2025-01-27 | formwork | Check vertical band formwrok and allow to start concrete work | (+131.0) | Grid A/11-12 | A | 2025-02-05
| Sub Structure | 10th floor | IT/663 | 2025-01-27 | 2025-01-27 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid A/19-21, 23-25 | A | 2025-02-05
| Sub Structure | 10th floor | IT/664 | 2025-01-27 | 2025-01-27 | reinforcement | Check vertical band rienforcement and allow for concrete pouring | (+131.0) | Grid A/13-14, 15-16 | A | 2025-01-29
| Sub Structure | Mummty floor | IT/665 | 2025-01-28 | 2025-01-28 | formwork | Check lift wall formwork and allow to start concrete |  | Grid A/17-18 | B | 2025-01-31
| Sub Structure | 10th floor | IT/666 | 2025-01-29 | 2025-01-29 | formwork | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid A/2-4 | A | 2025-02-05
| Sub Structure | 10th floor | IT/667 | 2025-01-30 | 2025-01-30 | formwork | Check vertical band formwork and allow to start concrete | (+118.0) | Grid A/13-14 | A | 2025-02-08
| Sub Structure | 10th floor | IT/668 | 2025-01-31 | 2025-01-31 | formwork | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid A/15-16 | A | 2025-02-08
| Sub Structure | 10th floor | IT/669 | 2025-01-31 | 2025-02-01 | formwork | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid A/19-21 | A | 2025-02-08
| Sub Structure | 10th floor | IT/670 | 2025-02-03 | 2025-02-01 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+118.0) | Grid A/23-25 | A | 2025-02-03
| Sub Structure | 11th floor | IT/671 | 2025-02-01 | 2025-02-01 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid A/6-8 | A | 2025-02-08
| Sub Structure | 10th floor | IT/672 | 2025-02-03 | 2025-02-03 | formwork | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid A/23-25 | A | 2025-02-08
| Sub Structure | 5th floor | IT/673 | 2025-02-04 | 2025-02-04 | formwrok | Check nib formwork and allow to start concrete | (+63.0) | Grid A-B/26 | A | 2025-02-08
| Sub Structure | 5th floor | IT/674 | 2025-02-04 | 2025-02-04 | formwork | Check nib formwork and allow to start concrete | (+63.0) | Grid F/8-9 | A | 2025-02-08
| Sub Structure | 5th floor | IT/675 | 2025-02-04 | 2025-02-04 | formwork | Check leftover slab formwork and allow to start concrete work | (+63.0) | Grid A-B/26 | A | 2025-02-19
| Sub Structure | 11th floor | IT/676 | 2025-02-05 | 2025-02-05 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid A/2-4 | A | 2025-02-19
| Sub Structure | 11th floor | IT/677 | 2025-02-05 | 2025-02-05 | formwork | Check leftover slab formwrok and allow to start concrete work | (+131.0) | Grid A/13-14 | A | 2025-02-19
| Sub Structure | 11th floor | IT/678 | 2025-02-06 | 2025-02-06 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+131.0) | Grid A/6-8 | A | 2025-02-08
| Sub Structure | 11th floor | IT/679 | 2025-02-07 | 2025-02-07 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid A/11-12, 15-16 | A | 2025-02-07
| Sub Structure | 11th floor | IT/680 | 2025-02-07 | 2025-02-07 | formwork | Check vertical band formwork and allow to start concrete work | (+131.0) | Grid A/6-8 | A | 2025-02-19
| Sub Structure | 11th floor | IT/681 | 2025-02-08 | 2025-02-08 | reinforcement | check vertical band reinforcement and allow for concrete pouring | (+131.0) | Grid A/2-4, 13-14 | B | 2025-02-13
| Sub Structure | 11th floor | IT/682 | 2025-02-08 | 2025-02-08 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid A/19-21 | A | 2025-02-19
| Sub Structure | 11th floor | IT/683 | 2025-02-10 | 2025-02-11 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid a/23-25 | A | 2025-02-19
| Sub Structure | 11th floor | IT/684 | 2025-02-10 | 2025-02-10 | reinforcement | Check vertical band reinforcement and allow for concrete pouring | (+131.0) | Grid A/15-16 | B | 2025-02-13
| Sub Structure | 11th floor | IT/685 | 2025-02-10 | 2025-02-10 | formwork | Check vertical band fomwrok and allow to start concrete work | (+131.0) | Grid A/13-14 | A | 2025-02-19
| Sub Structure | 11th floor | IT/686 | 2025-02-10 | 2025-02-10 | formwrok | Check vertical band formwork and allow to start concrete work | (+131.0) | Grid A/2-4 | A | 2025-02-19
| Sub Structure | Top floor | IT/687 | 2025-04-13 | 2025-04-13 | formwork | Check head water tank formwork |  | Grid A-B/8-9 | A | 2025-04-16
| Sub Structure | top floor | IT/688 | 2025-02-10 | 2025-02-10 | formwork | Check lift slab formwork at roof mummty level |  | Grid A/17-18 | A | 2025-02-13
| Sub Structure | Top floor | IT/689 | 2025-02-10 | 2025-02-10 | formwork | Check parapet wall formwork and allow to start concrete work |  | Grid A/9-10 | A | 2025-02-11
| Sub Structure | top floor | IT/690 | 2025-02-11 | 2025-02-11 | formwork | Check parapet wall formwork and allow to start concrete work |  | Grid B/16-19 | A | 2025-02-13
| Sub Structure | 11th floor | IT/691 | 2025-02-13 | 2025-02-13 | reinforcement | Check vertical band reinforcement and allow to start formwrok |  | Grid A/11-12 | A | 2025-02-13
| Sub Structure | 11th floor | IT/692 | 2025-02-12 | 2025-02-12 | formwork | Check vertical band formwrok and allow to start concrete work |  | Grid A/15-16 | A | 2025-02-19
| Sub Structure | 11th floor | IT/693 | 2025-02-12 | 2025-02-12 | formwork | Check vertical band formwork and allow to start concrete work |  | Grid A/11-12 | A | 2025-02-19
| Sub Structure | 11th floor | IT/694 | 2025-02-13 | 2025-02-13 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+131.0) | Grid A/19-21 | A | 2025-02-19
| Sub Structure | top floor | IT/695 | 2025-02-13 | 2025-02-13 | formwork | Check vertical band formwork and allow to start concrete work | (+131.0) | Grid A/19-21
| Sub Structure | top floor | IT/696
| Sub Structure | 11th floor | IT/697 | 2025-02-17 | 2025-02-17 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+130.0) | Grid A/23-25 | A | 2025-02-19
| Sub Structure | 5th floor | IT/698 | 2025-02-14 | 2025-02-14 | reinforcement | check vertical bends reinforcement and allow for formwrok | (+63.0) | Grid A-B/26 | A | 2025-02-19
| Sub Structure | 11th floor | IT/699 | 2025-02-14 | 2025-02-14 | formwork | Check vertical band formwork and allow to start concrete work | (+130.75) | Grid A/19-21 | A | 2025-02-14
| Sub Structure | top floor | IT/700
| Sub Structure | Top floor | IT/701 | 2025-02-15 | 2025-02-15 | reinforcement | Check reinforcement and formwork of balcony slabs & beam and allow to start concrete | (+145.75) | Grid A-E/1 | A | 2025-02-19
| Sub Structure | 11th floor | IT/702 | 2025-02-16 | 2025-02-17 | formwork | Check vertical band formwork and allow to start concrete work | (+130.75) | Grid A/23-25 | A | 2025-02-19
| Sub Structure | top floor | IT/703 | 2025-02-19 | 2025-02-19 | formwork | Check beam formwork and allow to start concrete work | (+145.75) | Grid A-E/1, | A | 2025-02-27
| Sub Structure | Ground floor | IT/704 | 2025-02-22 | 2025-02-22 | formwrok | Check ramp wall formwork and allow to start concrete work |  | Grid F/7-8,12-13,14-15,19-21,22-24 | A | 2025-02-27
| Sub Structure | Top floor | IT/705 | 2025-02-21 | 2025-02-21 | reinforcement | check reinforcement and formwork of leftover slab and beam, and allow to start concrete |  | Grid A/2-8 | A | 2025-02-27
| Sub Structure | 5th floor | IT/706 | 2025-02-24 | 2025-02-24 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid A-B/26 | A | 2025-03-03
| Sub Structure | Top floor | IT/707 | 2025-02-28 | 2025-02-28 | reinforcement | Check reinforcement and formwork of parapet wall and allow to start concrete work |  | Grid A/2-8 | A | 2025-03-03
| Sub Structure | 6th floor | IT/708 | 2025-03-01 | 2025-03-01 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete work | (+74.0) | Grid A-B/26 | A | 2025-03-04
| Sub Structure | 3rd floor | IT/709 | 2025-03-03 | 2025-03-03 | brick wrok | Check brick work on internal sides of façade work | (+41.0) | Grid A-F/2-25 | A | 2025-03-12
| Sub Structure | 4th floor | IT/710 | 2025-03-03 | 2025-03-03 | brick wrok | Check brick work on internal sides of façade work | (+52.0) | Grid A-F/2-25 | A | 2025-03-12
| Sub Structure | 5th floor | IT/711 | 2025-03-03 | 2025-03-03 | brick wrok | Check brick work on internal sides of façade work | (+63.0) | Grid A-F/2-25 | A | 2025-03-13
| Sub Structure | 6th floor | IT/712 | 2025-03-04 | 2025-03-04 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+74.0) | Grid A-B/26 | A | 2025-03-06
| Sub Structure | 6th floor | IT/713 | 2025-03-05 | 2025-03-06 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid A-B/26 | A | 2025-03-12
| Sub Structure | Top floor | IT/714 | 2025-03-05 | 2025-03-05 | reinforcement | check reinforcement and formwork of leftover slab and beam and allow to start concrete |  | Grid A/13-16 | A | 2025-03-12
| Sub Structure | Top floor | IT/715 | 2025-03-06 | 2025-03-07 | reinforcement | check reinforcement and formwork of leftover slab and beam and allow to start concrete |  | Grid A/11-13 | A | 2025-03-12
| Sub Structure | 7th floor | IT/716 | 2025-03-07 | 2025-03-08 | formwork | Check leftover slab formwork and allow to start concrete work | (+85.0) | Grid A-B/26 | A | 2025-03-12
| Sub Structure | Top floor | IT/717 | 2025-03-10 | 2025-03-10 | reinforcement | Check reinforcement and leftover slab and beam and allow to start concrete work |  | Grid A/19-23 | A | 2025-03-13
| Sub Structure | Top floor | IT/718 | 2025-03-08 | 2025-03-10 | reinforcement | Check reinforcement and formwork of horizontal band, allow to start concrete work |  | Grid A/13-16 | A | 2025-03-13
| Sub Structure | 7th floor | IT/719 | 2025-03-10 | 2025-03-10 | reinforcement | Check vertical band reinforcement and allow to start formwork |  | Grid A-B/26 | A | 2026-03-12
| Sub Structure | 7th floor | IT/720 | 2025-03-10 | 2025-03-10 | formwork | Check vertical band formwork and allow to start concrete work |  | Grid A-B/26 | A | 2025-03-13
| Sub Structure | Ground floor | IT/721 | 2025-03-12 | 2025-03-13 | formwork | Check ramp wall formwork |  | Grid A-B/11-12, 15-16 | A | 2025-03-15
| Sub Structure | Top floor | IT/722 | 2025-03-13 | 2025-03-13 | reinforcement | Check reinforcement and formwork of horizontal band, allow to start concrete work |  | Grid A/11-13 | A | 2025-03-15
| Sub Structure | 8th floor | IT/723 | 2025-03-13 | 2025-03-14 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete work |  | Grid A-B/26 | A | 2025-03-19
| Sub Structure | Top floor | IT/724 | 2025-03-14 | 2025-03-15 | reinforcement | check reinforcement and formwrok of horizontal band allow to start concrete |  | Grid A/19-23 | A | 2025-03-21
| Sub Structure | 8th floor | IT/725 | 2025-03-17 | 2025-03-17 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+96.0) | Grid A-B/26 | A | 2025-03-19
| Sub Structure | 8th floor | IT/726 | 2025-03-17 | 2025-03-17 | formwork | Check vertical band formwork and allow to start concrete | (+96.0) | Grid A-B/26 | A | 2025-03-19
| Sub Structure | Ground floor | IT/727 | 2025-03-17 | 2025-03-17 | level | Check level poihnts screed |  | Grid B-F/12-16 | A | 2025-03-24
| Sub Structure | 9th floor | IT/728 | 2025-03-18 | 2025-03-18 | formwork | Check slab leftover formwork and allow to start concrete work | (+107.0) | Grid A-B/26 | A | 2025-03-21
| Sub Structure | 9th floor | IT/729 | 2025-03-18 | 2025-03-19 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+107.0) | Grid A-B/26 | A | 2025-03-22
| Sub Structure | 9th floor | IT/730 | 2025-03-19 | 2025-03-19 | formwork | Check vertical band formwork and allow to start concrete work | (+107.0) | Grid A-B/26 | A | 2025-03-22
| Sub Structure | 10th floor | IT/731 | 2025-03-21 | 2025-03-21 | formwork | Check leftover slab formwork and allow to start concrete work | (+118.0) | Grid A-B/26 | A | 2025-03-24
| Sub Structure | 10th floor | IT/732 | 2025-03-22 | 2025-03-24 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+118.0) | Grid A-B/26 | A | 2025-03-24
| Sub Structure | 10th floor | IT/733 | 2025-03-22 | 2025-03-24 | formwork | Check vertical band formwork and allow to start concrete work | (+118.0) | Grid A-B/26 | A | 2025-03-24
| Sub Structure | 8th floor | IT/734 | 2025-03-25 | 2025-03-26 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete work | (+96.0) | Grid A-C/1 | A | 2025-04-08
| Sub Structure | 11th floor | IT/735 | 2025-03-24 | 2025-03-25 | formwork | Check leftover slab formwork and allow to start concrete work | (+146.0) | Grid A-B/26 | A | 2025-04-14
| Sub Structure | 11th floor | IT/736 | 2025-03-26 | 2025-03-27 | formwork | Check vertical band formwork and allow to start concrete work | (+131.00) | Grid A-B/26 | A | 2025-04-14
| Sub Structure | 11th floor | IT/737 | 2025-03-26 | 2025-03-27 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+131.0) | Grid A-B/26 | A | 2025-03-27
| Sub Structure | Ground floor | IT/738 | 2025-03-26 | 2025-03-26 | level | Check level points for screeding in ground floor |  | Grid B-F/9-13 | A | 2025-04-08
| Sub Structure | 5th floor | IT/739 | 2025-03-27 | 2025-03-28 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete work | (+63.0) | Grid A-C/1 | A | 2025-04-16
| Sub Structure | 2nd floor | IT/740 | 2025-03-27 | 2025-03-27 | level | Check screed level | (+0.0) | Grid B-F/9-12 | A | 2025-04-08
| Sub Structure | Top floor | IT/741 | 2025-04-17 | 2025-04-17 | formwork | Check over head water tank wall formwork |  | Grid A-B/18-19 | A | 2025-04-22
| Sub Structure | 1st to floor to top | IT/742 | 2025-04-14 | 2025-04-14 | plaster work | Check external façade plaster work | (+19.0 to +146.0) | Grid A-E/1 | A | 2025-04-24
| Sub Structure | 10th floor | IT/743 | 2025-04-14 | 2025-04-14 | brick work | Check demolish brick work for tie column | (+118.0) | Grid A-F/1-26 | A | 2025-04-19
| Sub Structure | 11th floor | IT/744 | 2025-04-14 | 2025-04-14 | brick work | Check demolish brick work for tie column | (+131.0) | Grid A-F/1-11 | A | 2025-04-19
| Sub Structure | Top floor | IT/745 | 2025-04-14 | 2025-04-14 | formwork | Check planter wall formwork |  | Grid B-C/10-11 | A | 2025-04-19
| Sub Structure | 1st floor | IT/746 | 2025-04-19 | 2025-04-19 | plaster work | Check plaster work for tile apartment No. 103 | (+19.0) | Grid A-B/5-8 | B | 2025-04-19
| Sub Structure | 11th floor | IT/747 | 2025-04-19 | 2025-04-19 | brick work | Check demolish brick work for column zone 2-3 | (+131.0) | Grid A-F/11-26 | A | 2025-04-24
| Sub Structure | 10th floor | IT/748 | 2025-04-19 | 2025-04-19 | layout | Check layout of tie column & brick work and allow to start tie column | (+118.0) | Grid A-F/1-26 | A | 2025-04-24
| Sub Structure | 11th floor | IT/749 | 2025-04-19 | 2025-04-19 | layout | Check layout of tie column & brick work and allow to start tie column | (+131.0) | Grid A-F/1-26 | A | 2025-04-24
| Sub Structure | 1st floor | IT/750 | 2025-04-19 | 2025-04-19 | plaster work | Check plaster work for tiles | (+19.0) | Grid A-F/1-23 | A | 2025-05-09
| Sub Structure | 10th floor | IT/751 | 2025-04-21 | 2025-04-21 | reinforcement | Check tie column reinforcement and allow to start concrete work |  | Grid A-F/1-8 | A | 2025-05-08
| Sub Structure | 1st floor | IT/752 | 2025-04-22 | 2025-04-23 | plaster work | Check tiles plaster work apartment No. 107-111, 111-114 | (+19.0) | Grid A-F/12-14, 16-22 | A | 2025-05-09
| Sub Structure | Top floor | IT/753 | 2025-04-24 | 2025-04-24 | formwork | Check over head water tank slab formwrok |  | Grid A-B/18-19 | A | 2025-05-08
| Sub Structure | 1st floor | IT/754 | 2025-04-24 | 2025-04-24 | plaster work | Check plaster work for tiles | (+19.0) | Grid A-F/14-17, 22-26 | A | 2025-05-09
| Sub Structure | 2nd floor | IT/755 | 2025-04-24 | 2025-04-24 | plaster work | Check plaster work fir tiles | (+30.0) | Grid A-F/14-26 | A | 2025-05-09
| Sub Structure | 2nd floor | IT/756 | 2025-04-26 | 2025-04-26 | plaster work | Check plaster work for tiles | (+30.0) | Grid A-F/10-14 | A | 2025-05-09
| Sub Structure | 1st floor | IT/757 | 2025-04-26 | 2025-04-26 | plaster work | Check plaster work for tiles | (+19.0) | Grid C-F/4-10 | A | 2025-05-09
| Sub Structure | Top floor | IT/758 | 2025-04-26 | 2025-04-26 | formwork | Check OHWT wall formwork |  | Grid A-B/8-9 | A | 2025-05-09
| Sub Structure | Top floor | IT/759 | 2025-04-26 | 2025-04-26 | formwork | check Genset slab formwork |  | Grid A-B/1-8 | A | 2025-05-09
| Sub Structure | 2nd floor | IT/760 | 2025-04-27 | 2025-04-27 | plaster work | check plaster work for tiles | (+30.0) | Grid B-F/1-9 | A | 2025-05-09
| Sub Structure | 2nd floor | IT/761 | 2025-04-28 | 2025-04-28 | plaster work | Check tile and allow to start plaster work | (+30.0) | Grid B-F/9-17 | A | 2025-05-09
| Sub Structure | 5th floor | IT/762 | 2025-04-28 | 2025-04-28 | plaster work | Check tile and allow to start plaster work | (+63.0) | Grid A-C/1-14 | A | 2025-05-09
| Sub Structure | Top floor | IT/763 | 2025-04-29 | 2025-04-29 | formwork | Check ramp slab formwork |  | Grid C/16-17 | A | 2025-05-09
| Sub Structure | 5th floor | IT/764 | 2025-04-30 | 2025-04-30 | plaster work | Check plaster work for tiles | (+63.0) | Grid A-F/4-26 | A | 2025-05-09
| Sub Structure | 10th floor | IT/765 | 2025-04-30 | 2025-04-30 | reinforcement | Check tie column reinforcement and allow to start concrete work |  | Grid A-F/8-14 | A | 2025-05-09
| Sub Structure | 1st floor | IT/766 | 2025-05-01 | 2025-05-01 | brick work | Check dressing area brick work | (+19.0) | Grid A-F/1-26 | A | 2025-05-02
| Sub Structure | 2nd floor | IT/767 | 2025-05-01 | 2025-05-01 | brick work | Check dressing area brick work | (+30.0) | Grid A-F/1-26 | A | 2025-05-02
| Sub Structure | Top floor | IT/768 | 2025-05-01 | 2025-05-01 | formwork | Check planter wall formwork | (+146.0) | Grid B-D/15-17 | A | 2025-05-09
| Sub Structure | Top floor | IT/769 | 2025-05-02 | 2025-05-02 | formwork | Check over head water tank slab formwrok | (+146.0) | Grid A-C/8-9 | A | 2025-05-09
| Sub Structure | Top floor | IT/770 | 2025-05-02 | 2025-05-02 | formwork | Check over head water tank parapet wall formwrok |  | Grid A-C/18-19 | A | 2025-05-09
| Sub Structure | 6th floor | IT/771 | 2025-05-05 | 2025-05-05 | plaster work | Check plaster work for tiles | (+74.0) | Grid A-F/5-26 | A | 2025-05-09
| Sub Structure | 5th floor | IT/772 | 2025-05-05 | 2025-05-05 | plaster work | Allow to start plaster work for tiles | (+63.0) | Grid A-F/23-26 | A | 2025-05-09
| Sub Structure | 1st floor | IT/773 | 2025-05-06 | 2025-05-06 | plaster work | Check plaster work and allow to start tiles zone 1 | (102-106) | Grid A-F/1-10 | A | 2025-05-07
| Sub Structure | 1st floor | IT/774 | 2025-05-06 | 2025-05-06 | plaster work | Check plaster work and allow to start tiles zone 1 | (108,110,112,105,107,109 | Grid A-F/10-17 | A | 2025-05-07
| Sub Structure | 1st floor | IT/775 | 2025-05-06 | 2025-05-06 | plaster work | Check plaster work and allow to start tiles |  | Grid A-F/17-26 | A | 2025-05-08
| Sub Structure | 1st floor | IT/776 | 2025-05-09 | 2025-05-09 | tile work | Check tiles work | 1.0411e+17 | Grid A-F/4-22 | A | 2025-05-14
|  | 1st floor | IT/777 | 2025-05-13 | 2025-05-13 | tile work | Check tile work |  | Grid A-F/1-26 | A | 2025-05-14
|  | 10th floor | IT/778 | 2025-05-13 | 2025-05-13 | reinforcement | Check rienforcement for tie column and allow to start concrete work |  | Grid A-F/15-26 | A | 2025-05-13
|  | 10th floor | IT/779 | 2025-05-13 | 2025-05-13 | level | Check level points for screeding | (+118.0) | Grid A-F/1-8 | A | 2025-05-14
|  | top floor | IT/780 | 2025-05-13 | 2025-05-14 | formwork | Check swimming pool wall formwork |  | Grid A-F/12-15 | A | 2025-05-14
|  | 10th floor | IT/781 | 2025-05-15 | 2025-05-15 | level | Check screeding level points in apartments & corridor | (+118.0) | Grid A-F/8-14 | A | 2025-05-19
|  | 10th floor | IT/782 | 2025-05-17 | 2025-05-17 | level | check screeding level in apartments | (+118.0) | Grid A-F/1-9 | B | 2025-05-19
|  | Top floor | IT/783 | 2025-05-17 | 2025-05-17 | formwork | Check swimming pool wall formwork |  | Grid A-C/12-15 | A | 2025-05-20
|  | Top floor | IT/784 | 2025-05-18 | 2025-05-18 | formwork | check leftover slab formwork and allow to start concrete work | (+146.0) | Grid A-B, C-D/26 | A | 2025-05-19
|  | 2nd floor | IT/785 | 19-May--25 | 19-May--25 | plaster work | check plaster work and allow to start tiles work zone 1 |  | Grid B-F/1-10 | A | 2025-05-19
|  | 2nd floor | IT/786 | 19-May--25 | 19-May--25 | plaster work | Check plaster work and allow to start tiles work zone 2 |  | Grid A-F/10-17 | A | 2025-05-19
|  | 2nd floor | IT/787 | 19-May--25 | 19-May--25 | plaster work | Check plaster work and allow to start tiles work |  | Grid A-F/17-26 | A | 2025-05-19
|  | Top floor | IT/788 | 2025-05-21 | 2025-05-21 | reinforcement | Check reinforcement and formwrok of horizontal band and allow to start concrete work | (+146.0) | Grid A-E/26 | A | 2025-05-21
|  | 10th floor | IT/789 | 2025-05-22 | 2025-05-22 | level | Check level points for screeding in apartments | (+118.0) | Grid A-F/14-18 | OP
|  | 10th floor | IT/790 | 2025-05-22 | 2025-05-22 | level | Check level points for screeding in apartments | (+118.0) | Grid A-F/9-14 | A | 2025-05-24
|  | 1st floor | IT/791 | 2025-05-22 | 2025-05-22 | tile work | Check living roo, bath room and powder room tiles |  | Grid A-F/1-26 | B | 2025-05-23
|  | 1st floor | IT/791 R01 | 2025-07-04 | 2025-07-04 | tile work | Check living roo, bath room and powder room tiles |  | Grid A-F/1-26 | A | 2025-07-26
|  | 2nd floor | IT/792 | 2025-05-22 | 2025-05-22 | tile work | check bed room and living room tile work |  | Grid A-F/10-14, 23-26 | B | 2025-05-23
|  | 2nd floor | IT/792 R01 | 2025-07-04 | 2025-07-04 | tile work | check bed room and living room tile work |  | Grid A-F/10-14, 23-26 | A | 2025-07-26
|  | Top floor | IT/793 | 2025-05-22 | 2025-05-22 | plaster work | check plaster work on back side of façade | (+19.0 - +146.0) | Grid A/2-4,6-8,11-12 | A | 2025-05-23
|  | 1st floor | IT/794 | 2025-05-22 | 2025-05-22 | tile work | check inspection of living room, bath room and powder room tiles |  | Grid A-F/10-16 | B | 2025-05-23
|  | 1st floor | IT/794 R01 | 2025-07-04 | 2025-07-04 | tile work | check inspection of living room, bath room and powder room tiles |  | Grid A-F/10-16 | A | 2025-07-26
|  | 1st floor | IT/795 | 2025-05-22 | 2025-05-22 | tile work | check inspection of living room, bath room and powder room tiles |  | Grid A-F/17-26 | B | 2025-05-24
|  | 1st floor | IT/795 | 2025-07-04 | 2025-07-04 | tile work | check inspection of living room, bath room and powder room tiles |  | Grid A-F/17-26 | A | 2025-07-26
IT/796
IT/797
IT/798
IT/799
IT/800
IT/801
IT/802
|  | 5th floor | IT/803 | 2025-05-27 | 2025-05-27 | plaster work | check plaster work and allow to start tile work zone 1 | 501-506 | Grid A-F/1-10 | A | 2025-05-29
|  | 5th floor | IT/804 | 2025-05-27 | 2025-05-27 | plaster work | Check plaster work and allow to start tile work zone 2 | 505-512 | Grid A-F/11-16 | A | 2025-05-29
|  | 5th floor | IT/805 | 2025-05-27 | 2025-05-27 | plaster work | Check plaster work and allow to start tile work zone 3 | 511-516 | Grid A-F/16-26 | A | 2025-05-30
|  | 2nd floor | IT/806 | 2025-05-24 | 2025-05-24 | tile work | check inspection of living room, bath room and powder room tiles |  | Grid A-F/1-26 | B | 2025-05-26
|  | 2nd floor | IT/806 R01 | 2025-07-04 | 2025-07-04 | tile work | check inspection of living room, bath room and powder room tiles |  | Grid A-F/1-26 | A | 2025-07-26
|  | 10th floor | IT/807 | 2025-05-27 | 2025-05-27 | level | check level points for screeding | (+118.0) | Grid A-F/23-26 | OP
|  | 10th floor | IT/808 | 2025-05-29 | 2025-05-29 | level | check screeding level in apartments | (+118.0) | Grid A-F/17-23 | A | 2025-05-29
|  | 10th floor | IT/809 | 2025-05-29 | 2025-05-29 | level | check screeding level in apartments |  | Grid A-F/22-26, C-F/9-10 | A | 2025-05-29
IT/810
|  | Top floor | IT/811 | 2025-06-02 | 2025-06-02 | layout | check layout of female locker room, changing room, toilet area and electrical room for brick |  | Grid A-B/10-11 | A | 2025-06-03
|  | 10th floor | IT/812 | 2025-06-16 | 2025-06-16 | plaster work | check level of screeding in flooring apartments | (+118.0) | Grid A-F/15-16 | A | 2025-06-21
|  | 10th floor | IT/813 | 2025-06-16 | 2025-06-17 | tie column work | check tie column work and re brick work | (+118.0) | Grid A-F/1-26 | A | 2025-06-17
|  | 1st floor | IT/814 | 2025-06-17 | 2025-06-17 | vanity work | check vanity work including formwork, drilling rebar, reinforcement and placing concrete |  | Grid A-F/1-26 | OP
|  | 11th floor | IT/815 | 2025-06-17 | 2025-06-18 | reinforcement | check tie column reinforcement and allow to start formwork |  | Grid A-F/1-12 | A | 2025-06-18
|  | 6th floor | IT/816 | 2025-06-20 | 2025-06-20 | plaster work | Check plaster work for tiles, | (+74.0) | Grid B-F/23-26 | OP
|  | 7th floor | IT/817 | 2025-06-23 | 2025-06-23 | plaster work | check plaster work fir tiles | (+74.0) | Grid A-F/19-26 | OP
|  | Top floor | IT/818 | 2025-06-23 | 2025-06-23 | plaster work | check plaster work on back side of façade | (+19.0 to +146.0) | Grid A/13-16 | A | 2025-06-24
|  | Top floor | IT/819 | 2025-06-24 | 2025-06-24 | layout | check layout of male locker room, changing room, toilet area and electrical room and allow for brick |  | Grid A-B/15-17 | OP
|  | 6th floor | IT/820 | 2025-06-28 | 2025-06-28 | plaster work | Check plaster work for tiles, | (603-606) | Grid A-F/4-10 | OP
|  | 6th floor | IT/821 | 2025-06-28 | 2025-06-28 | plaster work | Check plaster work for tiles, | (605,607-610) | Grid A-F/10-17 | OP
|  | 6th floor | IT/822 | 2025-06-28 | 2025-06-28 | plaster work | Check plaster work for tiles, | (611,614-615) | Grid A-F/17-26 | OP
|  | 7th floor | IT/823 | 2025-06-28 | 2025-06-28 | plaster work | Check plaster work for tiles, | (701-706)(+74) | Grid A-F/1-10 | OP
|  | 7th floor | IT/824 | 2025-06-28 | 2025-06-28 | plaster work | Check plaster work for tiles, | (705, 707-712)(+74) | Grid A-F/10-17 | OP
|  | 7th floor | IT/825 | 2025-06-28 | 2025-06-28 | plaster work | Check plaster work for tiles, | (711-714)(+74) | Grid A-F/17-22 | OP
|  | 11th floor | IT/826 | 2025-06-28 | 2025-06-28 | reinforcement | Check tie column reinforcement and allow to start formwork | (1107-1116) | Grid A-F/12-26 | OP
|  | 11th floor | IT/827 | 2025-07-02 | 2025-07-02 | level | check screeding level in apartments | 1101-1104 | Grid A-F/1-8 | A | 2025-07-14
|  | 8th floor | IT/828 | 2025-07-03 | 2025-07-03 | reinforcement | Check reinforcement and formwrok of horizontal band and allow to start concrete work | (+96.0) | Grid A/4-6,12-13 | A | 2025-07-03
|  | 5th floor | IT/829 | 2025-07-04 | 2025-07-04 | tile work | Check the final inspection of bed room tiles | 501503504506 | Grid A-F/01-26 | A | 2025-07-21
|  | 5th floor | IT/829 R01 | 2025-07-23 | 2025-07-23 | tile work | Check the final inspection of bed room tiles | 501503504506 | Grid A-F/01-26 | OP
|  | 5th floor | IT/830 | 2025-07-04 | 2025-07-04 | tile work | Check the final inspection of PWD/LND/BATH tiles work | 503514 | Grid A-F/05-08,17-18 | B | 2025-07-19
|  | 5th floor | IT/830 R01 | 2025-07-23 | 2025-07-23 | tile work | Check the final inspection of PWD/LND/BATH tiles work | 503514 | Grid A-F/05-08,17-18 | A | 2025-07-28
|  | 6th floor | IT/831 | 2025-07-04 | 2025-07-04 | tile work | Check the final inspection of bed room tiles | 608-611 ,614 | Grid A-F/01-26 | B | 2025-07-19
|  | 6th floor | IT/831 R01 | 2025-07-23 | 2025-07-23 | tile work | Check the final inspection of bed room tiles | 608-611 ,614 | Grid A-F/01-26 | A | 2025-07-26
|  | 2nd floor | IT/832 | 2025-07-04 | 2025-07-04 | tile work | Check the final inspection of bed room tiles |  | Grid A-F/01-26 | A | 2025-07-26
|  | 5th floor | IT/833 | 2025-07-04 | 2025-07-04 | level | Check the level of ceiling and allow to ceiling work | (+63.0) | Grid A-F/01-12 | A | 2025-07-19
|  | 4th floor | IT/834 | 2025-07-04 | 2025-07-04 | level | Check the level of ceiling and allow to ceiling work | (+52.0) | Grid A-C/01-14 | A | 2025-07-19
|  | 1st floor | IT/835 | 2025-07-04 | 2025-07-04 | tile work | Check the final inspection of PWD/LND/BATH tiles work |  | Grid A-F/01-10 | A | 2025-07-26
|  | 1st floor | IT/836 | 2025-07-04 | 2025-07-04 | tile work | Check the final inspection of PWD/LND/BATH tiles work |  | Grid A-F/10-16 | A | 2025-07-26
|  | 1st floor | IT/837 | 2025-07-04 | 2025-07-04 | tile work | Check the final inspection of PWD/LND/BATH tiles work |  | Grid A-F/17-26 | A | 2025-07-26
|  | 2nd floor | IT/838 | 2025-07-04 | 2025-07-04 | tile work | Check the final inspection of PWD/LND/BATH tiles work |  | Grid A-F/4-8,14-16,24-26 | A | 2025-07-26
|  | 5th floor | IT/839 | 2025-07-04 | 2025-07-04 | tile work | Check the final inspection of bed room tiles | 505, 507-510,512 | Grid A-F/10-16 | B | 2025-07-19
|  | 5th floor | IT/839 R01 | 2025-07-23 | 2025-07-23 | tile work | Check the final inspection of bed room tiles | 505, 507-510,512 | Grid A-F/10-16 | OP
|  | 5th floor | IT/840 | 2025-07-04 | 2025-07-04 | tile work | Check the final inspection of bed room tiles | 511513514516 | Grid A-F/16-26 | B | 2025-07-19
|  | 5th floor | IT/840 R01 | 2025-07-23 | 2025-07-23 | tile work | Check the final inspection of bed room tiles | 511513514516 | Grid A-F/16-26 | OP
|  | 11th floor | IT/841 | 2025-07-11 | 2025-07-11 | level | check screeding level in apartments | (101-104) | Grid A-F/01-08 | A | 2025-07-17
|  | 11th floor | IT/842 | 2025-07-10 | 2025-07-10 | level | check screeding level in apartments | (1106, 1108) | Grid F-C/03/13,9-13 | A | 2025-07-11
|  | 11th floor | IT/843 | 2025-07-15 | 2025-07-15 | level | check screeding level in apartments | (1109-1112 | Grid A-F/14-16 & C/13-16 | A | 2025-07-17
|  | 11th floor | IT/844 | 2025-07-19 | 2025-07-19 | level | check screeding level in apartments | (1106 & 1108) | Grid F-C/03-13 & F-C/09-13 | A | 2025-07-22
|  | 5th floor | IT/845 | 2025-07-19 | 2025-07-19 | reinforcement & formwork | Check reinforcement and formwork of horizontal band and allow to start concrete work | (+63.0) | Grid A/14-15 | A | 2025-07-26
|  | 4th floor | IT/846 | 2025-07-17 | 2025-07-17 | level | Check the level of Ceiling and allow to start ceiling work | (+52.0) | Grid A-F/14-26 | A | 2025-07-19
|  | 7th floor | IT/847 | 2025-07-17 | 2025-07-17 | plaster work | Check plaster work for tiles, | 713715716 | Grid A-F/19-26 | A | 2025-07-26
|  | 7th floor | IT/848 | 2025-07-17 | 2025-07-17 | plaster work | Check plaster work for tiles, | 701703704 | Grid A-F/1-10 | A | 2025-07-19
|  | 7th floor | IT/849 | 2025-07-17 | 2025-07-17 | plaster work | Check plaster work for tiles, | 708-709,712 | Grid A-F/10-17 | B | 2025-07-26
|  | 7th floor | IT/849 R01 | 2025-07-28 | 2025-07-28 | plaster work | Check plaster work for tiles, | 708-709,712 | Grid A-F/10-17 | OP
|  | 7th floor | IT/850 | 2025-07-17 | 2025-07-17 | plaster work | Check plaster work for tiles, | 711714 | Grid A-F/17-22 | A | 2025-07-19
|  | 11th floor | IT/851 | 2025-07-19 | 2025-07-19 | level screed | Check Level for screed flooring | 111111141116 | Grid A-F/16-26 | A | 2025-07-22
|  | Top floor | IT/852 | 2025-07-19 | 2025-07-19 | Formwork | Check formwork of kids pool and allow tu start concrete |  | Grid C-F/10-12 | A | 2025-07-22
|  | Top floor | IT/854 | 2025-07-21 | 2025-07-21 | Formwork | Check formwork of kids pool |  | Grid C-F/10-12 | OP
|  | 1st floor | IT/855 | 2025-07-21 | 2025-07-21 | level | Check levelk point and allow to start façade plaster work |  | Grid A/23-25 | A | 2025-07-22
|  | 1st floor | IT/856 | 2025-07-21 | 2025-07-21 | level | Check levelk point and allow to start façade plaster work |  | Grid B, C-E/26 | A | 2025-07-22
|  | 1st floor | IT/857 | 2025-07-21 | 2025-07-21 | level | Check levelk point and allow to start façade plaster work |  | Grid B, C-E/26 | A | 2025-07-22
|  | 11th floor | IT/858 | 2025-07-22 | 2025-07-22 | level | Chevk level of screed flooring in bed room & living room | 11091112 | Grid A-F/14, C/12-17 | A | 2025-07-26
|  | 11th floor | IT/859 | 2025-07-22 | 2025-07-22 | level | Chevk level of screed flooring in bed room & living room | 110511071110 | Grid A-F/11-14, | A | 2025-07-26
|  | Top floor | IT/860 | 2025-07-22 | 2025-07-22 | formwork | Check formwork of Lounging pool bed |  | Grid C-F/15-16, | A | 2025-07-26
|  | 4th floor | IT/860 | 2025-07-22 | 2025-07-22 | ceiling work | Check final inspection of ceiling work(Bed room and living room) | 401403405 | Grid A-C/1-12, | R | 2025-07-26
|  | 4th floor | IT/860 R01 | 2025-07-28 | 2025-07-28 | ceiling work | Check final inspection of ceiling work(Bed room and living room) | 401403405 | Grid A-C/1-12, | A | 2025-07-28
|  | 4th floor | IT/861 | 2025-07-22 | 2025-07-22 | ceiling work | Check final inspection of ceiling work(Bed room and living room) | 409411413415 | Grid A-C/14-26, | R | 2025-07-26
|  | 4th floor | IT/861 R01 | 2025-07-28 | 2025-07-28 | ceiling work | Check final inspection of ceiling work(Bed room and living room) | 409411413415 | Grid A-C/14-26, | A | 2025-07-28
|  | 11th floor | IT/862 | 2025-07-22 | 2025-07-22 | Column woek | Check the complete Column work |  | Grid A-F/1-26, | B | 2025-07-26
|  | 11th floor | IT/862 R01 | 2025-07-26 | 2025-07-26 | Column woek | Check the complete Column work |  | Grid A-F/1-26, | A | 2025-07-28
|  | 11th floor | IT/863 | 2025-07-22 | 2025-07-22 | Brick work | Check the complete re-brick work |  | Grid A-F/1-26, | R | 2025-07-26
|  | 11th floor | IT/863 R01 | 2025-07-28 | 2025-07-28 | Brick work | Check the complete re-brick work |  | Grid A-F/1-26, | R | 2025-07-28
|  | 11th floor | IT/863 R02 | 2025-08-02 | 2025-08-02 | Brick work | Check the complete re-brick work |  | Grid A-F/1-26, | A | 2025-08-04
|  | 11th floor | IT/864 | 2025-07-23 | 2025-07-23 | level | Chevk level of screed flooring in bed room & living room | 1114,1116,Coridor | Grid C-F/17-23, | A | 2025-07-26
|  | 8th floor | IT/865 | 2025-07-24 | 2025-07-24 | plaster work | Check plasterwork for tiles | 811,813-816 | Grid A-F/17-26, | A | 2025-07-28
|  | 8th floor | IT/866 | 2025-07-24 | 2025-07-24 | plaster work | Check plasterwork for tiles | 805,807-810,812 | Grid A-F/11-16, | A | 2025-07-28
|  | 8th floor | IT/867 | 2025-07-24 | 2025-07-24 | plaster work | Check plasterwork for tiles | 801-804,806 | Grid A-F/01-10 | A | 2025-07-30
|  | 8th floor | IT/868 | 2025-07-24 | 2025-07-24 | plaster work | Check plasterwork | 801802806808810 | Grid B-F/01-14 | B | 2025-07-26
|  | 8th floor | IT/868 R01 | 2025-07-28 | 2025-07-28 | plaster work | Check plasterwork | 801802806808810 | Grid B-F/01-14 | A | 2025-07-28
|  | 11th floor | IT/869 | 2025-07-26 | 2025-07-26 | level | Check level of screed flooring in bed room & living room | 1111,1113,1115 & corridor\ | Grid A-F/19-26 | A | 2025-07-30
|  | 1st floor | IT/870 | 2025-07-28 | 2025-07-28 | ceiling work | Check final inspection of ceiling work(Balcony) |  | Grid F/15-16 | A | 2025-07-30
|  | Top floor | IT/871 | 2025-07-28 | 2025-07-28 | plaster work | check plaster work on back side of façade |  | Grid A/19-21,23-25 | A | 2025-07-30
|  | 6th floor | IT/872 | 2025-07-29 | 2025-07-29 | level | Check the level of ceiling and allow to ceiling work |  | Grid A-F/01-11 | A | 2025-08-01
|  | 3rd floor | IT/873 | 2025-07-30 | 2025-07-30 | Brick work | Check Complete brick work (dressing and bed room wardrobe) |  | Grid A-F/01-26 | A | 2025-08-01
|  | 4th floor | IT/874 | 2025-07-30 | 2025-07-30 | Brick work | Check Complete brick work (dressing and bed room wardrobe) |  | Grid A-F/01-26 | A | 2025-08-01
|  | 4th floor | IT/875 | 2025-07-30 | 2025-07-30 | Brick work | Check the complete kitchen pad |  | Grid A-F/01-26 | A | 2025-08-01
|  | 3rd floor | IT/876 | 2025-07-30 | 2025-07-30 | Brick work | Check the complete kitchen pad |  | Grid A-F/01-26 | A | 2025-08-01
|  | 2nd floor | IT/877 | 2025-07-30 | 2025-07-30 | Brick work | Check the complete kitchen pad |  | Grid A-F/01-26 | A | 2025-08-01
|  | 1st floor | IT/878 | 2025-07-30 | 2025-07-30 | Brick work | Check the complete kitchen pad |  | Grid A-F/01-26 | A | 2025-08-01
|  | 6th floor | IT/879 | 2025-07-31 | 2025-07-31 | tile work | Check final inspection of bed rooms tiles work |  | Grid A-F/04-23 | A | 2025-08-01
IT/880
IT/881
IT/882
|  | 5th floor | IT/883 | 2025-08-20 | 2025-08-20 | tile work | Check final inspection of Living rooms tiles work |  | Grid C-F/10-12 | A | 2025-08-25
|  | 5th floor | IT/884 | 2025-08-20 | 2025-08-20 | tile work | Check final inspection of Living rooms tiles work |  | Grid B-C/03-08 | A | 2025-08-25
|  | 5th floor | IT/885 | 2025-08-20 | 2025-08-20 | tile work | Check final inspection of Living rooms tiles work |  | Grid A-C/01-04 | A | 2025-08-25
|  | 6th floor | IT/886 | 2025-07-30 | 2025-07-30 | tile work | Check final inspection of PWD/LND & Bathroom tile work |  | Grid A-F/1-15 | A | 2025-08-01
|  | 5th floor | IT/887 | 2025-07-30 | 2025-07-30 | tile work | Check final inspection of PWD/LND & Bathroom tile work |  | Grid A-F/15-23 | A | 2025-07-31
|  | 2nd floor | IT/888 | 2025-07-30 | 2025-07-30 | tile work | Check final inspection of PWD/LND & Bathroom tile work |  | Grid A-F/15-23 | A | 2025-08-01
|  | 11th floor | IT/889 | 2025-07-30 | 2025-07-30 | level | Chevk level of screed flooring in bed room & living room |  | Grid A-F/18-26 | A | 2025-07-31
|  | 1st floor | IT/890 | 2025-08-01 | 2025-08-01 | tile work | Check final inspection of PWD/LND & Bathroom tile work |  | Grid A-F/01-22 | R | 2025-08-04
|  | 1st floor | IT/890 R01 | 2025-08-22 | 2025-08-22 | tile work | Check final inspection of PWD/LND & Bathroom tile work |  | Grid A-F/01-22 | A | 2025-08-25
|  | 1st floor | IT/891 | 2025-08-01 | 2025-08-01 | tile work | Check final inspection of PWD/LND & Bathroom tile work |  | Grid A-F/10-12 | A | 2025-08-04
|  | 11th floor to 1st floor | IT/892 | 2025-08-08 | 2025-08-08 | plaster work | Check the complete façade vertical band plaster work |  | Grid B-E/6
|  | 11th floor | IT/893 | 2025-08-09 | 2025-08-09 | plaster work | Check the complete façade(vertical band) plaster work |  | Grid C-E/26 | B | 2025-08-12
|  | 11th floor | IT/893 R01 | 2025-08-13 | 2025-08-13 | plaster work | Check the complete façade(vertical band) plaster work |  | Grid C-E/26 | B | 2025-08-15
|  | 11th floor | IT/893 R02 | 2025-08-18 | 2025-08-18 | plaster work | Check the complete façade(vertical band) plaster work |  | Grid C-E/26 | A | 2025-08-23
|  | 5th floor | IT/894 | 2025-08-20 | 2025-08-20 | tile work | Check final inspection of Living rooms tiles work |  | Grid A-C/13-17 | A | 2025-08-26
|  | 5th floor | IT/895 | 2025-08-21 | 2025-08-21 | tile work | Check final inspection of Living rooms tiles work |  | Grid A-C/19-26 | A | 2025-08-25
|  | 5th floor | IT/896 | 2025-08-21 | 2025-08-21 | tile work | Check final inspection of Living rooms tiles work |  | Grid C-F/16-23 | A | 2025-08-25
|  | 5th floor | IT/897 | 2025-08-20 | 2025-08-20 | tile work | Check final inspection of Living rooms tiles work |  | Grid C-F/14-16 | A | 2025-08-25
|  | 5th floor | IT/898 | 2025-09-04 | 2025-09-04 | Ceiling work | Check the final inspection of ceiling work |  | Grid A-C/05-09 | R | 2025-09-10
|  | 5th floor | IT/898 R1 | 2025-09-29 | 2025-09-29 | Ceiling work | Check the final inspection of ceiling work |  | Grid A-C/05-09 | R | 2025-10-02
|  | 5th floor | IT/899 | 2025-09-04 | 2025-09-04 | Ceiling work | Check the final inspection of ceiling work |  | Grid C-F/04-08 | R | 2025-09-14
|  | 5th floor | IT/899 R01 | 2025-09-19 | 2025-09-19 | Ceiling work | Check the final inspection of ceiling work |  | Grid C-F/04-08 | A | 2025-09-23 | CM
|  | 5th floor | IT/899 R02 | 2025-10-22 | 2025-10-22 | Ceiling work | Check the final inspection of ceiling work |  | Grid C-F/04-08 | A | 2025-10-23
|  |  | IT/900 | 2025-09-04 | 2025-09-04 | Ceiling work | Check the final inspection of ceiling work |  | Grid A-E/11-13 | R | 2025-09-10
|  |  | IT/900 R1 | 2025-10-20 | 2025-10-20 | Ceiling work | Check the final inspection of ceiling work |  | Grid A-E/11-13 | B | 2025-10-21
|  |  | IT/900 R2 | 2025-11-03 | 2025-11-03 | Ceiling work | Check the final inspection of ceiling work |  | Grid A-E/11-13 |  | 2025-11-05
|  |  | IT/900 R3 | 2025-11-10 | 2025-11-10 | Ceiling work | Check the final inspection of ceiling work |  | Grid A-E/11-13 | B | 2025-11-12
|  |  | IT/901 | 2025-09-04 | 2025-09-04 | Ceiling work | Check the final inspection of ceiling work |  | Grid A-C/15-17 | B | 2025-09-10
|  |  | IT/901 R01 | 2025-09-29 | 2025-09-29 | Ceiling work | Check the final inspection of ceiling work |  | Grid A-C/15-17 | R | 2025-10-02
|  |  | IT/901 R02 | 2025-11-10 | 2025-11-10 | Ceiling work | Check the final inspection of ceiling work |  | Grid A-C/15-17 | B | 2025-11-12
|  | 5th floor | IT/902 | 2025-08-14 | 2025-08-14 | reinforcement & formwork | Check reinforcement and formwork of horizentalband and allow to start concrete |  | Grid A/12-15 | A
|  |  | IT/903 | 2025-08-15 | 2025-08-15 | layout | Check the layout of wall and allow to start brick masnory |  | Grid D-E/11-23 | A
|  |  | IT/904 | 2025-08-10 | 2025-08-10 | reinforcement & formwork | Check reinforcement and formwork of horizentalband and allow to start concrete |  | Grid A/14-15, 21-23 | A
|  | Top floor | IT/905 | 2025-08-18 | 2025-08-18 | brick work | Check complete internal brickwork of the horizontal band |  | Grid A/02-25 | A | 2025-08-24
|  | Top floor | IT/906 | 2025-08-18 | 2025-08-18 | brick work | Check complete internal brickwork of the horizontal band |  | Grid A-E/26 | A | 2025-08-24
|  | 8th floor | IT/907 | 2025-08-18 | 2025-08-18 | brick work | Check complete internal brickwork of the horizontal band |  | Grid A/02-25 | A | 2025-08-24
|  | 4th floor | IT/908 | 2025-12-18 | 2025-12-18 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/11-12
|  | 4th floor | IT/908 R01 | 2025-09-02 | 2025-09-02 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/11-12 | R | 2025-09-05
|  | 4th floor | IT/908 R02 | 2025-09-27 | 2025-09-27 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/11-12 | R | 2025-10-02
|  | 4th floor | IT/908 R04 | 2025-11-27 | 2025-11-27 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/11-12 | OP
|  | 4th floor | IT/909 | 2025-08-20 | 2025-08-20 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid C-E/09-10 | B | 2025-08-23
|  | 4th floor | IT/909 R01 | 2025-09-02 | 2025-09-02 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid C-E/09-10 | R | 2025-09-05
|  | 4th floor | IT/909 R02 | 2025-09-29 | 2025-09-29 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid C-E/09-10 | R | 2025-10-02
|  | 4th floor | IT/909 R04 | 2025-11-27 | 2025-11-27 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid C-E/09-10 | OP
|  | 4th floor | IT/910 | 2025-08-20 | 2025-08-20 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/15-16 | B | 2025-08-25
|  | 4th floor | IT/910 R01 | 2025-09-02 | 2025-09-02 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/15-16 | B | 2025-09-05
|  | 4th floor | IT/910 R02 | 2025-10-22 | 2025-10-22 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/15-16 | A | 2025-10-23
|  | 4th floor | IT/911 | 2025-08-21 | 2025-08-21 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/19-22 | B | 2025-08-26
|  | 4th floor | IT/911R01 | 2025-09-02 | 2025-09-02 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/19-22 | A | 2025-09-05
|  | 4th floor | IT/911R02 | 2025-10-22 | 2025-10-22 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/19-22 | A | 2025-10-23
|  | 4th floor | IT/912 | 2025-08-21 | 2025-08-21 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/23-26 | B | 2025-08-25
|  | 4th floor | IT/912 R01 | 2025-09-02 | 2025-09-02 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/23-26 | A | 2025-09-05
|  | 4th floor | IT/912 R02 | 2025-10-22 | 2025-10-22 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid A-C/23-26 | A | 2025-10-23
|  | 4th floor | IT/913 | 2025-08-21 | 2025-08-21 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid B-E/24-26 | B | 2025-08-25
|  | 4th floor | IT/913 R01 | 2025-09-02 | 2025-09-02 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid B-E/24-26 | A | 2025-09-05
|  | 4th floor | IT/913 R02 | 2025-10-22 | 2025-10-22 | ceiling work | Check the final inspection of ceiling work at 4th floor |  | Grid B-E/24-26 | A | 2025-10-23
|  | 1st floor | IT/914 | 2025-08-21 | 2025-08-21 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-C/01-05 | A | 2025-08-25
|  | 1st floor | IT/915 | 2025-08-21 | 2025-08-21 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid C-F/17-18 | A | 2025-08-25
|  | 2nd floor | IT/916 | 2025-08-21 | 2025-08-21 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid B-F/17-18,01-03 | R | 2025-08-25
|  | 2nd floor | IT/916 R03 | 2025-10-06 | 2025-10-06 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid B-F/17-18,01-03 | A | 2025-10-07
|  |  | IT/917 | 2025-08-21 | 2025-08-21 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-C/05-08 | R | 2025-08-25
|  | 1st floor | IT/918 | 2025-08-22 | 2025-08-22 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-F/19-26 | A | 2025-08-25
|  | 1st floor | IT/919 | 2025-08-22 | 2025-08-22 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-F/12-18 | A | 2025-08-26
|  | 1st floor | IT/920 | 2025-08-22 | 2025-08-22 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-F/09-12 | A | 2025-08-25
|  |  | IT/921 | 2025-08-28 | 2025-08-28 | level | Check level point for screed ground floor back side main entrance gate |  | Grid A-B/10-11, 16-17 | A | 2025-09-01
|  | 6th floor | IT/922 | 2025-08-29 | 2025-08-29 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-F/01-26 | R | 2025-09-05
|  | 6th floor | IT/922 R01 | 2025-10-04 | 2025-10-04 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-F/01-26 | B
|  | 6th floor | IT/922 R02 | 2025-10-04 | 2025-10-04 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-F/01-26 | A | 2025-10-10
|  | 5th floor | IT/923 | 2025-08-29 | 2025-08-29 | reinforcement & formwork | Check reinforcement and formwork of horizentalband and allow to start concrete |  | Grid A/14-15, 04-06 | A | 2025-09-01
|  | 5th floor | IT/924 | 2025-08-30 | 2025-08-30 | tile work | Check the final inspection of living room tile work |  | Grid A-B/10-13 | B | 2025-09-05
|  | 5th floor | IT/924 R01 | 2025-09-19 | 2025-09-19 | tile work | Check the final inspection of living room tile work |  | Grid A-B/10-13 | A | 2025-09-23 | CM
|  | 5th floor | IT/925 | 2025-08-30 | 2025-08-30 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid B-F/23-26 | B | 2025-09-05
|  | 5th floor | IT/925 R01 | 2025-09-15 | 2025-09-15 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid B-F/23-26 | R | 2025-09-16 | Saqib
|  | 5th floor | IT/925 R02 | 2025-09-19 | 2025-09-19 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid B-F/23-26 | A | 2025-09-23 | CM
|  | 2nd floor | IT/926 | 2025-08-30 | 2025-08-30 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-C/05-09 | B | 2025-09-05
|  | 2nd floor | IT/926 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-C/05-09 | B | 2025-09-17 | Bilal
|  | 2nd floor | IT/926 R02 | 2025-09-19 | 2025-09-19 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-C/05-09 | A | 2025-09-23
|  | 2nd floor | IT/927 | 2025-08-30 | 2025-08-30 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-F/04-13 | R | 2025-09-05
|  | 2nd floor | IT/927 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-F/04-13 | B | 2025-09-23
|  | 2nd floor | IT/927 R02 | 2025-10-06 | 2025-10-06 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-F/04-13 | A | 2025-10-07
|  | 2nd floor | IT/928 | 2025-08-30 | 2025-08-30 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-F/09-15 | R | 2025-09-05
|  | 2nd floor | IT/928 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-F/09-15 | R | 2025-09-17
|  | 2nd floor | IT/928 R02 | 2025-09-19 | 2025-09-19 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-F/09-15 | A | 2025-09-23 | CM
|  | 2nd floor | IT/929 | 2025-08-30 | 2025-08-30 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-F/12-22 | A | 2025-09-10
|  | 2nd floor | IT/930 | 2025-08-30 | 2025-08-30 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-F/16-26 | B | 2025-09-09
|  | 2nd floor | IT/930 R01 | 2025-09-17 | 2025-09-17 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-F/16-26 | A | 2025-09-23
|  | Ground floor | IT/931 | 2025-09-03 | 2025-09-03 | brick work | Check the wall brickwork at gf |  | Grid D-E/11& 15, B/13 & 14 | A | 2025-09-03
|  | 7th floor | IT/932 | 2025-09-03 | 2025-09-03 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid A-B/10-14 | A | 2025-09-30
|  | 7th floor |  | 2025-09-03 | 2025-09-03 | tile work | Check the final inspection of Bed rooms & living room tile work |  | Grid C-F/13-18 | A | 2025-09-30
|  | 6th floor | IT/934 | 2025-09-03 | 2025-09-03 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/05-08 | R | 2025-09-05
|  | 6th floor | IT/934 R01 | 2025-09-27 | 9//2025 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/05-08 | B | 2025-10-02
|  |  | IT/935 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/11-12 | A | 2025-09-10
|  |  | IT/935 R01 | 2025-11-10 | 2025-11-10 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/11-12 | B | 2025-11-12
|  | 6th floor | IT/936 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/11-12 | B | 2025-09-11
|  | 6th floor | IT/936 R1 | 2025-10-22 | 2025-10-22 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/11-12 | A | 2025-10-23
|  | 6th floor | IT/937 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/15-16 | R | 2025-09-12
|  | 6th floor | IT/937 R01 | 2025-10-01 | 2025-10-01 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/15-16 | B | 2025-10-07
|  | 6th floor | IT/937 R02 | 2025-10-08 | 2025-10-08 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/15-16 | A | 2025-10-10
|  | 6th floor | IT/938 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/17-18 | B | 2025-09-12
|  | 6th floor | IT/938 R01 | 2025-10-03 | 2025-10-03 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/17-18 | B | 2025-10-07
|  | 6th floor | IT/938 R02 | 2025-10-08 | 2025-10-08 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/17-18 | A | 2025-10-10
|  | 6th floor | IT/939 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/19-22 | B | 2025-09-12
|  | 6th floor | IT/939 R01 | 2025-10-01 | 2025-10-01 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/19-22 | B | 2025-10-07
|  | 6th floor | IT/939 R02 | 2025-10-08 | 2025-10-08 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/19-22 | A | 2025-10-10
|  | 6th floor | IT/940 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/19-22 | R | 2025-09-12
|  | 6th floor | IT/940 R01 | 2025-09-27 | 2025-09-27 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/19-22 | A | 2025-10-07
|  | 6th floor | IT/940 R02 | 2025-10-22 | 2025-10-22 | ceiling work | Check the final inspection of ceiling work |  | Grid C-F/19-22 | A | 2025-10-23
|  | 6th floor | IT/941 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work |  | Grid A-B/5-8 | R | 2025-09-04
|  | 6th floor | IT/942 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work |  | Grid A-B/15-16 | R | 2025-09-04
|  | 6th floor | IT/942 R02 | 2025-10-01 | 2025-10-01 | ceiling work | Check the final inspection of ceiling work |  | Grid A-B/15-16 | A | 2025-10-07
|  | 6th floor | IT/942 R03 | 2025-10-22 | 2025-10-22 | ceiling work | Check the final inspection of ceiling work |  | Grid A-B/15-16 | A | 2025-10-23
|  | 5th floor | IT/943 | 2025-09-05 | 2025-09-05 | brick work | Check the complete kitchen pad brickwork |  | Grid A-F/1-26 | A | 2025-09-12
|  | 6th floor | IT/944 | 2025-09-05 | 2025-09-05 | brick work | Check the complete kitchen pad brickwork |  | Grid A-F/1-26 | A | 2025-09-13
|  | 6th floor | IT/945 | 2025-09-05 | 2025-09-05 | brick work | Check the complete brickwork(dressing and bed room wardrobe) |  | Grid A-F/1-26 | B | 2025-09-16
|  | 6th floor | IT/945 R01 | 2025-09-17 | 2025-09-17 | brick work | Check the complete brickwork(dressing and bed room wardrobe) |  | Grid A-F/1-26 | A | 2025-09-23
|  | 5th floor | IT/946 | 2025-09-05 | 2025-09-05 | brick work | Check the complete brickwork(dressing and bed room wardrobe) |  | Grid A-F/1-26 | A | 2025-09-13
|  | 1st floor | IT/947 | 2025-09-05 | 2025-09-05 | dummy wall | Check the complete dummy wall (vanity wall) |  | Grid A-F/1-26 | A | 2025-09-13
|  | 2nd floor | IT/948 | 2025-09-05 | 2025-09-05 | dummy wall | Check the complete dummy wall (vanity wall) |  | Grid A-F/1-26 | A | 2025-09-14
|  | 3rd floor | IT/949 | 2025-09-05 | 2025-09-05 | dummy wall | Check the complete dummy wall (vanity wall) |  | Grid A-F/1-26 | A | 2025-09-12
|  | 4th floor | IT/950 | 2025-09-08 | 2025-09-08 | dummy wall | Check the complete dummy wall (vanity wall) |  | Grid A-F/1-26 | A | 2025-09-13 | Saqib
|  | 5th floor | IT/951 | 2025-09-08 | 2025-09-08 | dummy wall | Check the complete dummy wall (vanity wall) |  | Grid A-F/1-26 | A | 2025-09-10 | Saqib
|  | 6th floor | IT/952 | 2025-09-08 | 2025-09-08 | dummy wall | Check the complete dummy wall (vanity wall) |  | Grid A-F/1-26 | A | 2025-09-13 | Saqib
|  |  | IT/953 | 2025-09-08 | 2025-09-08 | reinforcement & formwork | Check reinforcement and formwork of horizentalband and allow to start concrete |  | Grid A/21-23 | A | 2025-09-13 | Hassan jameel
|  |  | IT/953 R01 | 2025-09-09 | 2025-09-09 | reinforcement & formwork | Check reinforcement and formwork of horizentalband and allow to start concrete |  | Grid A/21-23 | A | 2025-09-10 | Hassan jameel
|  | GF | IT/954 | 2025-09-11 | 2025-09-11 | brickwork | Check complete Brickwork at GF |  | Grid A-F/01-26 | A | 2025-09-13 | Asad Butt
|  |  | IT/955 | 2025-09-11 | 2025-09-11 | reinforcement & formwork | Check reinforcement and formwork of horizentalband and allow to start concrete |  | Grid A-C/26 | A | 2025-09-13 | Saqib
|  |  | IT/956 | 2025-09-11 | 2025-09-11 | ceiling work | Check the final inspection of ceiling work |  | Grid A-C/01-04 | A | 2025-09-13 | Saqib
|  |  | IT/956 R1 | 2025-10-22 | 2025-10-22 | ceiling work | Check the final inspection of ceiling work |  | Grid A-C/01-04 | A | 2025-10-23
|  |  | IT/957 | 2025-09-11 | 2025-09-11 | ceiling work | Check the final inspection of ceiling work |  | Grid A-C/05-08 | B | 2025-09-13 | Saqib
|  |  | IT/957 R01 | 2025-09-17 | 2025-09-17 | ceiling work | Check the final inspection of ceiling work |  | Grid A-C/05-08 | A | 2025-09-23
|  |  | IT/958 | 2025-09-11 | 2025-09-11 | ceiling work | Check the final inspection of ceiling work |  | Grid A-C/01-04 | R | 2025-09-12 | Asad Butt
|  |  | IT/958 R01 | 2025-10-02 | 2025-10-02 | ceiling work | Check the final inspection of ceiling work |  | Grid A-C/01-04 | A | 2025-10-08 | Asad Butt
|  |  | IT/958 R02 | 2025-10-22 | 2025-10-22 | ceiling work | Check the final inspection of ceiling work |  | Grid A-C/01-04 | A | 2025-10-23
|  | 1st floor | IT/959 | 2025-09-12 | 2025-09-12 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid C-F/01-04 | R | 2025-09-12 | Asad Butt
|  | 1st floor | IT/959 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid C-F/01-04 | R | 2025-09-15 | Asad Butt
|  | 1st floor | IT/959 R02 | 2025-09-17 | 2025-09-17 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid C-F/01-04 | A | 2025-09-23 | Asad Butt
|  | 1st floor | IT/960 | 2025-09-12 | 2025-09-12 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-C/04-06 | R | 2025-09-12 | Asad Butt
|  | 1st floor | IT/960 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-C/04-06 | R | 2025-09-15 | Asad Butt
|  | 1st floor | IT/960 R02 | 2025-09-17 | 2025-09-17 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-C/04-06 | A | 2025-09-23 | Asad Butt
|  |  | IT/961 | 2025-09-12 | 2025-09-12 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid C-F/03-05 | R | 2025-09-12 | Asad Butt
|  |  | IT/961 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid C-F/03-05 | R | 2025-09-15 | Asad Butt
|  |  | IT/961 R02 | 2025-09-17 | 2025-09-17 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid C-F/03-05 | A | 2025-09-23 | Asad Butt
|  |  | IT/962 | 2025-09-12 | 2025-09-12 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-B/13-06 | R | 2025-09-12 | Asad Butt
|  |  | IT/962 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-B/13-06 | R | 2025-09-15
|  |  | IT/962 R02 | 2025-09-17 | 2025-09-17 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work |  | Grid A-B/13-06 | A | 2025-09-23 | Asad Butt
|  |  | IT/963 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work |  | 103, 104 | R | 2025-09-13 | Asad Butt
|  |  | IT/963 R1 | 2025-09-17 | 2025-09-17 | tile work | Check the inspection of Balcony tile work |  | 103, 104 | A | 2025-09-20 | Asad Butt
|  |  | IT/964 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work |  | 105108 | R | 2025-09-15 | Asad Butt
|  |  | IT/964 R01 | 2025-09-17 | 2025-09-17 | tile work | Check the inspection of Balcony tile work |  | 105108 | A | 2025-09-20 | Asad Butt
|  |  | IT/965 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work |  | 107 , 110 | R | 2025-09-15 | Asad Butt
|  |  | IT/965 R1 | 2025-09-17 | 2025-09-17 | tile work | Check the inspection of Balcony tile work |  | 107 , 110 | A | 2025-09-20 | Asad Butt
|  |  | IT/966 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work |  | 114, 116 | R | 2025-09-15 | Asad Butt
|  |  | IT/966 R1 | 2025-09-17 | 2025-09-17 | tile work | Check the inspection of Balcony tile work |  | 114, 116 | A | 2025-09-20 | Asad Butt
|  |  | IT/967 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work |  | 109, 111 | B | 2025-09-15 | Asad Butt
|  |  | IT/967 R01 | 2025-09-17 | 2025-09-17 | tile work | Check the inspection of Balcony tile work |  | 109, 111 | A | 2025-09-20
|  |  | IT/968 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work |  | 101, 106 | R | 2025-09-15 | Asad Butt
|  |  | IT/968 R1 | 2025-09-17 | 2025-09-17 | tile work | Check the inspection of Balcony tile work |  | 101, 106 | A |  | Asad Butt
|  |  | IT/969 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work |  | 102, 115 | R | 2025-09-15 | Asad Butt
|  |  | IT/969 R01 | 2025-09-17 | 2025-09-17 | tile work | Check the inspection of Balcony tile work |  | 102, 115 | A | 2025-09-18 | Asad Butt
|  |  | IT/970 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work |  | 113 | R | 2025-09-15 | Asad Butt
|  |  | IT/970 R01 | 2025-09-17 | 2025-09-17 | tile work | Check the inspection of Balcony tile work |  | 113 | A | 2025-09-20 | Asad Butt
|  |  | IT/971 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of living room tile work |  | 212 | A | 2025-09-17
|  |  | IT/972 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of bath Tiles |  | 212 | R | 2025-09-17
|  |  | IT/972 R01 | 2025-09-19 | 2025-09-19 | tile work | Check the final inspection of bath Tiles |  | 212 | A | 2025-09-23
|  |  | IT/973 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of bath Tiles |  | 202 | A | 2025-09-17
|  | 7th floor | IT/974 | 2025-09-15 | 2025-09-15 | Brick work | Check Complete brick work (dressing and bed room wardrobe) |  | Grid A-F/01-26 | R | 2025-09-17
|  | 7th floor | IT/974 R01 | 2025-09-19 | 2025-09-19 | Brick work | Check Complete brick work (dressing and bed room wardrobe) |  | Grid A-F/01-26 | A | 2025-09-30 | CM
|  | 7th floor | IT/975 | 2025-09-15 | 2025-09-15 | Vanity wall | Check Dummy wall (vanity wall) |  | Grid A-F/01-26 | R | 2025-09-17
|  | 7th floor | IT/975 R01 | 2025-09-19 | 2025-09-19 | Vanity wall | Check Dummy wall (vanity wall) |  | Grid A-F/01-26 | A | 2025-09-30 | CM
|  | 5th floor | IT/976 | 2025-09-15 | 2025-09-15 | tile work | Check the final inspection of bed room Tiles |  | Grid C-F/01-04 | R | 2025-09-16 | Saqib
|  | 5th floor | IT/976 R01 | 2025-09-19 | 2025-09-19 | tile work | Check the final inspection of bed room Tiles |  | Grid C-F/01-04 | A | 2025-09-23 | CM
|  | 5th floor | IT/977 | 2025-09-15 | 2025-09-15 | tile work | Check the final inspection of living room Tiles |  | Grid C-F/01-04 | R | 2025-09-15
|  | 5th floor | IT/977 R01 | 2025-09-19 | 2025-09-19 | tile work | Check the final inspection of living room Tiles |  | Grid C-F/01-04 | A | 2025-09-23 | CM
|  | 9th floor | IT/978 | 2025-09-15 | 2025-09-15 | plaster work | Check leve point and allow to start plaster |  | 903. 904, 905 | A | 2025-09-17 | Mustansar
|  |  | IT/979 | 2025-09-17 | 2025-09-17 | ceiling work | Check the final inspection of ceiling work at 5th floor |  | 506 & 514 | B | 2025-09-23
|  |  | IT/979 R01 | 2025-10-08 | 2025-10-08 | ceiling work | Check the final inspection of ceiling work at 5th floor |  | 506 & 514 | A | 2025-10-10
|  | 9th floor | IT/980 | 2025-09-17 | 2025-09-17 | plaster work | Check plaster work and allow to start tile work |  | 903 & 905 | A | 2025-09-18
|  |  | IT/981 | 2025-09-18 | 2025-09-18 | ceiling work | Check the final inspection of ceiling work at 5th floor |  | 511 | A | s
|  |  | IT/982 | 2025-09-22 | 2025-09-22 | Level | Check level point and allow to start plaster work |  | Grid C-F/10-15 | A | 2025-09-23 | Mustansar
|  |  | IT/983 | 2025-09-22 | 2025-09-22 | Level | Check level point and allow to start plaster work |  | Grid C-F/16-23 | A | 2025-09-23 | Mustansar
|  | 7th floor | IT/984 | 2025-09-24 | 2025-09-24 | tile work | Check Final Inspection of Bed Room & Living room tile work |  | 701 | A | 2025-09-26
|  |  | IT/985 | 2025-09-24 | 2025-09-24 | tile work | Check Final Inspection of Bed Room & Living room tile work |  | 702 | A | 2025-09-26
|  |  | IT/986 | 2025-09-24 | 2025-09-24 | tile work | Check Final Inspection of Bed Room & Living room tile work |  | 704 | A | 2025-09-30
|  |  | IT/987 | 2025-09-24 | 2025-09-24 | tile work | Check Final Inspection of Bed Room & Living room tile work |  | 706 | A | 2025-09-30
|  |  | IT/988 | 2025-09-24 | 2025-09-24 | tile work | Check Final Inspection of Bed Room & Living room tile work |  | 708 | A | 2025-09-30
|  |  | IT/989 | 2025-09-25 | 2025-09-25 | reinforcement & formwork | Kindly check the horizontal band reinforcement & formwork and allow to start concrete at 8th floor of I-Tower |  | Grid A-C/26 | A | 2025-10-07
|  |  | IT/990 | 2025-09-25 | 2025-09-25 | tile work | Kindly check the final inspection of Bed rooms & Living Room tile work at 6th floor Apartment No. ( #602) of I-Tower |  | 602 | B | 2025-09-26
|  |  | IT/990 R01 | 2025-10-03 | 2025-10-03 | tile work | Kindly check the final inspection of Bed rooms & Living Room tile work at 6th floor Apartment No. ( #602) of I-Tower |  | 602 | A | 2025-10-10
|  |  | IT/991 | 2025-09-25 | 2025-09-25 | tile work | Kindly check the final inspection of Living Room tile work at 6th floor Apartment No. ( #605) of I-Tower |  | 605 | A | 2025-10-02
|  |  | IT/992 | 2025-09-25 | 2025-09-25 | tile work | Kindly check the final inspection of Living Room tile work at 6th floor Apartment No. ( #607) of I-Tower |  | 607 | A | 2025-10-02
|  |  | IT/993 | 2025-09-25 | 2025-09-25 | tile work | Kindly check the final inspection of Living Room tile work at 6th floor Apartment No. ( #609) of I-Tower |  | 609 | A | 2025-10-02
|  |  | IT/994 | 2025-09-25 | 2025-09-25 | tile work | Kindly check the final inspection of Living Room tile work at 6th floor Apartment No. ( #611) of I-Tower |  | 611 | A | 2025-10-02
|  |  | IT/995 | 2025-09-25 | 2025-09-25 | tile work | Kindly check the final inspection of Bed rooms & Living Room tile work at 6th floor Apartment No. ( #612) of I-Tower |  | 612 | B | 2025-09-26
|  |  | IT/995 R01 | 2025-10-03 | 2025-10-03 | tile work | Kindly check the final inspection of Bed rooms & Living Room tile work at 6th floor Apartment No. ( #612) of I-Tower |  | 612 | A | 2025-10-10
|  |  | IT/996 | 2025-09-25 | 2025-09-25 | tile work | Kindly check the final inspection of Bed rooms & Living Room tile work at 6th floor Apartment No. ( #615) of I-Tower |  | 615 | R | 2025-09-26
|  |  | IT/997 | 2025-09-27 | 2025-09-27 | tile work | Kindly check the final inspection of Bed rooms & Living Room tile work at 6th floor Apartment No. ( #604) of I-Tower |  | 604 | A | 2025-10-02
|  |  | IT/998 | 2025-09-27 | 2025-09-27 | ceiling work | Kindly check the final inspection of ceiling work at 4th floor [Except Pelmet] Apartment No.s ( #408) of I-Tower |  | 408 | R | 2025-10-02
|  |  | IT/999 | 2025-09-27 | 2025-09-27 | ceiling work | Kindly check the final inspection of ceiling work at 4th floor [Except Pelmet] Apartment No.s ( #416) of I-Tower |  | 416 | R | 2025-10-07
|  |  | IT/1000 | 2025-09-27 | 2025-09-27 | ceiling work | Kindly check the final inspection of ceiling work at 5th floor [Except Balcony & Pelmet] Apartment No.s ( #510) of I-Tower |  | 510 | A | 2025-10-02
|  |  | IT/1001 | 2025-09-27 | 2025-09-27 | ceiling work | Kindly check the final inspection of ceiling work at 5th floor Apartment No. ( #514) of I-Tower |  | 514 | A | 2025-10-02
|  |  | IT/1002 | 2025-09-27 | 2025-09-27 | ceiling work | Kindly check the final inception of ceiling work [Except Balcony & Pelmet] at 6th floor Apartment No. 606 of I-Tower |  | 606 | B | 2025-10-02
|  |  | IT/1003 | 2025-09-30 | 2025-09-30 | ceiling work | Kindly check the final inception of ceiling work [Except Balcony & Pelmet] at 6th floor Apartment No. 610 of I-Tower |  | 610 | R | 2025-10-02
|  |  | IT/1004 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #501) of I-Tower |  | 501 | B | 2025-10-02
|  |  | IT/1004 R01 | 2025-10-04 | 2025-10-04 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #501) of I-Tower |  | 501 | A | 2025-10-10
|  |  | IT/1005 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #502) of I-Tower |  | 502 | R | 2025-10-02
|  |  | IT/1005 R01 | 2025-10-16 | 2025-10-16 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #502) of I-Tower |  | 502 | R | 2025-10-18
|  |  | IT/1005 R02 | 2025-10-20 | 2025-10-20 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #502) of I-Tower |  | 502 | R | 2025-10-21
|  |  | IT/1005 R03 | 2025-11-07 | 2025-11-07 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #502) of I-Tower |  | 502 | R | 2025-11-10
|  |  | IT/1006 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #503) of I-Tower |  | 503 | B | 2025-10-02
|  |  | IT/1006 R01 | 2025-10-04 | 2025-10-04 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #503) of I-Tower |  | 503 | A | 2025-10-10
|  |  | IT/1007 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #504) of I-Tower | s | 504 | B | 2025-10-07
|  |  | IT/1007 R01 | 2025-10-08 | 2025-10-08 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #504) of I-Tower | s | 504 | A | 2025-10-10
|  |  | IT/1008 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #506) of I-Tower |  | 506 | B | 2025-10-07
|  |  | IT/1008 R01 | 2025-10-08 | 2025-10-08 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #506) of I-Tower |  | 506 | A | 2025-10-10
|  |  | IT/1009 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #508) of I-Tower |  | 508 | B | 2025-10-07
|  |  | IT/1009 R01 | 2025-10-08 | 2025-10-08 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #508) of I-Tower |  | 508 | A | 2025-10-10
|  |  | IT/1010 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #505) of I-Tower |  | 505 | B | 2025-10-07
|  |  | IT/1010 R01 | 2025-10-08 | 2025-10-08 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #505) of I-Tower |  | 505 | A | 2025-10-10
|  |  | IT/1011 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #507) of I-Tower |  | 507 | B | 2025-10-07
|  |  | IT/1011 R01 | 2025-10-08 | 2025-10-08 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #507) of I-Tower |  | 507 | A | 2025-10-10
|  |  | IT/1012 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #510) of I-Tower |  | 510 | B | 2025-10-07
|  |  | IT/1012 R01 | 2025-10-08 | 2025-10-08 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #510) of I-Tower |  | 510 | A | 2025-10-10
|  |  | IT/1013 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #514) of I-Tower |  | 514 | B | 2025-10-07
|  |  | IT/1013 R01\ | 2025-10-08 | 2025-10-08 | tile work | Kindly check the final inspection of bath floor tiles work at 5th floor Apartment No. ( #514) of I-Tower |  | 514 | A | 2025-10-10
|  |  | IT/1014 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #516) of I-Tower |  | 516 | A | 2025-10-02
|  |  | IT/1015 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #513) of I-Tower |  | 513 | B | 2025-10-07
|  |  | IT/1015 R01 | 2025-10-08 | 2025-10-08 | tile work | Kindly check the final inspection of bath floor & bath wall tiles work at 5th floor Apartment No. ( #513) of I-Tower |  | 513 | A | 2025-10-10
|  |  | IT/1016 | 2025-09-30 | 2025-09-30 | tile work | Kindly check the final inspection of bath wall tiles work at 1st floor Apartment No. ( #101) of I-Tower |  | 101 | A | 2025-10-08
|  |  | IT/1017 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath floor tiles work at 2nd floor Apartment No. ( #212) of I-Tower |  | 212 | B | 2025-10-02
|  |  | IT/1017 R01 | 2025-10-06 | 2025-10-06 | tile work | Kindly check the final inspection of bath floor tiles work at 2nd floor Apartment No. ( #212) of I-Tower |  | 212 | A | 2025-10-07
|  |  | IT/1018 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath wall tiles work at 5th floor Apartment No. ( #515) of I-Tower |  | 515 | B | 2025-10-07
|  |  | IT/1018 R01 | 2025-10-08 | 2025-10-08 | tile work | Kindly check the final inspection of bath wall tiles work at 5th floor Apartment No. ( #515) of I-Tower |  | 515 | A | 2025-10-10
|  |  | IT/1019 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #604) of I-Tower |  | 604 | B | 2025-10-02
|  |  | IT/1019 R01 | 2025-10-21 | 2025-10-21 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #604) of I-Tower |  | 604 | B | 2025-10-23
|  |  | IT/1020 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #605) of I-Tower |  | 605 | A | 2025-10-02
|  |  | IT/1021 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #607) of I-Tower |  | 607 | A | 2025-10-02
|  |  | IT/1022 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #608) of I-Tower |  | 608 | B | 2025-10-02
|  |  | IT/1023 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of Bed rooms & Living Room tile work at 7th floor Apartment No. ( #703) of I-Tower |  | 703 | B | 2025-10-02
|  |  | IT/1023 R01 | 2025-10-04 | 2025-10-04 | tile work | Kindly check the final inspection of Bed rooms & Living Room tile work at 7th floor Apartment No. ( #703) of I-Tower |  | 703 | A | 2025-10-11
|  |  | IT/1024 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of Bed rooms tile work at 7th floor Apartment No. ( #714) of I-Tower |  | 714 | A | 2025-12-15
|  |  | IT/1024 R01 | 2025-10-13 | 2025-10-13 | tile work | Kindly check the final inspection of Bed rooms tile work at 7th floor Apartment No. ( #714) of I-Tower |  | 714 | OP
|  |  | IT/1025 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of Bed rooms tile work at 8th floor Apartment No. ( #804) of I-Tower |  | 804 | A | 2025-10-02
|  |  | IT/1026 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of Bed rooms tile work at 8th floor Apartment No. ( #807) of I-Tower |  | 807 | B | 2025-10-02
|  |  | IT/1027 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of Bed rooms tile work at 8th floor Apartment No. ( #808) of I-Tower |  | 808 | B | 2025-10-02
|  |  | IT/1028 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of Bed rooms tile work at 8th floor Apartment No. ( #810) of I-Tower |  | 810 | B | 2025-10-02
|  |  | IT/1029 | 2025-10-01 | 2025-10-01 | ceiling work | Kindly check the final inspection of ceiling work at 5th floor Apartment No. ( #516) of I-Tower |  | 516 | A | 2025-10-02
|  |  | IT/1030 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of Bed rooms tile work at 8th floor Apartment No. ( #812) of I-Tower |  | 812 | B | 2025-10-02
|  |  | IT/1031 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of Bed rooms tile work at 8th floor Apartment No. ( #814) of I-Tower |  | 814 | B | 2025-10-02
|  |  | IT/1032 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of living room tile work at 8th floor Apartment No. ( #804) of I-Tower |  | 804 | A | 2025-10-02
|  |  | IT/1033 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #609) of I-Tower |  | 609 | B | 2025-10-02
|  |  | IT/1033 R1 | 2025-10-14 | 2025-10-14 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #609) of I-Tower |  | 609 | B | 2025-10-15
|  |  | IT/1034 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #610) of I-Tower |  | 610 | B | 2025-10-02
|  |  | IT/1034 R01 | 2025-10-21 | 2025-10-21 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #610) of I-Tower |  | 610 | A | 2025-10-23
|  |  | IT/1035 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #612) of I-Tower |  | 612 | B | 2025-10-02
|  |  | IT/1035 R1 | 2025-10-21 | 2025-10-21 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #612) of I-Tower |  | 612 | A | 2025-10-23
|  |  | IT/1036 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #614) of I-Tower |  | 614 | B | 2025-10-02
|  |  | IT/1036 R01 | 2025-10-21 | 2025-10-21 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #614) of I-Tower |  | 614 | A | 2025-10-23
|  |  | IT/1037 | 2025-10-01 | 2025-10-01 | tile work | Kindly check the final inspection of bath wall tiles work at 6th floor Apartment No. ( #611) of I-Tower |  | 611 | B | 2025-10-02
|  |  | IT/1038 | 2025-10-02 | 2025-10-02 | plaster work | Kindly check the plaster work and allow to start tiles work at 7th floor apartment No. 715 of I-Tower |  | 715 | A | 2025-10-02
|  |  | IT/1039 | 2025-10-02 | 2025-10-02 | ceiling work | Check the final Inspection of balcony Ceiling Work |  | 110 | A | 2025-10-08
|  |  | IT/1039 R1 | 2025-10-22 | 2025-10-22 | ceiling work | Check the final Inspection of balcony Ceiling Work |  | 110 | A | 2025-10-23
|  |  | IT/1040 | 2025-10-03 | 2025-10-03 | tile work | Check final inspection of living room tile works |  | 515 | A | 2025-10-10
|  |  | IT/1041 | 2025-10-04 | 2025-10-04 | tile work | Check the final Inspection of vanity wall tile work on the Bath/PWR/LND at 2nd floor |  | 205-207, 210 | R | 2025-10-07
|  |  | IT/1042 | 2025-10-04 | 2025-10-04 | tile work | Check the final Inspection of vanity wall tile work on the Bath/PWR/LND at 2nd floor |  | 211, 213, 216 | R | 2025-10-07
|  |  | IT/1043 | 2025-10-04 | 2025-10-04 | tile work | Check the final Inspection of vanity wall tile work on the Bath/PWR/LND at 5th\ floor |  | 501-504 | A | 2025-10-10
|  |  | IT/1044 | 2025-10-04 | 2025-10-04 | tile work | Check the final Inspection of vanity wall tile work on the Bath/PWR/LND at 5th\ floor |  | 505507509510 | A | 2025-10-10
|  |  | IT/1045 | 2025-10-04 | 2025-10-04 | tile work | Check the final Inspection of vanity wall tile work on the Bath/PWR/LND at 5th\ floor |  | 511512514 | A | 2025-10-10
|  |  | IT/1046 | 2025-10-04 | 2025-10-04 | ceiling work | Check ceiling work |  | 501 | A | 2025-10-10
|  |  | IT/1046 R01 | 2025-10-22 | 2025-10-22 | ceiling work | Check ceiling work |  | 501 | A | 2025-10-23
|  |  | IT/1047 | 2025-10-04 | 2025-10-04 | ceiling work | Check ceiling work |  | 502 | A | 2025-10-10
|  |  | IT/1047 R01 | 2025-10-22 | 2025-10-22 | ceiling work | Check ceiling work |  | 502 | A | 2025-10-23
|  |  | IT/1048 | 2025-10-04 | 2025-10-04 | tile work | Check the bath floor tile work |  | 509 | A | 2025-10-10
|  |  | IT/1049 | 2025-10-04 | 2025-10-04 | tile work | Check the bath floor tile work |  | 512 | A | 2025-10-10
|  |  | IT/1050 | 2025-10-04 | 2025-10-04 | tile work | Check Final Inspection of Bed Room & Living room tile work |  | 801 | A | 2025-10-11 | Mustansar
|  |  | IT/1051 | 2025-10-04 | 2025-10-04
|  |  | IT/1052 | 2025-10-04 | 2025-10-04 | tile work | Check Final Inspection of Bed Room & Living room tile work |  | 803 | A | 2025-10-11 | Mustansar
|  |  | IT/1053 | 2025-10-04 | 2025-10-04 | tile work | Check Final Inspection of Bed Room & Living room tile work |  | 804 | A | 2025-10-11 | Mustansar
|  |  | IT/1054 | 2025-10-04 | 2025-10-04 | tile work | Check Final Inspection of Bed Room & Living room tile work |  | 806 | A | 2025-10-11 | Mustansar
|  |  | IT/1055 | 2025-10-06 | 2025-10-06 | tile work | Check the bath floor and bath wall tiles work on the bath/PWR/LND |  | 201 | A | 2025-10-09
|  |  | IT/1056 | 2025-10-06 | 2025-10-06 | tile work | Check the bath floor and bath wall tiles work on the bath/PWR/LND |  | 208 | A | 2025-10-09
|  |  | IT/1057 | 2025-10-06 | 2025-10-06 | tile work | Check the bath floor and bath wall tiles work on the bath/PWR/LND |  | 508 | A | 2025-10-10
|  |  | IT/1058 | 2025-10-07 | 2025-10-07 | tile work | Check the bath floor tiles work |  | 511 | A | 2025-10-10
|  |  | IT/1059 | 2025-10-07 | 2025-10-07 | tile work | Check the bath floor tiles work |  | 515 | A | 2025-10-10
|  |  | IT/1060 | 2025-10-08 | 2025-10-08 | tile work | Check the Bed room tile works |  | 212 | A | 2025-10-09
|  |  | IT/1061 | 2025-10-08 | 2025-10-08 | tile work | Check the Balcony tile works |  | 209, 211 | A | 2025-10-09
|  |  | IT/1062 | 2025-10-08 | 2025-10-08 | tile work | Check the Balcony tile works |  | 214, 216 | A | 2025-10-09
|  |  | IT/1063 | 2025-10-09 | 2025-10-09 | tile work | Check the Balcony tile works |  | 205, 210 , 213 | A | 2025-10-10
|  |  | IT/1064 | 2025-10-09 | 2025-10-09 | tile work | Check the Balcony tile works |  | 501, 504 | A | 2025-10-11
|  |  | IT/1065 | 2025-10-09 | 2025-10-09 | tile work | Check the Balcony tile works |  | 511-513 | A | 2025-10-11
|  |  | IT/1066 | 2025-10-09 | 2025-10-09 | tile work | Check the Balcony tile works |  | 514, 516 | A | 2025-10-11
|  |  | IT/1067 | 2025-10-10 | 2025-10-10 | ceiling work | Check ceiling work |  | 513 | R | 2025-10-11
|  |  | IT/1067 R01 | 2025-10-13 | 2025-10-13 | ceiling work | Check ceiling work |  | 513 | A | 2025-10-14
|  |  | IT/1068 | 2025-10-10 | 2025-10-10 | tile work | heck the Bath tiles Work |  | 101 | A | 2025-10-11
|  |  | IT/1069 | 2025-10-11 | 2025-10-11 | ceiling work | Check the Ceiling work |  | 607 | A | 2025-10-11
|  |  | IT/1070 | 2025-10-11 | 2025-10-11 | ceiling work | Check the Ceiling work |  | 611 | A | 2025-10-11
|  |  | IT/1071 | 2025-10-13 | 2025-10-13 | tile work | Check the Balcony tile works |  | 604,612, 614 | A | 2025-10-13
|  |  | IT/1072 | 2025-10-13 | 2025-10-13 | tile work | Check the Living Room tile works |  | 613 | A | 2025-10-13
|  |  | IT/1073 | 2025-10-13 | 2025-10-13 | tile work | Check the Living Room tile works |  | 614 | A | 2025-10-13
|  |  | IT/1074 | 2025-10-14 | 2025-10-14 | tile work | Check the Balcony tile works |  | 204, 207 | B | 2025-10-15
|  |  | IT/1074 R01 | 2025-10-23 | 2025-10-23 | tile work | Check the Balcony tile works |  | 204, 207 | A | 2025-10-24
|  |  | IT/1075 | 2025-10-14 | 2025-10-14 | tile work | Check the Balcony tile works |  | 208, 212 | B | 2025-10-15
|  |  | IT/1075 R01 | 2025-10-23 | 2025-10-23 | tile work | Check the Balcony tile works |  | 208, 212 | A | 2025-10-24
|  |  | IT/1076 | 2025-10-13 | 2025-10-13 | tile work | Check the bath floor tiles work |  | 203 | R | 2025-10-14
|  |  | IT/1076 R01 | 2025-10-20 | 2025-10-20 | tile work | Check the bath floor tiles work |  | 203 | A | 2025-10-24
|  |  | IT/1077 | 2025-10-14 | 2025-10-14 | tile work | Check the Balcony tile works |  | 503, 505 | B | 2025-10-15
|  |  | IT/1077 R01 | 2025-10-31 | 2025-10-31 | tile work | Check the Balcony tile works |  | 503, 505 | A | 2025-11-01
|  |  | IT/1078 | 2025-10-14 | 2025-10-14 | tile work | Check the Balcony tile works |  | 507, 509 | B | 2025-10-15
|  |  | IT/1078 R01 | 2025-10-28 | 2025-10-28 | tile work | Check the Balcony tile works |  | 507, 509 | A | 2025-10-29
|  |  | IT/1079 | 2025-10-14 | 2025-10-14 | tile work | Check the Balcony tile works |  | 605, 607, 609 | R | 2025-10-15
|  |  | IT/1079 R01 | 10/31\/2025 | 2025-10-31 | tile work | Check the Balcony tile works |  | 605, 607, 609 | A | 2025-11-01
|  |  | IT/1080 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor tiles work |  | 605 | A | 2025-10-15
|  |  | IT/1081 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor tiles work |  | 607 | A | 2025-10-15
|  |  | IT/1082 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor tiles work |  | 609 | A | 2025-10-15
|  |  | IT/1083 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor And Bath wall tiles work |  | 603 | B | 2025-10-15
|  |  | IT/1083 R01 | 2025-11-07 | 2025-11-07 | tile work | Check the bath floor And Bath wall tiles work |  | 603 | B | 2025-11-10
|  |  | IT/1084 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor tiles work |  | 604 | A | 2025-10-15
|  |  | IT/1085 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor tiles work |  | 606 | A | 2025-10-15
|  |  | IT/1086 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor tiles work |  | 608 | A | 2025-10-15
|  |  | IT/1087 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor tiles work |  | 610 | B | 2025-10-15
|  |  | IT/1087 R01 | 2025-10-21 | 2025-10-21 | tile work | Check the bath floor tiles work |  | 610 | A | 2025-10-23
|  |  | IT/1088 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor tiles work |  | 611 | A | 2025-10-15
|  |  | IT/1089 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor tiles work |  | 612 | A | 2025-10-15
|  |  | IT/1090 | 2025-10-14 | 2025-10-14 | tile work | Check the bath floor tiles work |  | 613 | A | 2025-10-15
|  |  | IT/1091 | 2025-10-14 | 2025-10-14 | tile work | Check the Balcony tile works |  | 502, 508 | B | 2025-10-15
|  |  | IT/1091 R01 | 2025-10-28 | 2025-10-28 | tile work | Check the Balcony tile works |  | 502, 508 | A | 2025-10-29
|  |  | IT/1092 | 2025-10-15 | 2025-10-15 | tile work | Check the Balcony tile works |  | 510 | A | 2025-10-16
|  |  | IT/1093 | 2025-10-15 | 2025-10-15 | ceiling work | Check the Ceiling work at corridor |  | 1st floor | A | 2025-10-18
|  |  | IT/1094 | 2025-10-16 | 2025-10-16 | ceiling work | Check the Ceiling work |  | 605 | A | 2025-10-18
|  |  | IT/1095 | 2025-10-16 | 2025-10-16 | ceiling work | Check the Ceiling work |  | 615 | A | 2025-10-18
|  |  | IT/1096 | 2025-10-17 | 2025-10-17 | ceiling work | Check the Ceiling work |  | 601 | B | 2025-10-20
|  |  | IT/1096 R01 | 2025-10-29 | 2025-10-29 | ceiling work | Check the Ceiling work |  | 601 | A | 2025-10-31
|  |  | IT/1097 | 2025-10-17 | 2025-10-17 | ceiling work | Check the Ceiling work Bed room and Living Pelmet |  | 602 | B | 2025-10-20
|  |  | IT/1098 | 2025-12-18 | 2025-12-18 | ceiling work | Check the Ceiling work |  |  |  | 2025-10-21
|  |  | IT/1099 | 2025-10-20 | 2025-10-20 | ceiling work | Check the Ceiling work |  | 610 | A | 2025-10-21
|  |  | IT/1100 | 2025-10-20 | 2025-10-20 | Brick work | Check the brickwork of male locker room, female locker room & OHWT brickwork |  | Top floor | A | 2025-10-23
|  |  | IT/1101 | 2025-10-20 | 2025-10-20 | ceiling work | Check the Peimet ceiling work |  | 108 | A | 2025-10-21
|  |  | IT/1102 | 2025-10-21 | 2025-10-21 | tile work | Check the bath floor tiles work at 6th floor |  | 601 | A | 2025-10-23
|  |  | IT/1103 | 2025-10-21 | 2025-10-21 | tile work | Check the bath floor tiles work at 6th floor |  | 602 | A | 2025-10-23
|  |  | IT/1104 | 2025-10-21 | 2025-10-21 | tile work | Check the bath floor tiles work at 6th floor |  | 614 | A | 2025-10-23
|  |  | IT/1105 | 2025-10-21 | 2025-10-21 | tile work | Check the Bath/PWR/LND wall tiles work |  | 601 | A | 2025-10-23
|  |  | IT/1106 | 2025-10-21 | 2025-10-21 | tile work | Check the Bath/PWR/LND wall tiles work |  | 602 | A | 2025-10-23
|  |  | IT/1107 | 2025-10-21 | 2025-10-21 | tile work | Check the Bath/PWR/LND wall tiles work |  | 606 | A | 2025-10-23
|  |  | IT/1108 | 2025-10-21 | 2025-10-21 | tile work | Check the Bath/PWR/LND wall tiles work |  | 613 | A | 2025-10-23
|  |  | IT/1109 | 2025-10-21 | 2025-10-21 | tile work | Check the Living Room tile works |  | 608 | A | 2025-10-23
|  |  | IT/1110 | 2025-10-21 | 2025-10-21 | tile work | Check the Living Room tile works |  | 610 | A | 2025-10-23
|  |  | IT/1111 | 2025-10-21 | 2025-10-21 | ceiling work | Check the mark point of excess panel and allow to start remove existing ceiling sheet |  | 201-216 | A | 2025-10-29
|  |  | IT/1112 | 2025-10-21 | 2025-10-21 | Brick work | Check the complete brick masonry of internal side of façade |  | 6th floor | A | 2025-10-23
|  |  | IT/1113 | 2025-10-21 | 2025-10-21 | Brick work | Check the complete brick masonry of internal side of façade |  | 7th floor | A | 2025-10-21
|  |  | IT/1114 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 702 | B | 2025-10-23 |  |  |  | 2025-10-22
|  |  | IT/1114 R01 | 2025-11-07 | 2025-11-07 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 702 | A | 2025-11-11 |  |  |  | 2025-10-22
|  |  | IT/1115 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 703 | B | 2025-10-23
|  |  | IT/1115 R01 | 2025-11-07 | 2025-11-07 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 703 | A | 2025-11-11
|  |  | IT/1116 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 704 | A | 2025-12-15
|  |  | IT/1116 R01 | 2025-11-07 | 2025-11-07 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 704 | R | 2025-11-11
|  |  | IT/1117 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 706 | B | 2025-10-23
|  |  | IT/1117 R01 | 2025-11-07 | 2025-11-07 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 706 | R | 2025-11-11
|  |  | IT/1118 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 708 | A | 2025-12-15
|  |  | IT/1118 R01 | 2025-11-07 | 2025-11-07 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 708 | R | 2025-11-11
|  |  | IT/1119 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 701 | A | 2025-12-15
|  |  | IT/1119 R01 | 2025-11-07 | 2025-11-07 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 701 | R | 2025-11-11
|  |  | IT/1120 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 711 | B | 2025-10-23
|  |  | IT/1121 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 803 | A | 2025-10-23
|  |  | IT/1122 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 804 | R | 2025-10-23
|  |  | IT/1122 R1 | 2025-11-11 | 2025-11-11 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 804 | A | 2025-11-14
|  |  | IT/1123 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 806 | B | 2025-10-23
|  |  | IT/1124 | 2025-10-22 | 2025-10-22 | Tile work | Check the Bath/PWR/LND wall tiles work |  | 805 | B | 2025-10-23
|  |  | IT/1125 | 2025-10-23 | 2025-10-23 | ceiling work | Check the cleaning work and allow to start plaster work |  | 1001 & 1008 | A | 2025-10-23
|  |  | IT/1126 | 2025-10-23 | 2025-10-23 | tile work | Check the Balcony tile works |  | 201-203 | A | 2025-10-27
|  |  | IT/1127 | 2025-10-24 | 2025-10-24 | plaster work | Check the cleaning work and allow to start plaster work |  | 1005 | A | 2025-10-28
|  |  | IT/1128 | 2025-10-24 | 2025-10-24 | plaster work | Check the plaster work |  | 808 | A | 2025-10-24
|  |  | IT/1129 | 2025-10-24 | 2025-10-24 | plaster work | Check the cleaning work and allow to start plaster work |  | 1010 | A | 2025-10-28
|  |  | IT/1130 | 2025-10-25 | 2025-10-25 | plaster work | Check the cleaning work and allow to start plaster work |  | 1004, 1007 | A | 2025-10-28
|  |  | IT/1131 | 2025-10-25 | 2025-10-25 | plaster work | Check the cleaning work and allow to start plaster work |  | 815 | A | 2025-10-29
|  |  | IT/1132 | 2025-10-25 | 2025-10-25 | tile work | Check the bed room tile works |  | 201 | A | 2025-10-28
|  |  | IT/1133 | 2025-10-27 | 2025-10-27 | plaster work | Check the cleaning work and allow to start plaster work |  | 1009, 1014 | A | 2025-10-31
|  |  | IT/1134 | 2025-10-28 | 2025-10-28 | tile work | Check the Balcony tile works |  | 608, 610 | A | 2025-10-29
|  |  | IT/1135 | 2025-10-28 | 2025-10-28 | tile work | Check the Balcony tile works |  | 613, 616 | A | 2025-10-29
|  |  | IT/1136 | 2025-10-28 | 2025-10-28 | tile work | Check the bath floor and bath wall tiles work |  | 616 | A | 2025-10-29
|  |  | IT/1137 | 2025-10-28 | 2025-10-28 | ceiling work | Check the ceiling work |  | 705 | A | 2025-10-29
|  |  | IT/1138 | 2025-10-28 | 2025-10-28 | ceiling work | Check the ceiling work |  | 707 | A | 2025-10-29
|  |  | IT/1139 | 2025-10-29 | 2025-10-29 | ceiling work | Check the ceiling work |  | 602 | A | 2025-10-31
|  |  | IT/1140 | 2025-10-30 | 2025-10-30 | ceiling work | Check the ceiling work |  | 708 | R | 2025-10-31
|  |  | IT/1140 R01 | 2025-11-14 | 2025-11-14 | ceiling work | Check the ceiling work |  | 708 | A | 2025-11-18
|  |  | IT/1141 | 2025-10-31 | 2025-10-31 | tile work | Check the Balcony tile works |  | 603 | A | 2025-11-01
|  |  | IT/1142 | 2025-10-31 | 2025-10-31 | tile work | Check the bed room room & Living room |  | 815 | A | 2025-11-05
|  |  | IT/1143 | 2025-10-31 | 2025-10-31 | tile work | Check the plaster work and allow to start tile work |  | 1001, 1002, 1004, 1006, 1008 | R | 2025-11-10
|  |  | IT/1144 | 2025-10-31 | 2025-10-31 | tile work | Check the plaster work and allow to start tile work |  | 1010, 1012, 1014 | A | 2025-11-14
|  |  | IT/1145 | 2025-10-31 | 2025-10-31 | tile work | Check the plaster work and allow to start tile work |  | 1005, 1007 | A | 2025-11-10
|  |  | IT/1146 | 2025-10-31 | 2025-10-31 | plaster work | Check the cleaning work and allow to start plaster work |  | 1016 | OP
|  |  | IT/1147 | 2025-10-31 | 2025-10-31 | tile work | Check the bed room room & Living room |  | 901902904 | A | 2025-11-05
|  |  | IT/1148 | 2025-11-01 | 2025-11-01 | tile work | Check the bath wall tiles work at 2nd floor |  | 203 | A | 2025-11-05
|  |  | IT/1149 | 2025-11-07 | 2025-11-07 | ceiling work | Check the access panel, pelmet ceiling work & repairing work |  | 1st floor | OP
|  |  | IT/1150 | 2025-11-04 | 2025-11-04 | tile work | Check the bath floor and wall tiles works at 7th floor |  | 705 | A | 2025-12-15
|  |  | IT/1151 | 2025-11-04 | 2025-11-04 | tile work | Check the bath floor and wall tiles works at 7th floor |  | 707 | A | 2025-12-15
|  |  | IT/1152 | 2025-11-04 | 2025-11-04 | tile work | Check the bath floor and wall tiles works at 7th floor |  | 710 | A | 2025-11-10
|  |  | IT/1153 | 2025-11-04 | 2025-11-04 | tile work | Check the bath floor and wall tiles works at 7th floor |  | 712 | A | 2025-12-15
|  |  | IT/1154 | 2025-11-04 | 2025-11-04 | tile work | Check the bed room and living room tile works |  | 716 | A | 2025-11-10
|  |  | IT/1155 | 2025-11-04 | 2025-11-04 | ceiling work | Check the ceiling work at 5th floor |  | 515 | A | 2025-11-10
|  |  | IT/1156 | 2025-11-04 | 2025-11-04 | tile work | Check the Living Room tile works |  | 603 | A | 2025-11-10
|  |  | IT/1157 | 2025-11-04 | 2025-11-04 | plaster work | Check the cleaning work and allow to start plaster work |  | corridor(Zone 1-3) | A | 2025-11-10
|  |  | IT/1158 | 2025-11-06 | 2025-11-06 | level | Check the level ponts for screed flooring at ground floor |  | GF | A | 2025-11-11
|  |  | IT/1159 | 2025-11-07 | 2025-11-07 | Tile work | Check the bed room and living room tiles work |  | 903 | A | 2025-11-12
|  |  | IT/1160 | 2025-11-07 | 2025-11-07 | Tile work | Check the bed room and living room tiles work |  | 906 | A | 2025-11-12
|  |  | IT/1161 | 2025-11-07 | 2025-11-07 | Tile work | Check the Balcony tile works |  | 202 | A | 2025-11-10
|  |  | IT/1162 | 2025-11-07 | 2025-11-07 | Tile work | Check the Balcony tile works |  | 601 | A | 2025-11-10
|  |  | IT/1163 | 2025-11-07 | 2025-11-07 | Tile work | Check the living room tile work |  | 606 | R | 2025-11-10
|  |  | IT/1164 | 2025-11-07 | 2025-11-07 | ceiling work | Check the ceiling work |  | 201 | A | 2025-11-10
|  |  | IT/1165 | 2025-11-08 | 2025-11-08 | access panel | Check the access panel, pelmet ceiling work & repairing work |  | 1st floor zone 2 | A | 2025-11-12
|  |  | IT/1166 | 2025-11-08 | 2025-11-08 | access panel | Check the access panel, pelmet ceiling work & repairing work |  | 1st floor zone 3 | A | 2025-11-11
|  |  | IT/1167 | 2025-11-10 | 2025-11-10 | ceiling work | Check the ceiling work |  | 509 | B | 2025-11-12
|  |  | IT/1168 | 2025-11-10 | 2025-11-10 | ceiling work | Check the ceiling work balcony and pelmet |  | 510 | B | 2025-11-12
|  |  | IT/1169 | 2025-11-10 | 2025-11-10 | level | Check the level of screeding Flooring |  | GF
|  |  | IT/1170 | 2025-11-11 | 2025-11-11 | ceiling work | Check the Ceiling work |  | 710 | A | 2025-11-14
|  |  | IT/1171 | 2025-11-11 | 2025-11-11 | ceiling work | Check the Ceiling work |  | 702 | A | 2025-11-18
|  |  | IT/1172 | 2025-11-11 | 2025-11-11 | ceiling work | Check the Ceiling work |  | 709 | A | 2025-11-14
|  |  | IT/1173 | 2025-11-11 | 2025-11-11 | ceiling work | Check the Ceiling work |  | 712 | A | 2025-11-14
|  |  | IT/1174 | 2025-11-11 | 2025-11-11 | Tile work | Check the bath PWD/LND wall and floor tiles work |  | 801 | A | 2025-11-14
|  |  | IT/1175 | 2025-11-11 | 2025-11-11 | Tile work | Check the bath PWD/LND wall and floor tiles work |  | 802 | A | 2025-11-14
|  |  | IT/1176 | 2025-11-11 | 2025-11-11 | Tile work | Check the bath PWD/LND wall and floor tiles work |  | 803 | A | 2025-11-14
|  |  | IT/1177 | 2025-11-12 | 2025-11-12 | Brick work | Check the dismantling of brick work |  | GF Zone 3 | A | 2025-11-14
|  |  | IT/1178 | 2025-11-12 | 2025-11-12 | Layout | Check the layout of wall and allow to start brick masnory |  | GF | OP
|  |  | IT/1178 R01 | 2025-11-22 | 2025-11-22 | Layout | Check the layout of wall and allow to start brick masnory |  | GF | A | 2025-11-26
|  |  | IT/1179 | 2025-11-13 | 2025-11-13 | ceiling work | Check the Ceiling work |  | 713 | OP
|  |  | IT/1179 R1 | 2025-11-20 | 2025-11-20 | ceiling work | Check the Ceiling work |  | 713 | A | 2025-11-21
|  |  | IT/1180 | 2025-11-13 | 2025-11-13 | ceiling work | Check the Ceiling work |  | 715 | A | 2025-11-18
|  |  | IT/1181 | 2025-11-13 | 2025-11-13 | ceiling work | Check the Ceiling work |  | 714 | A | 2025-11-14
|  |  | IT/1182 | 2025-11-15 | 2025-11-15 | Brick work | Check the complete brick masonry of internal side of façade |  | 8th floor | A | 2025-11-21
|  |  | IT/1183 | 2025-11-15 | 2025-11-15 | level | Check the level points and allow to start plaster work on internal side of façade |  | 8th floor | A | 2025-11-21
|  |  | IT/1183 R02 | 2025-11-20 | 2025-11-20 | level | Check the level points and allow to start plaster work on internal side of façade |  | 8th floor | A | 2025-11-21
|  |  | IT/1184 | 2025-11-14 | 2025-11-14 | tile work | Check the bath PWD/LND wall and floor tiles work |  | 805 | A | 2025-11-21
|  |  | IT/1185 | 2025-11-28 | 2025-11-29 | tile work | Check the bed room and living room tiles work | 8th floor | 807 | A | 2025-12-01
|  |  | IT/1186 | 2025-11-15 | 2025-11-15 | level | Check the level points for sereed flooring at GF Business center |  | Zone 3 | A | 2025-11-18
|  |  | IT/1187 | 2025-11-17 | 2025-11-17 | ceiling work | Check the ceiling work |  | 716 | A | 2025-11-18
|  |  | IT/1188 | 2025-11-19 | 2025-11-19 | ceiling work | Check the ceiling work |  | 711 | A | 2025-11-20
|  |  | IT/1189 | 2025-11-19 | 2025-11-19 | tile work | Check the bed room and living room tiles work |  | 905 | A | 2025-11-20
|  |  | IT/1190 | 2025-11-19 | 2025-11-19 | tile work | Check the bed room and living room tiles work |  | 907 | A | 2025-11-20
|  |  | IT/1191 | 2025-11-19 | 2025-11-19 | tile work | Check the bed room and living room tiles work |  | 908 | A | 2025-11-20
|  |  | IT/1192 | 2025-11-19 | 2025-11-19 | tile work | Check the bed room and living room tiles work |  | 909 | A | 2025-11-21
|  |  | IT/1193 | 2025-11-19 | 2025-11-19 | tile work | Check the bed room and living room tiles work |  | 910 | A | 2025-11-20
|  |  | IT/1194 | 2025-11-19 | 2025-11-19 | tile work | Check the bed room and living room tiles work |  | 912 | A | 2025-11-21
|  |  | IT/1195 | 2025-11-28 | 2025-11-29 | tile work | Check the bed room and living room tiles work | 8th floor | 806 | B | 2025-12-01
|  |  | IT/1196 | 2025-11-20 | 2025-11-20 | tile work | Check the Bath/PWR/LND wall tiles work |  | 809 | A | 2025-11-21
|  |  | IT/1197 | 2025-11-20 | 2025-11-20 | tile work | Check the Bath/PWR/LND wall tiles work |  | 811 | A | 2025-11-21
|  |  | IT/1198 | 2025-11-20 | 2025-11-20 | tile work | Check the Bath/PWR/LND wall tiles work |  | 812 | A | 2025-11-21
|  |  | IT/1199 | 2025-11-20 | 2025-11-20 | tile work | Check the Bath/PWR/LND wall tiles work |  | 814 | A | 2025-11-21
|  |  | IT/1200 | 2025-11-20 | 2025-11-20 | tile work | Check the Bath/PWR/LND wall tiles work |  | 810 | A | 2025-11-21
|  |  | IT/1201 | 2025-12-16 | 2025-12-16 | tile work | Check the bed room and living room tiles work | 9th floor | 914
|  |  | IT/1202 | 2025-12-16 | 2025-12-16 | tile work | Check the bed room and living room tiles work | 9th floor | 916
IT/1203
|  |  | IT/1204 | 2025-11-25 | 2025-11-25 | level | Check the level points,chicken mesh, corner beads and allow to start plaster work | 11th floor | 1102 | OP
|  |  | IT/1205 | 2025-11-21 | 2025-11-21 | Tile work | Check the bed room and living room tiles work |  | 811 | OP
|  |  | IT/1206 | 2025-11-21 | 2025-11-21 | Tile work | Check the bed room and living room tiles work |  | 812 | A | 2025-11-24
|  |  | IT/1207 | 2025-11-21 | 2025-11-21 | Tile work | Check the bed room and living room tiles work | 813 | 813 | A | 2025-11-24
|  |  | IT/1208 | 2025-11-21 | 2025-11-21 | Tile work | Check the bed room and living room tiles work |  | 814 | A | 2025-11-24
|  |  | IT/1209 | 2025-11-21 | 2025-11-21 | Tile work | Check the bed room and living room tiles work |  | 816 | A | 2025-11-24
|  |  | IT/1210 | 2025-11-21 | 2025-11-21 | Tile work | Check the bed room and living room tiles work |  | 911 | A | 2025-11-24
|  |  | IT/1211 | 2025-11-21 | 2025-11-21 | Tile work | Check the bed room and living room tiles work | 9th floor | 913 | A | 2025-11-24
|  |  | IT/1212 | 2025-11-22 | 2025-11-22 | level | Check the level points,chicken mesh, corner beads and allow to start plaster work | Top roof to GF |  | A | 2025-11-25
|  |  | IT/1213 | 2025-11-22 | 2025-11-22 | Tile work | Check the Bath/PWR/LND wall tiles work | 9th floor | 901 | A | 2025-11-24
|  |  | IT/1214 | 2025-11-22 | 2025-11-22 | Tile work | Check the Bath/PWR/LND wall tiles work | 9th floor | 902 | A | 2025-11-24
|  |  | IT/1215 | 2025-11-22 | 2025-11-22 | Tile work | Check the Bath/PWR/LND wall tiles work | 9th floor | 903 | A | 2025-11-24
|  |  | IT/1216 | 2025-11-22 | 2025-11-22 | Tile work | Check the Bath/PWR/LND wall tiles work | 9th floor | 904 | A | 2025-11-24
|  |  | IT/1217 | 2025-11-28 | 2025-11-29 | Tile work | Check the bed room and living room tiles work | 8th floor | 813 | A | 2025-12-04
|  |  | IT/1218 | 2025-11-28 | 2025-11-29 | ceiling work | Check the ceiling work | 8th floor | 805 | R | 2025-12-04
|  |  | IT/1219 | 2025-11-23 | 2025-11-23 | Reinforcement & Formwork | Check the epoxy , reinforcement ,formwork & allow to start concrete beam & slab at roof slab | Zone 3 |  | A | 2025-11-25
|  |  | IT/1220 | 2025-11-28 | 2025-11-29 | Reinforcement & Formwork | Check the reinforcement ,formwork & allow to start concrete Lift lintel zone 01 at 5th & 9th | Zone 1 | 11th & 10th | A | 2025-12-01
|  |  | IT/1221 | 2025-11-27 | 2025-11-27 | Reinforcement & Formwork | Check the reinforcement ,formwork & allow to start concrete Lift lintel zone 01 at 5th & 9th | Zone 1 |  | OP
IT/1222
|  |  | IT/1223 | 2025-12-01 | 2025-12-02
|  |  | IT/1224 | 2025-12-01 | 2025-12-02 | ceiling work | Check the ceiling work | 8th floor | 808 | A | 2025-12-04
|  |  | IT/1225 | 2025-12-01 | 2025-12-02 | ceiling work | Check the ceiling work | 8th floor | 807 | A | 2025-12-04
|  |  | IT/1226 | 2025-12-01 | 2025-12-02 | ceiling work | Check the ceiling work | 8th floor | 803 | A | 2025-12-04
|  |  | IT/1227 | 2025-12-01 | 2025-12-02 | ceiling work | Check the ceiling work | 8th floor | 801 | A | 2025-12-04
|  |  | IT/1228 | 2025-12-01 | 2025-12-02 | ceiling work | Check the ceiling work | 8th floor | 802 | A | 2025-12-04
|  |  | IT/1229 | 2025-12-01 | 2025-12-02 | ceiling work | Check the ceiling work | 8th floor | 812 | A | 2025-12-04
|  |  | IT/1230 | 2025-12-01 | 2025-12-02 | ceiling work | Check the ceiling work | 6th floor | 604 | B | 2025-12-04
|  |  | IT/1231 | 2025-12-17 | 2025-12-17 | ceiling work | Check the ceiling work | 6th floor | 608
|  |  | IT/1232 | 2025-12-01 | 2025-12-02 | Reinforcement & Formwork | Check the reinforcement ,formwork & allow to start concrete Lift lintel zone 01 04TH & 01TH | ZONE 1 |  | A | 2025-12-04
|  |  | IT/1233 | 2025-12-01 | 2025-12-02 | ceiling work | Check the ceiling work | 8th floor | 805 | A | 2025-12-04
|  |  | IT/1234 | 2025-12-01 | 2025-12-02 | level | Check the level points,chicken mesh, corner beads and allow to start plaster work | 11th floor | 1101 | R | 2025-12-04
|  |  | IT/1235 | 2025-12-01 | 2025-12-02 | Reinforcement & Formwork | Check the reinforcement ,formwork & allow to start concrete Lift lintel zone 01 04TH & 01TH | Zone-3 | 11th & 10th | A | 2025-12-04
|  |  | IT/1236 | 2025-12-01 | 2025-12-02 | formwork | Check planter wall formwork |  |  | A | 2025-12-04
|  |  | IT/1237 | 2025-12-05 | 2025-12-06 | Reinforcement & Formwork | Check the reinforcement ,formwork & allow to start concrete Lift lintel zone 01 AT top roof | ZONE 1 |  | A | 2025-12-06
|  |  | IT/1238 | 2025-12-05 | 2025-12-06 | level | Check the level points,chicken mesh, and allow to start plaster work | LINEA/01-02 | LINEA/01-02 | A | 2025-12-06
|  |  | IT/1239 | 2025-12-08 | 2025-12-10 | Tile work | Check the bed room and living room tiles work | 10TH FLOOR | 1005 | R | 2025-12-10
|  |  | IT/1240 | 2025-12-06 | 2025-12-08 | Tile work | Check the bed room and living room tiles work | 10TH FLOOR | 1007 | R | 2025-12-08
|  |  | IT/1241 | 2025-12-06 | 2025-12-10 | Tile work | Check the bed room and living room tiles work | 10TH FLOOR | 1008 | A | 2025-12-10
|  |  | IT/1242 | 2025-12-06 | 2025-12-10 | Tile work | Check the bed room and living room tiles work | 10TH FLOOR | 1014 | A | 2025-12-10
|  |  | IT/1243 | 2025-12-06 | 2025-12-10 | Tile work | Check the bed room and living room tiles work | 10TH FLOOR | 1016 | A | 2025-12-10
|  |  | IT/1244 | 2025-12-06 | 2025-12-08 | ceiling work | Check the ceiling work | 9th floor | 901 | A | 2025-12-08
|  |  | IT/1245 | 2025-12-08 | 2025-12-09 | Reinforcement & Formwork | Check the reinforcement ,formwork & allow to start concrete Lift lintel zone 03 1STH FLOOR TO 9TH FLOOR | ZONE 3 | 1STH FLOOR TO 9TH FLOOR | A | 2025-12-09
|  |  | IT/1246 | 2025-12-08 | 2025-12-10 | Tile work | Check the bed room and living room tiles work | 7TH FLOOR | 709 | A | 2025-12-10
|  |  | IT/1247 | 2025-12-08 | 2025-12-10 | Tile work | Check the bed room and living room tiles work | 10TH FLOOR | 1010 | A | 2025-12-10
|  |  | IT/1248 | 2025-12-08 | 2025-12-10 | Tile work | Check the bed room and living room tiles work | 10TH FLOOR | 1012 | A | 2025-12-10
|  |  | IT/1249 | 2025-12-08 | 2025-12-10 | Tile work | Check the bed room and living room tiles work | 9th floor | 909 | A | 2025-12-10
|  |  | IT/1250 | 2025-12-08 | 2025-12-10 | Tile work | Check the bed room and living room tiles work | 9th floor | 910 | A | 2025-12-10
|  |  | IT/1251 | 2025-12-08 | 2025-12-10 | Tile work | Check the bed room and living room tiles work | 9th floor | 912 | A | 2025-12-10
|  |  | IT/1252 | 2025-12-08 | 2025-12-10 | Tile work | Check the BALCONY TILES WORK | 7TH FLOOR | 701702 | A | 2025-12-10
|  |  | IT/1253 | 2025-12-08 | 2025-12-10 | Tile work | Check the BALCONY TILES WORK | 7TH FLOOR | 703704 | A | 2025-12-10
|  |  | IT/1254 | 2025-12-08 | 2025-12-10 | Tile work | Check the BALCONY TILES WORK | 7TH FLOOR | 705706 | B | 2025-12-10
|  |  | IT/1255 | 2025-12-08 | 2025-12-10 | Tile work | Check the BALCONY TILES WORK | 7TH FLOOR | 707708 | A | 2025-12-10
|  |  | IT/1256 | 2025-12-10 | 2025-12-10 | Tile work | Check the BALCONY TILES WORK | 7TH FLOOR | 709-710 | A | 2025-12-12
|  |  | IT/1257 | 2025-12-10 | 2025-12-10 | Tile work | Check the BALCONY TILES WORK | 7TH FLOOR | 711712 | A | 2025-12-12
|  |  | IT/1258 | 2025-12-10 | 2025-12-10 | Tile work | Check the BALCONY TILES WORK | 7TH FLOOR | 713714 | A | 2025-12-12
|  |  | IT/1259 | 2025-12-10 | 2025-12-10 | Tile work | Check the BALCONY TILES WORK | 7TH FLOOR | 716 | A | 2025-12-12
|  |  | IT/1260 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 11TH FLOOR | 1103 | A | 2025-12-15
|  |  | IT/1261 | 2025-12-16 | 2025-12-16 | Tile work | CHECK THE KITCHEN TILES WORK | 1ST FLOOR | 101-104 | A | 2025-12-18
|  |  | IT/1262 | 2025-12-16 | 2025-12-16 | Tile work | CHECK THE KITCHEN TILES WORK | 1st FLOOR | 105-108 | A | 2025-12-18
|  |  | IT/1263 | 2025-12-16 | 2025-12-16 | Tile work | CHECK THE KITCHEN TILES WORK | 1st FLOOR | 109-112 | A | 2025-12-18
|  |  | IT/1264 | 2025-12-16 | 2025-12-16 | Tile work | CHECK THE KITCHEN TILES WORK | 1st FLOOR | 113-116 | A | 2025-12-18
|  |  | IT/1265 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 7TH FLOOR | 713 | A | 2025-12-15
|  |  | IT/1266 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 7TH FLOOR | 714 | A | 2025-12-15
|  |  | IT/1267 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 7th floor | 715 | A | 2025-12-15
|  |  | IT/1268 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 7TH FLOOR | 716 | A | 2025-12-15
|  |  | IT/1269 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 7TH FLOOR | 711 | A | 2025-12-15
|  |  | IT/1270 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 7TH FLOOR | 713 | A | 2025-12-15
IT/1271
IT/1272
|  |  | IT/1273 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 10TH FLOOR | 1009 | A | 2025-12-15
|  |  | IT/1274 | 2025-12-17 | 2025-12-17 | Tile work | Check the corridor tiles work at first floor | 1ST FLOOR | ZONE 01 | A | 2025-12-18
|  |  | IT/1275 | 2025-12-18 | 2025-12-18 | Tile work | Check the corridor tiles work at first floor | 1st floor to 11th floor | zone 03 | R | 2025-12-18
|  |  | IT/1276 | 2025-12-17 | 2025-12-17 | Tile work | Check the corridor tiles work at first floor | 1ST FLOOR | ZONE 02 | A | 2025-12-18
|  |  | IT/1277 | 2025-12-17 | 2025-12-17 | ceiling work | Check the ceiling work | 1ST FLOOR | ZONE 01 | A | 2025-12-18
|  |  | IT/1278 | 2025-12-17 | 2025-12-17 | ceiling work | Check the ceiling work | 1ST FLOOR | ZONE 02 | A | 2025-12-18
IT/1279
|  |  | IT/1280 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 9th floor | 911 | A | 2025-12-15
|  |  | IT/1281 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 9th floor | 913 | A | 2025-12-15
|  |  | IT/1282 | 2025-12-13 | 2025-12-13 | Tile work | Check the bed room and living room tiles work | 9TH FLOOR | 9TH FLOOR 915 | A | 2025-12-13
|  |  | IT/1283 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 7TH FLOOR | 709 | A | 2025-12-15
|  |  | IT/1284 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 9th floor | 914 | A | 2025-12-13
|  |  | IT/1285 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 9th floor | 916 | A | 2025-12-15
|  |  | IT/1286 | 2025-12-15 | 2025-12-15 | BRICK WORK | CHECK THE INTERNAL WORK AT VERTICAL BAND | 8TH FLOOR
|  |  | IT/1287 | 2025-12-15 | 2025-12-15 | PLASTER WORK | CHECK THE INTERNAL WORK AT VERTICAL BAND
|  |  | IT/1288 | 2025-12-13 | 2025-12-13 | Tile work | Check the bed room and living room tiles work | 10th floor 1004
|  |  | IT/1289 | 2025-12-13 | 2025-12-13 | Tile work | Check the bed room and living room tiles work | 10th floor 1006
|  |  | IT/1290 | 2025-12-13 | 2025-12-13 | Tile work | Check the bed room and living room tiles work | 10TH FLOOR 1003
|  |  | IT/1291 | 2025-12-13 | 2025-12-13 | level | Check the level points,chicken mesh, and allow to start plaster work | 11th floor 1111
|  |  | IT/1292 | 2025-12-15 | 2025-12-15 | Tile work | Check the BALCONY TILES WORK | 8TH FLOOR 801-802
|  |  | IT/1293 | 2025-12-15 | 2025-12-15 | Tile work | Check the BALCONY TILES WORK | 8TH FLOOR 803-804
|  |  | IT/1294 | 2025-12-15 | 2025-12-15 | Tile work | Check the BALCONY TILES WORK | 8TH FLOOR 805-807
|  |  | IT/1295 | 2025-12-15 | 2025-12-15 | Tile work | Check the BALCONY TILES WORK | 8TH FLOOR 808-809
|  |  | IT/1296 | 2025-12-15 | 2025-12-15 | Tile work | Check the BALCONY TILES WORK | 8TH FLOOR 810-811
|  |  | IT/1297 | 2025-12-15 | 2025-12-15 | BRICK WORK | check the demolished brick work at 11th floor on all appartments main door | 11th floor
|  |  | IT/1298 | 2025-12-15 | 2025-12-15 | Tile work | Check the bed room and living room tiles work | 8th floor 815
|  |  | IT/1299 | 2025-12-15 | 2025-12-15 | BRICK WORK | check the brickwork and internal side plaster work of window 15 | 1st to 10 floor |  | A | 2025-12-18
|  |  | IT/1300 | 2025-12-15 | 2025-12-15 | BRICK WORK | check the brickwork at ground floor | ground floor |  | A | 2025-12-18
|  |  | IT/1301 | 2025-12-15 | 2025-12-15 | level | Check the level points and allow to start plaster work | ground floor |  | A | 2025-12-18
|  |  | IT/1302 | 2025-12-15 | 2025-12-15 | level | Check the level points and allow to start plaster work | SOG OF PLANTER AREA |  | A | 2025-12-18
|  |  | IT/1303 | 2025-12-15 | 2025-12-15 | LINTEL | CHECK THE LINTEL WORK AT LIFE AREA OF ZONE -1-03 GROUND FLOUR | GROUND FLOOR TO TOP FLOOR | GROUND FLOOR TO TOP FLOOR | A | 2025-12-18
|  |  | IT/1304 | 2025-12-16 | 2025-12-16 | Tile work | Check the BALCONY TILES WORK | 8th floor 812-813
|  |  | IT/1305 | 2025-12-16 | 2025-12-16 | Tile work | Check the BALCONY TILES WORK | 8th floor 814-816
|  |  | IT/1306 | 2025-12-16 | 2025-12-16 | PLASTER WORK | Check the plaster work | 3th floor zone 1
|  |  | IT/1307 | 2025-12-17 | 2025-12-17 | ceiling work | Check the ceiling work | zone 1 | f-c/01~10
|  |  | IT/1308 | 2025-12-17 | 2025-12-17 | ceiling work | Check the ceiling work | zone 2 | c/10~18
|  |  | IT/1309 | 2025-12-17 | 2025-12-17 | ceiling work | Check the ceiling work | zone 3 | f-c/18~23
|  |  | IT/1310 | 2025-12-17 | 2025-12-17 | ceiling work | Check the ceiling work | 9th floor | 902
|  |  | IT/1311 | 2025-12-17 | 2025-12-17 | ceiling work | Check the ceiling work | 9th floor | 903
|  |  | IT/1312 | 2025-12-17 | 2025-12-17 | Tile work | Check the living room tile work | 2nd floor | 201
|  |  | IT/1313 | 2025-12-17 | 2025-12-17 | level | Check the level points,chicken mesh, and allow to start plaster work at external side | 1st floor to 11th floor | 1st floor to 11th floor
|  |  | IT/1314 | 2025-12-17 | 2025-12-17 | level | check the level and allow to start pcc on the lift area (5') at basement | Basement | A~B/09~10
|  |  | IT/1315 | 2025-12-18 | 2025-12-18 | Tile work | Check the living room tile work | 10th floor | 1011
|  |  | IT/1316 | 2025-12-18 | 2025-12-18 | Tile work | Check the living room tile work | 10th floor | 1013
|  |  | IT/1317 | 2025-12-19 | 2025-12-19 | PLASTER WORK | Check the plaster work | 11th floor | 1101
|  |  | IT/1318 | 2025-12-19 | 2025-12-19 | PLASTER WORK | Check the plaster work | UMT SIDE | UMT SIDE
IT/1319
IT/1320
IT/1321
IT/1322
IT/1323
IT/1324
IT/1325
IT/1326
IT/1327
IT/1328
IT/1329
IT/1330
IT/1331
IT/1332
IT/1333
IT/1334
IT/1335
IT/1336
IT/1337
IT/1338
IT/1339
IT/1340
IT/1341
IT/1342
IT/1343
IT/1344
IT/1345
IT/1346
IT/1347
IT/1348
IT/1349
IT/1350
IT/1351
IT/1352
IT/1353
IT/1354
IT/1355
IT/1356
IT/1357
IT/1358
IT/1359
IT/1360
IT/1361
IT/1362
IT/1363
IT/1364
IT/1365
IT/1366
IT/1367
IT/1368
IT/1369
IT/1370
IT/1371
IT/1372
IT/1373
IT/1374
IT/1375
IT/1376
IT/1377
IT/1378
IT/1379
IT/1380
IT/1381
IT/1382
IT/1383
IT/1384
IT/1385
IT/1386
IT/1387
IT/1388
IT/1389
IT/1390
IT/1391
IT/1392
IT/1393
IT/1394
IT/1395
IT/1396
IT/1397
IT/1398
IT/1399
IT/1400
IT/1401
IT/1402
IT/1403
IT/1404
IT/1405
IT/1406
IT/1407
IT/1408
IT/1409
IT/1410
IT/1411
IT/1412
IT/1413
IT/1414
IT/1415
IT/1416
IT/1417
IT/1418
IT/1419
IT/1420
IT/1421
IT/1422
IT/1423
IT/1424
IT/1425
IT/1426
IT/1427
IT/1428
IT/1429
IT/1430
IT/1431
IT/1432
IT/1433
IT/1434

## GE L2 Tower
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (L2 Tower) | [5 empty] | Fully Approved (A) |  | 663
[9 empty] | Approved with comments (B) |  | 73
[9 empty] | Rejected ( R) |  | 19
[9 empty] | Open/Pending (OP) |  | 19
[9 empty] | Total |  | 774
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | basement | LT-2-001 | 2024-05-24 | 2024-05-20 | column formwork | Check columns (10 Nos) formwork Zone 6 & 7 | (-11.75) | Grid Q-T/1, T/3-11 | A | 2024-05-29
2 | Sub Structure | basement | LT-2-002 | 2024-05-24 | 2024-05-21 | vertical formwork | Check columns (11 Nos) formwork Zone 7 | (-11.75) | Grid G-P/1, L-M/7, N/3 | B | 2024-05-29
3 | Sub Structure | basement | LT-2-003 | 2024-05-24 | 2024-05-22 | vertical formwork | Check vertical columns (6 Nos) formwork Zone 6 & 7 | (-11.75) | Grid R-T/12, H-K/7, G/3, N/10 | A | 2024-05-29
4 | Sub Structure | basement | LT-2-004 | 2024-05-24 | 2024-05-23 | vertical formwork | Check columns (5 Nos) formwork Zone 6 & 7 | (-11.75) | Grid R/12, N/12, G/3-6 | B | 2024-05-29
5 | Sub Structure | basement | LT-2-005 | 2024-05-24 | 2024-05-24 | vertical formwork | Check columns (5 Nos) formwork Zone 6 & 7 | (-11.75) | Grid T/12, G/7, K-L/5 | A | 2024-05-29
6 | Sub Structure | basement | LT-2-006 | 2024-05-25 | 2024-05-25 | column formwork | Check vertical columns (3 Nos) formwork Zone 6 | (-11.75) | Grid R/12, N/10-11 | B | 2024-06-01
7 | Sub Structure | basement | LT-2-007 | 2024-05-27 | 2024-05-27 | column formwork | Check vertical columns (5 Nos) formwork Zone 6 & 7 | (-11.75) | Grid L/5, N/9, P-R/10, P/11 | A | 2024-06-01
8 | Sub Structure | basement | LT-2-008 | 2024-05-28 | 2024-05-28 | column formwork | Check columns (5 Nos) formwork Zone 6 & 7 | (-11.75) | Grid M/5, N/8, P-R/9, R/11 | A | 2024-06-03
9 | Sub Structure | basement | LT-2-009 | 2024-05-29 | 2024-05-29 | column formwork | Check columns (5 Nos) formwork Zone 6 & 7 | (-11.75) | Grid M/3, P/3, R/3, P/8, R/8 | A | 2024-06-03
10 | Sub Structure | basement | LT-2-010 | 2024-05-31 | 2024-05-31 | RW formwork | Check RW formwork Zone 6 | (-11.75) | Grid 10-13 | B | 2024-06-07
11 | Sub Structure | basement | LT-2-011 | 2024-06-01 | 2024-06-01 | column formwork | Check columns (2 Nos) formwork Zone 7 | (-11.75) | Grid R/5, R/7 | A | 2024-06-07
12 | Sub Structure | basement | LT-2-012 | 2024-06-05 | 2024-06-05 | ramp formwork | Check ramp formwork Zone 6 | (-11.75 to +0.0) | Grid Q-S/6-12 | B | 2024-06-12
13 | Sub Structure | basement | LT-2-013 | 2024-06-05 | 2024-06-05 | RW formwork | Check RW formwork Zone 6 | (-11.75) | Grid 7-10 | B | 2024-06-07
14 | Sub Structure | basement | LT-2-014 | 2024-06-08 | 2024-06-08 | RW formwork | Check RW formwork Zone 6 | (-11.75) | Grid 1-7 | B | 2024-06-12
15 | Sub Structure | basement | LT-2-015 | 2024-06-10 | 2024-06-10 | RW formwork | Check RW formwork Zone 7 | (-11.75) | Grid T-T/1-2 | B | 2024-06-12
16 | Sub Structure | basement | LT-2-016 | 2024-06-13 | 2024-06-13 | ramp formwork | Check ramp beams formwork Zone 6 | (-11.75) | Grid Q-S/6-12 | B | 2024-06-14
17 | Sub Structure | basement | LT-2-017 | 2024-06-13 | 2024-06-13 | RW formwork | Check RW formwork Zone 7 | (-11.75) | Grid R-T | B | 2024-06-14
18 | Sub Structure | basement | LT-2-018 | 2024-06-27 | 2024-06-27 | beam formwork | Check beam formwork and ground floor slab Zone 6 | (+0.0) | Grid M-U/12-13 | A | 2024-06-14
19 | Sub Structure | basement | LT-2-019 | 2024-06-29 | 2024-06-30 | RTW formwork | Check RTW formwork Zone 7 | (-11.75) | Grid L-R | B | 2024-07-01
20 | Sub Structure | basement | LT-2-020 | 2024-07-01 | 2024-07-01 | lift formwork | Check service lift formwork Zone 7 | (-11.75) | Grid H-J/3-4 | A | 2024-07-02
21 | Sub Structure | basement | LT-2-021 | 2024-07-02 | 2024-07-02 | beam formwork | Check beam formwork & SOG Zone 6 & 7 | (+0.00) | Grid S-U/5-12 | B | 2024-07-08
22 | Sub Structure | basement | LT-2-022 | 2024-07-03 | 2024-07-03 | beam formwork | Check beam & slab formwork Zone 6 | (+2.0) | Grid N-Q/7-12 | B | 2024-07-08
23 | Sub Structure | basement | LT-2-023 | 2024-07-05 | 2024-07-05 | RTW Formwork | Check RTW formwork Zone 7 | (-11.75) | Grid G-L | B | 2024-07-08
24 | Sub Structure | basement | LT-2-024 | 2024-07-05 | 2024-07-05 | beam formwork | Check beam formwork and SOG Zone 7 | (+0.00) | Grid G-M/1-4 | B | 2024-07-18
25 | Sub Structure | basement | LT-2-025 | 2024-07-05 | 2024-07-05 | slab formwork | Check slab / beam formwork Zone 7 | (+2.0) | Grid G-N/1-7 | B | 2024-07-18
26 | Sub Structure | basement | LT-2-026 | 2024-07-08 | 2024-07-08 | lift stair formwork | Check lift & stair formwork Zone 7 | (-11.75') | Grid N-P/4-7 | B | 2024-07-10
27 | Sub Structure | basement | LT-2-027
28 | Sub Structure | basement | LT-2-028 | 2024-07-11 | 2024-07-11 | beam formwork | Check beam formwork & SOG Zone 7 | (+0.000) | Grid S-U/1-7 | B | 2024-07-18
29 | Sub Structure | basement | LT-2-029 | 2024-07-13 | 2024-07-13 | beam formwork | Check beam and slab formwork Zone 7 | (+2.0) | Grid N-S/1-7 | B | 2024-07-20
30 | Sub Structure | basement | LT-2-030 | 2024-07-20 | 2024-07-20 | formwork | Check columns (5 Nos) formwork Zone 6 | (+0.00) | Grid U/8, U/10, U/9, U/11, U/12 | A | 2024-07-23
31 | Sub Structure | basement | LT-2-031 | 2024-07-21 | 2024-07-21 | formwork | Check columns (5 Nos) formwork Zone 6 | (+0.00) | Grid N/12, S/10, S/11, S/12 | A | 2024-07-23
32 | Sub Structure | basement | LT-2-032 | 2024-07-21 | 2024-07-21 | formwork | Check vertical columns (6 Nos) formwork Zone 7 | (+0.00) | Grid G/1, G/5, G/7, H/1, H/7, J/1 | B | 2024-07-23
33 | Sub Structure | 1st floor | LT-2-033 | 2024-07-22 | 2024-07-22 | formwork | Check vertical column formwork (4 Nos) Zone 6 | (+0.00) | grid U/9, U/10, U/11, U/12 | A | 2024-07-23
34 | Sub Structure | GF | LT-2-034 | 2024-07-22 | 2024-07-22 | formwork | Check vertical columns (5 Nos) formwork Zone 6 & 7 | (+0.00) | Grid H/5, K/7, L/7, N/9, N/10 | B | 2024-07-23
35 | Sub Structure | GF | LT-2-035 | 2024-07-22 | 2024-07-22 | formwork | Check formwork of vertical columns (2 Nos) Zone 6 | (+0.00) | Grid S/9, Q/11 | A | 2024-07-26
36 | Sub Structure | basement | LT-2-036 | 2024-07-23 | 2024-07-23 | formwork | Check vertical column formwork (6 Nos) for first height Zone 6 & 7 | (+0.00) | Grid G/2, L/1, M/1, M/7, N/8 | A | 2024-07-26
37 | Sub Structure | GF | LT-2-037 | 2024-07-23 | 2024-07-23 | formwork | Check vertical columns (6 Nos) formwork Zone 6 & 7 | (+0.00) | Grid H/5, N/9, N/10, N/12, S/12, U/8 | A | 2024-07-26
38 | Sub Structure | GF | LT-2-038 | 2024-07-23 | 2024-07-23 | formwork | Check vertical columns formwork Zone 6 | (+0.00) | Grid M/3, M/5, N/3, P/1, Q/1, Q/9/ P/10, P/12, R/1, T/1, U/1 | A | 2024-07-26
39 | Sub Structure | GF | LT-2-039 | 2024-07-24 | 2024-07-24 | formwork | Check vertical columns (4 Nos) for second height Zone 7 | (+0.00) | Grid G/5, G/7, H/7, K/7 | B | 2024-07-26
40 | Sub Structure | GF | LT-2-040 | 2024-07-25 | 2024-07-25 | formwork | Check formwork of (9 Nos) columns Zone 7 | (+0.00) | Grid G/1, H/1, J/1, K/1, L/1, M/1, M/7, P/1 | A | 2024-07-26
41 | Sub Structure | GF | LT-2-041 | 2024-07-25 | 2024-07-25 | formwork | Check vertical columns (6 Nos) formwork Zone 6 & 7 | (+0.00) | Grid N/11, S/7, Q/8, U/3-4, U/6 | B | 2024-07-26
42 | Sub Structure | GF | LT-2-042 | 2024-07-26 | 2024-07-26 | formwork | Check column (6 Nos) formwork for first height Zone 7 | (+0.00) | Grid K/7, L/7, Q/3, U/3-4, U/6 | B | 2024-07-30
43 | Sub Structure | GF | LT-2-043 | 2024-07-26 | 2024-07-26 | formwork | Check column (6 Nos) formwork for 2nd height Zone 7 | (+0.00) | Grid M/3, M/5, N/3, Q/1, R/1 | A | 2024-07-30
44 | Sub Structure | GF | LT-2-044 | 2024-07-27 | 2024-07-27 | formwork | Check lift & stair formwork Zone 7 | (+2.0) | Grid n-p/4-7 | B | 2024-07-30
45 | Sub Structure | GF | LT-2-045 | 2024-07-27 | 2024-07-27 | formwork | Check vertical columns (2 Nos) formwork Zone 7 | (+0.00) | Grid K/3, L/3 | B | 2024-07-31
46 | Sub Structure | GF | LT-2-046 | 2024-07-27 | 2024-07-27 | formwork | Check formwork of (3 Nos) columns Zone 7 | (+0.00) | Grid U/3-4, 6 | A | 2024-07-31
47 | Sub Structure | GF | LT-2-047 | 2024-07-30 | 2024-07-30 | service lift formwork | Check service lift formwork Zone 7 | (+2.000) | Grid H-J/3-4 | B | 2024-08-03
48 | Sub Structure | GF | LT-2-048 | 2024-07-30 | 2024-07-30 | column formwork | Check column (3 No) formwork Zone 7 | (+0.00) | Grid Q/3, T/1, U/1 | A | 2024-07-31
49 | Sub Structure | GF | LT-2-049 | 2024-07-30 | 2024-07-30 | column formwork | Check column (1 No) formwork Zone 7 | (+0.00) | Grid S/3 | A | 2024-07-31
50 | Sub Structure | 1st floor | LT-2-050 | 2024-07-31 | 2024-07-31 | beam formwork | Check beam formwork & slab Zone 6 | (+18.75) | Grid N-U/7-12 | B | 2024-08-07
51 | Sub Structure | 1st floor | LT-2-051 | 2024-08-03 | 2024-08-03 | beam formwork | Check beam formwork and slab of first floor Zone 7 | (+18.75) | Grid G-N/1-8 | B | 2024-08-13
52 | Sub Structure | 1st floor | LT-2-052 | 2024-08-06 | 2024-08-06 | formwork | Check vertical (5 Nos) formwork Zone 6 | (+18.75) | Grid U/8-12 | A | 2024-08-07
53 | Sub Structure | 1st floor | LT-2-053 | 2024-08-06 | 2024-08-06 | formwork | Check vertical (3 Nos) formwork Zone 6 | (+18.75) | Grid R/10-12 | B | 2024-08-07
54 | Sub Structure | 1st floor | LT-2-054 | 2024-08-07 | 2024-08-07 | beam formwork | Check beam and slab formwork Zone 7 | (+18.75) | Grid M-U/1-8 | B | 2024-08-13
55 | Sub Structure | 1st floor | LT-2-055 | 2024-08-07 | 2024-08-07 | column formwork | Check columns (6 Nos) formwork zone 6 | (+18.75) | Grid N/8, N/10, N/12, Q/12, S/8, S/9 | A | 2024-08-13
56 | Sub Structure | 1st floor | LT-2-056 | 2024-08-09 | 2024-08-09 | column formwork | Check columns (6 Nos) formwork Zone 6 | (+18.75) | Grid N/8-12, Q/8 | A | 2024-08-13
57 | Sub Structure | 1st floor | LT-2-057 | 2024-08-10 | 2024-08-10 | column formwork | Check columns (8 Nos) formwork Zone 7 | (+18.75) | Grid G/5, 7, H/5,7, K/5, L/5, 7 | A | 2024-08-13
58 | Sub Structure |  | LT-2-058
59 | Sub Structure | 1st floor | LT-2-059 | 2024-08-12 | 2024-08-12 | column formwork | Check columns (7 Nos) formwork Zone 7 | (+18.75) | Grid G/1, H/1, J/1, K/1, L/1, M/1, R/1 | B | 2024-08-15
60 | Sub Structure | 1st floor | LT-2-060 | 2024-08-12 | 2024-08-12 | column formwork | Check columns (7 Nos) formwork Zone 7 | (+18.75) | Grid G/3, K/3, L/3, M/3, L/5, L/7, S/8 | A | 2024-08-15
61 | Sub Structure | 1st floor | LT-2-061 | 2024-08-12 | 2024-08-12 | lift formwork | Check lift service formwork Zone 7 | (+18.75) | Grid H-J/3-4 | A | 2024-08-21
62 | Sub Structure | 1st floor | LT-2-062 | 2024-08-13 | 2024-08-13 | column formwork | Check columns (7 Nos) formwork Zone 7 | (+18.75) | Grid N/3, Q/3, S/3,7, U/3-4, U/6 | B | 2024-08-20
63 | Sub Structure | 1st floor | LT-2-063 | 2024-08-13 | 2024-08-13 | column formwork | Check columns (4 Nos) formwork Zone 7 | (+18.75) | Grid P/1, Q/1, T/1, U/1 | B | 2024-08-20
64 | Sub Structure | 2nd floor | LT-2-064 | 2024-08-16 | 2024-08-16 | beam formwork | Check beam and slab formwork Zone 6 | (+29.75) | Grid M-U/7-12 | B | 2024-08-24
65 | Sub Structure | 1st floor | LT-2-065 | 2024-08-19 | 2024-08-19 | lift formwork | Check lift & stair walls formwork Zone 7 | (+18.75) | Grid N-P/4-7 | B | 2024-08-21
66 | Sub Structure | 2nd floor | LT-2-066 | 2024-08-19 | 2024-08-19 | slab formwork | Check beam & slab formwork Zone 7 | (+29.75) | Grid G-N/1-8 | B | 2024-08-28
67 | Sub Structure | 2nd floor | LT-2-067 | 2024-08-28 | 2024-08-28 | column formwork | Check columns (5 Nos) formwork Zone 7 | (+29.75) | Grid S/8, S/10, S/11-12 | A | 2024-09-03
68 | Sub Structure | 2nd floor | LT-2-068 | 2024-08-28 | 2024-08-28 | column formwork | Check columns (5 Nos) formwork Zone 7 | (+29.75) | Grid U/8-11, S/12 | A | 2024-09-03
69 | Sub Structure | 2nd floor | LT-2-069 | 2024-08-29 | 2024-08-29 | formwork | Check vertical columns formwork Zone 7 | (+29.75) | Grid S/3,5 T/1, U/3-4 | A | 2024-09-03
70 | Sub Structure | basement | LT-2-070 | 2024-08-30 | 2024-08-30 | formwork | Check formwork of internal walls of septic tank Zone 7 | (-11.75) | Grid G-L/1-1 | A | 2024-09-03
71 | Sub Structure | 2nd floor | LT-2-071 | 2024-08-31 | 2024-08-31 | formwork | Check column (5 Nos) formwork Zone 6 & 7 | (+29.75) | grid Q/9-11, S/7, U/6 | A | 2024-09-03
72 | Sub Structure | 2nd floor | LT-2-072 | 2024-08-31 | 2024-08-31 | formwork | Check vertical column formwork (5 Nos) Zone 6 | (+29.75) | Grid N/8-10, N/12, Q/12 | A | 2024-09-03
73 | Sub Structure | 2nd floor | LT-2-073 | 2024-09-01 | 2024-09-01 | formwork | Check vertical columns (6 Nos) Zone 7 | (+29.75) | Grid M/1-5, N/3, P/1 | B | 2024-09-03
74 | Sub Structure | 2nd floor | LT-2-074 | 2024-09-01 | 2024-09-01 | formwork | Check formwork columns (5 Nos) Zone 6 & 7 | (+29.75) | Grid Q/1,8, R/1, Q/3, U/1 | A | 2024-09-03
75 | Sub Structure | 2nd floor | LT-2-075 | 2024-09-02 | 2024-09-02 | formwork | Check columns (7 Nos) formwork Zone 7 | (+29.75) | Grid H/7, K/5, K/7, L/5, L/7, M/7 | A | 2024-09-06
76 | Sub Structure | 2nd floor | LT-2-076 | 2024-09-04 | 2024-09-04 | formwork | Check formwork of 1 No vertical share wall Zone 6 | (+29.75) | Grid N/11, S/7, Q/8, U/3-4, U/6 | A | 2024-09-09
77 | Sub Structure | 2nd floor | LT-2-077 | 2024-09-04 | 2024-09-04 | formwork | check formowrk of lift & stair case wall Zone 7 | (+29.75) | Grid N-P/4-7 | B | 2024-09-09
78 | Sub Structure | 2nd floor | LT-2-078 | 2024-09-04 | 2024-09-04 | formwork | Check vertical columns (4 Nos) formwork Zone 7 | (+29.75) | Grid G/1,3,5,7 | B | 2024-09-09
79 | Sub Structure | 3rd floor | LT-2-079 | 2024-09-05 | 2024-09-05 | formwork | Check beam and slab formwork Zone 6 & 7 | (+40.75) | Grid M-U/4-12 | B | 2024-09-10
80 | Sub Structure | 2nd floor | LT-2-080 | 2024-09-06 | 2024-09-06 | formwork | Check vertical columns (3 Nos) formwork Zone 7 | (+29.75) | Grid G/1,7, H/1 | A | 2024-09-07
81 | Sub Structure | GF | LT-2-081 | 2024-09-06 | 2024-09-06 | layout | Check layout and allow to start brick work | (+02.0) | Grid N-U/7-12 | A | 2024-09-10
82 | Sub Structure | 2nd floor | LT-2-082 | 2024-09-07 | 2024-09-07 | formwork | Check vertical columns (1 Nos) formwork Zone 7 | (+29.75) | Grid L/1 | A | 2024-09-12
83 | Sub Structure | 2nd floor | LT-2-083 | 2024-09-07 | 2024-09-07 | formwork | Check service lift formowrk Zone 7 | (+29.75) | Grid H-J/3-4 | A | 2024-09-10
84 | Sub Structure | 3rd floor | LT-2-084 | 2024-09-09 | 2024-09-09 | formwork | Check formwork of beam & slab Zone 7 | (+40.75) | Grid G-U/1-8 | B | 2024-09-18
85 | Sub Structure | 2nd floor | LT-2-085 | 2024-09-11 | 2024-09-11 | chicken mesh | Check plumb points & chicken mesh for plaster work on external sides Zone 6 | (+2.0to+19.0) | Grid Q/8-12 | A | 2024-09-12
86 | Sub Structure | 3rd floor | LT-2-086 | 2024-09-11 | 2024-09-11 | formwork | Check formwork of vertical column (10 Nos) zone 6 | (+40.75 to +52.75) | Grid S/9-11, U/8-12 | A | 2024-09-16
87 | Sub Structure | basement | LT-2-087 | 2024-09-12 | 2024-09-12 | formwork | Check formwork on external walls of septic tank Zone 7 | (-11.75-0.00) | Grid G-L/1-1 | A | 2024-09-20
88 | Sub Structure | 3rd floor | LT-2-088 | 2024-09-12 | 2024-09-12 | formwork | Check vertical columns (8 Nos) formwork Zone 6 | (+40.75-52.75) | Grid N/8-10,12, Q/8-11 | A | 2024-09-18
89 | Sub Structure | GF | LT-2-089 | 2024-09-13 | 2024-09-13 | brick work | Check brick work on external/internal sides of building Zone 6 | (+02.0) | Grid N-Q/7-12 | A | 2024-09-18
90 | Sub Structure | GF | LT-2-090 | 2024-09-13 | 2024-09-13 | plaster work | Check plaster work on external sides Zone 6 | (+02.0) | Grid Q/8-12 | A | 2024-09-18
91 | Sub Structure | GF | LT-2-091 | 2024-09-13 | 2024-09-13 | chicken mesh | Check plumb points and chicken mesh for plaster work | (+02.0-+19.0) | Grid N/8-12, N-Q/12 | A | 2024-09-18
92 | Sub Structure | 3rd floor | LT-2-092 | 2024-09-13 | 2024-09-14 | formwork | check vertical column formwork Zone 6 | (+40.75) | Grid Q/12 | A | 2024-09-18
93 | Sub Structure | 3rd floor | LT-2-093 | 2024-09-15 | 2024-09-15 | formwork | Check vertical columns (6 Nos) formwork zone 7 | (+40.75 to +52.75) | Grid R/1, T/1, U/1,3,4,6 | A | 2024-09-20
94 | Sub Structure | 3rd floor | LT-2-094 | 2024-09-15 | 2024-09-15 | formwork | Check vertical columns (6 Nos) formwork zone 7 | (+40.75 to +52.75) | Grid N/3, Q/3, S/3,5,7 | A | 2024-09-20
95 | Sub Structure | 3rd floor | LT-2-095 | 2024-09-16 | 2024-09-16 | formwork | Check vertical (10 Nos) formwork Zone 7 | (+40.75 to +52.75) | Grid J/1, K/1, L/1,3,5, M/1,3,5, P/1 | A | 2024-09-20
96 | Sub Structure | 3rd floor | LT-2-096 | 2024-09-16 | 2024-09-16 | formwork | Check shear wall (1 No) formwork zone 6 | (+40.75 to +51.75) | Grid N/11 | A | 2024-09-20
97 | Sub Structure | 3rd floor | LT-2-097 | 2024-09-18 | 2024-09-18 | formwork | Check columns (8 Nos) formwork Zone 7 | (+40.75 to +52.75) | Grid G/3,5, H/5,7,K/5,7, L/7, M/7 | A | 2024-09-24
98 | Sub Structure | 4th floor | LT-2-098 | 2024-09-18 | 2024-09-18 | formwork | Check beam & slab formwork Zone 6 | (+51.75) | Grid M-U/8-12 | B | 2024-09-26
99 | Sub Structure | 3rd floor | LT-2-099 | 2024-09-19 | 2024-09-19 | formwork | Check column (3 Nos) formwork Zone 7 | (+40.75 to +52.75) | Grid G/1, 7 | A | 2024-09-24
100 | Sub Structure | 4th floor | LT-2-100 | 2024-09-19 | 2024-09-19 | formwork | Check beam and slab formwork zone 7 | (+51.75) | Grid M-U/5-8 | A | 2024-09-26
101 | Sub Structure | 3rd floor | LT-2-101 | 2024-09-20 | 2024-09-21 | formwork | Check lift formwork & stair case shear wall zone 7 | (+40.75 to +51.75) | Grid N-R/4-7 | A | 2024-09-30
102 | Sub Structure | 3rd floor | LT-2-102 | 2024-09-23 | 2024-09-23 | formwork | Check service lift formwork zne 7 | (+40.75 to +51.75) | Grid H-J/3-4 | A | 2024-09-26
103 | Sub Structure | SOG | LT-2-103 | 2024-09-23 | 2024-09-23 | formwork | Check septic tank slab / sog formwork zone 7 | (+0.0) | Grid G-L/1-1 | A | 2024-09-30
104 | Sub Structure | 4th floor | LT-2-104 | 2024-09-24 | 2024-09-24 | formwork | Check beam & slab formwork zone 7 | (+51.75) | Grid G-U/1-8 | B | 2024-10-02
105 | Sub Structure | 4th floor | LT-2-105 | 2024-09-24 | 2024-09-24 | formwork | Check slab/beam formwork zone 7 | (+51.75) | Grid G-K/1-5 | OP
106 | Sub Structure | 4th floor | LT-2-106 | 2024-09-25 | 2024-09-25 | formwork | Check columns (10 Nos) formwork zone 7 | (+51.75 to +62.75) | Grid U/6,8,9,10,11,12,S/7,8,9,10 | A | 2024-09-30
107 | Sub Structure | 4th floor | LT-2-107 | 2024-09-26 | 2024-09-26 | formwork | Check columns (10 Nos), shear wall (1 Nos) formwork zone 6 | (+51.75 to +62.75) | Grid N/8-12, Q/8-12, S/11-12 | A | 2024-09-30
108 | Sub Structure | 4th floor | LT-2-108 | 2024-09-30 | 2024-09-30 | formwork | Check columns (10 Nos) formwork and one no shear wall zone 6 & 7 | (+51.75 to +62.75) | Grid U/1,3,4, T/1, S/3,5, R/1, Q/1,3 P/1, N/11 | A | 2024-10-02
109 | Sub Structure | 4th floor | LT-2-109 | 2024-10-01 | 2024-10-01 | formwork | Check columns (10 Nos) formwork zone 7 | (+51.75 to +62.75) | Grid K/1-5, L/1-5, M/1-5, N/3 | A | 2024-10-04
110 | Sub Structure | 6th floor | LT-2-110 | 2024-10-02 | 2024-10-02 | formwork | Check beam / slab formwork zone 6 | (+62.75) | Grid M-U/8-12 | B | 2024-10-11
111 | Sub Structure | 4th floor | LT-2-111 | 2024-10-02 | 2024-10-02 | formwork | Check columns (10 Nos) formwork zone 7 | (+51.75 to +62.75) | Grid G/1,3,5,7, H/1,5,7,J/1, K/7, L/7, M/7 | A | 2024-10-09
112 | Sub Structure | 4th floor | LT-2-112 | 2024-10-04 | 2024-10-04 | formwork | Check lift formwork and stair case shear wall zone 7 | (+51.75 to +62.75) | Grid N-R/4-7 | A | 2024-10-09
113 | Sub Structure | basement | LT-2-113 | 2024-10-05 | 2024-10-05 | formwork | Check internal wall formwork of rain water tank zone 7 | (-11.75 to +0.00) | Grid L-Q/1 | B | 2024-10-09
114 | Sub Structure | 5th floor | LT-2-114 | 2024-10-07 | 2024-10-07 | formwork | Check beam & slab formwork zone 7 | (+62.0) | Grid G-U/1-8 | B | 2024-10-24
115 | Sub Structure | 4th floor | LT-2-115 | 2024-10-09 | 2024-10-08 | formwork | Check service lift formwork zone 7 | (+51.75 to +62.75) | Grid H-J/3-4 | A | 2024-10-11
116 | Sub Structure | 5th floor | LT-2-116 | 2024-10-10 | 2024-10-10 | formwork | Check columns (10 Nos) formworik zone 6 | (+62.75 to +73.75) | Grid U/8-12, S/8-12 | A | 2024-10-11
117 | Sub Structure | basement | LT-2-117 | 2024-10-10 | 2024-10-10 | formwork | Check external wall water tank formwork zone 7 | (-11.75 to +0'-00'') | Grid L-Q/1 | A | 2024-10-15
118 | Sub Structure | 5th floor | LT-2-118 | 2024-10-11 | 2024-10-11 | formwork | Check columns (7 Nos) and shear wall (1 Nos) formwork zone 6 | (+62.75 to +73.75) | Grid S/7, Q/9-12, N/9-12, | A | 2024-10-15
119 | Sub Structure | 5th floor | LT-2-119 | 2024-10-13 | 2024-10-13 | formwork | Check columns (3 Nos) formwork and one no. shear wall zone 6 & 7 | (+62.75 to +73.75) | Grid N/8,11, Q/8, U/6 | A | 2024-10-18
120 | Sub Structure | 5th floor | LT-2-120 | 2024-10-14 | 2024-10-14 | formwork | Check (1 Nos) columns zone 7 | (+62.75 to +73.75) | Grid Q/1, N/4, Q/3, R/1, S/3,5, T/1, U/1-4 | A | 2024-10-18
121 | Sub Structure | 5th floor | LT-2-121 | 2024-10-15 | 2024-10-15 | formwork | Check columns (8 Nos) formwork zone 7 | (+62.75 to +73.75) | Grid L/1,3,5, M/1,3,5,7, P/1 | A | 2024-10-18
122 | Sub Structure | 6th floor | LT-2-122 | 2024-10-16 | 2024-10-16 | formwork | Check slab/beam formwork zone 6 & 7 | (+73.75) | Grid M-U/5-12 | B | 2024-10-24
123 | Sub Structure | 5th floor | LT-2-123 | 2024-10-16 | 2024-10-16 | formwork | check columns (7 Nos) formwork zone 7 | (+62.75 to +73.75) | Grid M/7, L/5,7, K/5,7, H/1, G/1 | A | 2024-10-24
124 | Sub Structure | basement | LT-2-124 | 2024-10-17 | 2024-10-17 | formwork | Check rain water harvesting tank slab/sog formwork zone 7 | (+0.000) | Grid L-Q/1 | A | 2024-10-24
125 | Sub Structure | 5th floor | LT-2-125 | 2024-10-17 | 2024-10-17 | formwork | Check columns (8 Nos) formwork zone 7 | (+62.75 to +73.75) | Grid G/3-5, 7, H/5, 7, J/1, K/1-3 | A | 2024-10-21
126 | Sub Structure | 5th floor | LT-2-126 | 2024-10-18 | 2024-10-18 | formwork | Check lift & stair case shear wall formwork zone 7 | (+62.75 to +73.75) | Grid N-R/4-7 | B | 2024-10-24
127 | Sub Structure | basement | LT-2-127 | 2024-10-21 | 2024-10-21 | formwork | Check internal wall formwork of rain water tank zone 7 | (-11.75' to +0'-00'') | Grid Q-T/1, | B | 2024-10-24
128 | Sub Structure | 5th floor | LT-2-128 | 2024-10-21 | 2024-10-21 | formwork | Check service lift formwork zone 7 | (+62.75 to +73.75) | Grid H-J/3-4 | A | 2024-10-24
129 | Sub Structure | 6th floor | LT-2-129 | 2024-10-23 | 2024-10-23 | formwork | Check beam and slab formwork zone | (+73.75) | Grid G-U/1-8 | B | 2024-10-31
130 | Sub Structure | 6th floor | LT-2-130 | 2024-10-23 | 2024-10-23 | formwork | Check columns (10 Nos) formwork Zone 6 | (+73.75 to +84.75) | Grid U/8-12, S/8-12 | A | 2024-10-31
131 | Sub Structure | 6th floor | LT-2-131 | 2024-10-24 | 2024-10-24 | formwork | Check columns (9 Nos) and (2 Nos) Shear wall zone 6 | (+73.75 to +84.75) | Grid N/8-12, Q/9-11, S/7 | A | 2024-10-31
132 | Sub Structure | basement | LT-2-132 | 2024-10-26 | 2024-10-26 | formwork | Check external wall formwork for rain water tank zone 7 | (-11.75 to +0'-00'') | Grid Q-T/1 | B | 2024-11-06
133 | Sub Structure | 6th floor | LT-2-133 | 2024-10-27 | 2024-10-27 | formwork | Check columns (11 Nos) formwork zone 7 | (+73.75 to +84.75) | Grid N/3, Q/3, R/1, S/3,5, T/1, U/1,3,4,6 | A | 2024-10-31
| Sub Structure | basement | LT-2-134 | 2024-10-28 | 2024-10-28 | formwork | Check rain water harvesting tank slab/sog formowrk zone 7 | (+0'-00'') | Grid P-T/1, T/1-3 | A | 2024-11-06
| Sub Structure | 6th floor | LT-2-135 | 2024-10-28 | 2024-10-28 | formwork | Check columns (7 Nos) formwork zone 7 | (+73.75 to +84.75) | Grid P/1, M/1,3,5,7, L/5,7 | A | 2024-10-31
| Sub Structure | 6th floor | LT-2-136 | 2024-10-29 | 2024-10-29 | formwork | Check columns (7 Nos) formwork zone 7 | (+73.75 to +84.75) | Grid L/1, L/3, K/1,3,5, J/1, H/5 | A | 2024-11-06
| Sub Structure | 7th floor | LT-2-137 | 2024-10-29 | 2024-10-29 | formwork | Check beam and slab formwork zone 6 & 7 | (+84.75) | Grid M-U/5-12 | B | 2024-11-06
| Sub Structure | 6th floor | LT-2-138 | 2024-10-30 | 2024-10-30 | formwork | Check columns (5 Nos) formwork zone 7 | (+73.75 to +84.75) | Grid G/3,5,7, H/7, K/7 | A | 2024-11-06
| Sub Structure | 6th floor | LT-2-139 | 2024-10-30 | 2024-10-31 | formwork | Check lift & stair formwork zone 7 | (+73.75 to +84.75) | Grid N-R/4-7 | A | 2024-11-06
| Sub Structure | 6th floor | LT-2-140 | 2024-11-02 | 2024-11-02 | formwork | Check service lift formwork zone 7 | (+73.75 to +84.75) | Grid H-J/3-4 | A | 2024-11-06
| Sub Structure | 6th floor | LT-2-141 | 2024-11-02 | 2024-11-02 | formwork | Check columns (2 Nos) formwork zone 7 | (+73.75 to +84.75) | Grid G/1, H/1 | A | 2024-11-06
| Sub Structure | 7th floor | LT-2-142 | 2024-11-04 | 2024-11-05 | formwork | Check beam & slab formwork zone 7 | (+84.75) | Grid G-U/1-9 | B | 2024-11-09
| Sub Structure | 7th floor | LT-2-143 | 2024-11-05 | 2024-11-05 | formwork | Check columns(10 Nos) formwork zone 6 & 7 | (+84.75 to +95.75) | Grid U/6,8,9,10,11,12, S/9-12 | A | 2024-11-09
| Sub Structure | 7th floor | LT-2-144 | 2024-11-06 | 2024-11-06 | formwork | Check columns (10 Nos) and Shear wall (1 No) formwork zone 6 | (+84.75 to +95.75) | Grid N/8-12, Q/8-12, S/8 | A | 2024-11-09
| Sub Structure | basement | LT-2-145 | 2024-11-07 | 2024-11-07 | formwork | Check formwork for external wall of rain water tank zone 7 | (-11.75 to +0'-00'') | Grid U/5-9 | A | 2024-11-14
| Sub Structure | 7th floor | LT-2-146 | 2024-11-09 | 2024-11-09 | formwork | Check columns (10 Nos) formwork zone 6 & 7 | (+84.75 to +95.75) | Grid P/1, Q/1,3, R/1, S/3-5, T/1, U/1-4 | A | 2024-11-14
| Sub Structure | 7th floor | LT-2-147 | 2024-11-10 | 2024-11-10 | formwork | Check columns (10 Nos) formwork zone 7 | (+84.75 to +95.75) | Grid K/1-5, L/1-5, M/1-5, N/3 | A | 2024-11-14
| Sub Structure | 7th floor | LT-2-148 | 2024-11-11 | 2024-11-11 | formwork | Check columns (9 Nos) formwork zone 7 | (+84.75 to +95.75) | Grid G/3-7, H/5-7, J/1, L/7, M/7 | A | 2024-11-14
| Sub Structure | 7th floor | LT-2-149 | 2024-11-11 | 2024-11-11 | formwork | Check column (1 No) formwork and shear wall (1 No) zone 6 | (+84.75 to +95.75) | Grid S/7, N/11 | A | 2024-11-18
| Sub Structure | 8th floor | LT-2-150 | 2024-11-12 | 2024-11-12 | formwork | Check beam and slab formwork zone 6 & 7 | (+95.75) | Grid M-U/5-12 | B | 2024-11-28
| Sub Structure | 7th floor | LT-2-151 | 2024-11-13 | 2024-11-13 | formwork | Check lift formwork zone 6 & 7 | (+84.75 to +95.75) | Grid N-Q/4-7 | A | 2024-11-18
| Sub Structure | 7th floor | LT-2-152 | 2024-11-28 | 2024-11-28 | formwork | Check service lift and columns (2 Nos) formwork zone 7 | (+84.75 to +95.75) | Grid G-H/1, J-H/3-4 | A | 2024-12-02
| Sub Structure | 7th to 8th floor | LT-2-153 | 2024-11-29 | 2024-11-29 | formwork | Check beam and slab formwork zone 7 | (+95.75) | Grid U-G/1-8 | B | 2024-12-10
| Sub Structure | 8th floor | LT-2-154 | 2024-11-29 | 2024-11-29 | formwork | Check columns (8 Nos) formwork zone 6 | (+95.75 to +106.75) | Grid U/9-12, S/9-12 | A | 2024-12-10
| Sub Structure | 8th floor | LT-2-155 | 2024-11-30 | 2024-11-30 | formwork | Check columns (6 Nos) formwork | (+95.75 to +106.75) | Grid S/8, U/8, N/10, Q/11, N/12 | A | 2024-12-10
| Sub Structure | basement | LT-2-156 | 2024-12-01 | 2024-12-01 | formwork | Check external wall rain water tank formwork zone 7 | (-11.75 to +0-00) | Grid U/5-9 | A | 2024-12-16
| Sub Structure | 8th floor | LT-2-157 | 2024-12-01 | 2024-12-01 | formwork | Check shear wall formwork and allow to start concrete work zone 6 | (+96.0) | Grid Q/12 | A | 2024-12-10
| Sub Structure | 8th floor | LT-2-158 | 3-Dec-245 | 3-Dec-245 | formwrok | Check columns (6 Nos) and shear wall formwork | (+95.75 to +106.75) | Grid Q/8-9, N/8-9, U/6, S/7, N/11 | A | 2024-12-10
| Sub Structure | 8th floor | LT-2-159 | 2024-12-06 | 2024-12-06 | formwork | Check columns (9 Nos) formwork | (+95.75 to +106.75) | Grid U/1-4, T/1, S/3-5, R/1, Q/1-3 | A | 2024-12-10
| Sub Structure | 8th floor | LT-2-160 | 2024-12-07 | 2024-12-07 | formwork | Check column (7 Nos) formwork | (+95.75 to +106.75) | Grid G/1, H/1, P/1, N/3, M/1-3, L/1 | A | 2024-12-10
| Sub Structure | basement | LT-2-161 | 2024-12-09 | 2024-12-09 | formwrok | Check wall of water tank formwork | (-11.75 to +0'-00'') | Grid U/9-12 | A | 2024-12-10
| Sub Structure | 8th floor | LT-2-162 | 2024-12-09 | 2024-12-09 | formwork | Check column (10 Nos) formwork | (+95.75 to +106.75) | Grid J/1, K/1-7, L/3-7, M/5-7 | A | 2024-12-10
| Sub Structure | 8th floor | LT-2-163 | 2024-12-09 | 2024-12-09 | formwork | Check passenger lift formwork | (+95.75 to +106.75) | Grid N-Q/4-7 | A | 2024-12-16
| Sub Structure | 9th floor | LT-2-164 | 2024-12-09 | 2024-12-09 | formwork | Check beam and slab formwork zone 6 & 7 | (+106.75) | Grid M-U/5-12 | B | 2024-12-16
| Sub Structure | 8th floor | LT-2-165 | 2024-12-11 | 2024-12-11 | formwork | Check column (5 Nos) formwork | (+95.75 to +106.75) | Grid G/3-7, H/5-7, | A | 2024-12-16
| Sub Structure | 8th floor | LT-2-166 | 2024-12-13 | 2024-12-13 | formwork | Check service lift formwork | (+95.75 to +106.75) | Grid J-H/3-4 | A | 2024-12-16
| Sub Structure | 9th floor | LT-2-167 | 2024-12-15 | 2024-12-15 | formwork | Check beam and slab formwork zone 7 | (+106.75) | Grid G-U/1-8 | B | 2024-12-23
| Sub Structure | 9th floor | LT-2-168 | 2024-12-16 | 2024-12-16 | formwork | Check columns (10 Nos) formwork | (+106.75 to +117.75) | Grid U/8-12, S/8-12 | A | 2024-12-19
| Sub Structure | 9th floor | LT-2-169 | 2024-12-16 | 2024-12-16 | formwork | Check shear wall formwork and allow to start concrete work zone 6 | (+107.0) | Grid Q/12 | A | 2024-12-19
| Sub Structure | 9th floor | LT-2-170 | 2024-12-17 | 2024-12-17 | formwork | Check columns (11 Nos) formwork | (+106.75 to +117.75) | Grid U/6, S/7, Q/8-10, N/8-12 | A | 2024-12-19
| Sub Structure | 9th floor | LT-2-171 | 2024-12-21 | 2024-12-21 | formwork | Check columns (10 Nos) formwork | (+106.75 to +117.75) | Grid U/1-4, T/1, S/3-5, R/1, Q/1-3, P/1 | A | 2024-12-31
| Sub Structure | 9th floor | LT-2-172 | 2024-12-22 | 2024-12-22 | formwrok | Check columns (10 Nos) formwork | (+106.75 to +117.75) | Grid P/1, L/1-7, M/1-7, K/5 | A | 2024-12-31
| Sub Structure | basement | LT-2-173 | 2024-12-22 | 2024-12-22 | formwork | Check water tank wall formwork and allwo to start concrete work | (-11.75 to +0.00) | Grid U/9-12 | B | 2024-12-31
| Sub Structure | 9th floor | LT-2-174 | 2024-12-23 | 2024-12-23 | formwork | Check column (8 Nos) formwork | (+106.75 to +117.75) | Grid G/1,7, H/1,3,7, J/1 | A | 2024-12-31
| Sub Structure | 10th floor | LT-2-175 | 2024-12-23 | 2024-12-24 | formwork | Check beam & slab formwork zone 6 & 7 | (+117.75) | Grid M-U/5-12 | B | 2025-01-02
| Sub Structure | 9th floor | LT-2-176 | 2024-12-24 | 2024-12-24 | formwork | Check passenger lift formwork | (+106.75 to +117.75) | Grid N-Q/4-7 | A | 2024-12-31
| Sub Structure | 9th floor | LT-2-177 | 2024-12-24 | 2024-12-24 | formwork | Check columns (3 Nos) formwork | (+106.75 to +117.75) | Grid G/3,5, H/5 | A | 2024-12-31
| Sub Structure | 9th floor | LT-2-178 | 2024-12-28 | 2024-12-29 | formwork | Check service lift formwork zone 7 | (+106.75 to +117.75) | Grid H-J/3-4 | B | 2024-12-31
| Sub Structure | 10th floor | LT-2-179 | 2024-12-30 | 2024-12-30 | formwork | Check beam and slab formwork zone 7 | (+117.75) | Grid G-U/1-7 | B | 2025-01-07
| Sub Structure | 10th floor | LT-2-180 | 2024-12-31 | 2024-12-31 | formwork | Check column (10 Nos) formwork | (+117.75 to +130.75) | Grid U/6-12, S/9-12 | A | 2025-01-05
| Sub Structure | 10th floor | LT-2-181 | 2025-01-01 | 2025-01-01 | formwork | Check columns (7 Nos) formwork and shear wall | (+117.75 to +130.75) | Grid S/8, Q/8-12, N/10,12 | A | 2025-01-05
| Sub Structure | 10th floor | LT-2-182 | 2025-01-02 | 2025-01-02 | formwork | Chck columns (3 Nos) and one shear wall | (+117.75 to +130.75) | Grid N/8-9, U/6, Q/12 | A | 2025-01-05
| Sub Structure | 10th floor | LT-2-183 | 2025-01-04 | 2025-01-04 | formwork | Check shear wall formwork | (+117.75 to +130.75) | Grid N/11 | A | 2025-01-07
| Sub Structure | basement | LT-2-184 | 2025-01-04 | 2025-01-04 | formwork | Check water tank wall formwork and allow to start concrete work | (-117.75 to +0'-00'') | Grid U/11-13 | B | 2025-01-07
| Sub Structure | 10th floor | LT-2-185 | 2025-01-05 | 2025-01-05 | formwrok | Check columns (10 NOs0 formwork | (+117.75 to +130.75) | Grid U/1-4, T/1, S/3-5, R/1, Q/1-3, N/3 | A | 2025-01-07
| Sub Structure | 10th floor | LT-2-186 | 2025-01-06 | 2025-01-06 | formwork | Check columns (2 Nos) formwork | (+117.75 to +130.75) | Grid P/1, M/1 | A | 2025-01-07
| Sub Structure | 10th floor | LT-2-187 | 2025-01-07 | 2025-01-07 | formwork | Check column (10 Nos) formwork | (+117.75 to +130.75) | Grid G/1, H/1, J/1, K/1-3, L/1-5, M/3-5 | A | 2025-01-11
| Sub Structure | 11th floor | LT-2-188 | 2025-01-08 | 2025-01-08 | formwork | Check beam and slab formwork zone 6 & 7 | (+130.75) | Grid M-U/5-12 | A | 2025-02-10
| Sub Structure | 10th floor | LT-2-189 | 2025-01-08 | 2025-01-08 | formwrok | Check columns (9 Nos) formwork | (+117.75 to +130.75) | Grid G/3-7, H/5-7, K/5-7, M/7 | A | 2025-01-11
| Sub Structure | 10th floor | LT-2-190 | 2025-01-09 | 2025-01-10 | formwork | Check passenger lift formwork | (+117.75 to +130.75) | Grid N-Q/4-7 | B | 2025-01-11
| Sub Structure | 11th floor | LT-2-191 | 2025-01-14 | 2025-01-14 | formwork | Check beam and slab formwork zone 7 | (+130.75) | Grid G-U/1-7 | A | 2025-02-10
| Sub Structure | 10th floor | LT-2-192 | 2025-01-14 | 2025-01-14 | formwork | Check service lift formwork zone 7 | (+117.75 to +130.75) | Grid H-J/3-4 | B | 2025-01-17
| Sub Structure | 11th floor | LT-2-193 | 2025-01-15 | 2025-01-15 | formwork | Check columns (10 Nos) formwork | (+130.75 to +145.75) | Grid S-U/8, S-U/9, S-U/11, S-U/12 | B | 2025-01-17
| Sub Structure | 11th floor | LT-2-194 | 2025-01-15 | 2025-01-15 | formwork | Check shear wall formwork and allow to start concrete work zone 6 | (+130.75 to +145.75) | Grid Q/12 | B | 2025-01-20
| Sub Structure | GF | LT-2-195 | 2025-01-15 | 2025-01-15 | formwork | Check rain water harvesting tank slab/sog zone 6 & 7 | (+0'-00'') | Grid U/3-10 | B | 2025-01-17
| Sub Structure | 9th floor | LT-2-196 | 2025-01-16 | 2025-01-16 | formowork | Check vertical columns (10 Nos) formwork zone 6 | (+131.0 to +146.0) | Grid S-U/8-12 | A | 2025-01-20
| Sub Structure | 11th floor | LT-2-197 | 2025-01-17 | 2025-01-17 | formwork | Check shear wall formwork and allow to start concrete work | (+130.75 to +145.75) | Grid N/11 | A | 2025-01-20
| Sub Structure | 11th floor | LT-2-198 | 2025-01-17 | 2025-01-17 | formwork | Check columns (2 Nos) formwrok | (+130.75 to +145.75) | Grid Q/10-11 | A | 2025-01-20
| Sub Structure | 11th floor | LT-2-199 | 2025-01-18 | 2025-01-18 | formwork | Check columns (8 Nos) formwork zone 6 & 7 | (+130.75 to +145.75) | Grid U/6, S/7, N-Q/8-9, N/10,12 | A | 2025-01-22
| Sub Structure |  | LT-2-200 | 2025-01-18 | 2025-01-18 | formwork | Check vertical columns (2 Nos) formwork zone 6 | (+131.0 to +146.0) | Grid Q/10-11 | A | 2025-01-22
| Sub Structure | 11th floor | LT-2-201 | 2025-01-19 | 2025-01-19 | formwork | Check shear wall formwork and allow for concrete zone 6 | (+131.0 to +146.0) | Grid N/11 | A | 2025-01-22
| Sub Structure | 11th floor | LT-2-202 | 2025-01-19 | 2025-01-19 | formwork | Check shear wall formwork and allow to concrete pouring zone 6 | (+131.0 to +146.0) | Grid Q/12 | A | 2025-01-22
| Sub Structure | 11th floor | LT-2-203 | 2025-01-19 | 2025-01-19 | formwork | Check columns (8 Nos) formwork zone 6 & 7 | (+130.75 to 145.75) | Grid U/6, S/7, N-Q/8-9, N/10,12 | A | 2025-01-22
| Sub Structure | basement | LT-2-204 | 2025-01-20 | 2025-01-21 | formwork | Check water tank wall formwork and allow to start concrete work | (-11.75 to +0'-00'') | Grid U/12-13 | A | 2025-02-10
| Sub Structure | 11th floor | LT-2-205 | 2025-01-21 | 2025-01-21 | formwork | Check column (10 Nos) formwork zone 7 | (+130.75 to +145.75) | Grid Q-U/1, N-U/3, U/4, S/5 | A | 2025-01-27
| Sub Structure | 11th floor | LT-2-206 | 2025-01-22 | 2025-01-22 | formwork | Check column (8 Nos) formwork zone 7 | (+130.75 to +145.75) | Grid Q-T/1, Q-U/3, U/4, S/5 | A | 2025-01-27
| Sub Structure | basement | LT-2-207 | 2025-01-23 | 2025-01-23 | formwork | Check water tank slab & basement roof slab formwrok and allow to start concrete | (+0'-00'') | Grid U/9-12 | A | 2025-01-27
| Sub Structure | 11th floor | LT-2-208 | 2025-01-23 | 2025-01-23 | formwork | Check column (8 Nos) formwork zone 7 | (+130.75 to +145.75) | Grid G/1, H/1, K/1, L/1, M/1, P/1, L/3, M/3 | A | 2025-01-27
| Sub Structure | 11th floor | LT-2-209 | 2025-01-23 | 2025-01-23 | formwork | Check column (2 Nos) formwork | (+130.75 to +145.75) | Grid N/3, U/1 | A | 2025-01-27
| Sub Structure | 11th floor | LT-2-210 | 2025-01-24 | 2025-01-24 | formwork | check column (3 Nos) formwork | (+130.75 to +145.75) | Grid G/1, M/3, L/3 | A | 2025-01-27
| Sub Structure | 11th floor | LT-2-211 | 2025-01-24 | 2025-01-24 | formwork | Check column (2 Nos) formwork | (+130.75 to +145.75) | Grid M/5-7 | A | 2025-01-27
| Sub Structure | 11th floor | LT-2-212 | 2025-01-25 | 2025-01-25 | formwork | Check column (3 Nos) formwork | (+130.75 to +145.75) | Grid J/1, K/3, L/7 | A | 2025-01-29
| Sub Structure | 11th floor | LT-2-213 | 2025-01-25 | 2025-01-25 | formwork | Check column (7 Nos) formwork | (+130.75 to +145.75) | Grid H/1, K/1, L/1, M/1, P/1, M/5, M/7 | A | 2025-01-29
| Sub Structure | top floor | LT-2-214 | 2025-01-25 | 2025-01-25 | formwork | check beam & slab formwork zone 6 & 7 | (+145.75) | Grid M-U/5-12 | A | 2025-02-05
| Sub Structure | 11th floor | LT-2-215 | 2025-01-27 | 2025-01-27 | formwork | Check passenger lift formwork | (+130.75 to +145.75) | Grid N-Q/4-7 | B | 2025-01-29
| Sub Structure | 11th floor | LT-2-216 | 2025-01-27 | 2025-01-27 | formwork | Check column (7 Nos) formwork | (+130.75 to +145.75) | Grid G-H-K-L/7, G-H-K/5 | A | 2025-01-29
| Sub Structure | 11th floor | LT-2-217 | 2025-01-27 | 2025-01-27 | formwork | Check column (3 Nos) formwork | (+130.75 to +145.75) | Grid J/1, K/3, L/5 | A | 2025-01-29
| Sub Structure | 11th floor | LT-2-218 | 2025-01-28 | 2025-01-29 | formwork | Check columns (7 Nos) formwork | (+130.75 to +145.75) | Grid G-H-K-L/7, G-H-K/5 | A | 2025-01-31
| Sub Structure | 11th floor | LT-2-219 | 2025-01-28 | 2025-01-29 | formwork | Check columns (1 Nos) formwork | (+130.75 to +145.75) | Grid G/3 | A | 2025-01-31
| Sub Structure | 11th floor | LT-2-220 | 2025-01-30 | 2025-01-30 | formwork | Check column (1 No) formwork | (+130.75 to +145.75) | Grid G/3 | A | 2025-01-31
| Sub Structure | 11th floor | LT-2-221 | 2025-02-01 | 2025-02-01 | formwork | Check service lift formwork zone 7 | (+130.75 to +145.75) | Grid H-J/3-4 | A | 2025-02-05
| Sub Structure | 11th floor | LT-2-222 | 2025-02-01 | 2025-02-01 | formwork | Check beam & slab formwork zone 7 | (+130.75) | Grid G-U/1-7 | A | 2025-02-10
| Sub Structure | basement | LT-2-223 | 2025-02-06 | 2025-02-06 | formwork | Check septic tank wall formwork | (-11.75 to +0.00) | Grid G-F/1 | B | 2025-02-08
| Sub Structure | top floor | LT-2-224 | 2025-02-10 | 2025-02-08 | formwork | Check parapet wall formwork and columns (2 Nos) |  | Grid U/6-12, G/3, J/1 | B | 2025-02-08
| Sub Structure | top floor | LT-2-225 | 2025-02-10 | 2025-02-10 | formwork | Check service lift formwork zone 7 | (+145.75) | Grid H-J/3-4 | A | 2025-02-11
| Sub Structure | Top floor | LT-2-226 | 2025-02-10 | 2025-02-10 | formwork | Check column (1 No) formwork | (+145.75) | Grid H/1, | A | 2025-02-11
| Sub Structure | top floor | LT-2-227 | 2025-02-11 | 2025-02-10 | formwork | Check column (1 No) formwork | (+145.75) | Grid G/1 | A | 2025-02-13
| Sub Structure | top floor | LT-2-228 | 2025-02-10 | 2025-02-10 | formwork | Check parapet wall formwork |  | grid N-U/1 | A | 2025-02-13
| Sub Structure | basement | LT-2-229 | 2025-02-12 | 2025-02-12 | formwork | Check septic tank wall formwork | (-11.75 to +0.00) | Grid F/1 | A | 2025-02-14
| Sub Structure | Top floor | LT-2-230 | 2025-02-13 | 2025-02-14 | formwork | Check parapet wall formwrok | (+146.0) | Grid J-N/1 | A | 2025-02-14
| Sub Structure | Top floor | LT-2-231 | 2025-02-14 | 2025-02-14 | formwork | Check core wall formwork zone 7 | (+146.0) | Grid N-R/5-7 | A | 2025-02-27
| Sub Structure | Mummty to Roof | LT-2-232 | 2025-02-17 | 2025-02-17 | formwork | Check Slab formwork zone 7 |  | Grid G-J/1-3 | A | 2025-02-27
| Sub Structure | Top floor | LT-2-233 | 2025-02-19 | 2025-02-19 | formwork | Check parapet wall formwork |  | Grid U/1-6 | A | 2025-02-27
| Sub Structure | top floor | LT-2-234 | 2025-02-22 | 2025-02-22 | formwork | Check parapet wall formwork |  | Grid N/8-12 | A | 2025-02-27
| Sub Structure | Top floor | LT-2-235 | 2025-02-24 | 2025-02-24 | formwork | Check head water tank bottom slab formwrok |  | Grid N-R/7-8 | A | 2025-04-14
| Sub Structure | Top floor | LT-2-236 | 2025-02-25 | 2025-02-25 | formwork | Check parapet wall formwork |  | Grid G-N/4-7 | A | 2025-02-27
| Sub Structure | Mummty to Roof | LT-2-237 | 2025-02-28 | 2025-02-28 | formwork | Check mummty roof slab formwork |  | Grid N-Q/5-7 | A | 2025-03-06
| Sub Structure | Mummty to Roof | LT-2-238 | 2025-03-05 | 2025-03-05 | formwork | Check machinery room wall formwork and mummty roof wall |  | Grid G-J/1-4 | A | 2025-03-12
| Sub Structure | Mummty | LT-2-239 | 2025-03-11 | 2025-03-12 | formwork | Check machinery room wall formwork |  | Grid N-Q/5-6 | A | 2025-03-13
| Sub Structure | Mummty | LT-2-240 | 2025-03-12 | 2025-03-13 | formwork | Check machinery room slab formwrok |  | Grid N-Q/5-6 | A | 2025-03-15
| Sub Structure | Ground floor | LT-2-241 | 2025-03-12 | 2025-03-13 | formwork | Check front platform wall formwork |  | Grid N/7-12 | A | 2025-03-15
| Sub Structure | Mummty Top | LT-2-242 | 2025-03-13 | 2025-03-14 | formwork | Check mummty formwork |  | Grid N-Q/5-7 | A | 2025-03-15
| Sub Structure | Mummty | LT-2-243 | 2025-03-14 | 2025-03-15 | formwork | Check machinery room slab formwork |  | Grid N-Q/5-6 | A | 2025-03-18
| Sub Structure | Ground floor | LT-2-244 | 2025-03-14 | 2025-03-15 | formwork | Check front platform wall formwork |  | Grid G-N/7 | A | 2025-03-19
| Sub Structure | Mummty Roof | LT-2-245 | 2025-03-17 | 2025-03-18 | formwork | Check parapet wall formwrok |  | Grid H-J/3-4, N-Q/4-6 | A | 2025-03-21
| Sub Structure | 1st floor | LT-2-246 | 2025-03-17 | 2025-03-17 | formwork | Check leftover slab formwork and allow to start concrete work | (+19.0) | Grid N/8-9 | A | 2025-04-22
| Sub Structure | 1st floor | LT-2-247 | 2025-03-18 | 2025-03-18 | formwork | Check leftover slab formwork and allow to start concrete work | (+19.0) | Grid N/10-11 | A | 2025-04-22
| Sub Structure | 1st floor | LT-2-248 | 2025-04-19 | 2025-04-19 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+19.0) | Grid N/10-11 | A | 2025-04-22
| Sub Structure | 1st floor | LT-2-249 | 2025-04-18 | 2025-04-18 | formwork | Check vertical band formwrok and allow to start concret work | (+19.0) | Grid N/8-9 | A | 2025-04-22
| Sub Structure | Mummty Roof | LT-2-250
| Sub Structure | 1st floor | LT-2-251 | 2025-04-19 | 2025-04-19 | formwork | Check vertical band formwork and allow to start concrete work | (+19.0) | Grid N/10-11 | A | 2025-04-24
| Sub Structure | 2nd floor | LT-2-252 | 2025-04-20 | 2025-04-20 | formwork | Check leftover slab formwork and allow to start concrete work | (+30.0) | Grid N/8-9 | A | 2025-04-24
| Sub Structure | 2nd floor | LT-2-253 | 2025-04-21 | 2025-04-21 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+30.0) | Grid N/8-9 | A | 2025-04-24
| Sub Structure | 2nd floor | LT-2-254 | 2025-04-22 | 2025-04-22 | formwork | Check leftover slab formwork and allow to start concrete work | (+30.0) | Grid N/10-11 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-255 | 2025-04-22 | 2025-04-22 | formwrok | Check vertical band formwork and allow to start concrete work | (+30.0) | Grid N/8-9 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-256 | 2025-05-01 | 2025-05-01 | dismantling | Check beam dismantling | (+19.0) | Grid H-K, L-M/7, K-L, M-P, R-T/1, U/4-6 | A | 2025-05-21
| Sub Structure | 2nd floor | LT-2-257 | 2025-04-23 | 2025-04-23 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+30.0) | Grid N/10-11 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-258 | 2025-04-23 | 2025-04-23 | formwork | Check vertical band formwork and allow to start concrete work | (+30.0) | Grid N/10-11 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-259 | 2025-04-23 | 2025-04-23 | formwrok | Check leftover slab formwork and allow to start concrete work | (+41.0) | Grid N/8-9 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-260 | 2025-04-24 | 2025-04-24 | reinforcement | Check vertical band reinforcement and allow to start formwrok | (+41.0) | Grid N/8-9 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-261 | 2025-04-24 | 2025-04-24 | formwork | Check vertical band formwork and allow to start concrete work | (+41.0) | Grid N/8-9 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-262 | 2025-04-24 | 2025-04-24 | formwork | Check leftover slab formwork and allow to start concrete work | (+41.0) | Grid N/10-11 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-263 | 2025-04-26 | 2025-04-26 | reinforcement | check vertical band rienforcement and allow to start formwork | (+41.0) | Grid N;/10-11 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-264 | 2025-04-26 | 2025-04-26 | formwork | Check vertical band formwork and allow to start concrete work | (+41.0) | Grid N/10-11 | A | 2025-05-08
| Sub Structure | 4th floor | LT-2-265 | 2025-04-26 | 2025-04-26 | formwork | Check leftover slab formwrok and allow to start concrete work | (+52.0) | Grid N/8-9 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-266 | 2025-04-26 | 2025-04-26 | layout | Check layout and allow to start brick work on external side | (+19.0) | Grid G-U/1-12 | A | 2025-05-08
| Sub Structure | 4th floor | LT-2-267 | 2025-04-26 | 2025-04-26 | formwork | Check leftover slab formwork and allow to start concrete work | (+52.0) | Grid N/10-11 | A | 2025-05-08
| Sub Structure | 4th floor | LT-2-268 | 2025-04-26 | 2025-04-26 | reinforcement | check vertical band rinforcemetn and allow to start formwork | (+52.0) | Grid N/8-9 | A | 2025-05-08
| Sub Structure | 4th floor | LT-2-269 | 2025-04-26 | 2025-04-26 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid N/8-9 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-270 | 2025-04-26 | 2025-04-26 | formwrok | Check leftover slab formwork and allow to start concrete work | (+19.0) | Grid U/8-11 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-271 | 2025-04-28 | 2025-04-28 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+19.0) | Grid U/8-11, | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-272 | 2025-04-29 | 2025-04-29 | formwork | Check vertical band formwork and allow to start concrete work | (+19.0) | Grid U/8-11 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-273 | 2025-04-29 | 2025-04-29 | formwork | Check leftover slab formwork and allow to start concrete work | (+19.0) | Grid U/.4-6 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-274 | 2025-04-29 | 2025-04-29 | formwork | Check leftover slab formwork and allow to start concrete work | (+19.0) | Grid H-K, L-M/7 | A | 2025-05-08
| Sub Structure | 4th floor | LT-2-275 | 2025-04-29 | 2025-04-29 | reinforcement | check vertical band reinforcement and allow to start formwork | (+52.0) | Grid U/10-11 | A | 2025-05-08
| Sub Structure | 4th floor | LT-2-276 | 2025-04-29 | 2025-04-29 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid U/10-11 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-277 | 2025-04-30 | 2025-04-30 | layout | Check layout and allow to start brick work | (+19.0) | Grid G-U/1-12 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-278 | 2025-04-30 | 2025-04-30 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+19.0) | Grid U/4-6 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-279 | 2025-04-30 | 2025-04-30 | formwork | Check vertical band formwork and allow to start concrete work | (+19.0) | Grid U/4-6 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-280 | 2025-04-30 | 2025-04-30 | formwork | Check leftover slab formwork and allow to start concrete work | (+30.0) | Grid U/8-11 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-281 | 2025-05-01 | 2025-05-01 | formwork | Check leftover slab formwork and allow to start concrete work | (+19.0) | Grid U/1-3 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-282 | 2025-05-01 | 2025-05-01 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+19.0) | Grid H-K, L-M/7 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-283 | 2025-05-01 | 2025-05-01 | formwork | Check vertical band formwork and allow to start concrete work | (+19.0) | Grid H-K, L-M/7 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-284 | 2025-05-01 | 2025-05-01 | reinforcement | Check vertical band reinforcement and allow to startt formwork | (+30.0) | Grid U/8-11 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-285 | 2025-05-02 | 2025-05-02 | formwork | Check vertical band formwork and allow to start concrete work | (+30.0) | Grid U/8-11 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-286 | 2025-05-02 | 2025-05-02 | formwork | Check leftover slab formwork and allow to start concrete work | (+30.0) | Grid H-K, L-M/7 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-287 | 2025-05-02 | 2025-05-02 | formwork | Check leftover slab formwork and allow to start concrete work | (+30.0) | Grid U/4-6 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-288 | 2025-05-03 | 2025-05-03 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+30.0) | Grid H-K, L-M/7 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-289 | 2025-05-03 | 2025-05-03 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+19.0) | Grid U/3 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-290 | 2025-05-03 | 2025-05-03 | formwrok | Check leftover slab formwork and allow to start concrete work | (+42.0) | Grid U/8-11 | A | 2025-05-03
| Sub Structure | 2nd floor | LT-2-291 | 2025-05-03 | 2025-05-03 | formwork | Check vertical band formwork and allow to start concrete work | (+30.0) | Grid H-K, L-M/7 | A | 2025-05-09
| Sub Structure | 1st floor | LT-2-292 | 2025-05-03 | 2025-05-03 | formwork | Check vertical band formwork and allow to start concrete work | (+19.0) | Grid U/3 | A | 2025-05-09
| Sub Structure | 2nd floor | LT-2-293 | 2025-05-03 | 2025-05-03 | formwork | Check leftover slab formwork and allow to start concrete work | (+30.0) | Grid U/3 | A | 2025-05-15
| Sub Structure | 3rd floor | LT-2-294 | 2025-05-03 | 2025-05-03 | formwork | Check leftover slab formwork and allow to start concrete work | (+42.0) | Grid H-K, L-M/7 | A | 2025-05-15
| Sub Structure | 3rd floor | LT-2-295 | 2025-05-03 | 2025-05-03 | formwork | check vertical band reinforcement and allow to start formwork | (+42.0) | Grid U/8-11 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-296 | 2025-05-07 | 2025-05-07 | formwork | Check vertical band formwork and allow to start concrete work | (+42.0) | Grid U/10-11 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-297 | 2025-05-03 | 2025-05-03 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+30.0) | Grid U/4-6 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-298 | 2025-05-03 | 2025-05-03 | formwork | Check vertical band formwork and allow to start concrete work | (+30.0) | Grid U/4-6 | A | 2025-05-15
| Sub Structure | 1st floor | LT-2-299 | 2025-05-03 | 2025-05-03 | formwork | Check leftover slab formwork and allow to start concrete work | (+19.0) | Grid U/1 | A | 2025-05-15
| Sub Structure | 1st floor | LT-2-300 | 2025-05-05 | 2025-05-05 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+19.0) | Grid U/1 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-301 | 2025-05-05 | 2025-05-05 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+19.0) | Grid U/3 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-302 | 2025-05-05 | 2025-05-05 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+41.0) | Grid H-K, L-M/7 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-303 | 2025-05-05 | 2025-05-05 | layout | Check layout and allow to start brick work on external side | (+43.0) | Grid G-U/1-12 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-304 | 2025-05-07 | 2025-05-07 | formwork | Check leftover slab formwork and allow to start concrete work | (+41.0) | Grid U/4-6 | A | 2025-05-08
| Sub Structure | 1st floor | LT-2-305 | 2025-05-06 | 2025-05-06 | formwork | Check vertical band formwrok and allow to start concrete wrok | (+19.0) | Grid U/1 | A | 2025-05-08
| Sub Structure | 2nd floor | LT-2-306 | 2025-05-06 | 2025-05-06 | formwork | Check vertical band formwork and allow to start concrete work | (+30.0) | Grid U/3 | A | 2025-05-08
| Sub Structure | 3rd floor | LT-2-307 | 2025-05-06 | 2025-05-06 | formwork | Check vertical band formwork and allow to start concrete work | (+41.0) | , L-M/7 | A | 2025-05-08
| Sub Structure | Ground floor | LT-2-308 | 2025-05-06 | 2025-05-06 | formwrok | Check deck slab formwork and allow to start weight concrete work |  | Grid J-N/7-12 | A | 2025-05-08
|  | 4th floor | LT-2-309 | 2025-05-07 | 2025-05-08 | formwork | Check leftover slab formwork and allow to start concrete work | (+63.0) | Grid H-K/7 | A | 2025-05-09
|  | 4th floor | LT-2-310 | 2025-05-07 | 2025-05-07 | formwork | Check leftover slab formwork and allow to start concrete work | (+63.0) | Grid L-M/7 | A | 2025-05-09
|  | 3rd floor | LT-2-311 | 2025-05-07 | 2025-05-07 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid U/8-9 | A | 2025-05-09
|  | 3rd floor | LT-2-312 | 2025-05-06 | 2025-05-06 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid H-K/7 | A | 2025-05-06
|  | 3rd floor | LT-2-313 | 2025-05-07 | 2025-05-07 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+52.0) | Grid U/4-6 | A | 2025-05-09
|  | 4th floor | LT-2-314 | 2025-05-07 | 2025-05-07 | reinforcement | Check vertical band reinforcement and allow to start formwrok | (+63.0) | Grid H-K/7 | A | 2025-05-09
|  | 3rd floor | LT-2-315 | 2025-05-07 | 2025-05-07 | formwork | Check vertical band formwork and allow to start concrete wrok | (+52.0) | Grid U/4-6 | A | 2025-05-09
|  | 4th floor | LT-2-316 | 2025-05-08 | 2025-05-08 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+52.0) | Grid H-K, L-M/7 | A | 2025-05-09
|  | 4th floor | LT-2-317 | 2025-05-08 | 2025-05-09 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid H-K, L-M/7 | A | 2025-05-09
|  | 2nd floor | LT-2-318 | 2025-05-08 | 2025-05-08 | formwork | Check leftover slab formwork and allow to start concrete work | (+30.0) | Grid U/1 | A | 2025-05-09
|  | 3rd floor | LT-2-319 | 2025-05-08 | 2025-05-08 | formwork | Check leftover slab formwrok and allow to start concrete work | (+41.0) | Grid U/3 | A | 2025-05-09
|  | 4th floor | LT-2-320 | 2025-05-08 | 2025-05-09 | formwork | check leftover slab formwrok and allow to start concrete work | (+52.0) | Grid U/8-11 | A | 2025-05-10
|  | 5th floor | LT-2-321 | 2025-05-09 | 2025-05-09 | reinforcement | Check reinforcement and formwork of leftover slab and allow to start concrete | (+63.0) | Grid N/8-11 | A | 2025-05-09
|  | 3rd floor | LT-2-322 | 2025-05-09 | 2025-05-09 | reinforcement | check vertical band rienforcement and allow to start formwork | (+41.0) | Grid U/3 | A | 2025-05-10
|  | 2nd floor | LT-2-323 | 2025-05-09 | 2025-05-09 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+30.0) | Grid U/1 | A | 2025-05-10
|  | 2nd floor | LT-2-324 | 2025-05-09 | 2025-05-09 | formwork | Check vertical band formwork and allow to start concret ework | (+30.0) | Grid U/1 | A | 2025-05-10
|  | 3rd floor | LT-2-325 | 2025-05-09 | 2025-05-09 | formwork | Check vertical band formwork and allow to start concret ework | (+41.0) | Grid U/3 | A | 2025-05-10
|  | 4th floor | LT-2-326 | 2025-05-09 | 2025-05-09 | formwork | Check leftover slab formwork and allow to start concrete work | (+52.0) | Grid U/4-6 | A | 2025-05-10
|  | 5th floor | LT-2-327 | 2025-05-10 | 2025-05-10 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+63.0) | Grid N/8-11 | A | 2025-05-13
|  | 1st floor | LT-2-328 | 2025-05-10 | 2025-05-10 | reinforcement | check reinforcement and formwork of leftover slab and allow to start concrete work | (+19.0) | Grid N/12 | A | 2025-05-10
|  | 5th floor | LT-2-329 | 2025-05-10 | 2025-05-10 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid N/8-11 | A | 2025-05-12
|  | 3rd floor | LT-2-330 | 2025-05-10 | 2025-05-10 | formwork | Check leftover slab and allow to start concrete work | (+41.0) | Grid U/1 | A | 2025-05-12
|  | 4th floor | LT-2-331 | 2025-05-12 | 2025-05-12 | formwork | Check leftover slab formwork and allow to start concrete work | (+52.0) | Grid U/3 | A | 2025-05-13
|  | Top floor | LT-2-332 | 2025-05-10 | 2025-05-10 | formwork | Check genset beam formwork | (+146.0) | Grid J-L/1-3 | A | 2025-05-12
|  | 1st floor | LT-2-333 | 2025-05-12 | 2025-05-12 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+19.0) | Grid N/12 | A | 2025-05-12
|  | 4th floor | LT-2-334 | 2025-05-12 | 2025-05-12 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+52.0) | Grid U/4-11 | A | 2025-05-12
|  | 1st floor | LT-2-335 | 2025-05-12 | 2025-05-12 | formwork | Check vertical band formwork and allow to start concrete work | (+19.0) | Grid N/12 | A | 2025-05-12
|  | 4th floor | LT-2-336 | 2025-05-12 | 2025-05-12 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid U/10-11 | A | 2025-05-12
|  | 6th floor | LT-2-337 | 2025-05-12 | 2025-05-12 | formwork | check leftover slab formwork and allow to start concrete work | (+74.0) | Grid N/8-11 | A | 2025-05-12
|  | 3rd floor | LT-2-338 | 2025-05-12 | 2025-05-12 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+41.0) | Grid U/1 | A | 2025-05-13
|  | 6th floor | LT-2-339 | 2025-05-13 | 2025-05-13 | reinforcement | check vertical band rienforcement and allow to start formwork | (+74.0) | Grid N/8-11 | A | 2025-05-13
|  | 4th floor | LT-2-340 | 2025-05-13 | 2025-05-13 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid U/8-9 | A | 2025-05-13
|  | 6th floor | LT-2-341 | 2025-05-13 | 2025-05-13 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid N/8-9 | A | 2025-05-13
|  | 6th floor | LT-2-342 | 2025-05-13 | 2025-05-13 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid N/10-11 | A | 2025-05-13
|  | 2nd floor | LT-2-343 | 2025-05-14 | 2025-05-15 | layout | Check layout and allow to start brick work on external side | (+.30.0) | Grid G-U/1-12 | A | 2025-05-15
|  | 5th floor | LT-2-344 | 2025-05-14 | 2025-05-14 | reinforcement | Check reinforcement and formwrok of leftover slab and allow to start concrete | (+63.0) | Grid H-K, L-M/7 | A | 2025-05-14
|  | 3rd floor | LT-2-345 | 2025-05-14 | 2025-05-14 | formwork | Check vertical band formwork and allow to start concrete work | (+41.0) | Grid U/1 | A | 2025-05-14
|  | 4th floor | LT-2-346 | 2025-05-14 | 2025-05-14 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid U/4-6 | A | 2025-05-14
|  | 2nd floor | LT-2-347 | 2025-05-14 | 2025-05-14 | formwork | Check leftover slab formwork and allow to start concrete work | (+30.0) | Grid N/12, | A | 2025-05-14
|  | 7th floor | LT-2-348 | 2025-05-15 | 2025-05-15 | formwork | check leftover slab formwork and allow to start concrete work | (+85.0) | Grid N/8-11 | A | 2025-05-15
|  | 4th floor | LT-2-349 | 2025-05-15 | 2025-05-15 | formwork | check leftover slab formwork and allow to start concrete work | (+52.0) | Grid U/1 | A | 2025-05-15
|  | 5th floor | LT-2-350 | 2025-05-15 | 2025-05-15 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+63.0) | Grid H-K, L-M/7 | A | 2025-05-15
|  | Top floor | LT-2-351 | 2025-05-17 | 2025-05-17 | formwork | check over head formwork and FSS tank wall |  | Grid N-Q/7-8 | A | 2025-05-19
|  | 5th floor | LT-2-352 | 2025-05-15 | 2025-05-15 | formwrok | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid H-K/7 | A | 2025-05-15
|  | 5th floor | LT-2-353 | 2025-05-15 | 2025-05-15 | formwork | Check vertical band formwork and allow to start concrete work | (+63.0) | Grid L-M/7 | A | 2025-05-16
|  | 2nd floor | LT-2-354 | 2025-05-16 | 2025-05-16 | reinforcement | check vertical band formwork and allow to start formwork | (+30.0) | Grid N/12 | A | 2025-05-16
|  | 2nd floor | LT-2-355 | 2025-05-16 | 2025-05-16 | formwork | Check vertical band formwork and allow to start concrete work | (+30.0) | Grid N/12 | A | 2025-05-16
|  | 4th floor | LT-2-356 | 2025-05-16 | 2025-05-16 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+52.0) | Grid U/3 | A | 2025-05-16
|  | 4th floor | LT-2-357 | 2025-05-16 | 2025-05-16 | formrowkr | check vertical band formwrok and allow to start concrete work | (+41.0) | Grid U/3 | A | 2025-05-16
|  | 6th floor | LT-2-358 | 2025-05-16 | 2025-05-16 | formrowkr | check leftover slab formwork and allow to start concrete work | (+74.0) | Grid H-K/7 | A | 2025-05-16
|  | 7th floor | LT-2-359 | 2025-05-16 | 2025-05-16 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+85.0) | Grid N/8-11 | A | 2025-05-16
|  | 7th floor | LT-2-360 | 2025-05-17 | 2025-05-17 | formwork | check vertical band formwork and allow to start concrete work | (+85.0) | Grid N/8-9 | A | 2025-05-17
|  | 4th floor | LT-2-361 | 2025-05-17 | 2025-05-17 | layout | check layout and allow to start brick work on external side | (+52.0) | Grid G-U/1-12 | A | 2025-05-19
|  | 5th floor | LT-2-362 | 2025-05-17 | 2025-05-17 | layout | Check layout and allow to start brick work on external side | (+63.0) | Grid U/1-12 | A | 2025-05-19
|  | 4th floor | LT-2-363 | 2025-05-17 | 2025-05-17 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+52.0) | Grid U/1 | A | 2025-05-17
|  | 4th floor | LT-2-364 | 2025-05-17 | 2025-05-17 | formwork | check vertical band formwork and allow to start concrete work | (+52.0) | Grid U/1 | A | 2025-05-17
|  | 6th floor | LT-2-365 | 2025-05-17 | 2025-05-17 | formwork | check leftover slab formwork and allow to start concrete work | (+74.0) | Grid L-M/7 | A | 2025-05-17
|  | 7th floor | LT-2-366 | 2025-05-17 | 2025-05-17 | reinforcement | Check vertical band reinforcement and allow to start formwrok | (+85.0) | Grid N/10-11 | A | 2025-05-17
|  | 7th floor | LT-2-367 | 2025-05-17 | 2025-05-17 | formwork | check vertical band formwork and allow to start concrete work | (+85.0) | Grid N/10-11 | A | 2025-05-19
|  | 3rd floor | LT-2-368 | 2025-05-17 | 2025-05-17 | formwork | check leftover slab formwrok and allow to start concrete work | (+41.0) | Grid N/12 | A | 2025-05-20
|  | 6th floor | LT-2-369 | 2025-05-17 | 2025-05-17 | reinforcement | check vertical band reinforcement and allow for formwork | (+74.0) | Grid H-K, L-M/7 | A | 2025-05-19
|  | 6th floor | LT-2-370 | 2025-05-17 | 2025-05-17 | formwork | check vertical band formwork and allow to start concrete work | (+74.0) | Grid H-K, L-M/7 | A | 2025-05-19
|  | 5th floor | LT-2-371 | 2025-05-19 | 2025-05-19 | formwork | Check leftover slab formwork and allow to start concrete work | (+63.0) | Grid U/10-11 | A | 2025-05-19
|  | 7th floor | LT-2-372 | 2025-05-20 | 2025-05-20 | formwork | Check leftover slab formwork and allow to start concrete work | (+85.0) | Grid H-K/7 | A | 2025-05-21
|  | 5th floor | LT-2-373 | 2025-05-20 | 2025-05-20 | reinforcement | check reinforcement and formwork of leftover slab and allow to start concrete work | (+63.0) | Grid U/8-9 | A | 2025-05-21
|  | Top floor | LT-2-374 | 2025-05-21 | 2025-05-21 | formwork | Check head water tank and fss formwrok |  | Grid N-Q/7-8 | A | 2025-05-24
|  | 7th floor | LT-2-375 | 2025-05-21 | 2025-05-21 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+85.0) | Grid H-K/7 | A | 2025-05-21
|  | 3rd floor | LT-2-376 | 2025-05-21 | 2025-05-21 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+41.0) | Grid N/12 | A | 2025-05-21
|  | 3rd floor | LT-2-377 | 2025-05-22 | 2025-05-22 | formwork | Check vertical band formwork and allow to start concrete work | (+41.0) | Grid N/12 | A | 2025-05-22
|  | 7th floor | LT-2-378 | 2025-05-21 | 2025-05-21 | formwrok | check vertical band formwork and allow to start concrete work | (+85.0) | Grid H-K/7 | A | 2025-05-22
|  | 7th floor | LT-2-379 | 2025-05-22 | 2025-05-22 | formwork | Check leftover slab formwork and allow to start concrete work | (+85.0) | Grid L-M7 | A | 2025-05-22
|  | 5th floor | LT-2-380 | 2025-05-22 | 2025-05-22 | reinforcement | check vertical band reinforcement and allow to start formwork | (+52.0) | Grid U/10-11 | A | 2025-05-22
|  | 8th floor | LT-2-381 | 2025-05-22 | 2025-05-22 | formwork | check leftover slab formwrok and allow to start concrete work | (+96.0) | Grid N/8-11 | A | 2025-05-22
|  | 5th floor | LT-2-382 | 2025-05-22 | 2025-05-22 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid U/10-11 | A | 2025-05-22
|  | 5th floor | LT-2-383 | 2025-05-22 | 2025-05-22 | reinforcement | check vertical band reinforcement and allow to start formwork | (+52.0) | Grid U/8-9 | A | 2025-05-22
|  | 5th floor | LT-2-384 | 2025-05-22 | 2025-05-22 | formwork | check leftover slab formwork and allow to start concrete work | (+63.0) | Grid N/4-6 | A | 2025-05-22
|  | 7th floor | LT-2-385 | 2025-05-22 | 2025-05-22 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+85.0) | Grid L-M/7 | A | 2025-05-22
|  | 1st floor | LT-2-386 | 2025-05-22 | 2025-05-22 | brick work | check external brick work | (+19.0) | Grid G-U/1-12 | A | 2025-05-22
|  | 2nd floor | LT-2-387 | 2025-05-22 | 2025-05-22 | brick work | check external brick work | (+30.0) | Grid G-U/1-12 | A | 2025-05-22
|  | 3rd floor | LT-2-388 | 2025-05-22 | 2025-05-22 | brick work | check external brick work | (+41.0) | Grid G-U/1-12 | A | 2025-05-22
|  | 4th floor | LT-2-389 | 2025-05-22 | 2025-05-22 | brick work | check external brick work | (+52.0) | Grid G-U/1-12 | R | 2025-05-22
|  | 4th floor | LT-2-389 R03 | 2025-10-30 | 2025-10-30 | brick work | check external brick work | (+52.0) | Grid G-U/1-12 | A | 2025-11-01
|  | 5th floor | LT-2-390 | 2025-05-22 | 2025-05-22 | brick work | check external brick work | (+63.0) | Grid G-U/1-12 | R | 2025-05-22
|  | 5th floor | LT-2-390 R.01 | 2025-07-07 | 2025-07-07 | brick work | check external brick work | (+63.0) | Grid G-U/1-12 | A | 2025-07-08
|  | 5th floor | LT-2-390 R.02 | 2025-07-07 | 2025-07-07 | brick work | check external brick work | (+63.0) | Grid G-U/1-12 | A | 2025-07-19
|  | 5th floor | LT-2-390 R.03 | 2025-10-30 | 2025-10-30 | brick work | check external brick work | (+63.0) | Grid G-U/1-12 | A | 2025-10-31
|  | 5th floor | LT-2-391 | 2025-05-22 | 2025-05-22 | reinforcement | check reinforcement and formwork of horizontal band and allow to concrete | (+63.0) | Grid G-H, K-L/7 | OP
|  | 7th floor | LT-2-392 | 2025-05-22 | 2025-05-22 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+85.0) | Grid L-M/7 | A | 2025-05-23
|  | 7th floor | LT-2-393 | 2025-05-22 | 2025-05-22 | formwork | check vertical band formwork and allow to start concrete work | (+85.0) | Grid L-M/7 | A | 2025-05-23
|  | 4th floor | LT-2-394 | 2025-05-23 | 2025-05-23 | formwork | Check leftover slab formwork and allow to start concrete work | (+52.0) | Grid N/12 | A | 2025-05-24
|  | 8th floor | LT-2-395 | 2025-05-23 | 2025-05-23 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+96.0) | Grid N/8-11 | A | 2025-05-23
|  | 8th floor | LT-2-396 | 2025-05-23 | 2025-05-23 | formwork | check vertical band formwork and allow to start concrete work | (+96.0) | Grid N/8-9 | A | 2025-05-24
|  | 8th floor | LT-2-397 | 2025-05-23 | 2025-05-23 | formwork | check vertical band formwrok and allow to start concrete work | (+96.0) | Grid N/10-11 | A | 2025-05-24
|  | 5th floor | LT-2-398 | 2025-05-23 | 2025-05-23 | formwork | check leftover slab formwrok and allow to start concrete work | (+63.0) | Grid U/1-3 | A | 2025-05-24
|  | 6th floor | LT-2-399 | 2025-05-23 | 2025-05-23 | formwork | check leftover slab formwrok and allow to start concrete work | (+72.0) | Grid U/10-11 | A | 2025-05-24
LT-2-400
|  | 6th floor | LT-2-401 | 2025-05-24 | 2025-05-24 | layout | check layout and allow to start brick work on external side | (+74.0) | Grid G-U/1-12 | A | 2025-05-26
LT-2-402
|  | 5th floor | LT-2-403 | 2025-05-24 | 2025-05-24 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+63.0) | Grid U/1-6 | A | 2025-05-26
LT-2-404
LT-2-405
LT-2-406
|  | Ground floor | LT-2-407 | 2025-05-24 | 2025-05-24 | formwork | check stair step formwork |  | Grid N/10-12 | A | 2025-05-26
|  | 1st floor | LT-2-408 | 2025-05-26 | 2025-05-26 | formwork | check leftover slab formwork and allow to start concrete work | (+19.0) | Grid K-L/1 | OP
|  | 9th floor | LT-2-409 | 2025-05-26 | 2025-05-26 | reinforcement | check vertical band reinforcement and allow to start formwork | (+107.0) | Grid U/8-11 | A | 2025-05-26
|  | Top floor | LT-2-410 | 2025-05-26 | 2025-05-26 | formwork | check over head water tank formwork and FSS tank parapet wall |  | Grid N-Q/7-8 | A | 2025-05-26
|  | 9th floor | LT-2-411 | 2025-05-26 | 2025-05-26 | formwork | che k vertical band formwork and allow to start concrete work | (+107.0) | Grid N/8-11 | OP
|  | 4th floor | LT-2-412 | 2025-05-26 | 2025-05-26 | formwork | check vertical band formwork and allow to start concrete work | (+52.0) | Grid N/12 | OP
|  | 1st floor | LT-2-413 | 2025-05-26 | 2025-05-26 | formwork | check leftover slab formwork and allow to start concrete work | (+19.0) | Grid M-P/1 | A | 2025-05-27
|  | 6th floor | LT-2-414 | 2025-05-27 | 2025-05-27 | reinforcement | check vertical band reinforcement and allow to start formwork | (+74.0) | Grid U/10-11 | A | 2025-05-27
LT-2-415
|  | 10th floor | LT-2-416 | 2025-05-27 | 2025-05-27 | formwork | check leftover slab formwork and allow to start concrete work | (+118.0) | Grid N/8-11 | A | 2025-05-27
|  | 8th floor | LT-2-417 | 2025-05-27 | 2025-05-27 | formwork | Check leftover slab formwork and allow to start concrete work | (+96.0) | Grid L-M/7 | A | 2025-05-29
|  | 6th floor | LT-2-418 | 2025-05-28 | 2025-05-28 | formwork | check vertical band formwork and allow to start concrete work | (+74.0) | Grid U/10-11 | A | 2025-05-27
|  | 6th floor | LT-2-419 | 2025-05-27 | 2025-05-27 | reinforcement | check vertical band reinforcement and allow to start formwork | (+74.0) | Grid U/8-9 | A | 2025-05-27
|  | 6th floor | LT-2-420 | 2025-05-28 | 2025-05-28 | formwork | check leftover slab formwork and allow to start concrete work | (+74.0) | Grid U/1-6 | A | 2025-05-29
|  | 8th floor | LT-2-421 | 2025-05-28 | 2025-05-28 | formwork | Check leftover slab formwork and allow to start concrete work | (+96.0) | Grid H-K/7 | A | 2025-05-29
|  | 10th floor | LT-2-422 | 2025-05-28 | 2025-05-28 | reinforcement | check vertical band reinforcement and allow to start formowork | (+118.0) | Grid N/8-11 | A | 2025-05-29
|  | 10th floor | LT-2-423 | 2025-05-28 | 2025-05-28 | formwork | check vertical band formwork and allow to start concrete work | (+118.0) | Grid N/8-11 | A | 2025-05-29
|  | 6th floor | LT-2-424 | 2025-05-28 | 2025-05-28 | formwork | check vertical band formwork and allow to start concrete work | (+74.0) | Grid U/8-9 | A | 2025-05-29
|  | 8th floor | LT-2-425 | 2025-05-28 | 2025-05-28 | reinforcement | check vertical band rienforcement and allow to start formwork | (+96.0) | Grid H-K, L-M/7 | A | 2025-05-29
|  | 8th floor | LT-2-426 | 2025-05-29 | 2025-05-29 | formwork | check vertical band formwork and allow to start concrete work | (+96.0) | Grid H-K/7, L-M | A | 2025-05-29
|  | 7th floor | LT-2-427 | 2025-05-29 | 2025-05-29 | formwork | check leftover slab formwork and allow to start concrete work | (+85.0) | Grid U/10-11 | A | 2025-05-29
|  | 6th floor | LT-2-428 | 2025-05-30 | 2025-05-30 | reinforcement | check vertical band reinforcement and allow to start formwork | (+74.0) | Grid U/1-6 | A | 2025-05-30
|  | 6th floor | LT-2-429 | 2025-05-30 | 2025-05-30 | formwork | check vertical band formwrok and allow to start concrete work | (+74.0) | Grid U/4-6 | A | 2025-05-30
|  | 1st floor | LT-2-430 | 2025-05-30 | 2025-05-30 | reinforcement | check vertical band rienforcement and allow to start formwork | (+19.0) | Grid K-L/1, M-P | A | 2025-05-30
|  | 9th floor | LT-2-431 | 2025-05-30 | 2025-05-30 | formwork | check leftover slab formwork and allow to start concrete work | (+107.0) | Grid H-K, L-M/7 | A | 2025-05-30
|  | 7th floor | LT-2-432 | 2025-05-31 | 2025-05-31 | formwork | check leftover slab formwork and allow to start concrete work | (+85.0) | Grid U/8-9 | A | 2025-05-31
|  | 6th floor | LT-2-433 | 2025-05-31 | 2025-05-31 | formwork | Check vertical band formwork and allow to start concrete work | (+74.0) | Grid U/1-3 | A | 2025-05-31
|  | 9th floor | LT-2-434 | 2025-05-31 | 2025-05-31 | reinforcement | check vertical band reinforcement and allow to start formwork | (+107.0) | Grid H-K, L-M/7 | A | 2025-05-31
|  | 5th floor | LT-2-435 | 2025-05-31 | 2025-05-31 | layout | Check layout and allow to start brick work on external side | (+63.0) | Grid G-U/1-12 | A | 2025-05-31
|  | 9th floor | LT-2-436 | 2025-05-31 | 2025-05-31 | formwork | check vertical band formwork and allow to start concrete work | (+107.0) | Grid H-K, L-M/7 | A | 2025-06-02
|  | 11th floor | LT-2-437 | 2025-05-31 | 2025-05-31 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid N/8-11 | A | 2025-06-02
|  | 1st floor | LT-2-438 | 2025-05-31 | 2025-05-31 | formwork | Check vertical band formwork and allow to start concrete work | (+19.0) | Grid K-L, M-P/1 | A | 2025-05-31
|  | 10th floor | LT-2-439 | 2025-05-31 | 2025-05-31 | formwork | check leftover slab formwork and allow to start concrete work | (+118.0) | Grid H-K/7, L-M | A | 2025-06-02
|  | 7th floor | LT-2-440 | 2025-05-31 | 2025-05-31 | formwork | Check leftover slab formwork and allow to start concrete work | (+85.0) | Grid U/4-6 | A | 2025-06-02
|  | 2nd floor | LT-2-441 | 2025-05-31 | 2025-05-31 | formwork | Check leftover slab formwork and allow to start concrete work | (+30.0) | Grid K-L, M-P/1 | A | 2025-06-02
|  | 1st floor | LT-2-442 | 2025-05-31 | 2025-05-31 | formwork | check leftover slab formwork and allow to start concrete work | (+19.0) | Grid R-T/1 | A | 2025-06-02
|  | 7th floor | LT-2-443 | 2025-05-31 | 2025-05-31 | reinforcement | check reinforcement of vertical band and allow to start formwork | (+85.0) | Grid U/10-11 | A | 2025-06-02
|  | 1st floor | LT-2-444 | 2025-05-31 | 2025-05-31 | reinforcement | Check vertical band reinforcement and allow to start formwork | (+19.0) | Grid U/12 | A | 2025-06-02
|  | 10th floor | LT-2-445 | 2025-05-31 | 2025-05-31 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+119.0) | Grid N/8-11 | A | 2025-06-02
|  | 7th floor | LT-2-446 | 2025-05-31 | 2025-05-31 | formwork | check vertical band formwork and allow to start concrete work | (+85.0) | Grid U/10-11 | A | 2025-06-02
|  | 1st floor | LT-2-447 | 2025-05-31 | 2025-05-31 | formwork | check vertical band formwork and allow to start concrete work | (+19.0) | Grid U/12 | A | 2025-06-02
|  | 11th floor | LT-2-448 | 2025-06-02 | 2025-06-02 | formwork | check vertical band formwork and allow to start concrete work | (+131.0) | Grid N/8-11 | A | 2025-06-02
|  | 7th floor | LT-2-449 | 2025-05-31 | 2025-05-31 | formwork | check leftover slab formwork and allow to start concrete work | (+85.0) | Grid U/1-3 | A | 2025-06-02
|  | 11th floor | LT-2-450 | 2025-06-02 | 2025-06-02 | reinforcement | check reinforcement of vertical band and allow to start formwork | (+131.0) | Grid N/8-11 | A | 2025-06-02
|  | 7th floor | LT-2-451 | 2025-06-02 | 2025-06-02 | reinforcement | check vertical band reinforcement and allow to start formwork | (+85.0) | Grid U/8-9 | A | 2025-06-02
|  | 7th floor | LT-2-452 | 2025-06-02 | 2025-06-02 | formwork | check vertical band formwork and allow to start concrete work | (+131.0) | Grid U/8-9 | A | 2025-06-02
|  | 1st floor | LT-2-453 | 2025-06-03 | 2025-06-03 | reinforcement | check vertical band reinforcement and allow to start formwork | (+19.0) | Grid R-T/1 | A | 2025-06-03
|  | 10th floor | LT-2-454 | 2025-06-03 | 2025-06-03 | reinforcement | check vertical band reinforcement and allow to start formwork | (+107.0) | Grid H-K, L-M/7 | A | 2025-06-03
|  | 7th floor | LT-2-455 | 2025-06-03 | 2025-06-03 | reinforcement | check vertical band reinforcement and allow to start formwork | (+85.0) | Grid U/1-6 | A | 2025-06-03
|  | 2nd floor | LT-2-456 | 2025-06-03 | 2025-06-03 | reinforcement | check vertical band reinforcement and allow to start formwork | (+30.0) | Grid M-P/1 | R | 2025-06-03
|  | 2nd floor | LT-2-457 | 2025-06-03 | 2025-06-03 | formwork | check leftover slab formwork and allow to start concrete work | (+30.0) | Grid U/12 | A | 2025-06-03
|  | 7th floor | LT-2-458 | 2025-06-03 | 2025-06-03 | formwork | check vertical band formwork and allow to start concrete work | (+85.0) | Grid U/1-6 | A | 2025-06-03
|  | 10th floor | LT-2-459 | 2025-06-03 | 2025-06-03 | formwork | Check vertical band formwork and allow to start concrete work | (+107.0) | Grid H-K, L-M/7 | A | 2025-06-03
|  | 1st floor | LT-2-460 | 2025-06-03 | 2025-06-03 | formwork | check veretical band formwork and allow to start concrete work | (+19.0) | Grid R-T/1 | A | 2025-06-03
|  | 7th floor | LT-2-461 | 2025-06-03 | 2025-06-03 | formwork | check vertical band formwork and allow to start concrete work | (+85.0) | Grid U/1-3 | A | 2025-06-04
|  | 2nd floor | LT-2-462 | 2025-06-04 | 2025-06-04 | reinforcement | check vertical band and allow to start formwork | (+30.0) | Grid K-L, M-P/1 | A | 2025-06-04
|  | 2nd floor | LT-2-463 | 2025-06-04 | 2025-06-04 | formwork | check vertical band formwork and allow to start concrete work | (+30.0) | Grid K-L, M-P/1 | A | 2025-06-04
|  | 2nd floor | LT-2-464 | 2025-06-04 | 2025-06-04 | formwork | check leftover slab formwork and allow to start concrete work | (+30.0) | Grid R-T/1 | A | 2025-06-14
|  | 2nd floor | LT-2-465 | 2025-06-16 | 2025-06-16 | reinforcement | check vertical band reinforcement and allow to start formwork | (+30.0) | Grid U/12 | A | 2025-06-16
|  | 2nd floor | LT-2-466 | 2025-06-16 | 2025-06-16 | reinforcement | check vertical band reinforcement and allow to start formwork | (+30.0) | Grid R-T/1 | A | 2025-06-16
|  | 2nd floor | LT-2-467 | 2025-06-16 | 2025-06-16 | formwork | check vertical band formwork and allow to start concrete work | (+30.0) | Grid U/12 | A | 2025-06-16
|  | 3rd floor | LT-2-468 | 2025-06-16 | 2025-06-16 | formwork | check leftover slab formwork and allow to start concrete work | (+41.0) | Grid K-L, M-P/1 | A | 2025-06-16
|  | 11th floor | LT-2-469 | 2025-06-16 | 2025-06-16 | formwork | check leftover slab formwork and allow to start concrete work | (+131.0) | Grid H-K, L-M/7 | A | 2025-06-17
|  | 2nd floor | LT-2-470 | 2025-06-17 | 2025-06-18 | formwork | check vertical band formwork and allow to start concrete work | (+30.0) | Grid R-T/1 | A | 2025-06-18
|  | 3rd floor | LT-2-471 | 2025-06-17 | 2025-06-17 | formwork | check leftover slab formwork and allow to start concrete work | (+41.0) | Grid U/12 | A | 2025-06-17
|  | 3rd floor | LT-2-472 | 2025-06-17 | 2025-06-17 | reinforcement | Check vertical band rienforcement and allow to start formwork | (+41.0) | Grid K-L, M-P/1 | A | 2025-06-17
|  | 8th floor | LT-2-473 | 2025-06-17 | 2025-06-17 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+96.0) | Grid G-H, K-L/7 | A | 2025-06-17
|  | 3rd floor | LT-2-474 | 2025-06-17 | 2025-06-18 | formwork | Check vertical band formwork and allow to start concrete work | (+41.0) | Grid K-L, M-P/1 | A | 2025-06-18
|  | 11th floor | LT-2-475 | 2025-06-18 | 2025-06-18 | reinforcement | check vertical band reinforcement and allow to start formwork | (+131.0) | Grid H-K, L-M/7 | A | 2025-06-18
|  | 3rd floor | LT-2-476 | 2025-06-19 | 2025-06-19 | formwork | check vertical band formwork and allow to start concrete work | (+41.0) | Grid M-P/1 | A | 2025-06-19
|  | 5th floor | LT-2-477 | 2025-06-18 | 2025-06-18 | reinforcement | Check reinforcement and formwork of horizontal band and allow to start concrete | (+63.0) | Grid U/6-10 | A | 2025-06-18
|  | 11th floor | LT-2-478 | 2025-06-19 | 2025-06-19 | formwork | check vertical band formwork and allow to start concrete work | (+131.0) | Grid H-K, L-M/7 | A | 2025-06-18
|  | 3rd floor | LT-2-479 | 2025-06-19 | 2025-06-19 | reinforcement | check vertical band reinforcement and allow to start formwork | (+41.0) | Grid U/12 | A | 2025-06-19
|  | 3rd floor | LT-2-480 | 2025-06-19 | 2025-06-19 | formwork | check vertical band formwork and allow to start concrete work | (+41.0) | Grid U/12 | A | 2025-06-20
|  | 3rd floor | LT-2-481 | 2025-06-19 | 2025-06-19 | formwork | check leftover slab formwork and allow to start concrete work | (+41.0) | Grid R-T/1 | A | 2025-06-20
|  | 4th floor | LT-2-482 | 2025-06-19 | 2025-06-19 | formwork | check leftover slab formwork and allow to start concrete work | (+52.0) | Grid K-L/1 | A | 2025-06-20
|  | 4th floor | LT-2-483 | 2025-06-20 | 2025-06-20 | formwork | Check leftover slab formwork and allow to start concrete work | (+52.0) | Grid M-P/1 | A | 2025-06-20
|  | 3rd floor | LT-2-484 | 2025-06-20 | 2025-06-20 | reinforcement | check vertical band reinforcement and allow to start formwork | (+41.0) | Grid R-T/1 | A | 2025-06-20
|  | 4th floor | LT-2-485 | 2025-06-20 | 2025-06-20 | reinforcement | check vertical band reinforcement and allow to start formwork | (+52.0) | Grid K-L/1 | A | 2025-06-20
|  | 3rd floor | LT-2-486 | 2025-06-20 | 2025-06-20 | formwork | check vertical band formwork and allow to start concrete work | (+41.0) | Grid R-T/1 | A | 2025-06-21
|  | 4th floor | LT-2-487 | 2025-06-20 | 2025-06-20 | formwork | check vertical band formwork and allow to start concrete work | (+52.0) | Grid K-L/1 | A | 2025-06-21
|  | 4th floor | LT-2-488 | 2025-06-20 | 2025-06-20 | formwork | Check leftover slab formwork and allow to start concrete work | (+52.0) | Grid U/12 | A | 2025-06-21
|  |  | LT-2-489 | 2025-06-21 | 2025-06-21 | layout | check layout and allow to start brick work on external side | (+96.0) | Grid G-U/01-12 | A | 2025-06-21
|  | 4th floor | LT-2-490 | 2025-06-21 | 2025-06-21 | reinforcement | check reinforcement of vertical band and allow to start formwork | (+52.0) | Grid M-P/1 | A | 2025-06-21
|  | 4th floor | LT-2-491 | 2025-06-21 | 2025-06-21 | formwork | check vertical band formwork and allow to start concrete work | (+52.0) | Grid M-P/1 | A | 2025-06-21
|  | 8th floor | LT-2-492 | 2025-06-21 | 2025-06-21 | formwork | Check leftover slab formwork and allow to start concrete work | (+96.0) | Grid U/10-11 | A | 2025-06-23
|  |  | LT-2-493 | 2025-06-21 | 2025-06-21 | reinforcement | check reinforcement of vertical band and allow to start formwork | (+52.0) | Grid U/12 | A | 2025-06-23
|  | 4th floor | LT-2-494 | 2025-06-21 | 2025-06-21 | formwork | check vertical band formwork and allow to start concrete work | (+52.0) | Grid U/12 | A | 2025-06-23
|  | 4th floor | LT-2-495 | 2025-06-21 | 2025-06-21 | formwork | Check leftover slab formwork and allow to start concrete work | (+52.0) | Grid R-T/01 | A | 2025-06-23
|  | 8th floor | LT-2-496 | 2025-06-21 | 2025-06-21 | formwork | Check leftover slab formwork and allow to start concrete work | (+96.0) | Grid U/8-9 | A | 2025-06-23
|  | 5th floor | LT-2-497 | 2025-06-21 | 2025-06-21 | reinforcement | Check reinforcemnt & formwork of horizantal band and allow to start concrete | (+63.0) | Grid U/1-4 | A | 2025-06-24
|  | 8th floor | LT-2-498 | 2025-06-23 | 2025-06-23 | reinforcement | check vertical band rienforcement and allow to start formwork | (+96.0) | Grid U/10-11 | A | 2025-06-23
|  | 8th floor | LT-2-499 | 2025-06-23 | 2025-06-23 | formwork | Check leftover slab formwork and allow to start concrete work | (+96.0) | Grid U/1-3 | OP
LT-2-500
|  | 4th floor | LT-2-501 | 2025-06-23 | 2025-06-23 | reinforcement | check vertical band reinforcement and allow to start formwork | (+52.0) | Grid R-T/1 | A | 2025-06-24
|  | 8th floor | LT-2-502 | 2025-06-23 | 2025-06-23 | formwork | check vertical band formwork and allow to start concrete work | (+96.0) | Grid U/10-11 | A | 2025-06-24
|  | 4th floor | LT-2-503 | 2025-06-24 | 2025-06-24 | formwork | Check vertical band formwork and allow to start concrete work | (+52.0) | Grid R-T/1 | A | 2025-06-25
|  | 5th floor | LT-2-504 | 2025-06-24 | 2025-06-24 | formwork | Check leftover slab formwork and allow to start concrete work | (+63.0) | Grid U/12 | OP
|  | 8th floor | LT-2-505 | 2025-06-24 | 2025-06-24 | formwork | Check leftover slab formwork and allow to start concrete work | (+96.0) | Grid U/4-6 | A | 2025-06-25
|  | 8th floor | LT-2-506 | 2025-06-25 | 2025-06-25 | reinforcement | check vertical band rienforcement and allow to start formwork | (+96.0) | Grid U/8-9 | A | 2025-06-25
|  | 8th floor | LT-2-507 | 2025-06-25 | 2025-06-25 | formwork | Check vertical band formwork and allow to start concrete work | (+96.0) | Grid U/8-9 | A | 2025-06-25
|  | Top floor | LT-2-508 | 2025-06-25 | 2025-06-25 | formwork | Check leftover slab formwork and allow to start concrete work | (+146.0) | Grid N/10-11 | A | 2025-06-26
|  | 9th floor | LT-2-509 | 2025-06-25 | 2025-06-25 | layout | check layout and allow start brick masnory on external side | (+107.0) | Grid U/01-12 | A | 2025-06-28
LT-2-510
LT-2-511
|  | 8th floor | LT-2-512 | 2025-06-27 | 2025-06-27 | reinfocrment | Check vertical band reinforcement and allow to start to formwork | (+96.0) | Grid U/03 & 04-06 | A | 2025-06-24
|  | Top floor | LT-2-513 | 2025-06-27 | 2025-06-27 | formwork | Check leftover slab formwork and allow to start concrete work | (+146.0) | Grid N/08-09 | OP
|  | 5th floor | LT-2-514 | 2025-06-27 | 2025-06-27 | formwork | Check leftover slab formwork and allow to start concrete work | (+63.0) | Grid 01/M-P | A | 2025-06-28
|  | 8th floor | LT-2-515 | 2025-06-27 | 2025-06-27 | formwork | check vertical band formwork and allow to start concrete work | (+96.0) | Grid U/03 & 04-06 | A | 2025-06-28
|  | 5th floor | LT-2-516 | 2025-06-27 | 2025-06-27 | formwork | Check leftover slab formwork and allow to start concrete work | (+63.0) | Grid R-T/01 | A | 2025-06-28
|  | 9th floor | LT-2-517 | 2025-06-27 | 2025-06-27 | formwork | Check leftover slab formwork and allow to start concrete work | (+107.0) | Grid U/8-9 | A | 2025-06-28
LT-2-518
|  | 5th floor | LT-2-519 | 2025-06-28 | 2025-06-28 | formwork | check vertical band formwork and allow to start concrete work | (+63.0) | Grid N/12 | A | 2025-06-30
|  | 5th floor | LT-2-520 | 2025-06-28 | 2025-06-28 | reinforcement | Check vertical band reinforcement and allow to start to formwork | (+63.0) | Grid K-L/01 | OP
|  | 10th floor | LT-2-521 | 2025-06-28 | 2025-06-28 | layout | check layout and allow start brick masnory on external side | (+118.0) | Grid G-U/01-12 | A | 2025-07-08
|  | 5th floor | LT-2-522 | 2025-06-28 | 2025-06-28 | formwork | check vertical band formwork and allow to start concrete work | (+63.0) | Grid K-L/01 | A | 2025-06-30
|  | 5th floor | LT-2-523 | 2025-06-28 | 2025-06-28 | reinforcement | Check vertical band reinforcement and allow to start to formwork | (+63.0) | Grid M-P/01 | OP
|  | 5th floor | LT-2-524 | 2025-06-28 | 2025-06-28 | formwork | check vertical band formwork and allow to start concrete work | (+63.0) | Grid M-P/01 | A | 2025-07-01
|  | 5th floor | LT-2-524 R01 | 2025-06-30 | 2025-06-30 | formwork | check vertical band formwork and allow to start concrete work | (+63.0) | Grid M-P/01 | OP
|  | 9th floor | LT-2-525 | 2025-06-28 | 2025-06-28 | formwork | check vertical band formwork and allow to start concrete work | (+107.0) | Grid U/10-11 | A | 2025-07-01
|  | 9th floor | LT-2-526 | 2025-06-28 | 2025-06-28 | reinforcement | Check vertical band reinforcement and allow to start to formwork | (+107.0) | Grid U/08-09 | OP
|  | 9th floor | LT-2-527 | 2025-06-28 | 2025-06-28 | formwork | check vertical band formwork and allow to start concrete work | (+107.0) | Grid U/08-09 | A | 2025-07-02
|  | 9th floor | LT-2-527 R01 | 2025-06-30 | 2025-06-30 | formwork | check vertical band formwork and allow to start concrete work | (+107.0) | Grid U/08-09 | OP
|  | 6th floor | LT-2-528 | 2025-06-28 | 2025-06-28 | formwork | Check leftover slab formwork and allow to start concrete work | (+74.0) | Grid N/12 | A | 2025-06-30
|  | 9th floor | LT-2-529 | 2025-06-28 | 2025-06-28 | formwork | Check leftover slab formwork and allow to start concrete work | (+107.0) | Grid U/03 | R
|  | 9th floor | LT-2-529 | 2025-06-28 | 2025-06-28 | formwork | Check leftover slab formwork and allow to start concrete work | (+107.0) | Grid U/03 | A | 2025-07-01
|  | 9th floor | LT-2-530 | 2025-06-30 | 2025-06-30 | formwork | Check leftover slab formwork and allow to start concrete work | (+107.0) | Grid U/01 & 04-06 | A | 2025-06-30
|  | 7th floor | LT-2-531 | 2025-06-30 | 2025-06-30 | brick work | Check Complete brickwork | (+85.0) | Grid G-U/01-12 | A
|  | 7th floor | LT-2-531 R01 | 2025-10-31 | 2025-10-31 | brick work | Check Complete brickwork | (+85.0) | Grid G-U/01-12 | A | 2025-11-01
|  | 8th floor | LT-2-532 | 2025-06-30 | 2025-06-30 | brick work | Check Complete brickwork | (+96.0) | Grid G-U/01-12 | A
|  | 8th floor | LT-2-532 R01 | 2025-10-31 | 2025-10-31 | brick work | Check Complete brickwork | (+96.0) | Grid G-U/01-12 | A | 2025-11-01
|  | 9th floor | LT-2-533 | 2025-06-30 | 2025-06-30 | brick work | Check Complete brickwork | (+107.0) | Grid G-U/01-12 | A
|  | 9th floor | LT-2-533 R01 | 2025-10-30 | 2025-10-30 | brick work | Check Complete brickwork | (+107.0) | Grid G-U/01-12 | A | 2025-11-01
|  | 5th floor | LT-2-534 | 2025-07-01 | 2025-07-01 | formwork | check vertical band formwork and allow to start concrete work | (+63.0) | Grid R-T/01 | A | 2025-07-02
LT-2-535
|  | 9th floor | LT-2-536 | 2025-07-01 | 2025-07-01 | formwork | check vertical band formwork and allow to start concrete work | (+107.0) | Grid U/03, 04-06 | A | 2025-07-02
|  | 6th floor | LT-2-537 | 2025-07-01 | 2025-07-01 | formwork | Check leftover slab formwork and allow to start concrete work | (+74.0) | Grid K-L/01 | A | 2025-07-01
|  | 10th floor | LT-2-538 | 2025-07-01 | 2025-07-01 | formwork | Check leftover slab formwork and allow to start concrete work | (+118.0) | Grid U/10-11 | A | 2025-07-03
LT-2-539
LT-2-540
|  |  | LT-2-540 R01 | 2025-10-30 | 2025-10-30 | brick work | Check the complete external brick masonry work |  | 6th floor | A | 2025-11-01
LT-2-541
|  | 6th floor | LT-2-542 | 2025-07-02 | 2025-07-02 | formwork | Check leftover slab formwork and allow to start concrete work | (+74.0) | Grid M-P/01 | A | 2025-07-03
LT-2-543
|  | 10th floor | LT-2-544 | 2025-07-03 | 2025-07-03 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid U/03 | A | 2025-07-03
LT-2-545
LT-2-546
LT-2-547
|  | 10th floor | LT-2-548 | 2025-07-03 | 2025-07-03 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid U/08-09 | A | 2025-07-03
|  | 10th floor | LT-2-549 | 2025-07-03 | 2025-07-03 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid U/04-06 | A | 2025-07-04
|  | 6th floor | LT-2-550 | 2025-07-03 | 2025-07-03 | formwork | Check leftover slab formwork and allow to start concrete work | (+74.0) | Grid R-T/01 | A | 2025-07-03
|  | 6th floor | LT-2-551 | 2025-07-04 | 2025-07-04 | Formwork | check vertical band formwork and allow to start concrete work | (+74.0) | Grid M-P/01 | A | 2025-07-04
|  | 10th floor | LT-2-552 | 2025-07-04 | 2025-07-04 | Formwork | check vertical band formwork and allow to start concrete work | (+118.0) | Grid U/08-09 | A | 2025-07-04
|  | 10th floor | LT-2-553 | 2025-07-04 | 2025-07-04 | Formwork | check vertical band formwork and allow to start concrete work | (+118.0) | Grid U/10-11 | A | 2025-07-05
LT-2-554
LT-2-555
|  | 7th floor | LT-2-556 | 2025-07-04 | 2025-07-04 | formwork | Check leftover slab formwork and allow to start concrete work | (+85.0) | Grid M-P/01 | A | 2025-07-07
|  | 7th floor | LT-2-557 | 2025-07-04 | 2025-07-04 | formwork | Check leftover slab formwork and allow to start concrete work | (+85.0) | Grid K-L/01 | A | 2025-07-05
|  | 7th floor | LT-2-558 | 2025-07-04 | 2025-07-04 | formwork | Check leftover slab formwork and allow to start concrete work | (+85.0) | Grid N/12 | A | 2025-07-05
|  | 6th floor | LT-2-559 | 2025-07-04 | 2025-07-04 | reinforcement | Check vertical band reinforcement and allow to start to formwork | (+74.0) | Grid R-T/1 | A | 2025-07-17
|  | 10th floor | LT-2-560 | 2025-07-04 | 2025-07-04 | formwork | check vertical band formwork and allow to start concrete work | (+118.0) | Grid U/3-6 | A | 2025-07-17
|  | 11th floor | LT-2-561 | 2025-07-07 | 2025-07-07 | layout | check layout and allow start brick masnory on external side | (+131.0) | Grid G-U/1-12 | A | 2025-07-08
|  | 7th floor | LT-2-562 | 2025-07-08 | 2025-07-08 | reinforcement | Check vertical band reinforcement and allow to start to formwork | (+85.0) | Grid K-L/01 | A | 2025-07-08
|  | 7th floor | LT-2-563 | 2025-07-08 | 2025-07-08 | reinforcement,formwork | Check reinforcemnt & formwork of horizantal band and allow to start concrete | (+85.0) | Grid L-M/01 | A | 2025-07-17
|  | 5th floor | LT-2-564 | 2025-07-08 | 2025-07-08 | reinforcement,formwork | Check reinforcemnt & formwork of horizantal band and allow to start concrete | (+52.0) | Grid M-Q/01-12 | A | 2025-07-17
LT-2-565
|  | 11th floor | LT-2-566 | 2025-07-08 | 2025-07-08 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid U/3,4-6 | A | 2025-07-08
|  | 7th floor | LT-2-567 | 2025-07-09 | 2025-07-09 | formwork | check vertical band formwork and allow to start concrete work | (+85.0) | Grid K-L/01 | A | 2025-07-09
|  | 7th floor | LT-2-568 | 2025-07-09 | 2025-07-09 | reinforcement | Check vertical band reinforcement and allow to start to formwork | (+85.0) | Grid M-P/01 | A | 2025-07-09
|  | 7th floor | LT-2-569 | 2025-07-09 | 2025-07-10 | formwork | check vertical band formwork and allow to start concrete work | (+85.0) | Grid M-P/01 | A | 2025-07-17
|  | 7th floor | LT-2-570 | 2025-07-09 | 2025-07-10 | formwork | Check leftover slab formwork and allow to start concrete work | (+85.0) | Grid R-T/01 | A | 2025-07-17
|  | 11th floor | LT-2-571 | 2025-07-09 | 2025-07-09 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid U/10-11 | A | 2025-07-09
|  | 7th floor | LT-2-572 | 2025-07-09 | 2025-07-09 | formwork | check vertical band formwork and allow to start concrete work | (+85.0) | Grid N/12 | A | 2025-07-09
|  | 11th floor | LT-2-573 | 2025-07-09 | 2025-07-10 | formwork | Check leftover slab formwork and allow to start concrete work | (+131.0) | Grid U/08-09 | A | 2025-07-11
|  | 11th floor | LT-2-574 | 2025-07-11 | 2025-07-11 | Reinforcement | Check vertical band reinforcement and allow to start to formwork | (+131.0) | Grid U/03 | A | 2025-07-17
|  | 11th floor | LT-2-575 | 2025-07-11 | 2025-07-11 | Reinforcement | Check vertical band reinforcement and allow to start to formwork | (+131.0) | Grid U/04-06 | A | 2025-07-17
|  |  | LT-2-576 | 2025-07-11 | 2025-07-11 | Formwork | Check leftover slab formwork and allow to start concrete work | (+146.0) | Grid H-K/07, L-M/7 | A | 2025-07-26
|  | 8th floor | LT-2-577 | 2025-07-11 | 2025-07-11 | Formwork | Check leftover slab formwork and allow to start concrete work | (+96.0) | Grid Q/12 | A | 2025-07-17
|  | 8th floor | LT-2-578 | 2025-07-12 | 2025-07-12 | formwork reinforcement | Check reinforcement and formwork of horizental band and allow concrete | (+96.0) | Grid U/06-08 | A | 2025-07-17
|  | 8th floor | LT-2-579 | 2025-07-12 | 2025-07-12 | formwork reinforcement | Check reinforcement and formwork of horizental band and allow concrete | (+96.0) | Grid U/09-10 | A | 2025-07-17
|  | 8th floor | LT-2-580 | 2025-07-12 | 2025-07-14 | Formwork | Check leftover slab formwork and allow to start concrete work | (+96.0) | Grid N/12 | A | 2025-07-19
|  | 11th floor | LT-2-581 | 2025-07-12 | 2025-07-12 | Formwork | Check vertical band reinforcement and allow to start to formwork | (+131.0) | Grid U/03, 04-06 | A | 2025-07-17
|  | 11th floor | LT-2-582 | 2025-07-12 | 2025-07-12 | Reinforcement | Check vertical band reinforcement and allow to start to formwork | (+131.0) | Grid U/10-11 | A | 2025-07-17
|  | Top floor | LT-2-583 | 2025-07-12 | 2025-07-12 | formwork reinforcement | Check reinforcement and formwork of horizental band and allow concrete |  | Grid N/08-11 | A | 2025-07-17
|  | 11th floor | LT-2-584 | 2025-07-12 | 2025-07-12 | reinforcement | Check vertical band reinforcement and allow to start to formwork | (+131.0) | Grid U/08-09 | A | 2025-07-17
|  | 11th floor | LT-2-585 | 2025-07-12 | 2025-07-14 | formwork | Check vertical band reinforcement and allow to start to formwork | (+131.0) | Grid U/08-09 | A | 2025-07-19
|  | 5th floor | LT-2-586 | 2025-07-14 | 2025-07-14 | formwork reinforcement | Check reinforcement and formwork of horizental band and allow concrete | (+63.0) | Grid P-R/01 | A | 2025-07-17
|  | 5th floor | LT-2-587 | 2025-07-14 | 2025-07-14 | formwork reinforcement | Check reinforcement and formwork of horizental band and allow concrete | (+63.0) | Grid N/11-12 | A | 2025-07-19
|  | 8th floor | LT-2-588 | 2025-07-14 | 2025-07-14 | formwork reinforcement | Check reinforcement and formwork of horizental band and allow concrete | (+96.0) | Grid U/1-2 | A | 2025-07-19
|  | 11th floor | LT-2-589 | 2025-07-15 | 2025-07-15 | formwork | Check vertical band reinforcement and allow to start to formwork | (+131.0) | Grid U/8-9 | A | 2025-07-19
|  | 11th floor | LT-2-590 | 2025-07-15 | 2025-07-15 | formwork | Check vertical band reinforcement and allow to start to formwork | (+131.0) | Grid R-T/01 | A | 2025-07-19
|  | Top floor | LT-2-591 | 2025-07-17 | 2025-07-17 | formwork reinforcement | Check reinforcement and formwork of horizental band and allow concrete | (+146.0) | Grid H-M/07 | A | 2025-07-26
|  | 8th floor | LT-2-592 | 2025-07-17 | 2025-07-17 | formwork reinforcement | Check reinforcement and formwork of horizental band and allow concrete | (+96.0) | Grid N/11-12 | A | 2025-07-26
|  | 5th floor | LT-2-593 | 2025-07-21 | 2025-07-21 | formwork | Check leftover slab formwork and allow to start concrete work | (+63.0) | Grid S/12 | A | 2025-07-26
|  | Top floor | LT-2-594 | 2025-07-21 | 2025-07-21 | formwork | Check leftover slab formwork and allow to start concrete work | (+146.0) | Grid U/10-11 | A | 2025-07-26
|  | 8th floor | LT-2-595 | 2025-07-22 | 2025-07-22 | formwork | Check leftover slab formwork and allow to start concrete work | (+96.0) | Grid K-L/01 | A | 2025-07-26
|  | Top floor | LT-2-596 | 2025-07-22 | 2025-07-22 | formwork | Check leftover slab formwork and allow to start concrete work | (+146.0) | Grid U/08-09 | A | 2025-07-26
|  | first floor to top floor | LT-2-597 | 2025-07-22 | 2025-07-22 | level | Check level points and allow to start plaster work | (+19.00-+148.50) | Grid N/10-11 | R | 2025-07-26
|  | first floor to top floor | LT-2-597 R01 | 2025-07-26 | 2025-07-26 | level | Check level points and allow to start plaster work | (+19.00-+148.50) | Grid N/10-11 | A | 2025-07-30
|  | Top floor | LT-2-598 | 2025-07-23 | 2025-07-23 | formwork | Check leftover slab formwork and allow to start concrete work | (+146.00) | Grid U/03,04-06 | A | 2025-07-28
|  | 5th floor | LT-2-599 | 2025-07-23 | 2025-07-23 | formwork & reinforcement | Check the reinforcement and formwork of horizontal band allow to start concrete | (+63.00) | Grid U/11-12 | A | 2025-07-28
|  | 8th floor | LT-2-600 | 2025-07-23 | 2025-07-23 | formwork | Check leftover slab formwork and allow to start concrete work | (+96.00) | Grid M-P/01 | A | 2025-07-28
|  | 11th floor | LT-2-601 | 2025-07-23 | 2025-07-23 | layout | Check layouyt and allow start brick masonry work 9" wall | (+131.00) | Grid G-U/01-12 | A | 2025-07-30
|  | 8th floor | LT-2-602 | 2025-07-23 | 2025-07-23 | reinforcement | Check reinforcement of vertical band and allow to start formwork | (+96.00) | Grid K-L/01 | A | 2025-07-26
|  | Top floor | LT-2-603 | 2025-07-25 | 2025-07-25 | formwork & reinforcement | Check the reinforcement and formwork of horizontal band allow to start concrete | (+146.00) | Grid U/09-11 | A | 2025-07-30
|  | first floor to top floor | LT-2-604 | 2025-07-25 | 2025-07-25 | level | Check level points and allow to start FACADE plaster work | (+19.00-148.50)) | Grid N/12 | A | 2025-07-30
|  | Top floor | LT-2-605 | 2025-07-25 | 2025-07-25 | formwork & reinforcement | Check the reinforcement and formwork of horizontal band allow to start concrete | (+146.00) | Grid U/08-09 | A | 2025-07-30
|  | 8th floor | LT-2-606 | 2025-07-24 | 2025-07-24 | formwork | Check leftover slab formwork and allow to start concrete work | (+96.00) | Grid R-T/01 | A | 2025-07-30
|  | 11th floor | LT-2-607 | 2025-07-24 | 2025-07-24 | layout | Check layout and allow to start external brick masonry |  | Grid G-N/07 | A | 2025-07-30
|  | 8th floor | LT-2-608 | 2025-07-24 | 2025-07-24 | Reinforcement | Check reinforcement of vertical band and allow to start formwork |  | Grid M-P/01 | A | 2025-07-28
|  | 8th floor | LT-2-609 | 2025-07-25 | 2025-07-25 | formwork | Check formwork of left over slab and allow to start concrete |  | Grid U/12 | A | 2025-07-30
|  | 8th floor | LT-2-610 | 2025-07-25 | 2025-07-25 | formwork | Check formwork of vertical band and allow to start concrete |  | Grid K-L/01 & M-P/01 | A | 2025-07-30
|  | 8th floor | LT-2-611 | 2025-07-26 | 2025-07-26 | reinforcement | Check reinforcement of vertical band and allow to start formwork |  | Grid R-T/01 | A | 2025-07-28
|  | 8th floor | LT-2-612 | 2025-07-26 | 2025-07-26 | formwork | Check formworkof vertical band and allow to start concrete | (+96.00) | Grid R-T/01 | A | 2025-07-30
|  | 9th floor | LT-2-613 | 2025-07-26 | 2025-07-26 | formwork | Check leftover slab formwork and allow to start concrete work | (+107.00) | Grid K-L,M-P/01 | A | 2025-07-30
|  | Top floor | LT-2-614 | 2025-07-26 | 2025-07-26 | reinforcement & formwork | Check the reinforcement and formwork of horizontal band allow to start concrete | (+146.00) | Grid U/03-8 | A | 2025-07-30
|  | Top floor to first floor | LT-2-615 | 2025-07-28 | 2025-07-28 | level | Check level points and allow to start FACADE plaster work |  | Grid U/10-11 | A | 2025-07-30
|  | 9th floor | LT-2-616 | 2025-07-28 | 2025-07-28 | reinforcement | Check reinforcement of vertical band and allow to start formwork |  | Grid K-L,M-P/01 | A | 2025-07-30
|  | 9th floor | LT-2-617 | 2025-07-28 | 2025-07-28 | formwork | Check leftover slab formwork and allow to start concrete work |  | Grid R-T/01 | A | 2025-07-30
|  | 9th floor | LT-2-618 | 2025-07-29 | 2025-07-29 | formwork | Check the formwork of vertical band and allow to start concrete |  | Grid K-L,M-P/01 | A | 2025-07-30
|  | 9th floor | LT-2-619 | 2025-07-29 | 2025-07-29 | reinforcement | Check reinforcement of vertical band and allow to start formwork | (+107.00) | Grid R-T/01 | A | 2025-07-30
|  | 8th floor | LT-2-620 | 2025-07-29 | 2025-07-29 | formwork & reinforcement | Check the reinforcement and formwork of horizontal band allow to start concrete | (+96.00) | Grid L-M/01 | A | 2025-07-30
|  | 10th floor | LT-2-621 | 2025-07-30 | 2025-07-30 | brick work | Check the 80% external brick masonary |  | Grid G-U/1-12 | A | 2025-07-30
|  | 11th floor | LT-2-622 | 2025-07-30 | 2025-07-30 | brick work | Check the 80% external brick masonary |  | Grid G-U/1-12 | A | 2025-07-30
|  | 9th floor | LT-2-623 | 2025-07-30 | 2025-07-30 | formwork | Check the formwork of vertical band and allow to start concrete |  | Grid R-T/1 | A | 2025-07-31
|  | 10th floor | LT-2-624 | 2025-07-30 | 2025-07-30 | formwork | Check leftover slab formwork and allow to start concrete work |  | Grid K-L/01, M-P/01 | A | 2025-07-31
|  | 6th floor | LT-2-625 | 2025-07-31 | 2025-07-31 | formwork | Check leftover slab formwork and allow to start concrete work |  | Grid U/12 | A | 2025-07-31
|  | 8th floor | LT-2-626 | 2025-07-31 | 2025-07-31 | formwork | Check leftover slab formwork and allow to start concrete work |  | Grid S/12 | A | 2025-07-31
|  | 10th floor | LT-2-627 | 2025-07-31 | 2025-07-31 | reinforcement | Check reinforcement of vertical band and allow to start formwork |  | Grid K-L,M-P/01 | A | 2025-07-31
|  | 8th floor | LT-2-628 | 2025-07-31 | 2025-07-31 | formwork & reinforcement | Check the reinforcement and formwork of horizontal band allow to start concrete |  | Grid P-R/01 | A | 2025-07-31
|  | 10th floor | LT-2-629 | 2025-08-01 | 2025-08-01 | formwork | Check leftover slab formwork and allow to start concrete work |  | Grid R-T/01 | A | 2025-08-02
|  | 10th floor | LT-2-630 | 2025-08-01 | 2025-08-01 | formwork | Check formworkof vertical band and allow to start concrete |  | Grid M-P/01 | A | 2025-08-02
|  | 10th floor | LT-2-631 | 2025-08-01 | 2025-08-01 | formwork | Check formworkof vertical band and allow to start concrete |  | Grid K-L/01 | A | 2025-08-02
|  | 10th floor | LT-2-632 | 2025-08-01 | 2025-08-01 | formwork | Check the formwork of vertical band and allow to start concrete |  | Grid R-T/01 | OP
|  | 10th floor | LT-2-633 | 2025-08-01 | 2025-08-01 | formwork | Check the formwork of vertical band and allow to start concrete |  | Grid R-T/01 | A | 2025-08-04
|  | 11th floor | LT-2-634 | 2025-08-02 | 2025-08-02 | formwork | Check leftover slab formwork and allow to start concrete work |  | Grid K-L,M-P/01 | A | 2025-08-04
|  | 11th floor | LT-2-635 | 2025-08-04 | 2025-08-04 | formwork | Check leftover slab formwork and allow to start concrete work |  | Grid R-T/01 | A | 2025-08-05
|  | 11th floor | LT-2-636 | 2025-08-04 | 2025-08-04 | reinforcement | Check reinforcement of vertical band and allow to start formwork |  | Grid K-L,M-P/01 | A | 2025-08-05
|  | 11th floor | LT-2-637 | 2025-08-04 | 2025-08-04 | formwork | Check the formwork of vertical band and allow to start concrete |  | Grid K-L/01 | A | 2025-08-05
|  | 11th floor | LT-2-638 | 2025-08-04 | 2025-08-04 | formwork | Check the formwork of vertical band and allow to start concrete |  | Grid M-P/01 | A | 2025-08-05
|  | 1st floor to top floor | LT-2-639 | 2025-08-04 | 2025-08-04 | plaster work | Check the complete façade vertical band plaster work at SOG |  | Grid N/10-11 | R | 2025-08-23
|  | 1st floor to top floor | LT-2-639 R01 | 2025-09-02 | 2025-09-02 | plaster work | Check the complete façade vertical band plaster work at SOG |  | Grid N/10-11 | A | 2025-09-05
|  | 1st floor to top floor | LT-2-640 | 2025-08-05 | 2025-08-05 | level | Check the level point and allow to start façade plaster work |  | Grid N/08-09 | A | 2025-08-08
|  | 11th floor | LT-2-641 | 2025-08-05 | 2025-08-05 | reinforcement | Check reinforcement of vertical band and allow to start formwork |  | Grid R-T/01 | A | 2025-08-07
|  | 1st floor to top floor | LT-2-642 | 2025-08-05 | 2025-08-05 | level | Check the level point and allow to start façade plaster work |  | Grid U/08-09 | A | 2025-08-08
|  | 1st floor to top floor | LT-2-643 | 2025-08-06 | 2025-08-06 | level | Check the level point and allow to start façade plaster work |  | Grid H-K/07 | R | 2025-08-08
|  | 11th floor | LT-2-644 | 2025-08-06 | 2025-08-06 | formwork | Check the formwork of vertical band and allow to start concrete |  | Grid R-T/01 | A | 2025-08-12
|  | 1st floor to 4th Floor | LT-2-645 | 2025-08-06 | 2025-08-06 | plaster work | Check the complete façade vertical band plaster work at 4th floor to 1st floor |  | Grid U/12 | A | 2025-08-08
|  | 11th floor to 1st floor | LT-2-646 | 2025-08-08 | 2025-08-08 | level | Check level points and allow to start FACADE plaster work |  | Grid U/04-06 | R | 2025-08-12
|  | 11th floor to 1st floor | LT-2-646 R01 | 2025-08-13 | 2025-08-13 | level | Check level points and allow to start FACADE plaster work |  | Grid U/04-06 | A | 2025-08-15
|  | top roof | LT-2-647 | 2025-08-09 | 2025-08-09 | blockwork | Check the complete Internal Blockwork of the horizental band at t op roof |  | Grid U/03-11 | A | 2025-08-12
|  |  | LT-2-648 | 2025-08-10 | 2025-08-10 | layout | Check layout and allow to start brick masonry |  | Grid G-U/01-4 | A | 2025-08-12
|  |  | LT-2-649 | 2025-08-09 | 2025-08-09 | formwork | Check leftover slab formwork and allow to start concrete work |  | Grid K-L/01 | A | 2025-08-12
|  | 1st floor | LT-2-650 | 2025-08-11 | 2025-08-11 | layout | Check the layout and allow to start brick work |  | Grid R-U/07-12 | A | 2025-08-12
|  | 7th floor | LT-2-651 | 2025-08-11 | 2025-08-11 | brick work | Check the complete Internal Blockwork of the vertical band |  | Grid U/01 | A | 2025-08-12
|  | 1st floor to top floor | LT-2-652 | 2025-08-11 | 2025-08-11 | brick work | Check the complete Internal Blockwork of the vertical band |  | Grid U/03 | A | 2025-08-12
|  | top roof | LT-2-653 | 2025-08-11 | 2025-08-11 | Reinforcement and form work | Check the reinforcement and formwork of left over slab |  | Grid M-P/01 | A | 2025-08-12
|  | 1st floor to top floor | LT-2-654 | 2025-08-11 | 2025-08-11 | plaster work | Check the complete façade vertical band plaster work at 1st floor to top roof |  | Grid U/10-11 | A | 2025-08-12
|  |  | LT-2-655 | 2025-08-12 | 2025-08-12 | formwork & reinforcement | Check the reinforcement and formwork of horizontal band allow to start concrete |  | Grid K-P/01 | A | 2025-08-15
|  |  | LT-2-656 | 2025-08-13 | 2025-08-13 | formwork & reinforcement | Check the reinforcement and formwork of horizontal band allow to start concrete |  | Grid R-T/01 | A | 2025-08-15
|  | 1st to 7th floor | LT-2-657 | 2025-08-13 | 2025-08-13 | Level | Check level points and allow to start FACADE plaster work |  | Grid U/01 | A | 2025-08-15
|  |  | LT-2-658 | 2025-08-13 | 2025-08-13 | Level | Check level points and allow to start FACADE plaster work |  | Grid U/03 | A | 2025-08-15
|  |  | LT-2-659 | 2025-08-13 | 2025-08-13 | Level | Check level points and allow to start FACADE plaster work |  | Grid L-M/07 | R | 2025-08-15
|  |  | LT-2-660 | 2025-08-15 | 2025-08-15 | plaster work | Check the Complete plaster work façade vertical band 1st t0 SOG side |  | Grid N/12 | A | 2025-08-15
|  |  | LT-2-661 | 2025-08-15 | 2025-08-15 | plaster work | Check the Complete plaster work façade vertical band 1st t0 top floor |  | Grid N/08-09 | A | 2025-08-15
|  | top roof | LT-2-662 | 2025-08-16 | 2025-08-16 | reinforcement & formwork | Check the reinforcement and formwork of horizontal band allow to start concrete |  | Grid P-T/01 | A | 2025-09-01
|  | top roof | LT-2-663 | 2025-08-16 | 2025-08-16 | brick work | Check 80% internal brickwork of horizental band |  | Grid H-M/07 | A | 2025-09-01
|  | 1st floor to top roof | LT-2-664 | 2025-08-16 | 2025-08-16 | plaster work | Check the Complete plaster work façade vertical band 1st t0 top floor |  | Grid U/08-09 | A | 2025-08-16
|  |  | LT-2-665 | 2025-08-16 | 2025-08-16 | plaster work | Check the Complete plaster work façade vertical band 1st t0 top floor |  | Grid U/04-06 | A | 2025-08-16
|  | 1st floor to Top floor | LT-2-666 | 2025-08-16 | 2025-08-16 | plaster work | Check the Complete plaster work façade vertical band 1st t0 top floor |  | Grid H-K/7 | A | 2025-08-23
|  |  | LT-2-667 | 2025-08-16 | 2025-08-16 | brick work | Check 80% internal brickwork of horizental band |  | Grid H-M/7 | A | 2025-09-01
|  | 5th floor | LT-2-668 | 2025-08-16 | 2025-08-16 | brick work | Check 80% internal brickwork of horizental band |  | Grid H-M/7 | A | 2025-09-01
|  | 5th floor | LT-2-669 | 2025-08-16 | 2025-08-16 | brick work | Check 80% internal brickwork of horizental band |  | Grid U/01-12 | A | 2025-09-01
|  | 5th floor | LT-2-669 R01 | 2025-09-09 | 2025-09-09 | brick work | Check internal brickwork of horizental band |  | Grid U/01-12 | A | 2025-09-11
|  | 8th floor | LT-2-670 | 2025-08-16 | 2025-08-16 | brick work | Check 80% internal brickwork of horizental band |  | Grid U/01-11 | A | 2025-09-01
|  |  | LT-2-670 R01 | 2025-09-10 | 2025-09-10 | brick work | Check internal brickwork of horizental band |  | Grid U/01-11 | A | 2025-09-12
|  |  | LT-2-671 | 2025-08-18 | 2025-08-18 | Level | Check level points and allow to start FACADE plaster work |  |  | A | 2025-08-23
|  |  | LT-2-672 | 2025-08-20 | 2025-08-20 | Level | Check level points and allow to start FACADE plaster work |  | Grid M-P/01 | A | 2025-08-23
|  |  | LT-2-673 | 2025-08-20 | 2025-08-20 | brick work | Check the internal brick work of thr horizental band 1st floor |  | Grid U/10-11 | A | 2025-08-24
|  | Ground floor | LT-2-674 | 2025-08-20 | 2025-08-20 | layout | Check layout and allow to start brick masnory |  | Grid G-U/01-07 | A | 2025-08-24
|  | top floor | LT-2-675 | 2025-08-23 | 2025-08-23 | layout | Check layout and allow to start brick masnory |  | Grid G-H/03-04 & P-Q/05-06 | A | 2025-08-23
|  | 1st floor to top floor | LT-2-676 | 2025-08-23 | 2025-08-23 | Level | Check level points and allow to start FACADE plaster work |  | Grid R-T/01 | A | 2025-08-25
|  |  | LT-2-677 | 2025-08-26 | 2025-08-26 | layout | Check layout and allow to start brick masnory |  | Grid N-R/09-12. | A | 2025-08-26
|  |  | LT-2-678 | 2025-08-28 | 2025-08-28 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  |  | R | 2025-09-01
|  | 1st floor to top floor | LT-2-679 | 2025-08-29 | 2025-08-29 | plaster work | Check the complete Façade (vertical band ) plaster work |  | Grid K-L/01 | A | 2025-09-01
|  |  | LT-2-680 | 2025-08-30 | 2025-08-30 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid U/08-12 | R | 2025-09-01
|  | 1st floor to top floor | LT-2-681 | 2025-09-01 | 2025-09-01 | plaster work | Check the complete Façade (vertical band ) plaster work |  | Grid M-P/01 | B | 2025-09-03
|  | 1st floor to top floor | LT-2-681 R01 | 2025-09-13 | 2025-09-13 | plaster work | Check the complete Façade (vertical band ) plaster work |  | Grid M-P/01 | A | 2025-09-16
|  | 1st floor to 7th floor | LT-2-682 | 2025-09-03 | 2025-09-03 | plaster work | Check the complete Façade (vertical band ) plaster work |  | Grid U/01(front side) | R | 2025-09-03
|  | 1st floor to 7th floor | LT-2-682 R01 | 2025-09-13 | 2025-09-13 | plaster work | Check the complete Façade (vertical band ) plaster work |  | Grid U/01(front side) | R | 2025-09-13 | Asad Butt
|  | 1st floor to 7th floor | LT-2-682 R02 | 2025-09-17 | 2025-09-17 | plaster work | Check the complete Façade (vertical band ) plaster work |  | Grid U/01(front side) | A | 2025-09-18 | Asad Butt
|  | 1st floor to top floor | LT-2-683 | 2025-09-03 | 2025-09-03 | plaster work | Check the complete Façade (vertical band ) plaster work |  | Grid U/03 (front side) | A | 2025-09-05
|  | 1st floor to top floor | LT-2-684 | 2025-09-03 | 2025-09-03 | plaster work | Check the complete Façade (vertical band ) plaster work |  | Grid L-M/07 (SOG side) | A | 2025-09-05
|  | 11 and 10th floor | LT-2-685 | 2025-09-09 | 2025-09-09 | level | Check level points, & chicken mesh and allow to start plaster work |  | Grid U/11-12 | A | 2025-09-11
|  | 1st floor | LT-2-686 | 2025-09-09 | 2025-09-09 | brick work | Check internal brickwork of horizental band |  | Grid K-T/01 | A | 2025-09-11
|  | 1st floor | LT-2-687 | 2025-09-09 | 2025-09-09 | brick work | Check internal brickwork of horizental band |  | Grid H-M/07-12 | A | 2025-09-12
|  | 5th floor | LT-2-688 | 2025-09-09 | 2025-09-09 | brick work | Check internal brickwork of horizental band |  | Grid K-T/01 | A | 2025-09-11
|  |  | LT-2-689 | 2025-09-10 | 2025-09-10 | layout | Check layout and allow to brick masnory |  | Grid N-U/3-9 | A | 2025-09-11
|  |  | LT-2-690 | 2025-09-10 | 2025-09-10 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid U/11-12 | A | 2025-09-12
|  | 8th floor | LT-2-691 | 2025-09-10 | 2025-09-10 | brick work | Check internal brickwork of horizental band |  | Grid K-T/01 | A | 2025-09-16
|  | Top roof | LT-2-692 | 2025-09-10 | 2025-09-10 | brick work | Check internal brickwork of horizental band |  | Grid K-T/01 | A | 2025-09-16
|  |  | LT-2-693 | 2025-09-11 | 2025-09-11 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid U/11-12 | A | 2025-09-15
|  |  | LT-2-694 | 2025-09-13 | 2025-09-13 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-N/07 | R | 2025-09-13 | Hassan Jameel
|  |  | LT-2-694 R01 | 2025-09-17 | 2025-09-17 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-N/07 | A | 2025-09-18 | Hassan Jameel
|  |  | LT-2-695 | 2025-09-13 | 2025-09-13 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid K-U/01 | R | 2025-09-13 | Hassan Jameel
|  |  | LT-2-695 R1 | 2025-09-15 | 2025-09-15 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid K-U/01 | R | 2025-09-13 | Hassan Jameel
|  |  | LT-2-696 | 2025-09-13 | 2025-09-13 | layout | Check layout and allow to start brickwork |  | Grid G-N/04-07 | R | 2025-09-13 | Hassan Jameel
|  |  | LT-2-696 R01 | 2025-09-15 | 2025-09-15 | layout | Check layout and allow to start brickwork |  | Grid G-N/04-07 | R | 2025-09-15 | Hassan Jameel
|  |  | LT-2-696 R02 | 2025-09-17 | 2025-09-17 | layout | Check layout and allow to start brickwork |  | Grid G-N/04-07 | A | 2025-09-18 | Hassan Jameel
|  |  | LT-2-697 | 2025-09-15 | 2025-09-15 | plaster work | Check the complete Façade (vertical band ) plaster work |  | Grid R-T/01 | A | 2025-09-16 | Bilal
|  |  | LT-2-698 | 2025-09-15 | 2025-09-15 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid K-U/01 | A | 2025-09-16 | Asad jawed
|  |  | LT-2-699 | 2025-09-15 | 2025-09-15 | layout | Check layout and allow to start brickwork |  | Grid N-U/05-12 | A | 2025-09-16
LT-2-700
|  |  | LT-2-701 | 2025-09-16 | 2025-09-16 | layout | Check layout and allow to start brickwork |  | Grid N-U/07-10 | A | 2025-09-18
|  |  | LT-2-702 | 2025-09-16 | 2025-09-16 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid K-U/01 | A | 2025-09-18
|  |  | LT-2-703 | 2025-09-17 | 2025-09-17 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid K-U/01 | A | 2025-09-18
|  |  | LT-2-704 | 2025-09-18 | 2025-09-18 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid N/08-09 | A | 2025-09-19
|  |  | LT-2-705 | 2025-09-20 | 2025-09-20 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-M/07 | A | 2025-09-23
|  |  | LT-2-706 | 2025-09-22 | 2025-09-22 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-K/07 | R | 2025-09-29
|  |  | LT-2-706 R01 | 2025-10-03 | 2025-10-03 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G-K/07 | A | 2025-10-09
|  |  | LT-2-707 | 2025-09-23 | 2025-09-23 | brick work | Check the complete brick work on internal side |  | 102 & 104 | A | 2025-09-29
|  |  | LT-2-708 | 2025-09-23 | 2025-09-23 | brick work | Check the complete brick work on internal side |  | 106, 108 | A | 2025-09-29
|  |  | LT-2-709 | 2025-09-23 | 2025-09-23 | brick work | Check the complete brick work on internal side |  | 109, 110 | A | 2025-09-29
|  |  | LT-2-710 | 2025-09-23 | 2025-09-23 | layout | Check the layout and allow to start brick work |  | 206, 208 | A | 2025-09-29
|  |  | LT-2-711 | 2025-09-24 | 2025-09-24 | plaster work | Kindly check the complete external plaster work front side at 1ST floor to 11TH floor of L2-Tower |  | Top Floor to 1st Floor | A | 2025-09-30
|  |  | LT-2-712 | 2025-09-24 | 2025-09-24 | plaster work | Kindly check the complete external plaster work front side at 1ST floor to 11TH floor of L2-Tower |  | Top Floor to 1st Floor | A | 2025-09-30
|  |  | LT-2-713 | 2025-09-26 | 2025-09-26 | Level | Kindly check the level points & chicken mesh and allow to start plaster work at 7th floor to 6th Floor of L2-Tower |  | 7th floor to 6th floor | A | 2025-10-09
|  |  | LT-2-714 | 2025-09-27 | 2025-09-27 | Level | Kindly check the level points & chicken mesh and allow to start external plaster work (Brickwork) at 5th floor to 1st floor on the UMT side of L2-Tower |  | 5th to 1st floor | A | 2025-09-30
|  |  | LT-2-715 | 2025-09-27 | 2025-09-27 | Level | Kindly check the level points & chicken mesh and allow to start external plaster work (Brickwork) at 11th floor to 1st floor on the UMT side of L2-Tower |  | Top Floor to 1st Floor | A | 2025-09-30
|  |  | LT-2-716 | 2025-09-27 | 2025-09-27 | Level | Kindly check the level points & chicken mesh and allow to start external plaster work (Brickwork) at 9th floor to 4TH floor on the SOG side of L2-Tower |  | 9th floor to 4th floor | A | 2025-09-30
|  |  | LT-2-717 | 2025-09-29 | 2025-09-29 | Level | Kindly check the level points & chicken mesh and allow to start external plaster work (Brickwork) at 3rd floor to 1st floor on the SOG side of L2-Tower |  | 3rd Floor to 1st floor | A | 2025-09-30
|  |  | LT-2-718 | 2025-10-01 | 2025-10-01 | plaster work | Check the External plaster work on the UMT side |  | 1st floor to Top floor | A | 2025-10-09
|  |  | LT-2-718 R1 | 2025-11-03 | 2025-11-03 | plaster work | Check the External plaster work on the UMT side |  | 1st floor to Top floor | A | 2025-11-06
|  |  | LT-2-719 | 2025-10-01 | 2025-10-01 | plaster work | Check the External plaster work on the UMT side |  | 1st floor to Top floor | A | 2025-10-09
|  |  | LT-2-719 R01 | 2025-11-08 | 2025-11-08 | plaster work | Check the External plaster work on the UMT side |  | 1st floor to Top floor | A | 2025-10-11
|  |  | LT-2-720 | 2025-10-03 | 2025-10-03 | plaster work | Check the complete External plaster work |  | Grid G-K/01 | A | 2025-10-09 | Asad jaweed
|  |  | LT-2-720 R01 | 2025-11-03 | 2025-11-03 | plaster work | Check the complete External plaster work |  | Grid G-K/01 | A | 2025-11-06 | Asad jaweed
|  |  | LT-2-721 | 2025-10-03 | 2025-10-03 | plaster work | Check the complete External plaster work |  | Grid T-U/01 | A | 2025-10-09
|  |  | LT-2-721 R1 | 2025-11-03 | 2025-11-03 | plaster work | Check the complete External plaster work |  | Grid T-U/01 | A | 2025-11-06
|  |  | LT-2-722 | 2025-10-03 | 2025-10-03 | Level | Check the level point and allow to start External Plaster work |  | Grid O-S/12 | A | 2025-10-09
|  |  | LT-2-723 | 2025-10-03 | 2025-10-03 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G/01-04 | A | 2025-10-09
|  |  | LT-2-724 | 2025-10-04 | 2025-10-04 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid G/01-04 | A | 2025-10-09
|  |  | LT-2-725 | 2025-10-04 | 2025-10-04 | level | check level point and aloow to start plaster work |  | Grid O-S/12 | A | 2025-10-09
|  |  | LT-2-726 | 2025-10-06 | 2025-10-06 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Grid M-U/12 | A | 2025-10-09
|  |  | LT-2-727 | 2025-10-15 | 2025-10-11 | brick work | Check the Complete Internal Brick masnory |  | 201 | A | 2025-10-16
|  |  | LT-2-728 | 2025-10-15 | 2025-10-11 | brick work | Check the Complete Internal Brick masnory |  | 202 | A | 2025-10-16
|  |  | LT-2-729 | 2025-10-15 | 2025-10-11 | brick work | Check the Complete Internal Brick masnory |  | 203 | B | 2025-10-16
|  |  | LT-2-729 R01 | 2025-10-21 | 2025-10-21 | brick work | Check the Complete Internal Brick masnory |  | 203 | A | 2025-10-24
|  |  | LT-2-730 | 2025-10-15 | 2025-10-11 | brick work | Check the Complete Internal Brick masnory |  | 204 | A | 2025-10-16
|  |  | LT-2-730 R01 | 2025-10-21 | 2025-10-21 | brick work | Check the Complete Internal Brick masnory |  | 204 | A | 2025-10-24
|  |  | LT-2-731 | 2025-10-13 | 2025-10-13 | layout | Check layout and allow to start brick masnory |  | 205, 207 | A | 2025-10-14
|  |  | LT-2-732 | 2025-10-15 | 2025-10-15 | layout | Check layout and allow to start brick masnory |  | 208 | A | 2025-10-16
|  |  | LT-2-733 | 2025-10-16 | 2025-10-16 | layout | Check layout and allow to start brick masnory |  | 209, 210 | A | 2025-10-17
|  |  | LT-2-734 | 2025-10-20 | 2025-10-20 | layout | Check level points, corner beads & chicken mesh and allow to start plaster work |  | Top Floor to 8th Floor | A | 2025-10-20
|  |  | LT-2-735 | 2025-10-21 | 2025-10-21 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | 7th floor to Ground floor | A | 2025-10-23
|  |  | LT-2-736 | 2025-10-22 | 2025-10-22 | brick work | Check the Complete Internal Brick masnory |  | 103 | A | 2025-10-24
|  |  | LT-2-737 | 2025-10-22 | 2025-10-22 | plaster work | Check the complete plaster work at external side(face to I tower |  |  | A | 2025-10-23
|  |  | LT-2-738 | 2025-10-22 | 2025-10-22 | plaster work | Check the complete plaster work at external side(face to L1 tower |  |  | A | 2025-10-23
|  |  | LT-2-739 | 2025-10-25 | 2025-10-25 | level | Check level points, corner beads & chicken mesh and allow to start plaster work |  | SOG side | A | 2025-10-28
|  |  | LT-2-740 | 2025-10-28 | 2025-10-28 | plaster work | Check the complete plaster work at external side(face to L1 tower |  | face to I tower | A | 2025-10-31
|  |  | LT-2-741 | 2025-10-29 | 2025-10-29 | brick work | Check the internal brick work appartment |  | 207 | A | 2025-10-30
|  |  | LT-2-742 | 2025-10-29 | 2025-10-29 | brick work | Check the internal brick work appartment |  | 206 | A | 2025-10-31
|  |  | LT-2-743 | 2025-10-29 | 2025-10-29 | brick work | Check the internal brick work appartment |  | 208 | A | 2025-10-30
|  |  | LT-2-744 | 2025-10-30 | 2025-10-30 | brick work | Check the internal brick work appartment |  | 205 | A | 2025-10-31
|  |  | LT-2-745 | 2025-11-04 | 2025-11-04 | layout | Check layout and allow to start brick masnory |  | 301303 | OP
|  |  | LT-2-746 | 2025-11-06 | 2025-11-06 | layout | Check layout and allow to start brick masnory |  | 302304 | A | 2025-11-11
|  |  | LT-2-747 | 2025-11-06 | 2025-11-06 | layout | Check layout and allow to start brick masnory |  | 402404406408 | A | 2025-11-11
|  |  | LT-2-748 | 2025-11-06 | 2025-11-06 | layout | Check layout and allow to start brick masnory |  | 306 | A | 2025-11-11
|  |  | LT-2-749 | 2025-11-06 | 2025-11-06 | brick work | Check the internal brick work |  | 209 | A | 2025-10-11
|  |  | LT-2-750 | 2025-11-06 | 2025-11-06 | brick work | Check the internal brick work |  | 210 | A | 2025-10-11
|  |  | LT-2-751 | 2025-11-06 | 2025-11-06 | brick work | Check the internal brick work |  | 101 | A | 2025-10-11
|  |  | LT-2-752 | 2025-11-07 | 2025-11-07 | layout | Check layout and allow to start brick masnory |  | 408-410 | A | 2025-11-11
|  |  | LT-2-753 | 2025-11-08 | 2025-11-08 | plaster work | Check the plaster work on the façade internal brick work |  | 11th floor | A | 2025-10-11
|  |  | LT-2-754 | 2025-11-08 | 2025-11-08 | plaster work | Check the plaster work on the façade internal brick work |  | 07th floor | A | 2025-10-11
|  |  | LT-2-755 | 2025-11-08 | 2025-11-08 | brick work | Check the internal brickwork |  | 105 | A | 2025-11-14
|  |  | LT-2-756 | 2025-11-08 | 2025-11-08 | brick work | Check the internal brickwork |  | 107 | A | 2025-10-11
|  |  | LT-2-757 | 2025-11-10 | 2025-11-10 | plaster work | Check the External plaster work on the SOG side |  | N/7-12 | A | 2025-10-11
LT-2-758
|  |  | LT-2-759 | 2025-11-26 | 2025-11-26 | brick work | Check the internal brickwork |  | 304 | OP
|  |  | LT-2-760 | 2025-11-26 | 2025-11-26 | brick work | Check the internal brickwork |  | 306 | OP
|  |  | LT-2-761 | 2025-11-26 | 2025-11-26 | brick work | Check the internal brickwork |  | 402 | OP
|  |  | LT-2-762 | 2025-11-26 | 2025-11-26 | brick work | Check the internal brickwork |  | 404 | OP
|  |  | LT-2-763 | 2025-12-02 | 2025-12-05 | brick work | Check the internal brickwork |  | 3TH FLOOR 310,308,309 | A | 2025-12-06
|  |  | LT-2-764 | 2025-12-09 | 2025-12-10 | brick work | Check the internal brickwork |  | 3TH FLOOR 301 | A | 2025-12-10
|  |  | LT-2-765 | 2025-12-09 | 2025-12-10 | brick work | Check the internal brickwork |  | 3TH FLOOR 302 | A | 2025-12-10
|  |  | LT-2-766 | 2025-12-09 | 2025-12-10 | brick work | Check the internal brickwork |  | 3TH FLOOR 303 | A | 2025-12-10
|  |  | LT-2-767 | 2025-12-09 | 2025-12-10 | brick work | Check the internal brickwork |  | 4TH FLOOR 406 | A | 2025-12-10
|  |  | LT-2-768 | 2025-12-11 | 2025-12-11 | brick work | Check the internal brickwork |  | 4TH FLOOR 409 | A | 2025-12-18
|  |  | LT-2-769 | 2025-12-11 | 2025-12-11 | layout | Check layout and allow to start brick masnory | 3RD FLOOR | 305-307 | A | 2025-12-18
|  |  | LT-2-770 | 2025-12-11 | 2025-12-11 | brick work | Check the internal brickwork |  | 405407 | A | 2025-12-12
|  |  | LT-2-771 | 2025-12-19 | 2025-12-19 | brick work | Check the internal brickwork | 4th floor | 408
LT-2-772
LT-2-773
LT-2-774
LT-2-775
LT-2-776
LT-2-777
LT-2-778
LT-2-779
LT-2-780
LT-2-781
LT-2-782
LT-2-783
LT-2-784
LT-2-785
LT-2-786
LT-2-787
LT-2-788
LT-2-789
LT-2-790
LT-2-791
LT-2-792
LT-2-793
LT-2-794
LT-2-795
LT-2-796
LT-2-797
LT-2-798
LT-2-799
LT-2-800
LT-2-801
LT-2-802
LT-2-803
LT-2-804
LT-2-805
LT-2-806
LT-2-807
LT-2-808
LT-2-809
LT-2-810
LT-2-811
LT-2-812
LT-2-813
LT-2-814
LT-2-815
LT-2-816
LT-2-817
LT-2-818
LT-2-819
LT-2-820
LT-2-821
LT-2-822
LT-2-823
LT-2-824
LT-2-825
LT-2-826
LT-2-827
LT-2-828
LT-2-829
LT-2-830
LT-2-831
LT-2-832
LT-2-833
LT-2-834
LT-2-835
LT-2-836
LT-2-837
LT-2-838
LT-2-839
LT-2-840
LT-2-841
LT-2-842
LT-2-843
LT-2-844
LT-2-845
LT-2-846
LT-2-847
LT-2-848
LT-2-849
LT-2-850
LT-2-851
LT-2-852
LT-2-853
LT-2-854
LT-2-855
LT-2-856
LT-2-857
LT-2-858
LT-2-859
LT-2-860
LT-2-861
LT-2-862
LT-2-863
LT-2-864
LT-2-865
LT-2-866
LT-2-867
LT-2-868
LT-2-869
LT-2-870
LT-2-871
LT-2-872
LT-2-873
LT-2-874
LT-2-875
LT-2-876
LT-2-877
LT-2-878
LT-2-879
LT-2-880
LT-2-881
LT-2-882
LT-2-883
LT-2-884
LT-2-885
LT-2-886
LT-2-887
LT-2-888
LT-2-889
LT-2-890
LT-2-891
LT-2-892
LT-2-893
LT-2-894
LT-2-895
LT-2-896
LT-2-897
LT-2-898
LT-2-899
LT-2-900
LT-2-901
LT-2-902
LT-2-903
LT-2-904
LT-2-905
LT-2-906
LT-2-907
LT-2-908
LT-2-909
LT-2-910
LT-2-911
LT-2-912
LT-2-913
LT-2-914
LT-2-915
LT-2-916
LT-2-917
LT-2-918
LT-2-919
LT-2-920
LT-2-921
LT-2-922
LT-2-923
LT-2-924
LT-2-925
LT-2-926
LT-2-927
LT-2-928
LT-2-929
LT-2-930
LT-2-931
LT-2-932
LT-2-933
LT-2-934
LT-2-935
LT-2-936
LT-2-937
LT-2-938
LT-2-939
LT-2-940
LT-2-941
LT-2-942
LT-2-943
LT-2-944
LT-2-945
LT-2-946
LT-2-947
LT-2-948
LT-2-949
LT-2-950
LT-2-951
LT-2-952
LT-2-953
LT-2-954
LT-2-955
LT-2-956
LT-2-957
LT-2-958
LT-2-959
LT-2-960
LT-2-961
LT-2-962
LT-2-963
LT-2-964
LT-2-965
LT-2-966
LT-2-967
LT-2-968
LT-2-969
LT-2-970
LT-2-971
LT-2-972
LT-2-973
LT-2-974
LT-2-975
LT-2-976
LT-2-977
LT-2-978
LT-2-979
LT-2-980
LT-2-981
LT-2-982
LT-2-983
LT-2-984
LT-2-985
LT-2-986
LT-2-987
LT-2-988
LT-2-989
LT-2-990
LT-2-991
LT-2-992
LT-2-993
LT-2-994
LT-2-995
LT-2-996
LT-2-997
LT-2-998
LT-2-999
LT-2-1000
LT-2-1001
LT-2-1002
LT-2-1003
LT-2-1004
LT-2-1005
LT-2-1006
LT-2-1007
LT-2-1008
LT-2-1009
LT-2-1010
LT-2-1011
LT-2-1012
LT-2-1013
LT-2-1014
LT-2-1015
LT-2-1016
LT-2-1017
LT-2-1018
LT-2-1019
LT-2-1020
LT-2-1021
LT-2-1022
LT-2-1023
LT-2-1024
LT-2-1025
LT-2-1026
LT-2-1027
LT-2-1028
LT-2-1029
LT-2-1030
LT-2-1031
LT-2-1032
LT-2-1033
LT-2-1034
LT-2-1035
LT-2-1036
LT-2-1037
LT-2-1038
LT-2-1039
LT-2-1040
LT-2-1041
LT-2-1042
LT-2-1043
LT-2-1044
LT-2-1045
LT-2-1046
LT-2-1047
LT-2-1048
LT-2-1049
LT-2-1050
LT-2-1051
LT-2-1052
LT-2-1053
LT-2-1054
LT-2-1055
LT-2-1056
LT-2-1057
LT-2-1058
LT-2-1059
LT-2-1060
LT-2-1061
LT-2-1062
LT-2-1063
LT-2-1064
LT-2-1065
LT-2-1066
LT-2-1067
LT-2-1068
LT-2-1069
LT-2-1070
LT-2-1071
LT-2-1072
LT-2-1073
LT-2-1074
LT-2-1075
LT-2-1076
LT-2-1077
LT-2-1078
LT-2-1079
LT-2-1080
LT-2-1081
LT-2-1082
LT-2-1083
LT-2-1084
LT-2-1085
LT-2-1086
LT-2-1087
LT-2-1088
LT-2-1089
LT-2-1090
LT-2-1091
LT-2-1092
LT-2-1093
LT-2-1094
LT-2-1095
LT-2-1096
LT-2-1097
LT-2-1098
LT-2-1099
LT-2-1100
LT-2-1101
LT-2-1102
LT-2-1103
LT-2-1104
LT-2-1105
LT-2-1106
LT-2-1107
LT-2-1108
LT-2-1109
LT-2-1110
LT-2-1111
LT-2-1112
LT-2-1113
LT-2-1114
LT-2-1115
LT-2-1116
LT-2-1117
LT-2-1118
LT-2-1119
LT-2-1120
LT-2-1121
LT-2-1122
LT-2-1123
LT-2-1124
LT-2-1125
LT-2-1126
LT-2-1127
LT-2-1128
LT-2-1129
LT-2-1130
LT-2-1131
LT-2-1132
LT-2-1133
LT-2-1134
LT-2-1135
LT-2-1136
LT-2-1137
LT-2-1138
LT-2-1139
LT-2-1140
LT-2-1141
LT-2-1142
LT-2-1143
LT-2-1144
LT-2-1145
LT-2-1146
LT-2-1147
LT-2-1148
LT-2-1149
LT-2-1150
LT-2-1151
LT-2-1152
LT-2-1153
LT-2-1154
LT-2-1155
LT-2-1156
LT-2-1157
LT-2-1158
LT-2-1159
LT-2-1160
LT-2-1161
LT-2-1162
LT-2-1163
LT-2-1164
LT-2-1165
LT-2-1166
LT-2-1167
LT-2-1168
LT-2-1169
LT-2-1170
LT-2-1171
LT-2-1172
LT-2-1173
LT-2-1174
LT-2-1175
LT-2-1176
LT-2-1177
LT-2-1178
LT-2-1179
LT-2-1180
LT-2-1181
LT-2-1182
LT-2-1183
LT-2-1184
LT-2-1185
LT-2-1186
LT-2-1187
LT-2-1188
LT-2-1189
LT-2-1190
LT-2-1191
LT-2-1192
LT-2-1193
LT-2-1194
LT-2-1195
LT-2-1196
LT-2-1197
LT-2-1198
LT-2-1199
LT-2-1200
LT-2-1201
LT-2-1202
LT-2-1203
LT-2-1204
LT-2-1205
LT-2-1206
LT-2-1207
LT-2-1208
LT-2-1209
LT-2-1210
LT-2-1211
LT-2-1212
LT-2-1213
LT-2-1214
LT-2-1215
LT-2-1216
LT-2-1217
LT-2-1218
LT-2-1219
LT-2-1220
LT-2-1221
LT-2-1222
LT-2-1223
LT-2-1224
LT-2-1225
LT-2-1226
LT-2-1227
LT-2-1228
LT-2-1229
LT-2-1230
LT-2-1231
LT-2-1232
LT-2-1233
LT-2-1234
LT-2-1235
LT-2-1236
LT-2-1237
LT-2-1238
LT-2-1239
LT-2-1240
LT-2-1241
LT-2-1242
LT-2-1243
LT-2-1244
LT-2-1245
LT-2-1246
LT-2-1247
LT-2-1248
LT-2-1249
LT-2-1250
LT-2-1251
LT-2-1252
LT-2-1253
LT-2-1254
LT-2-1255
LT-2-1256
LT-2-1257
LT-2-1258
LT-2-1259
LT-2-1260
LT-2-1261
LT-2-1262
LT-2-1263
LT-2-1264
LT-2-1265
LT-2-1266
LT-2-1267
LT-2-1268
LT-2-1269
LT-2-1270
LT-2-1271
LT-2-1272
LT-2-1273
LT-2-1274
LT-2-1275
LT-2-1276
LT-2-1277
LT-2-1278
LT-2-1279
LT-2-1280
LT-2-1281
LT-2-1282
LT-2-1283
LT-2-1284
LT-2-1285
LT-2-1286
LT-2-1287
LT-2-1288
LT-2-1289

## GE MH
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 62
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 5
[9 empty] | Open/Pending (OP) |  | 4
[9 empty] | Total |  | 71
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
| Sub Structure | MH | MH/001 | 2025-09-16 | 2025-09-16 | Level | Check the excavated level and allow to start lean concrete of Main hole On the left side L2 Tower |  | Grid K-U/01 | A | 2025-09-17
|  |  | MH/002 | 2025-09-19 | 2025-09-19 | Reinforcement | Check the reinforcement and allow to start formwork |  | Grid K-U/01 | A | 2025-09-20 | Hassan
|  |  | MH/003 | 2025-09-19 | 2025-09-19 | layout | Check layout and level of sewer line Main hole |  | 1, 2 , 3, 4 | A | 2025-09-23
|  |  | MH/004 | 2025-09-25 | 2025-09-25 | level | Kindly check the levels of sewer pipe line [Dia of 250 mm (Manhole 01 to 04)] and allow to start filling work at UMT side of L2-Tower |  | 01, 04 | A | 2025-09-25
|  |  | MH/005 R01 | 2025-09-26 | 2025-09-26 | Layout | Kindly check the top lean level and layout of sewerage manhole (M=10) and allow to start reinforcement at UMT side of L2-Tower |  | 10 | A | 2025-09-29
|  |  | MH/006 | 2025-09-26 | 2025-09-26 |  | Kindly check the water stopper, reinforcement & formwork and allow to start concrete at Manhole (M=4, size 4’x4.5’) bed of UMT side |  | 3 | A | 2025-09-30
|  |  | MH/007 | 2025-09-27 | 2025-09-27 | Reinforcement | Kindly check the reinforcement & formwork and allow to start concrete at Manhole Wall (M=3) on the UMT side |  | 10 | A | 2025-10-10
|  |  | MH/008 | 2025-09-27 | 2025-09-27 | Reinforcement | Kindly check the water stopper, reinforcement & formwork and allow to start concrete at Sewerage Manhole Bed (M=10, size 4’x4.5’) of UMT side |  |  | A | 2025-10-10
|  |  | MH/009 | 2025-09-30 | 2025-09-30 | level | Check the lean top level and layout and allow to start reinforcement of storm manhole at UMT side |  | 01,08,09 | A | 2025-10-02
|  |  | MH/010 | 2025-10-01 | 2025-10-01 | Reinforcement | Check the Water stopper & reinforcement of storm manhole |  | 01, 08 | A | 2025-10-09
|  |  | MH/011 | 2025-10-01 | 2025-10-01 | Formwork | Check the formwork and allow to start concrete at storm manhole |  | 01, 08 | A | 2025-10-02
|  |  | MH/012 | 2025-10-02 | 2025-10-02 | Reinforcement | Check the reinforcement of sewer manhole wall |  | 1 | A | 2025-10-09
|  |  | MH/013 | 2025-10-07 | 2025-10-07 | Level | Check the levels of sewer pipeline |  | 10 , 11 | A | 2025-10-08
|  |  | MH/014 | 2025-10-03 | 2025-10-03 | layout | Check the level and layout of Storm line manhole |  | 01 to 08 (UMT side) | A | 2025-10-07
|  |  | MH/015 | 2025-10-03 | 2025-10-03 | Excevation and level | Check the excevation and the level at storm manhole |  | 9 | OP
|  |  | MH/016 | 2025-10-03 | 2025-10-03 | Reinforcement | Check the reinforcement at storm manhole |  | 9 | A | 2025-10-09
|  |  | MH/017 | 2025-10-03 | 2025-10-03 | Formwork | Check the formwork and allow to start concrete at storm manhole |  | 9 | A | 2025-10-07
|  |  | MH/018 | 2025-10-06 | 2025-10-06 | Formwork | Check the formwork and allow to start concrete at storm manhole |  | 4 | R | 2025-10-06
|  |  | MH/018 R01 | 2025-10-08 | 2025-10-08 | Formwork | Check the formwork and allow to start concrete at storm manhole |  | 4 | R | 2025-10-06
|  |  | MH/019 | 2025-10-07 | 2025-10-07 | level | Check the lean top level and layout and allow to start reinforcement of storm manhole at UMT side |  | 10 | A | 2025-10-08
|  |  | MH/020 | 2025-10-07 | 2025-10-07 | level | Check the lean top level and layout and allow to start reinforcement of storm manhole at UMT side |  | 11 | A | 2025-10-08
|  |  | MH/021 | 2025-10-07 | 2025-10-07 | Reinforcement | Check the reinforcement at storm manhole |  | 11 | A | 2025-10-09
|  |  | MH/022 | 2025-10-07 | 2025-10-07 | Formwork | Check the formwork and allow to start concrete |  | 11 | A | 2025-10-08
|  |  | MH/023 | 2025-10-07 | 2025-10-07 | Reinforcement | Check the reinforcement at storm manhole |  | 10 | A | 2025-10-09
|  |  | MH/024 | 2025-10-07 | 2025-10-07 | Formwork | Check the formwork and allow to start concrete |  | 10 | A | 2025-10-08
|  |  | MH/025 | 2025-10-08 | 2025-10-08 | pipeline | Check the laying and level of storm pipeline manhole |  | 9, 10 | A | 2025-10-09
|  |  | MH/026 | 2025-10-08 | 2025-10-08 | Formwork | Check the formwork and allow to start concrete at sewer manhole Wall |  | 01, 02 | A | 2025-10-09
|  |  | MH/027 | 2025-10-09 | 2025-10-09 | pipeline | Check the laying and level of storm pipeline manhole |  | 1 | A | 2025-10-11 | Hassan Jameel
|  |  | MH/028 | 2025-10-09 | 2025-10-09 | Formwork | Check the formwork and allow to start concrete at sewer manhole Wall |  | 01, 08 | A | 2025-10-11
|  |  | MH/029 | 2025-10-13 | 2025-10-13 | Formwork | Check the formwork and allow to start concrete at sewer manhole Wall |  | 9 | A | 2025-10-14
|  |  | MH/030 | 2025-10-13 | 2025-10-13 | Formwork | Check the formwork and allow to start concrete at sewer manhole Wall |  | 10 | A | 2025-10-14
|  |  | MH/031 | 2025-10-16 | 2025-10-16 | laying | Check the laying and level of sever pipeline manhole |  | 11, 12 | A | 2025-10-17
|  |  | MH/032 | 2025-10-16 | 2025-10-16 | Formwork | Check the formwork and allow to start concrete at sewer manhole Wall |  | 11 | A | 2025-10-17
|  |  | MH/033 | 2025-10-16 | 2025-10-16 | Formwork | Check the formwork and allow to start concrete at sewer manhole Wall |  | 10 | A | 2025-10-17
|  |  | MH/034 | 2025-10-21 | 2025-10-21 | level | Check excavated level and allow to start lean concrete at sewer manhole |  | 9 | A | 2025-10-21
|  |  | MH/035 | 2025-10-21 | 2025-10-21 | level | Check excavated level and allow to start lean concrete at sewer manhole |  | 9 | A | 2025-10-22
|  |  | MH/036 | 2025-10-22 | 2025-10-22 | level | Check the lean top level and layout at sewer manhole |  | 9 | A | 2025-10-23
|  |  | MH/037 | 2025-10-23 | 2025-10-23 | level | Check the filling level and allow to start lean concrete at storm manhole |  | 7 | A | 2025-10-24
|  |  | MH/038 | 2025-10-23 | 2025-10-23 | level | Check excavated level and allow to start lean concrete at sewer manhole |  | empty plot side | A | 2025-10-24
|  |  | MH/039 | 2025-10-23 | 2025-10-23 | level | Check the excavated level and allow to start lean concrete at sewer pipe line Main hole On the left side L2 Tower |  | 9 | A | 2025-10-24
|  |  | MH/040 | 2025-10-24 | 2025-10-24 | level | Check the lean top level and layout at sewer manhole |  | 7 | A | 2025-10-24
|  |  | MH/041 | 2025-10-25 | 2025-10-25 | level | Check the concrete top level or invert level at gully trap |  | Umt side | A | 2025-10-27
|  |  | MH/042 | 2025-10-25 | 2025-10-25 | Reinforcement | Check the reinforcement sewer manhole bed |  | 9 | A | 2025-10-28
|  |  | MH/043 | 2025-10-27 | 2025-10-27 | Formwork | Check the formwork and allow to start concrete at sewer manhole Wall |  |  | A | 2025-10-28
|  |  | MH/044 | 2025-10-27 | 2025-10-27 | level | Check excavated level and allow to start lean concrete at storm manhole |  | 11 | A | 2025-10-28
|  |  | MH/045 | 2025-10-27 | 2025-10-27 | level | Check the excavated level and allow to start lean concrete at sewer pipe line Main hole 12 On the umt SIDE |  | 12 | A | 2025-10-28
|  |  | MH/046 | 2025-10-27 | 2025-10-27 | level | Check the lean top level and layout at sewer manhole |  | 11 | A | 2025-10-28
|  |  | MH/047 | 2025-10-27 | 2025-10-27 | Formwork | Check the formwork and allow to start concrete at sewer manhole Wall |  | 12 | A | 2025-10-28
|  |  | MH/048 | 2025-10-27 | 2025-10-27 | Reinforcement | Check the reinforcement sewer manhole bed |  | 11 | A | 2025-10-28
|  |  | MH/049 | 2025-10-28 | 2025-10-28 | level | Check the laying & levels of storm pipeline manhole |  | 11-----12 | A | 2025-10-30
|  |  | MH/050 | 2025-10-28 | 2025-10-28 | level | Check the laying & levels of storm pipeline manhole |  | 12-----13 | A | 2025-10-29
|  |  | MH/051 | 2025-10-29 | 2025-10-29 | level | Check the level and layout and allow to start lean concrete at storm manhole no 12 |  | 12 | A | 2025-10-30
|  |  | MH/052 | 2025-10-29 | 2025-10-29 | level | Check the lean top level and layout at sewer manhole |  | 12 | A | 2025-10-30
|  |  | MH/053 | 2025-10-30 | 2025-10-30 | Formwork | Check the formwork of sewer manhole wall n#12 and allow to start concrete |  | 12 | R | 2025-10-30
|  |  | MH/053 R01 | 2025-10-31 | 2025-10-31 | Formwork | Check the formwork of sewer manhole wall n#12 and allow to start concrete |  | 12 | A | 2025-11-01
|  |  | MH/054 | 2025-10-30 | 2025-10-30 | Formwork | Check the formwork of storm manhole wall n#12 and allow to start concrete |  | 11 | R | 2025-10-30
|  |  | MH/054 R01 | 2025-10-31 | 2025-10-31 | Formwork | Check the formwork of storm manhole wall n#12 and allow to start concrete |  | 11 | A | 2025-11-01
|  |  | MH/055 | 2025-10-30 | 2025-10-30 | Reinforcement | Check the foundation reinforcement sewer manhole 13 & storm manhole 12 |  | 13, 12 | A | 2025-11-04
|  |  | MH/056 | 2025-10-30 | 2025-10-30 | Formwork | Check the foundation formwork of sewer manhole 13 & storm manhole 12 |  | 13, 12 | R | 2025-10-30
|  |  | MH/056 R01 | 2025-10-31 | 2025-10-31 | Formwork | Check the foundation formwork of sewer manhole 13 & storm manhole 12 |  | 13, 12 | A | 2025-11-01
MH/057
|  |  | MH/058 | 2025-11-03 | 2025-11-03 | Formwork | Check the formwork of sewer manhole wall n#13 and Storm manhole wall 12 & allow to start concrete |  | 12,13 | A | 2025-11-04
|  |  | MH/059 | 2025-11-05 | 2025-11-05 | level | Check the foundation level and layout of sewer manhole 9 |  | UMT | A | 2025-11-06
|  |  | MH/060 | 2025-11-05 | 2025-11-05 | reinforcement & formwork | Check the reinforcement and formwork and allow to start concrete |  | 7 | A | 2025-11-07
|  |  | MH/061 | 2025-11-05 | 2025-11-05 | Formwork | Check the formwork of Storm manhole bed # 07 and allow to start concrete |  | 7 | A | 2025-11-06
|  |  | MH/062 | 2025-11-26 | 2025-11-26 | level | Check the excavated level and allow to start lean concrete at sewer Main hole 01,02,03 and Storm manhole 01 On the umt SIDE |  | L1-Tower | OP
|  |  | MH/063 | 2025-11-26 | 2025-11-26 | level | Check the excavated level and allow to start lean concrete af Gully Trap on the right Side of L1 tower |  | L1-Tower | OP
|  |  | MH/064 | 2025-11-26 | 2025-11-26 | layout | Check the layout and allow to start brick work of gully trap on the right & lift side L1 & L2 tower |  | L1-Tower, L2 tower | OP
MH/065
MH/066
|  |  | MH/067 | 2025-11-29 | 2025-11-29 | Formwork | Check the foundation formwork of sewer manhole bed & wall 01,02,03 |  | L1-Tower | A | 2025-12-01
|  |  | MH/068 | 2025-11-29 | 2025-11-29 | Formwork | Check the foundation formwork & water stopper at sewer manhole 01,02,03 |  | L1-Tower | A | 2025-12-01
|  |  | MH/069 | 2025-12-10 | 2025-12-10 | layout | Check the layout |  | L1-Tower | A | 2025-12-10
|  |  | MH/070 | 2025-12-11 | 2025-12-11 | Formwork | Check the foundation formwork of sewer manhole NO01 WALL CONCRETE ON THE EMPTY PLOT |  | L1-Tower | A | 2025-12-12
|  |  | MH/071 | 2025-12-17 | 2025-12-17 | Formwork | check the formwork and allow to start sewer manhole no02 wall concrete on the empty plot side |  | L1-Tower
MH/072
MH/073
MH/074
MH/075
MH/076
MH/077
MH/078
MH/079
MH/080
MH/081
MH/082
MH/083
MH/084
| Sub Structure |  | BW/174
| Sub Structure |  | BW/175
| Sub Structure |  | BW/176
| Sub Structure |  | BW/177
| Sub Structure |  | BW/178
| Sub Structure |  | BW/179
| Sub Structure |  | BW/180
| Sub Structure |  | BW/181
| Sub Structure |  | BW/182
| Sub Structure |  | BW/183
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
| Sub Structure | Basement | IT/277
| Sub Structure | Basement | IT/278
| Sub Structure | Basement | IT/279
| Sub Structure | Basement | IT/280
| Sub Structure | Basement | IT/281
| Sub Structure | Basement | IT/282
| Sub Structure | Basement | IT/283
| Sub Structure | Basement | IT/284
| Sub Structure | Basement | IT/285
| Sub Structure | Basement | IT/286
| Sub Structure | Basement | IT/287
| Sub Structure | Basement | IT/288
| Sub Structure | Basement | IT/289
| Sub Structure | Basement | IT/290
| Sub Structure | Basement | IT/291
| Sub Structure | Basement | IT/292
| Sub Structure | Basement | IT/293
| Sub Structure | Basement | IT/294
| Sub Structure | Basement | IT/295
| Sub Structure | Basement | IT/296
| Sub Structure | Basement | IT/297
| Sub Structure | Basement | IT/298
IT/299

## Ezymix I Tower
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) Ezymix | [5 empty] | Fully Approved (A) |  | 163
[9 empty] | Approved with comments (B) |  | 37
[9 empty] | Rejected ( R) |  | 20 |  | As of : |  | 2025-12-19
[9 empty] | Open/Pending (OP) |  | 16
[9 empty] | Total |  | 236
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR closing Date | Pour Card No. | Concrete Qty (m3) | Attachment | Remarks
1 | Sub Structure | Basement | IT/1 | 2024-06-06 | 2024-06-06 | wiremesh | Check wire mesh and allow for plasterwork |  | Corridor Zone 1,2,3 | A | 2024-06-12 |  |  | E:\Soft IRs\IIL\I Tower\1.pdf
2 | Sub Structure | 1st floor | IT/2 | 2024-06-12 | 2024-06-12 | plasterwork | Check plasterwork |  |  | R | 2024-06-04 |  |  | E:\Soft IRs\IIL\I Tower\2.pdf
3 | Sub Structure | 2nd floor | IT/3 | 2024-06-29 | 2024-06-29 | Pre plaster | Check pre plaster inspection including chicken mesh |  | Corridor Zone 1,2,3 | A | 2024-07-01 |  |  | E:\Soft IRs\IIL\I Tower\3.pdf
4 | Sub Structure | 2nd floor | IT/4 | 2024-07-06 | 2024-07-06 | Pre plaster | Check pre plaster inspection including chicken mesh |  |  | A | 2024-07-10 |  |  | E:\Soft IRs\IIL\I Tower\4.pdf
5 | Sub Structure | 2nd floor | IT/5 | 2024-07-10 | 2024-07-10 | plasterwork | Check plaster work |  |  | OP |  |  |  | E:\Soft IRs\IIL\I Tower\5.pdf
6 | Sub Structure | 2nd floor | IT/6 | 2024-07-11 | 2024-07-11 | plasterwork | Check plaster work |  |  | B | 2024-07-18 |  |  | E:\Soft IRs\IIL\I Tower\6.pdf
7 | Sub Structure | 1st floor | IT/7 | 2024-07-13 | 2024-07-15 | Pre plaster | check pre plaste inspection including chicken mesh |  | T1-101, T-103, T1-104 | A | 2024-08-24 |  |  | E:\Soft IRs\IIL\I Tower\7.pdf
8 | Sub Structure | Basement | IT/7A | [10 empty] | E:\Soft IRs\IIL\I Tower\7A.pdf
9 | Sub Structure | 1st floor | IT/8 | 2024-08-16 | 2024-08-16 | plasterwork | Check plaster inspection including chicken mesh |  | 105-116 | A | 2024-08-24 |  |  | E:\Soft IRs\IIL\I Tower\8.pdf
10 | Sub Structure | 2nd floor | IT/9 | 2024-07-30 | 2024-07-30 | pre-plaster | Check pre-plaster inspection including chicken mesh |  | T1-201, T1-203, T1204 | A | 2024-08-24 |  |  | E:\Soft IRs\IIL\I Tower\9.pdf
11 | Sub Structure | 1st floor | IT/10 | 2024-07-30 | 2024-07-30 | plasterwork | Check plasterwork |  | 101, 103, 104 | A | 2024-08-20 |  |  | E:\Soft IRs\IIL\I Tower\10.pdf
12 | Sub Structure | 1st floor | IT/11 | 2024-08-02 | 2024-08-02 | plasterwork | Check plasterwork |  | 1.0511e+23 | A | 2024-08-20 |  |  | E:\Soft IRs\IIL\I Tower\11.pdf
13 | Sub Structure | 1st floor | IT/12 | 2024-08-07 | 2024-08-07 | plasterwork | Check plasterwork |  | 111113116 | A | 2024-08-20 |  |  | E:\Soft IRs\IIL\I Tower\12.pdf
14 | Sub Structure | 2nd floor | IT/13 | 2024-08-12 | 2024-08-12 | plasterwork | Check plasterwork including chicken mesh |  | 2.0521e+23 | A | 2024-08-24 |  |  | E:\Soft IRs\IIL\I Tower\13.pdf
15 | Sub Structure | 2nd floor | IT/14 | 2024-08-16 | 2024-08-16 | preplaster work | Check pre plaster inspection including chicken mesh |  | 211213215216 | A | 2024-08-24 |  |  | E:\Soft IRs\IIL\I Tower\14.pdf
16 | Sub Structure | 1st floor | IT/15 | 2024-08-16 | 2024-08-16 | plasterwork | Check plaster work |  |  | A | 2024-08-20 |  |  | E:\14.Soft IRs\IIL\I Tower\15.pdf
17 | Sub Structure | 2nd floor | IT/16 | 2024-09-04 | 2024-09-04 | plasterwork | Check plaster work |  | 201202203204 | A | 2024-09-09 |  |  | E:\14.Soft IRs\IIL\I Tower\16.pdf
18 | Sub Structure | 2nd floor | IT/17 | 2024-08-30 | 2024-08-30 | plasterwork | Check plaster work |  | 205-240,212,214 | A | 2024-09-03 |  |  | E:\14.Soft IRs\IIL\I Tower\17.pdf
19 | Sub Structure | 2nd floor | IT/18 | 2024-08-27 | 2024-08-27 | plasterwork | Check plaster work |  | 211213215216 | A | 2024-09-09 |  |  | E:\14.Soft IRs\IIL\I Tower\18.pdf
20 | Sub Structure | 3rd floor | IT/19 | 2024-08-30 | 2024-08-30 | Pre-Plaster | Check pre-plaster inspection including chicken mesh |  | 301302303304 | A | 2024-09-03 |  |  | E:\14.Soft IRs\IIL\I Tower\19.pdf
21 | Sub Structure | 3rd floor | IT/20 | 2024-08-30 | 2024-08-30 | Pre-Plaster | Check pre-plaster inspection including chicken mesh |  | 305-310,312,314 | A | 2024-09-03 |  |  | E:\14.Soft IRs\IIL\I Tower\20.pdf
22 | Sub Structure | 3rd floor | IT/21 | 2024-08-30 | 2024-08-30 | Pre-Plaster | Check pre-plaster inspection including chicken mesh |  | 311313315316 | A | 2024-09-03 |  |  | E:\14.Soft IRs\IIL\I Tower\21.pdf
23 | Sub Structure | 1st floor | IT/22 | 2024-08-30 | 2024-08-30 | Pre-Plaster | Check pre-plaster inspection including chicken mesh |  |  | A | 2024-09-03
24 |  |  | IT/23
25 | Sub Structure | 2nd floor | IT/24 | 2024-09-04 | 2024-09-04 | plasterwork | Check plaster work |  | corridor, service room, electric room, garbage room | R | 2024-09-09
26 | Sub Structure | 3rd floor | IT/25 | 2024-09-03 | 2024-09-03 | plasterwork | Check plaster work |  | 311 | A | 2024-09-06
27 | Sub Structure | 3rd floor | IT/26 | 2024-09-03 | 2024-09-03 | plasterwork | Check plaster work |  | 313 | A | 2024-09-07
28 | Sub Structure | 3rd floor | IT/27 | 2024-09-03 | 2024-09-03 | plasterwork | Check plaster work |  | 314 | A | 2024-09-07
29 | Sub Structure | 3rd floor | IT/28 | 2024-09-03 | 2024-09-03 | plasterwork | Check plaster work |  | 316 | A | 2024-09-06
30 | Sub Structure | 3rd floor | IT/29 | 2024-09-03 | 2024-09-03 | plasterwork | Check plaster work |  | 312 | A | 2024-09-09
31 | Sub Structure | 3rd floor | IT/30 | 2024-09-03 | 2024-09-03 | plasterwork | Check plaster work |  | 309 | A | 2024-09-09
32 | Sub Structure | 3rd floor | IT/31 | 2024-10-26 | 2024-10-26 | plasterwork | Check plaster inspection including chicken mesh |  | 301302303304 | R | 2024-11-06
33 | Sub Structure | 3rd floor | IT/32 | 2024-10-26 | 2024-10-26 | plasterwork | Check pre plaster inspection including chicken mesh |  | 305306307308310 | B | 2024-11-06
34 | Sub Structure | 3rd floor | IT/33 | 2024-10-26 | 2024-10-26 | Pre plaster | Check plaster work |  | 315 | B | 2024-11-06
35 | Sub Structure | 3rd floor | IT/34 | 2024-10-26 | 2024-10-26 | Pre plaster | Check plaster work |  | corridor, service room, electric room, garbage room, stair room | A | 2024-11-06
36 | Sub Structure | 3rd floor | IT/35 | 2024-10-01 | 2024-10-01 | plaster work | Check plaster work |  |  | A | 2024-10-28
37 | Sub Structure | 3rd floor | IT/36 | 2024-10-01 | 2024-10-01 | plaster work | Check plaster work |  |  | A | 2024-10-28
38 | Sub Structure | 3rd floor | IT/37 | 2024-10-01 | 2024-10-01 | plaster work | Check plaster work |  |  | A | 2024-10-28
39 | Sub Structure | 3rd floor | IT/38 | 2024-10-01 | 2024-10-01 | plaster work | Check plaster work |  |  | A | 2024-10-28
40 | Sub Structure | 3rd floor | IT/39 | 2024-10-01 | 2024-10-01 | plaster work | Check plaster work |  |  | B | 2024-11-06
41 | Sub Structure | 3rd floor | IT/40 | 2024-12-27 | 2024-12-27 | plaster work | Check plaster work |  |  | OP
42 | Sub Structure | 3rd floor | IT/41 | 2024-12-26 | 2024-12-26 | plaster work | Check plaster work |  | 411413415416 | R | 2024-12-31
43 | Sub Structure | 4th floor | IT/42 | 2024-12-26 | 2024-12-26 | plaster work | Check plaster work |  | corridor, service room, electric room, garbage room, stair room | R | 2024-12-31
44 | Sub Structure | 3rd floor | IT/43 | 2024-10-01 | 2024-10-01 | plaster work | Check plaster work |  |  | A | 2024-10-28
45 | Sub Structure | 3rd floor | IT/44 | 2024-10-01 | 2024-10-01 | plaster work | Check plaster work |  |  | A | 2024-10-28
46 | Sub Structure | 3rd floor | IT/45 | 2024-10-01 | 2024-10-01 | plaster work | Check plaster work |  |  | A | 2024-10-28
47 | Sub Structure | 4th floor | IT/46 | 2024-10-02 | 2024-10-02 | plaster work | Check plaster work |  |  | A | 2024-10-28
48 | Sub Structure | Elevation | IT/47 | 2024-12-05 | 2024-12-05 | pre plaster | Check pre plaster inspection including chicken mesh zone 1 |  |  | B | 2024-12-07
49 | Sub Structure | Elevation | IT/48 | 2024-12-05 | 2024-12-05 | Pre plaster | Check pre plaster inspection including chicken mesh zone 2 |  |  | B | 2024-12-07
50 | Sub Structure | Elevation | IT/49 | 2024-12-05 | 2024-12-05 | Pre plaster | Check pre plaster inspection including chicken mesh zone 3 |  |  | B | 2024-12-07
51 | Sub Structure | 5th floor | IT/50 | 2024-10-28 | 2024-10-27 | plaster work | Check plaster work |  | 501502503504 | R | 2024-11-07
52 | Sub Structure | 5th floor | IT/51 | 2024-10-28 | 2024-10-27 | plaster work | Check plaster work |  | 505-514 | R | 2024-11-07
53 | Sub Structure | 5th floor | IT/52 | 2024-10-28 | 2024-10-27 | plaster work | Check plaster work |  | 511513515516 | R | 2024-11-07
54 | Sub Structure | 5th floor | IT/53 | 2024-10-28 | 2024-10-27 | plaster work | Check plaster work |  |  | OP
55 | Sub Structure | Elevation | IT/54 | 2024-10-28 | 2024-10-27 | plaster work | Check plaster work |  |  | OP
56 | Sub Structure | Elevation | IT/55 | 2024-10-28 | 2024-10-27 | plaster work | Check plaster work zone 2 |  |  | OP
57 | Sub Structure | Elevation | IT/56 | 2024-10-28 | 2024-10-27 | plaster work | Check plaster work zone 3 |  |  | OP
58 | Sub Structure | 6th floor | IT/57 | 2024-10-28 | 2024-10-27 | plaster work | Check pre plaster inspection including chicken mesh |  | 601602603604 | A | 2024-11-09
59 | Sub Structure | 6th floor | IT/58 | 2024-10-28 | 2024-10-27 | plaster work | Check pre plaster inspection including chicken mesh |  | 605606607 | A | 2024-11-09
60 | Sub Structure | 6th floor | IT/59 | 2024-11-29 | 2024-11-29 | plaster work | Check plaster work |  | 601602603604 | A | 2024-12-05
61 | Sub Structure | 6th floor | IT/60 | 2024-11-30 | 2024-11-30 | plaster work | Check plaster work |  | 605606608 | A | 2024-12-05
62 | Sub Structure | 4th floor | IT/61 | 2024-10-02 | 2024-10-02 | plaster work | Check plaster work |  |  | A | 2024-11-09
63 | Sub Structure | 6th floor | IT/62 | 2024-11-12 | 2024-11-12 | Pre plaster | Check pre plaster inspection including chicken mesh |  | 608609610611612 | B | 2024-11-22
64 | Sub Structure | 7th floor | IT/63 | 2024-11-19 | 2024-11-19 | plaster work | Check plaster work |  | 711713715716 | B | 2024-11-22
65 | Sub Structure | 7th floor | IT/64 | 2024-11-21 | 2024-11-21 | Pre plaster | Check pre plaster inspection including chicken mesh |  | 707709710712714 | A | 2024-11-22
66 | Sub Structure | 6ht floor | IT/65 | 2024-11-21 | 2024-11-21 | Pre plaster | Check pre plaster inspection including chicken mesh |  | 613614615616 | A | 2024-11-22
67 | Sub Structure | 7th floor | IT/66 | 2024-11-26 | 2024-11-26 | plaster work | Check plaster work |  | 712714 | A | 2024-12-06
68 | Sub Structure | 7th floor | IT/67 | 2024-11-26 | 2024-11-26 | Pre plaster | Check pre plaster inspection including chicken mesh |  | 705706708 | A | 2024-11-28
69 | Sub Structure | 7th floor | IT/68 | 2024-11-27 | 2024-11-27 | Pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | 701703 | A | 2024-11-28
70 | Sub Structure | 7th floor | IT/69 | 2024-11-28 | 2024-11-28 | Pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | 702704 | A | 2024-11-28
| Sub Structure | 7th floor | IT/70 | 2024-11-28 | 2024-11-28 | plaster work | Check plaster work |  | 710 | A | 2024-12-06
72 | Sub Structure | 7th floor | IT/71 | 2024-11-28 | 2024-11-28 | plaster work | Check plaster work |  | 705707 | A | 2024-12-06
73 | Sub Structure | 7th floor | IT/72 | 2024-11-29 | 2024-11-29 | plaster work | Check plaster work |  | 701703709 | A | 2024-12-05
74 | Sub Structure | 7th floor | IT/73 | 2024-12-03 | 2024-12-03 | Pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | corridor, electrick room, garbage room | A | 2024-12-04
75 | Sub Structure | 6th floor | IT/74 | 2024-12-03 | 2024-12-03 | Pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | corridor, electrick room, garbage room | A | 2024-12-04 |  |  |  |  | 2024-12-03
76 | Sub Structure | 7th floor | IT/75 | 2024-12-03 | 2024-12-03 | plaster work | Check plaster work |  | 702706 | A | 2024-12-04
77 | Sub Structure | 7th floor | IT/76 | 2024-12-04 | 2024-12-04 | plaster work | Check plaster work |  | 708 | A | 2024-12-05
78 | Sub Structure | 6th floor | IT/77 | 2024-12-04 | 2024-12-04 | plaster work | Check plaster work |  | 607609610612 | A | 2024-12-06
79 | Sub Structure | 6th floor | IT/78 | 2024-12-05 | 2024-12-05 | plaster work | Check plaster work |  | 614616 | A | 2024-12-07
80 | Sub Structure | 6th floor | IT/79 | 2024-12-09 | 2024-12-09 | plaster work | Check plaster work |  |  | B | 2024-12-10
81 | Sub Structure | 7th floor | IT/80 | 2024-12-09 | 2024-12-09 | plaster work | Check plaster work |  | corridor, electrick room, garbage room | B | 2024-12-10
82 | Sub Structure | 8th floor | IT/81 | 2024-12-07 | 2024-12-07 | Pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | 801802803804806 | A | 2024-12-07
83 | Sub Structure | 8th floor | IT/82 | 2024-12-13 | 2024-12-13 | Pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | 808 | A | 2024-12-16
84 | Sub Structure | 9th floor | IT/83 | 2024-12-13 | 2024-12-13 | Pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | 916 | A | 2024-12-16
85 | Sub Structure | 7th floor | IT/84 | 2024-12-26 | 2024-12-26 | plaster work | Check plaster work |  | 704 | R | 2024-12-31
86 | Sub Structure | 8th floor | IT/85 | 2025-02-12 | 2025-02-12 | plaster work | Check plaster work |  | 804806 | A | 2025-02-28
87 | Sub Structure | 2024-12-14 | IT/86 | 2024-12-14 | 2024-12-16 | plaster work | Check pre plaster inspection including chipping and chicken mesh |  | 810812814816 | A | 2024-12-16
88 | Sub Structure | 8th floor | IT/87 | 2025-02-12 | 2025-02-12 | plaste work` | Check plaster work |  | 801802 | A | 2025-02-28
89 | I Tower | 8th floor | IT/88 | 2025-01-07 | 2025-01-07 | plaste work` | Check plaster work |  | 808 | A | 2025-02-28
90 | I Tower | 6th floor | IT/89 | 2025-01-31 | 2025-01-31 | plaste work` | Check plaster work |  | 611 | A | 2025-02-28
91 | I Tower | 9th floor | IT/90 | 2024-12-26 | 2024-12-26 | plaste work` |  |  | 916 | R | 2024-12-31
92 | I Tower | 8th floor | IT/91 | 2024-12-23 | 2024-12-23 | pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | 805 | R | 2024-12-31
93 | I Tower | 9th floor | IT/92 | 2024-12-23 | 2024-12-23 | pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | 912914 | A | 2024-12-24
94 | I Tower | 8th floor | IT/93 | 2024-12-26 | 2024-12-26 | pre plaster | Chec pre plaster inspection including chipping and chicken mesh |  | 815 | B | 2024-12-31
95 | I Tower | 9th floor | IT/94 | 2024-12-26 | 2024-12-26 | pre plaster | Chec pre plaster inspection including chipping and chicken mesh |  | 910 | R | 2024-12-31
96 | I Tower | 8th floor | IT/95 | 2025-01-07 | 2025-01-07 | plaster work | Check plaster work |  | 803 | A | 2025-02-28
97 | I Tower | 9th floor | IT/96 | 2024-12-30 | 2024-12-30 | pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | 915 | B | 2024-12-31
98 | I Tower | 9th floor | IT/97 | 2025-01-01 | 2025-01-01 | plaster work | Check plaster work |  | 910912914 | OP
99 | I Tower | 8th floor | IT/98 | 2025-01-01 | 2025-01-01 | plaster work | Check plaster work |  | 810812814 | OP
100 | I Tower | 8th floor | IT/99 | 2025-01-01 | 2025-01-01 | plaster work | Check plaster work |  | 815816 | OP
101 | I Tower | Ground | IT/100
102 | I Tower | Ground | IT/101
103 | I Tower | 9th floor | IT/102 | 2025-01-01 | 2025-01-02 | Pre plaster | Check pre plaster inspection including chipping & chicken mesh |  | 910 | A | 2025-01-05
104 | I Tower | 8th floor | IT/103 | 2025-01-03 | 2025-01-03 | Pre plaster | Check pre plaster inspection including chipping and chicken mesh |  | 805 | A | 2025-01-05
105 | I Tower | 9th floor | IT/104 | 2025-02-17 | 2025-02-17 | plaster work | Check plaster work |  | 916 | A | 2025-02-28
106 | I Tower | 7th floor | IT/105 | 2025-01-03 | 2025-01-03 | plaster work | Check plaster work |  | 704 | B | 2025-01-05
107 | I Tower | 8th floor | IT/106 | 2025-01-07 | 2025-01-07 | Pre plaster | Check pre plaster inspection including chicken mesh |  | 807809811813 | B | 2025-01-09
108 | I Tower | Ground | IT/107
109 | I Tower | Ground | IT/108
110 | I Tower | 8th floor | IT/109 | 2025-01-07 | 2025-01-07 | plaster work | Check plaster work |  | 808 | OP
111 | I Tower | 8th floor | IT/110 | 2025-01-04 | 2025-01-04 | plaster work | Check plaster work |  | 810 | B | 2025-01-06
112 | I Tower | 8th floor | IT/111 | 2025-02-12 | 2025-02-12 | plaster work | Check plaster work |  | 812 | A | 2025-02-28
113 | I Tower | 8th floor | IT/112 | 2025-02-12 | 2025-02-12 | plaster work | Check plaster work |  | 814 | A | 2025-02-28
114 | I Tower | 8th floor | IT/113 | 2025-02-12 | 2025-02-12 | plaster work | Check plaster work |  | 816 | A | 2025-02-28
115 | I Tower | 9th floor | IT/114 | 2025-01-27 | 2025-01-27 | plaster work | Check plaster work |  | 914 | A | 2025-02-28
116 | I Tower | 9th floor | IT/115 | 2025-01-27 | 2025-01-27 | plaster work | Check plaster work |  | 912 | A | 2025-02-28
117 | I Tower | 9th floor | IT/116 | 2025-02-17 | 2025-02-17 | plaster work | Check plaster work |  | 910 | A | 2025-02-28
118 | I Tower | 9th floor | IT/117 | 2025-01-27 | 2025-01-27 | plaster work | Check plaster work |  | 908 | A | 2025-02-28
119 | I Tower | 9th floor | IT/118 | 2025-01-07 | 2025-01-07 | Pre plaster | Check pre plaster inspection including chicken mesh |  | 913915 | B | 2025-01-09
120 | I Tower | Elevation | IT/119 | 2025-01-09 | 2025-01-10 | Chiselling | Check chiselling work at earliest for plastering |  | Grid E-F/26 | R | 2025-01-10
121 | I Tower | 8th floor | IT/120 | 2025-01-10 | 2025-01-10 | plaster work | check plaster work |  | 805 | A | 2025-02-28
122 | I Tower | 8th floor | IT/121 | 2025-02-12 | 2025-02-12 | plaster work | Check plaster work |  | 815 | A | 2025-02-28
123 | I Tower | 6th floor | IT/122 | 2025-01-31 | 2025-01-31 | plaster work | Check plaster work |  | 613615 | A | 2025-02-28
124 | I Tower | 8th floor | IT/123 | 2025-01-20 | 2025-01-20 | pre plaster | Check pre plaster including chicken mesh in all respect |  | 807809 | OP
125 | I Tower | 1st Floor | IT/124
126 | I Tower | 9th floor | IT/125 | 2025-01-20 | 2025-01-20 | Pre plaster | Check pre plaster including chicken mesh in all respect |  | 901902903 | A | 2025-01-22
127 | I Tower | 9th floor | IT/126 | 2025-01-20 | 2025-01-20 | Pre plaster | Check pre plaster includiong chicken mesh |  | 904906911 | A | 2025-01-22
128 | I Tower | Elevation | IT/127 | 2025-01-13 | 2025-01-13 | Chiselling | Check chiselling work at earliest for plastering |  | Grid E-F/26 | B | 2025-01-24
129 | I Tower | 9th floor | IT/128 | 2025-02-17 | 2025-02-17 | plaster work | Check plaster work |  | 913915 | A | 2025-02-28
130 | I Tower | 10th floor | IT/129 | 2025-01-16 | 2025-01-16 | Pre plaster | Check pre plaster including chicken mesh in all respect |  | corridor | B | 2025-01-17
131 | I Tower | 10th to 11th floor | IT/130 | 2025-01-20 | 2025-01-20 | plaster work | Check plaster (cutting, chiselling, door size etc) |  |  | OP
132 | I Tower | 5th to 9th | IT/131 | 2025-01-20 | 2025-01-20 | Pre plaster | Check pre plaster including chicken mesh in all respect |  | Grid A-B/8-10 | B | 2025-01-24
133 | I Tower | 5th to 9th | IT/132 | 2025-01-20 | 2025-01-20 | Pre plaster | Check pre plaster including chicken mesh in all respect |  | Grid A-B/17-19 | B | 2025-01-24
134 | I Tower | 9th floor | IT/133 | 2025-01-22 | 2025-01-22 | plaster work | Check plaster work |  | 903905 | A | 2025-02-28
135 | I Tower | 9th floor | IT/134 | 2025-02-17 | 2025-02-17 | plaster work | Check plaster work |  | 901902 | A | 2025-02-28
136 | I Tower | 9th floor | IT/135 | 2025-02-17 | 2025-02-17 | plaster work | Check plaster work |  | 904906 | A | 2025-02-28
137 | I Tower | Elevation | IT/136 | 2025-01-24 | 2025-01-24 | Chiselling | Check available chiselling work |  | Grid A/21-23 | R | 2025-02-01
138 | I Tower | 9th floor | IT/137 | 2025-01-25 | 2025-01-25 | plaster work | Check plaster work |  | 907911 | A | 2025-02-28
139 | I Tower | 8th floor | IT/138 | 2025-01-27 | 2025-01-27 | plaster work | Check plaster work |  | 807 | A | 2025-02-28
140 | I Tower | 8th floor | IT/139 | 2025-01-27 | 2025-01-27 | plaster work | Check plaster work |  | 809 | A | 2025-02-28
142 | I Tower | 8th floor | IT/140 | 2025-02-12 | 2025-02-12 | plaster work | Check plaster work |  | 810 | A | 2025-02-28
143 | I Tower | 8th floor | IT/141 | 2025-02-12 | 2025-02-12 | plaster work | Check plaster work |  | 811 | A | 2025-02-28
144 | I Tower | 8th floor | IT/142 | 2025-02-12 | 2025-02-12 | plaster work | Check plaster work |  | 813 | A | 2025-02-28
145 | I Tower | 5th floor | IT/143 | 2025-12-15 | 2025-12-15 | Chiselling | Check chiselling work at earliest for plastering |  |  | A | 2025-01-29
146 | I Tower | 5th floor | IT/144 | 2025-01-30 | 2025-01-30 | pre plaster | check pre plaster including chicken mesh |  |  | B | 2025-02-01
147 | I Tower | 9th floor | IT/145 | 2025-01-27 | 2025-01-27 | Chiselling | Check chiselling work at earliest for plastering |  |  | R | 2025-01-29
148 | I Tower | 7th floor to 8th floor | IT/146 | 2025-12-15 | 2025-12-15 | Chiselling | Check chiselling work at earliest for plastering |  |  | A | 2025-01-29
149 | I Tower | 10th floor | IT/147 | 2025-02-12 | 2025-02-12 | plaster work | Check plaster work |  | corridor | A | 2025-02-28
150 | I Tower | 9th to 10th floor | IT/148 | 2025-01-27 | 2025-01-27 | Pre plaster | check pre plaster work including chicken mesh |  | stair area | B | 2025-01-28
151 | I Tower | 9th floor | IT/149 | 2025-02-17 | 2025-02-17 | plaster work | Check plaster work |  | 909 | A | 2025-02-28
152 | I Tower | 9th floor | IT/150 | 2025-01-31 | 2025-01-31 | plaster work | Check plaster work |  | corridor | A | 2025-02-19
153 | I Tower | 8th floor | IT/151 | 2025-01-28 | 2025-01-28 | plaster work | Check plaster work |  | corridor | A | 2025-02-28
154 | I Tower | Elevation | IT/152 | 2025-01-28 | 2025-01-28 | Pre plaster | Check pre plaster including mesh |  | Grid A/21-23 | A | 2025-01-29
155 | I Tower | Elevation | IT/153 | 2025-01-29 | 2025-01-29 | plastering | Check chiselling work at earliest for plastering |  |  | A | 2025-01-31
156 | I Tower | 1st floor | IT/154 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  |  | A | 2025-02-28
157 | I Tower | 2nd floor | IT/155 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  | Balcony apartment | B | 2025-05-14
158 | I Tower | 3rd floor | IT/156 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  |  | B | 2025-05-14
159 | I Tower | 4th floor | IT/157 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  |  | B | 2025-05-14
160 | I Tower | 5th floor | IT/158 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  |  | B | 2025-05-14
161 | I Tower | 6th floor | IT/159 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  |  | B | 2025-05-14
162 | I Tower | 7th floor | IT/160 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  |  | B | 2025-05-14
163 | I Tower | 11th floor | IT/161 | 2025-01-30 | 2025-01-30 | Pre plaster | Check pre plaster work |  | corridor+electrical, garbage room | B | 2025-02-13
164 | I Tower | 3rd to 9th floor | IT/162 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  | Grid A-B/8-9 | A | 2025-05-14
165 | I Tower | 2nd to 8th floor | IT/163 | 2025-02-18 | 2025-02-18 | plaster work | Check plaster work |  | Grid A-B/9-10 | A | 2025-05-14
166 | I Tower | 1st to 8th floor | IT/164 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  | Grid A-B/17-18 | A | 2025-05-14
167 | I Tower | GF to 8th floor | IT/165 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  | Grid A-B/18-19 | A | 2025-05-14
168 | I Tower | 8th floor | IT/166 | 2025-01-30 | 2025-01-30 | plaster work | Check plaster work |  |  | B | 2025-05-14
169 | I Tower | Ground Floor | IT/167 | 2025-02-04 | 2025-02-04 | Pre plaster | Check pre plaster work Zone 3 |  |  | A | 2025-02-05
170 | I Tower | 2nd to 9th floor | IT/168 | 2025-02-10 | 2025-02-10 | plaster work | Check plaster work |  | Grid A-B/8-9 | R | 2025-02-05
171 | I Tower | Ground floor | IT/169 | 2025-02-27 | 2025-02-27 | plaster work | Check plaster work zone 3 |  |  | A | 2025-03-06
172 | I Tower | 5th Floor | IT/170
173 | I Tower | 11th floor | IT/171 | 2025-02-27 | 2025-02-27 | plaster work | Check plaster work |  | corridor, electrical, garbage room | A | 2025-02-28
174 | I Tower | Ground floor | IT/172 | 2025-02-28 | 2025-02-28 | pre plaster | Check pre plaster including chicken mesh zone 1 |  |  | A | 2025-02-28
175 | I Tower | Elevation | IT/173 R01 | 2025-09-10 | 2025-09-10 | plaster work | Check plaster work |  | Grid F/8-9 | R | 2025-09-12
176 | I Tower | Elevation | IT/174 | 2025-02-28 | 2025-02-28 | plaster work | Check plaster work |  | Grid F/22-24 | R | 2025-02-28
177 | I Tower | Elevation | IT/175 | 2025-03-13 | 2025-03-13 | plaster work | Check plaster work |  | Grid F/22-24 | OP
178 | I Tower | Ground floor | IT/176 | 2025-03-07 | 2025-03-07 | Pre plaster | Check pre plaster including chicken mesh zone 1 |  | Grid A-F/1-13 | A | 2025-05-14
179 | I Tower | 1st floor | IT/177 | 2025-03-07 | 2025-03-07 | Pre plaster | Check pre plaster including chicken mesh |  |  | A | 2025-03-12
180 | I Tower | 2nd floor | IT/178 | 2025-03-07 | 2025-03-07 | Pre plaster | Check pre plaster including chicken mesh |  |  | A | 2025-03-12
181 | I Tower | 3rd floor | IT/179 | 2025-03-07 | 2025-03-07 | Pre plaster | Check pre plaster including chicken mesh |  |  | A | 2025-03-12
182 | I Tower | 4th floor | IT/180 | 2025-03-10 | 2025-03-10 | Pre plaster | Check pre plaster including chicken mesh |  |  | A | 2025-05-14
183 | I Tower | 1st floor | IT/181 | 2025-03-10 | 2025-03-10 | plaster work | Check plaster work |  |  | A | 2025-05-14
184 | I Tower | 2nd floor | IT/182 | 2025-03-10 | 2025-03-10 | plaster work | Check plaster work |  |  | A | 2025-05-14
185 | I Tower | 3rd floor | IT/183 | 2025-03-10 | 2025-03-10 | plaster work | Check plaster work |  |  | A | 2025-05-14
186 | I Tower | 1st floor | IT/184 | 2025-03-11 | 2025-03-11 | plaster work | Check plaster work |  | 101-116 | A | 2025-05-14
187 | I Tower | 4th floor | IT/185 | 2025-03-13 | 2025-03-13 | plaster work | Check plaster work |  | Façade | A | 2025-05-14
188 | I Tower | 5th floor | IT/186 | 2025-03-13 | 2025-03-13 | pre plaster | Check pre plaster including chicken mesh |  |  | A | 2025-05-14
189 | I Tower | Ground floor | IT/187 | 2025-05-08 | 2025-05-08 | plaster work | Check plaster work zone 1 |  | internal side | A | 2025-05-14
190 | I Tower | Ground floor | IT/188 | 2025-05-08 | 2025-05-08 | plaster work | Check plaster work zone 1 |  | external side | A | 2025-05-09
191 | I Tower | elevation | IT/189 R01 | 2025-09-04 | 2025-09-04 | plaster work | Check plaster work |  | Grid F/22-24 | A | 2025-09-05
192 | I Tower | 9-10th floor | IT/190 | 2025-05-08 | 2025-05-08 | plaster work | Check plaster work |  | Grid A-B/17-18 | A | 2025-05-10
193 | I Tower | GF, 1st, 9th | IT/191 | 2025-05-08 | 2025-05-08 | plaster work | Check plaster work |  | Grid A-B/9-10 | A | 2025-05-13
194 | I Tower | 7th Floor | IT/192
195 | I Tower | 10th floor | IT/193 | 2025-05-16 | 2025-05-16 | pre plaster | Check pre plaster including chicken mesh, corner, bead |  |  | A | 2025-05-17
196 | I Tower | 5th floor | IT/194 | 2025-03-07 | 2025-03-07 | plaster work | Check plaster work |  |  | A | 2025-05-07
197 | I Tower | 10th floor | IT/195 | 2025-05-19 | 2025-05-19 | pre plaster | Check pre plaster corner bead chicken mesh |  |  | A | 2025-05-20
198 | I Tower | Ground floor | IT/196 | 2025-05-24 | 2025-05-24 | plaster work | check plaster work |  | Grid F/1-26 | A | 2025-05-24
199 | I Tower | 10th floor | IT/197 | 2025-05-26 | 2025-05-24 | Pre plaster | check pre plaster including corner bead, chicken mesh |  |  | A | 2025-05-24
200 | I Tower | Elevation | IT/198 R01 | 2025-09-04 | 2025-09-04 | plaster work | check plaster work |  | Grid A/8-11 | A | 2025-09-07
201 | I Tower | 10th floor | IT/199 | 2025-05-29 | 2025-05-29 | Pre plaster | check pre plaster including chicken mesh & corner bead |  |  | A | 2025-05-29
202 | I Tower | 10th floor | IT/200 | 2025-05-29 | 2025-05-29 | plaster work | check plaster work |  | 1001 | A | 2025-05-29
203 | I Tower | 10th floor | IT/201 | 2025-05-29 | 2025-05-29 | plaster work | check plaster work |  | 1002 | A | 2025-05-29
204 | I Tower | 10th floor | IT/202 | 2025-06-21 | 2025-06-21 | Pre plaster | check pre plaster including chicken mesh & corner bead |  | 1005 | A | 2025-07-19
205 | I Tower | 8th Floor | IT/203 R02 | 2025-08-14 | 2025-08-14 | plaster work | check plaster work |  | 1003 | A | 2025-09-16
206 | I Tower | 10th floor | IT/204 R02 | 2025-08-15 | 2025-08-15 | plaster work | check plaster work |  | 1004 | A | 2025-09-16
207 | I Tower | 10th floor | IT/205 | 2025-06-23 | 2025-06-23 | plaster work | check pre plastger & corner bead and chicken mesh |  | 1006 | A | 2025-07-19
208 | I Tower | 8th Floor | IT/206
209 | I Tower | 10th floor | IT/207 R03 | 2025-09-15 | 2025-09-15 | plaster work | check plaster work |  | 1005 | A | 2025-09-15
210 | I Tower | 10th floor | IT/208 | 2025-07-17 | 2025-07-17 | plaster work | check plaster work |  | 1006 | A | 2025-08-15
|  | 10th floor | IT/208 R03 | 2025-09-15 | 2025-09-15 | plaster work | check plaster work |  | 1006 | A | 2025-09-15
212 | I Tower |  | IT/210 | 2025-07-13 | 2025-07-13 | Chiselling | Check chiselling work at earliest for plastering |  |  | OP
213 | I Tower |  | IT/211 | 2025-07-13 | 2025-07-13 | plaster work | Check available extra material and start to plastering work |  |  | OP
214 | I Tower | 9th Floor | IT/212 | 2025-08-20 | 2025-08-20 | plaster work | Check plaster work of bed room and ladger wall plaster |  | 3rd floor 301-316 | A | 2025-08-26
215 | I Tower | 8th Floor | IT/213 | 2025-07-14 | 2025-07-14 | plaster work | check pre plaster including corner bead, chicken mesh |  | 10th floor apt 1010 | A | 2025-07-19
216 | I Tower | 9th Floor | IT/214 R01 | 2025-08-11 | 2025-08-11 | plaster work | Check the beam plaster |  | 201-216 | A | 2025-08-16
217 | I Tower | 9th Floor | IT/215 R02 | 2025-08-14 | 2025-08-14 | plaster work | check plaster work |  | 1008 | A | 2025-08-16
218 | I Tower | 9th Floor | IT/216 | 2025-08-11 | 2025-08-11 | plaster work | Check the beam plaster |  | 401-416 | A | 2025-08-16
219 | I Tower | 9th Floor | IT/217 | 2025-08-24 | 2025-08-24 | plaster work | Check the Ladge wall plaster work |  | 201-216 | A | 2025-08-29
220 | I Tower | 9th Floor | IT/218
221 | I Tower | 9th Floor | IT/219
222 | I Tower | 4th floor | IT/220 R1 01 | 2025-09-25 | 2025-09-25 | plaster work | Check the Ladge wall plaster work |  | 401-416 | A | 2025-10-10
223 | I Tower | 9th Floor | IT/221 | 2025-08-30 | 2025-08-30 | pre-plaster | Check the pre-plaster and corner bead Complete with all respect |  | 1012 | A | 2025-09-01
224 | I Tower | 9th Floor | IT/222 | 2025-09-04 | 2025-09-04 | plaster work | Check plaster work at MEP Duct |  | 101113 | A | 2025-09-13
225 | I Tower | 9th Floor | IT/223 R01 | 2025-09-25 | 2025-09-25 | plaster work | Check plaster work at MEP Duct |  | 201213 | A | 2025-10-07
226 | I Tower | 9th Floor | IT/224 | 2025-09-04 | 2025-09-04 | plaster work | Check plaster work at MEP Duct |  | 301313 | A | 2025-09-12
227 | I Tower | 9th Floor | IT/225 R1 | 2025-09-25 | 2025-09-25 | plaster work | Check plaster work at MEP Duct |  | 401413 | A | 2025-10-10
228 | I Tower | 9th Floor | IT/226 | 2025-09-09 | 2025-09-09 | Corner bead | Check the left and right bed rooms pre-prepration corner bead complete with all recpect |  | 1011 | A | 2025-09-13 | Saqib
229 | I Tower | 10th Floor | IT/227 | 2025-09-09 | 2025-09-09 | plaster work | Check the plaster work of standing wall and zone 1 stair door wall |  |  | A | 2025-09-12
230 | I Tower | 5th floor | IT/228 R01 | 2025-09-25 | 2025-09-25 | plaster work | Check the beam plaster |  | 501-516 | A | 2025-10-10
231 | I Tower | 5th floor | IT/229 R01 | 2025-09-25 | 2025-09-25 | plaster work | Check ladge wall plaster |  | 501-516 | A | 2025-10-10
232 | I Tower | 6th floor | IT/230 R01 | 2025-09-25 | 2025-09-25 | plaster work | Check ladge wall plaster |  | 601-616 | A | 2025-10-10
233 | I Tower | 10th Floor | IT/231 | 2025-09-16 | 2025-09-16 | pre-Plaster | Check the pre-plaster and corner bead Complete with all respect |  | 1013 | A | 2025-09-19
234 | I Tower | 10th Floor | IT/232 | 2025-09-16 | 2025-09-16 |  | Check the pre-plaster and corner bead Complete with all respect |  | 1011 | A | 2025-09-19
235 | I Tower | 10th Floor | IT/233 | 2025-10-23 | 2025-10-23 | plaster work | Check the plaster work |  | 1007 | B | 2025-10-31
236 | I Tower | 10th Floor | IT/234 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work |  | 1012 | B | 2025-10-31
237 | I Tower | 10th Floor | IT/235 | 2025-10-22 | 2025-10-22 | plaster work | Check the plaster work |  | 1014 | B | 2025-10-31
238 | I Tower | 10th Floor | IT/236
239 | I Tower | 10th Floor | IT/237 | 2025-10-11 | 2025-10-11 | plaster work | Check plaster work |  | rear Elevation G.F to Top | R | 2025-10-11
240 | I Tower | 10th Floor | IT/238 R.01 | 2025-10-27 | 2025-10-27 | plaster work | Check plaster work of Façade |  | 6th floor | A | 2025-10-29
241 | I Tower | 11th Floor | IT/239 | 2025-10-22 | 2025-10-22 | plaster work | Check plaster work |  | 1009 | A | 2025-10-23
242 | I Tower | 11th Floor | IT/240 | 2025-10-22 | 2025-10-22 | plaster work | Check plaster work |  | 1011 | B | 2025-10-31
243 | I Tower | 11th Floor | IT/241 | 2025-10-22 | 2025-10-22 | plaster work | Check plaster work |  | 1013 | B | 2025-10-31
244 | I Tower | 11th Floor | IT/242 | 2025-10-22 | 2025-10-22 | plaster work | Check plaster work |  | zone 1 Stair Door | OP
245 | I Tower | 11th Floor | IT/243 | 2025-10-27 | 2025-10-27 | plaster work | Check the Ladge wall plaster work |  | 801-816 | A | 2025-10-29
246 | I Tower | 11th Floor | IT/244 | 2025-10-27 | 2025-10-27 | plaster work | Check the plaster of façade work |  | 701-716 | A | 2025-10-29
247 | I Tower | 11th Floor | IT/245 | 2025-10-28 | 2025-10-28 | plaster work | Check plaster work |  | 1016 | B | 2025-10-31
248 | I Tower | 11th Floor | IT/246 | 2025-10-29 | 2025-10-29 | plaster work | Check the Ladge wall plaster work |  | 701-716 | A | 2025-10-31
249 | I Tower | 11th Floor | IT/247 | 2025-10-30 | 2025-10-30 | plaster work | Check plaster work |  | 5th floor Zone 1stair | R | 2025-10-30
250 | I Tower | 11th Floor | IT/248 | 2025-10-30 | 2025-10-30 | plaster work | Check plaster work |  | 2nd floor zone 1 stair door | A | 2025-11-01
251 | I Tower | 11th Floor | IT/249 | 2025-12-15 | 2025-12-15 | plaster work | Check plaster work |  | 5TH 6TH 7TH FLOOR
252 | I Tower | 11th Floor | IT/250
253 | I Tower | 11th Floor | IT/251 | 2025-12-18 | 2025-12-18 | plaster work | Check plaster work |  | 6TH FLOOR GRIDB/18-19
254 | I Tower | 11th Floor | IT/252 | 2025-12-18 | 2025-12-18 | plaster work | Check plaster work |  | 7TH TO 10 FLOOR GRID B/18-19
255 | I Tower | 11th Floor | IT/253 | 2025-12-18 | 2025-12-18 | plaster work | Check plaster work |  | 3RD 4TH 9TH 10TH FLOOR GRIDA-B/8-9
256 | I Tower | 11th Floor | IT/254
257 | I Tower | 11th Floor | IT/255
258 | I Tower | 11th Floor | IT/256
259 | I Tower | 11th Floor | IT/257
260 | I Tower | 11th Floor | IT/258
261 | I Tower | 11th Floor | IT/259
| I Tower | 11th Floor | IT/260
| I Tower | 11th Floor | IT/261
| I Tower | 11th Floor | IT/262
| I Tower | 11th Floor | IT/263
| I Tower | 11th Floor | IT/264
| I Tower | 11th Floor | IT/265
| I Tower | 11th Floor | IT/266
| I Tower | 11th Floor | IT/267
| I Tower | 11th Floor | IT/268
| I Tower | 11th Floor | IT/269 | [12 empty] | v
| I Tower | 11th Floor | IT/270
| I Tower | 11th Floor | IT/271
| I Tower | 11th Floor | IT/272
| I Tower | 11th Floor | IT/273
| I Tower | 11th Floor | IT/274
| I Tower | 11th Floor | IT/275
| I Tower | 11th Floor | IT/276
| I Tower | 11th Floor | IT/277
| I Tower | 11th Floor | IT/278
| I Tower | 11th Floor | IT/279
| I Tower | 11th Floor | IT/280
| I Tower | 11th Floor | IT/281
| I Tower | 11th Floor | IT/282
| I Tower | 11th Floor | IT/283
| I Tower | 11th Floor | IT/284
2022-12-19

## QE I Tower
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) QE | [5 empty] | Fully Approved (A) |  | 222
[9 empty] | Approved with comments (B) |  | 164
[9 empty] | Rejected ( R) |  | 4 |  | As of : | 2025-12-19
[9 empty] | Open/Pending (OP) |  | 14
[9 empty] | Total |  | 404
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR closing Date | Pour Card No. | Concrete Qty (m3) | Status
1 | Sub Structure | 2nd floor | QE-01 | 2024-08-19 | 2024-08-19 | boxes installation | Check conduit and boxes installation and plumbing points |  | T1-212 | B | 2024-08-21
2 | Sub Structure | 2nd floor | QE-02 | 2024-08-19 | 2024-08-19 | boxes installation | Check back box installation |  | 1st and 2nd f corridor | OP
3 | Sub Structure | 1st floor | QE-03 | 2024-08-19 | 2024-08-19 | conduit, boxes | Check conduit and back boxes installations |  | T1-103 | B | 2024-08-21
4 | Sub Structure | 1st floor | QE-04 | 2024-08-19 | 2024-08-19 | boxes installation | Check conduit and boxes installation and plumbing points |  | T1-101 | B | 2024-08-21
5 | Sub Structure | Basement | QE-05
6 | Sub Structure | 1st floor | QE-06 | 2024-08-19 | 2024-08-19 | boxes installation | Check back box installation |  | T1-104 | A | 2024-08-21
7 | Sub Structure | 1st floor | QE-07 | 2024-08-19 | 2024-08-19 | boxes installation | Check back box installation |  | T1-105 | A | 2024-08-21
8 | Sub Structure | 1st floor | QE-08 | 2024-08-19 | 2024-08-19 | boxes installation | Check conduit and back boxes installations |  | T1-108 | A | 2024-08-21
9 | Sub Structure | 1st floor | QE-09 | 2024-08-19 | 2024-08-19 | boxes installation | Check conduit and back boxes installations |  | T1-109 | A | 2024-08-21
10 | Sub Structure | 1st floor | QE-10 | 2024-08-19 | 2024-08-19 | boxes installation | Check conduit and back boxes installations |  | T1-112 | A | 2024-08-21
11 | Sub Structure | 1st floor | QE-11 | 2024-08-19 | 2024-08-19 | boxes installation | Check conduit and back boxes installations |  | T1-116 | A | 2024-08-21
| Sub Structure | 1st floor | QE-12 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | Check pipe installation, core cuts and grouting done |  | T1-104 | B | 2024-08-21
12 | Sub Structure | 1st floor | QE-13 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | Check pipe installation, core cuts and grouting done |  | T1-105 | B | 2024-08-21
13 | Sub Structure | 1st floor | QE-14 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-108 | B | 2024-08-21
14 | Sub Structure | 1st floor | QE-15 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-109 | B | 2024-08-21
15 | Sub Structure | 1st floor | QE-16 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-112 | B | 2024-08-21
16 | Sub Structure | 1st floor | QE-17 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-116 | B | 2024-08-21
17 | Sub Structure | 1st floor | QE-18 | 2024-08-19 | 2024-08-19 | conduit, boxes | Check elec conduit and back boxes installation |  | T1-102 | A | 2024-08-21
18 | Sub Structure | 1st floor | QE-19 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-102 | B | 2024-08-21
19 | Sub Structure | 1st floor | QE-20 | 2024-08-19 | 2024-08-19 | conduit, boxes | Check elec conduit and back boxes installation |  | T1-106 | A | 2024-08-21
20 | Sub Structure | 1st floor | QE-21 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-106 | B | 2024-08-21
21 | Sub Structure | 1st floor | QE-22 | 2024-08-19 | 2024-08-19 | conduit, boxes | Check elec conduit and back boxes installation |  | T1-107 | A | 2024-08-21
| Sub Structure | 1st floor | QE-23 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-107 | B | 2024-08-21
| Sub Structure | 1st floor | QE-24 | 2024-08-19 | 2024-08-19 | conduit, boxes | Check elec conduit and back boxes installation |  | T1-110 | A | 2024-08-21
| Sub Structure | 1st floor | QE-25 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-110 | B | 2024-08-21
| Sub Structure | 1st floor | QE-26 | 2024-08-19 | 2024-08-19 | conduit, boxes | Check elec conduit and back boxes installation |  | T1-111 | A | 2024-08-21
| Sub Structure | 1st floor | QE-27 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-111 | B | 2024-08-21
| Sub Structure | 1st floor | QE-28 | 2024-08-19 | 2024-08-19 | conduit, boxes | Check elec conduit and back boxes installation |  | T1-114 | A | 2024-08-21
| Sub Structure | 1st floor | QE-29 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-114 | B | 2024-08-21
| Sub Structure | 1st floor | QE-30 | 2024-08-19 | 2024-08-19 | conduit, boxes | Check elec conduit and back boxes installation |  | T1-113 | A | 2024-08-21
| Sub Structure | 1st floor | QE-31 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-113 | B | 2024-08-21
| Sub Structure | 1st floor | QE-32 | 2024-08-19 | 2024-08-19 | conduit, boxes | Check elec conduit and back boxes installation |  | T1-115 | A | 2024-08-21
| Sub Structure | 1st floor | QE-33 | 2024-08-19 | 2024-08-19 | PPRC Pipe installation | PPRC Pipe installation, core cuts and grouting done |  | T1-115 | B | 2024-08-21
| Sub Structure | 2nd floor | QE-34 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-201 | B | 2024-09-12
| Sub Structure | 2nd floor | QE-35 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-202 | A | 2024-09-12
| Sub Structure | 2nd floor | QE-36 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-203 | B | 2024-09-12
| Sub Structure | 2nd floor | QE-37 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-204 | B | 2024-09-12
| Sub Structure | 2nd floor | QE-38 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-205 | B | 2024-09-12
| Sub Structure | 2nd floor | QE-39 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-206 | A | 2024-09-12
| Sub Structure | 2nd floor | QE-40 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-207 | A | 2024-09-12
| Sub Structure | 2nd floor | QE-41 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-208 | B | 2024-09-12
| Sub Structure | 2nd floor | QE-42 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-209 | A | 2024-09-12
| Sub Structure | 2nd floor | QE-43 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-210 | A | 2024-09-12
| Sub Structure | 2nd floor | QE-44 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-211 | A | 2024-09-12
| Sub Structure | 2nd floor | QE-45
| Sub Structure | 2nd floor | QE-46 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-213 | B | 2024-09-12
| Sub Structure | 2nd floor | QE-47 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-214 | A | 2024-09-12
| Sub Structure | 2nd floor | QE-48 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-215 | A | 2024-09-12
| Sub Structure | 2nd Floor | QE-49 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-216 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-50 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-301 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-51 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-302 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-52 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-303 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-53 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-304 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-54 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-305 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-55 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-306 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-56 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-307 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-57 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-308 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-58 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-309 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-59 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-310 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-60 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-311 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-61 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-312 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-62 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-313 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-63 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-314 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-64 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-315 | A | 2024-09-12
| Sub Structure | 3rd Floor | QE-65 | 2024-08-28 | 2024-08-27 | conduit, boxes | Check conduit and boxes installation and plumbing points |  | T1-316 | A | 2024-09-12
| Sub Structure | 4th floor | QE-66 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-401 | B | 2024-09-12
| Sub Structure | 4th floor | QE-67 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-402 | A | 2024-09-12
| Sub Structure | 4th floor | QE-68 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-403 | A | 2024-09-12
| Sub Structure | 4th floor | QE-69 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-404 | A | 2024-09-12
| Sub Structure | 4th floor | QE-70 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-405 | B | 2024-09-12
| Sub Structure | 4th floor | QE-71 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-406 | A | 2024-09-12
| Sub Structure | 4th floor | QE-72 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-407 | A | 2024-09-12
| Sub Structure | 4th floor | QE-73 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-408 | A | 2024-09-12
| Sub Structure | 4th floor | QE-74 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-409 | B | 2024-09-12
| Sub Structure | 4th floor | QE-75 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-410 | A | 2024-09-12
| Sub Structure | 4th floor | QE-76 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-411 | A | 2024-09-12
| Sub Structure | 4th floor | QE-77 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-412 | A | 2024-09-12
| Sub Structure | 4th floor | QE-78 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-413 | B | 2024-09-12
| Sub Structure | 4th floor | QE-79 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-414 | B | 2024-09-12
| Sub Structure | 4th floor | QE-80 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-415 | B | 2024-09-12
| Sub Structure | 4th floor | QE-81 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-416 | A | 2024-09-12
| Sub Structure | 5th floor | QE-82 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-501 | B | 2024-09-13
| Sub Structure | 5th floor | QE-83 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-502 | B | 2024-09-13
| Sub Structure | 5th floor | QE-84 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-503 | B | 2024-09-13
| Sub Structure | 5th floor | QE-85 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-504 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-86 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-505 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-87 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-506 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-88 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-507 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-89 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-508 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-90 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-509 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-91 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-510 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-92 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-511 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-93 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-512 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-94 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-513 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-95 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-514 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-96 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-515 | B | 2024-09-13
| Sub Structure | 5th Floor | QE-97 | 2024-08-29 | 2024-08-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-516 | B | 2024-09-13
| Sub Structure | 6th floor | QE-98 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-601 | B | 2024-10-29
| Sub Structure | 6th floor | QE-99 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-602 | B | 2024-10-29
| Sub Structure | 6th floor | QE-100 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-603 | B | 2024-10-29
| Sub Structure | 6th floor | QE-101 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-604 | B | 2024-10-29
| Sub Structure | 6th floor | QE-102 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-605 | B | 2024-10-29
| Sub Structure | 6th floor | QE-103 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-606 | B | 2024-10-29
| Sub Structure | 6th floor | QE-104 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-607 | B | 2024-10-29
| Sub Structure | 6th floor | QE-105 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-608 | B | 2024-10-29
| Sub Structure | 6th floor | QE-106 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-609 | B | 2024-10-29
| Sub Structure | 6th floor | QE-107 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-610 | B | 2024-10-29
| Sub Structure | 6th floor | QE-108 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-611 | B | 2024-10-29
| Sub Structure | 6th floor | QE-109 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-612 | B | 2024-10-29
| Sub Structure | 6th floor | QE-110 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-613 | B | 2024-10-29
| Sub Structure | 6th floor | QE-111 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-614 | B | 2024-10-29
| Sub Structure | 6th floor | QE-112 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-615 | B | 2024-10-29
| Sub Structure | 6th floor | QE-113 | 2024-10-14 | 2024-10-14 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-616 | B | 2024-10-29
| Sub Structure | 7th floor | QE-114 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-701 | B | 2024-10-28
| Sub Structure | 7th floor | QE-115 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-702 | B | 2024-10-28
| Sub Structure | 7th floor | QE-116 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-703 | B | 2024-10-28
| Sub Structure | 7th floor | QE-117 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-704 | B | 2024-10-28
| Sub Structure | 7th floor | QE-118 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-705 | B | 2024-10-28
| Sub Structure | 7th floor | QE-119 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-706 | B | 2024-10-28
| Sub Structure | 7th floor | QE-120 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-707 | B | 2024-10-28
| Sub Structure | 7th floor | QE-121 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-708 | B | 2024-10-28
| Sub Structure | 7th floor | QE-122 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-709 | B | 2024-10-28
| Sub Structure | 7th floor | QE-123 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-710 | B | 2024-10-28
| Sub Structure | 7th floor | QE-124 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-711 | B | 2024-10-28
| Sub Structure | 7th floor | QE-125 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-712 | B | 2024-10-28
| Sub Structure | 7th floor | QE-126 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-713 | B | 2024-10-28
| Sub Structure | 7th floor | QE-127 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-714 | B | 2024-10-28
| Sub Structure | 7th floor | QE-128 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-715 | B | 2024-10-28
| Sub Structure | 7th floor | QE-129 | 2024-10-18 | 2024-10-18 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-716 | B | 2024-10-28
| Sub Structure | 8th floor | QE-130 | 2024-10-29 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-801 | B | 2024-10-29
| Sub Structure | 8th floor | QE-131 | 2024-10-29 | 2024-10-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-802 | B | 2024-10-29
| Sub Structure | 8th floor | QE-132 | 2024-10-29 | 2024-10-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-803 | B | 2024-10-29
| Sub Structure | 8th floor | QE-133 | 2024-10-29 | 2024-10-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-804 | B | 2024-10-29
| Sub Structure | 8th floor | QE-134 | 2024-10-29 | 2024-10-29 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-805 | B | 2024-10-29
| Sub Structure | 8th floor | QE-135 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-806 | B | 2024-11-11
| Sub Structure | 8th floor | QE-136 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-807 | B | 2024-11-11
| Sub Structure | 8th floor | QE-137 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-808 | B | 2024-11-11
| Sub Structure | 8th floor | QE-138 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-809 | B | 2024-11-11
| Sub Structure | 8th floor | QE-139 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-810 | B | 2024-11-11
| Sub Structure | 8th floor | QE-140 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-811 | B | 2024-11-11
| Sub Structure | 8th floor | QE-141 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-812 | B | 2024-11-12
| Sub Structure | 8th floor | QE-142 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-813 | B | 2024-11-12
| Sub Structure | 8th floor | QE-143 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-814 | B | 2024-11-12
| Sub Structure | 8th floor | QE-144 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-815 | B | 2024-11-12
| Sub Structure | 8th floor | QE-145 | 2024-10-23 | 2024-10-23 | back boxes | Check back boxes installation, PPRC installation for electrical and plumbing point |  | T1-816 | B | 2024-11-12
| Sub Structure | 1st floor | QE-146 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-101 | B | 2024-10-28
| Sub Structure | 1st floor | QE-147 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-102 | B | 2024-10-28
| Sub Structure | 1st floor | QE-148 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-103 | B | 2024-10-28
| Sub Structure | 1st floor | QE-149 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-104 | B | 2024-10-28
| Sub Structure | 1st floor | QE-150 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-105 | B | 2024-10-28
| Sub Structure | 1st floor | QE-151 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-106 | B | 2024-10-28
| Sub Structure | 1st floor | QE-152 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-107 | B | 2024-10-28
| Sub Structure | 1st floor | QE-153 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-108 | B | 2024-10-28
| Sub Structure | 1st floor | QE-154 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-109 | B | 2024-10-28
| Sub Structure | 1st floor | QE-155 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-110 | B | 2024-10-28
| Sub Structure | 1st floor | QE-156 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-111 | B | 2024-10-28
| Sub Structure | 1st floor | QE-157 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-112 | B | 2024-10-28
| Sub Structure | 1st floor | QE-158 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-113 | B | 2024-10-28
| Sub Structure | 1st floor | QE-159 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-114 | B | 2024-10-28
| Sub Structure | 1st floor | QE-160 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-115 | B | 2024-10-28
| Sub Structure | 1st floor | QE-161 | 2024-10-24 | 2024-10-24 | pipe installation | Drain, soil and exhaust pipe installation |  | T1-116 | B | 2024-10-28
| Sub Structure | 1st, 2nd, 3rd, 4th | QE-162 | 2024-10-25 | 2024-10-25 | cable installation | Cable tray installation in corridors |  |  | A | 2024-10-28
| Sub Structure | 2nd floor | QE-163 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-201 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-164 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-202 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-165 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-203 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-166 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-204 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-167 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-205 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-168 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-206 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-169 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-207 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-170 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-208 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-171 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-209 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-172 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-210 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-173 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-211 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-174 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-212 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-175 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-213 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-176 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-214 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-177 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-215 | B | 2024-11-21
| Sub Structure | 2nd floor | QE-178 | 2024-11-20 | 2024-11-20 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-216 | B | 2024-11-21
| Sub Structure | 3rd floor | QE-179 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-301 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-180 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-302 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-181 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-303 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-182 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-304 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-183 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-305 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-184 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-306 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-185 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-307 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-186 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-308 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-187 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-310 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-188 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-311 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-189 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-313 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-190 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-314 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-191 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-315 | B | 2024-12-03
| Sub Structure | 3rd floor | QE-192 | 2024-12-02 | 2024-12-02 | pipe installation | Check drain, soil and exhaust pipe instalation |  | T1-316 | B | 2024-12-03
| Sub Structure | 2nd floor | QE-193 | 2024-12-09 | 2024-12-09 | cable laying | Check cable laying |  |  | A | 2024-12-09
| Sub Structure | 1st floor | QE-194 | 2024-12-09 | 2024-12-09 | AC drain | check AC drain installation |  |  | A | 2024-12-09
| Sub Structure | 2nd floor | QE-195 | 2024-12-09 | 2024-12-09 | AC drain | check AC drain installation |  |  | A | 2024-12-09
| Sub Structure | 3rd floor | QE-196 | 2024-12-09 | 2024-12-09 | AC drain | check AC drain installation |  |  | A | 2024-12-09
| Sub Structure | 5-7th floor | QE-197 | 2024-12-11 | 2024-12-11 | cable installation | Cable tray installation in corridors |  |  | A | 2024-12-12
| Sub Structure | 1st to 2nd floor | QE-198 | 2024-12-11 | 2024-12-11 | geyser installation | Geyser installation |  |  | A | 2024-12-12
| Sub Structure | 1st to 2nd floor | QE-199 | 2024-12-11 | 2024-12-11 | ball walves | Ball valves installation |  |  | A | 2024-12-12
| Sub Structure | 10th floor | QE-200 | 2024-12-11 | 2024-12-11 | core cut | core cuts |  |  | A | 2024-12-12
| Sub Structure | 3rd floor | QE-201 | 2024-12-11 | 2024-12-12 | cable laying | Check cable laying |  |  | A | 2024-12-12
| Sub Structure | 4th floor | QE-202 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-1401 | A | 2025-01-16
| Sub Structure | 4th floor | QE-203 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-402 | A | 2025-01-16
|  | 4th floor | QE-204 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-403 | A | 2025-01-16
|  | 4th floor | QE-205 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-404 | A | 2025-01-16
|  | 4th floor | QE-206 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-405 | A | 2025-01-16
|  | 4th floor | QE-207 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-406 | A | 2025-01-16
|  | 4th floor | QE-208 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-407 | A | 2025-01-16
|  | 4th floor | QE-209 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-408 | A | 2025-01-16
|  | 4th floor | QE-210 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-409 | A | 2025-01-16
|  | 4th floor | QE-211 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-410 | A | 2025-01-16
|  | 4th floor | QE-212 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-411 | A | 2025-01-16
|  | 4th floor | QE-213 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-412 | A | 2025-01-16
|  | 4th floor | QE-214 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-413 | A | 2025-01-16
|  | 4th floor | QE-215 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-414 | A | 2025-01-16
|  | 4th floor | QE-216 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-415 | A | 2025-01-16
|  | 4th floor | QE-217 | 2025-01-14 | 2025-01-14 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-416 | A | 2025-01-16
|  | 3-8th floor | QE-218 | 2025-01-15 | 2025-01-15 | geyser installation | check Geyser installation |  |  | A | 2025-01-15
|  | 5th floor | QE-219 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-501 | A | 2025-01-21
|  | 5th floor | QE-220 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-502 | A | 2025-01-21
|  | 5th floor | QE-221 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-503 | A | 2025-01-21
|  | 5th floor | QE-222 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-504 | A | 2025-01-21
|  | 5th floor | QE-223 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-505 | A | 2025-01-21
|  | 5th floor | QE-224 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-506 | A | 2025-01-21
|  | 5th floor | QE-225 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-507 | A | 2025-01-21
|  | 5th floor | QE-226 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-508 | A | 2025-01-21
|  | 5th floor | QE-227 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-509 | A | 2025-01-21
|  | 5th floor | QE-228 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-510 | A | 2025-01-21
|  | 5th floor | QE-229 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-511 | A | 2025-01-21
|  | 5th floor | QE-230 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-512 | A | 2025-01-21
|  | 5th floor | QE-231 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-513 | A | 2025-01-21
|  | 5th floor | QE-232 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-514 | R | 2025-01-21
|  | 5th floor | QE-233 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-515 | A | 2025-01-21
|  | 5th floor | QE-234 | 2025-01-17 | 2025-01-17 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-516 | A | 2025-01-21
|  | 6th floor | QE-235 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-602 | A | 2025-01-23
|  | 5th floor | QE-236 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-603 | A | 2025-01-23
|  | 6th floor | QE-237 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-604 | A | 2025-01-23
|  | 6th floor | QE-238 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-605 | A | 2025-01-23
|  | 6th floor | QE-239 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-606 | A | 2025-01-23
|  | 6th floor | QE-240 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-607 | A | 2025-01-23
|  | 6th floor | QE-241 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-608 | A | 2025-01-23
|  | 6th floor | QE-242 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-609 | A | 2025-01-23
|  | 6th floor | QE-243 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-610 | A | 2025-01-23
|  | 6th floor | QE-244 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-611 | A | 2025-01-23
|  | 6th floor | QE-245 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-612 | A | 2025-01-23
|  | 6th floor | QE-246 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-613 | A | 2025-01-23
|  | 6th floor | QE-247 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-614 | A | 2025-01-23
|  | 6th floor | QE-248 | 2025-01-22 | 2025-01-22 | pipe installation | Check Drain, soil and exhaust pipe installation |  | T1-615 | A | 2025-01-23
|  | 3rd floor | QE-249 | 2025-01-23 | 2025-01-23 | Circuit Wiring | Check circuit wiring |  | Corridor | A | 2025-01-23
|  | 1st floor | QE-250 | 2025-01-23 | 2025-01-23 | Circuit Wiring | Check circuit wiring |  |  | A | 2025-01-23
|  | 1st floor | QE-251 | 2025-01-23 | 2025-01-23 | Cable laying | Check cables laying |  | Corridor | A | 2025-01-23
|  | 2nd floor | QE-252 | 2025-01-23 | 2025-01-23 | Cable laying | Check cables laying |  | Corridor | A | 2025-01-23
|  | 3rd floor | QE-253 | 2025-01-23 | 2025-01-23 | Cable laying | Check cables laying |  | Corridor | A | 2025-01-23
|  | 1st floor | QE-254 | 2025-01-24 | 2025-01-24 | cable insulation | Check cable insulation test |  |  | A | 2025-01-24
|  | 2nd floor | QE-255 | 2025-01-24 | 2025-01-24 | cable insulation | Check cable insulation test |  |  | A | 2025-01-24
|  | 3rd floor | QE-256 | 2025-01-24 | 2025-01-24 | cable insulation | Check cable insulation test |  |  | A | 2025-01-24
|  | 1st floor | QE-257 | 2025-01-24 | 2025-01-24 | UPVC | Check UPVC Head test |  |  | A | 2025-01-24
|  | 2nd floor | QE-258 | 2025-01-24 | 2025-01-24 | UPVC | Check UPVC Head test |  |  | A | 2025-01-24
|  | 3rd floor | QE-259 | 2025-01-24 | 2025-01-24 | UPVC | Check UPVC Head test |  |  | A | 2025-01-24
|  | 3rd floor | QE-260 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-309 | A | 2025-03-01
|  | 3rd floor | QE-261 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-312 | A | 2025-03-01
|  | 5th floor | QE-262 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-514 | A | 2025-03-01
|  | 6th floor | QE-263 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-601 | B | 2025-03-01
|  | 6th floor | QE-264 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-616 | A | 2025-03-01
|  | 7th floor | QE-265 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-701 | A | 2025-02-27
|  | 7th floor | QE-266 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-702 | A | 2025-02-27
|  | 7th floor | QE-267 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-703 | A | 2025-02-27
|  | 7th floor | QE-268 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-704 | A | 2025-02-28
|  | 7th floor | QE-269 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-705 | A | 2025-02-28
|  | 7th floor | QE-270 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-706 | A | 2025-02-28
|  | 7th floor | QE-271 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-707 | A | 2025-02-28
|  | 7th floor | QE-272 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-708 | A | 2025-02-27
|  | 7th floor | QE-273 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-709 | A | 2025-02-27
|  | 7th floor | QE-274 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-710 | A | 2025-02-27
|  | 7th floor | QE-275 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-711 | A | 2025-02-27
|  | 7th floor | QE-276 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-712 | A | 2025-02-27
|  | 7th floor | QE-277 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-714 | A | 2025-02-27
|  | 7th floor | QE-278 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-715 | A | 2025-02-27
|  | 7th floor | QE-279 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-716 | A | 2025-02-27
|  | 7th floor | QE-280 | 2025-02-25 | 2025-02-25 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-713 | A | 2025-02-27
|  | 1-3rd floor | QE-281 | 2025-02-25 | 2025-02-25 | pipe installation | Check CPVC Pipe installation |  | corridor 1-rd floor | A | 2025-02-25
|  | 9th floor | QE-282 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-901 | B | 2025-03-01
|  | 9th floor | QE-283 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-902 | A | 2025-03-01
|  | 9th floor | QE-284 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-903 | B | 2025-03-01
|  | 9th floor | QE-285 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-904 | B | 2025-03-01
|  | 9th floor | QE-286 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-905 | B | 2025-03-01
|  | 9th floor | QE-287 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-906 | B | 2025-03-01
|  | 9th floor | QE-288 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-907 | B | 2025-03-01
|  | 9th floor | QE-289 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-908 | B | 2025-03-01
|  | 9th floor | QE-290 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-909 | B | 2025-03-01
|  | 9th floor | QE-291 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-910 | B | 2025-03-01
|  | 9th floor | QE-292 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-911 | B | 2025-03-01
|  | 9th floor | QE-293 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-912 | B | 2025-03-01
|  | 9th floor | QE-294 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-913 | B | 2025-03-01
|  | 9th floor | QE-295 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-914 | B | 2025-03-01
|  | 9th floor | QE-296 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-915 | B | 2025-03-01
|  | 9th floor | QE-297 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-916 | B | 2025-03-01
|  | 4th floor | QE-298 | 2025-02-26 | 2025-02-26 | Cable laying | Check cable laying |  |  | A | 2025-02-28
|  | 4th floor | QE-299 | 2025-02-26 | 2025-02-26 | Cable laying | Check cable laying |  |  | A | 2025-02-28
|  | 1-4th floor | QE-300 | 2025-02-26 | 2025-02-26 | Fire alarm system | Check wiring for whole fire alarm system |  |  | A | 2025-02-27
|  | 1-4th floor | QE-301 | 2025-02-26 | 2025-02-26 | wiring for public | Check installation of wiring for public address |  |  | A | 2025-02-27
|  | 9th floor | QE-302 | 2025-02-26 | 2025-02-26 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-921 | A | 2025-02-27
|  | 8th floor | QE-303 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-801 | B | 2025-03-09
|  | 8th floor | QE-304 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-802 | B | 2025-03-09
|  | 8th floor | QE-305 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-803 | B | 2025-03-09
|  | 8th floor | QE-306 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-804 | B | 2025-03-09
|  | 8th floor | QE-307 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-805 | A | 2025-03-09
|  | 8th floor | QE-308 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-806 | B | 2025-03-09
|  | 8th floor | QE-309 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-807 | B | 2025-03-09
|  | 8th floor | QE-310 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-808 | B | 2025-03-09
|  | 8th floor | QE-311 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-809 | B | 2025-03-09
|  | 8th floor | QE-312 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-810 | B | 2025-03-09
|  | 8th floor | QE-313 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-811 | A | 2025-03-09
|  | 8th floor | QE-314 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-812 | A | 2025-03-09
|  | 8th floor | QE-315 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-813 | A | 2025-03-01
|  | 8th floor | QE-316 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-814 | A | 2025-03-01
|  | 8th floor | QE-317 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-815 | A | 2025-03-01
|  | 8th floor | QE-318 | 2025-02-28 | 2025-02-28 | pipe installation | Check drain, soil and exhaust pipe installation |  | T1-816 | A | 2025-03-01
|  | 3rd to 6th floor | QE-319 | 2025-03-11 | 2025-03-11 | valves installation | Check ball valves installation size 1-1/4'' |  |  | A | 2025-03-13
|  | 1st to 2nd floor | QE-320 | 2025-03-11 | 2025-03-11 | valves installation | Check ball valves installation size 3/4'' |  |  | A | 2025-03-13
|  | 1st to 4th floor | QE-321 | 2025-03-11 | 2025-03-11 | alarm system | check wiring for whole fire alarm system (conduiting |  |  | A | 2025-03-13
|  | 1st to 4th floor | QE-322 | 2025-03-11 | 2025-03-11 | public address | Check installation of wiring for public address |  |  | A | 2025-03-13
|  | 1st to 5th floor | QE-323 | 2025-03-11 | 2025-03-11 | conduiting | Check conduiting for CCTV System |  |  | A | 2025-03-13
|  | 4th floor | QE-324 | 2025-03-11 | 2025-03-11 | Drain installation | Check AC Drain installation |  |  | A | 2025-03-13
|  | 5th floor | QE-325 | 2025-03-11 | 2025-03-11 | Drain installation | Check AC Drain installation |  |  | A | 2025-03-13
|  | 6th floor | QE-326 | 2025-03-13 | 2025-03-13 | Drain installation | Check AC Drain installation |  |  | A | 2025-03-14
|  | 7th floor | QE-327 | 2025-03-13 | 2025-03-13 | Drain installation | Check AC Drain installation |  |  | A | 2025-03-14
|  | 8th floor | QE-328 | 2025-03-13 | 2025-03-13 | Drain installation | Check AC Drain installation |  |  | A | 2025-03-14
|  | 5th floor | QE-329 | 2025-03-13 | 2025-03-13 | cable laying | Check Power cable laying |  |  | A | 2025-03-14
|  | 6th floor | QE-330 | 2025-03-13 | 2025-03-13 | cable laying | Check Power cable laying |  |  | A | 2025-03-14
|  | 8th floor | QE-331 | 2025-03-14 | 2025-03-14 | pipe installation | Check drain and soil pipe installation |  |  | A | 2025-03-18
|  | 8th floor | QE-332 | 2025-03-14 | 2025-03-14 | pipe installation | Check drain and soil pipe installation |  |  | A | 2025-03-18
|  | 8th floor | QE-333 | 2025-03-14 | 2025-03-14 | pipe installation | Check drain and soil pipe installation |  |  | A | 2025-03-18
|  | 8th floor | QE-334 | 2025-03-14 | 2025-03-14 | pipe installation | Check drain and soil pipe installation |  |  | A | 2025-03-18
|  | 8th floor | QE-335 | 2025-03-14 | 2025-03-14 | pipe installation | Check drain and soil pipe installation |  |  | A | 2025-03-18
|  | 8th floor | QE-336 | 2025-03-14 | 2025-03-14 | pipe installation | Check drain and soil pipe installation |  |  | A | 2025-03-18
|  | 8th floor | QE-337 | 2025-03-14 | 2025-03-14 | pipe installation | Check drain and soil pipe installation |  |  | A | 2025-03-18
|  | 8th floor | QE-338 | 2025-03-14 | 2025-03-14 | pipe installation | Check drain and soil pipe installation |  |  | A | 2025-03-18
|  | 1st to 9th floor | QE-339 | 2025-03-14 | 2025-03-14 | pipe installation | Check drain and soil pipe installation |  |  | A | 2025-03-15
|  | 4th floor | QE-340 | 2025-03-17 | 2025-03-15 | CPVC Pipe installation | Check CPVC Pipe installation |  |  | A | 2025-03-18
|  | 6th floor | QE-341 | 2025-03-17 | 2025-03-17 | Cable laying | Check cable laying |  |  | A | 2025-03-18
|  | 7th floor | QE-342 | 2025-03-17 | 2025-03-17 | Cable laying | Check cable laying |  |  | A | 2025-03-17
|  | Ground floor | QE-343 | 2025-03-17 | 2025-03-17 | Cable laying | Check cable laying |  |  | A | 2025-03-17
|  | Ground floor | QE-344 | 2025-03-17 | 2025-03-17 | Tray installation | check cable tray installation |  |  | A | 2025-03-17
|  | Ground floor | QE-345 | 2025-03-17 | 2025-03-17 | conduiting | Check electrical conduit installation |  |  | A | 2025-03-17
|  | Ground floor | QE-346 | 2025-04-24 | 2025-04-24 | Drain installation | Check drain, soil and vent pipe installation |  | Lobby area | A | 2025-04-26
|  | 1st-2nd floor | QE-347 | 2025-04-24 | 2025-04-24 | Drain installation | Check drain, soil and vent pipe installation |  |  | A | 2025-04-26
|  | 1st floor | QE-348 | 2025-04-24 | 2025-04-24 | core cuts | Check core cuts |  |  | A | 2025-04-26
|  | 1st to 5th floor | QE-349 | 2025-04-24 | 2025-04-24 | pipe installation | Check balcony drain and rain water pipe installation |  | balconies | A | 2025-04-26
|  | 1st to 6th floor | QE-350 | 2025-04-24 | 2025-04-24 | core cuts | Check core cuts of Acs changing from bulk head to washroom |  |  | A | 2025-04-26
|  | Ground floor | QE-351 | 2025-04-25 | 2025-04-25 | cable laying | Check cable laying in electrical room to DBs |  |  | A | 2025-04-26
|  | 1st-4th floor | QE-352 | 2025-04-25 | 2025-04-25 | cable laying | Check cable layihg from electrical room to exhaust fans |  |  | A | 2025-04-26
|  | Ground floor | QE-353 | 2025-04-25 | 2025-04-25 | cleanout | Cleanout for 150 mm dia pipe with horizontal |  |  | A | 2025-04-26
|  | Ground floor | QE-354 | 2025-04-25 | 2025-04-25 | conduiting | Check conduiting for cable laying |  |  | A | 2025-04-26
|  | 1st to 6th floor | QE-355 | 2025-04-25 | 2025-04-25 | location change | buld head to washroom location AC drains installation |  |  | A | 2025-04-26
|  | 1st to 6th floor | QE-356 | 2025-04-25 | 2025-04-25 | venti drain | Venti drain pipe change to 32 mm |  |  | A | 2025-04-26
|  | 8th floor | QE-357 | 2025-05-13 | 2025-05-13 | Circuit Wiring | circuit wiring |  |  | A | 2025-05-14
|  | Ground floor | QE-358 | 2025-05-13 | 2025-05-13 | conduiting | Installation of electrical conduit |  |  | A | 2025-05-14
|  | 1st to 9th floor | QE-359 | 2025-05-13 | 2025-05-13 | AC drain | Check bulk head to washroom location change AC drain installation |  |  | A | 2025-05-14
|  | 3rd, 4th floor | QE-360 | 2025-05-13 | 2025-05-13 | Drain installation | Drain soil and vent pipe installation |  |  | A | 2025-05-14
|  | 7th to 9th floor | QE-361 | 2025-05-13 | 2025-05-13 | pipe installation | Check venti drain pipe change to 32mm |  |  | A | 2025-05-14
|  | 9th floor | QE-362 | 2025-05-15 | 2025-05-15 | boxes installation | Check boxes installation, PPRC installation |  | 901-905 | A | 2025-05-16
|  | 9th floor | QE-363 | 2025-05-15 | 2025-05-15 | boxes installation | Check boxes installation, PPRC installation |  | 906-911 | A | 2025-05-16
|  | 9th floor | QE-364 | 2025-05-15 | 2025-05-15 | boxes installation | Check boxes installation, PPRC installation |  | 912-916 | A | 2025-05-16
|  | 8th, 9th | QE-365 | 2025-05-15 | 2025-05-15 | cable installation | Check cable tray installation in corridor |  |  | A | 2025-05-16
|  | 7th to 9th floor | QE-366 | 2025-05-15 | 2025-05-15 | AC changing | Check core cuts of Acs changing from bulk head to washroom |  |  | A | 2025-05-16
|  | 1st to 8th | QE-367 | 2025-05-16 | 2025-05-16 | Drain installation | Check dishwasher drain pipe 50mm |  |  | A | 2025-05-17
|  | 9th floor | QE-368 | 2025-05-16 | 2025-05-16 | AC drain | AC drain installation |  |  | A | 2025-05-17
|  | 9th floor | QE-369 | 2025-05-17 | 2025-05-17 | Circuit Wiring | Check circuit wiring |  |  | OP
|  | 7th floor | QE-370 | 2025-05-21 | 2025-05-21 | cable laying | check cable laying |  |  | A | 2025-05-20
|  | 5TH TO 8th | QE-371 | 2025-05-21 | 2025-05-21 | pipe installation | Check CPVC Pipe installation |  |  | A | 2025-05-21
|  | 5th to 6th | QE-372 | 2025-05-21 | 2025-05-21 | pipe installation | Check Drain, soil, and vent pipe installation |  |  | A | 2025-05-21
|  | 8th floor | QE-373 | 2025-05-21 | 2025-05-21 | cable laying | check cable laying |  |  | R | 2025-05-22
|  | 3rd to 5th | QE-374 | 2025-05-21 | 2025-05-21 | valves installation | check ball valbes installation |  |  | A | 2025-05-21
|  | 8th floor | QE-375
|  | 8th floor | QE-376
|  | 8th floor | QE-377
|  | 8th floor | QE-378
|  | 10th floor | QE-379 | 2025-08-08 | 2025-08-08 | pipe installation | Check drain, soil and vent pipe installation |  |  | A | 2025-08-11 |  |  | Matten sab
|  | 10th floor | QE-380 | 2025-08-08 | 2025-08-08 | valves installation | Installation of Lpg Pipe 3/4" & Valves |  |  | A | 2025-08-11 |  |  | Matten sab
|  | 8th floor | QE-381 | 2025-09-25 | 2025-09-25 | pipe installation | Upvc Exhaust Pipe |  |  | A | 2025-09-29
|  | 8th floor | QE-382 | 2025-09-25 | 2025-09-25 | Tray installation | Cable tray installation in corridors 10th floor |  |  | A | 2025-09-29
|  | 8th floor | QE-383 | 2025-09-25 | 2025-09-25 | conduit & back box | Electrical Conduit and back boxes installation |  | 11th floor | A | 2025-09-29
|  | 8th floor | QE-384 | 2025-09-25 | 2025-09-25 | pipe installation | Upvc Exhaust Pipe |  | 11th floor | A | 2025-09-29
|  | 8th floor | QE-385 | 2025-09-27 | 2025-09-27 | LPG Pipe | Installation of LPG pipe Dia 3/4" & Valves |  | 5th floor | A | 2025-09-29
|  | 8th floor | QE-386 | 2025-09-27 | 2025-09-27 | conduit & back box | Electrical Conduit and back boxes installation |  | 10TH floor | A | 2025-09-29
|  | 8th floor | QE-387 | 2025-09-27 | 2025-09-27 | Cable | Cable laying |  | 8th floor | A | 2025-09-29
|  | 8th floor | QE-388 | 2025-09-27 | 2025-09-27 | conduit & back box | Electrical Conduit and back boxes installation |  | 9th floor | A | 2025-09-29
|  | 8th floor | QE-389 | 2025-09-27 | 2025-09-27 | conduit & back box | Electrical Conduit and back boxes installation |  | 8th floor | A | 2025-09-29
|  | 8th floor | QE-390 | 2025-09-27 | 2025-09-27 | LPG Pipe | Installation of LPG pipe Dia 3/4" & Valves |  | 6th floor | A | 2025-09-29
|  | 8th floor | QE-391 | 2025-10-21 | 2025-10-21 | Tray installation | Cable tray installation in 10, 11th floor |  | 10th and 11th floor | A | 2025-10-21
|  | 8th floor | QE-392 | 2025-10-21 | 2025-10-21 | LPG Pipe | Installation of LPG pipe Dia 3/4" & Valves |  | 7-9th floor | R | 2025-10-21
|  | 8th floor | QE-393 | 2025-10-21 | 2025-10-21 | cable | Metering panel to appartment Cable Laying |  | 9th floor | A | 2025-10-21
|  | 8th floor | QE-394 | 2025-10-21 | 2025-10-21 | CCtv | Conduiting For CCTV system |  | 6-9th floor | A | 2025-10-21
|  | 8th floor | QE-395 | 2025-10-21 | 2025-10-21 | Conduiting | Wiring for whole fir alaram system |  | 5-7th floor | A | 2025-10-21
|  | 8th floor | QE-396 | 2025-10-21 | 2025-10-21 | Conduiting | Wiring for whole Public adress system system |  | 5-7th floor | A | 2025-10-21
|  | 8th floor | QE-397 | 2025-10-21 | 2025-10-21 | Cable | Power Cable Apartments Cable |  | 10th floor | R | 2025-10-21
|  | 8th floor | QE-398 | 2025-10-21 | 2025-10-21 | pipe installation | Rain Drain, Balcony pipe installation |  | 6th floor To 8th Floor | A | 2025-10-22
|  | 8th floor | QE-399 | 2025-11-26 | 2025-11-26 | LPG Pipe | Installation of LPG pipe Dia 3/4" & Valves |  | 7th to 9th floor | OP
|  | 8th floor | QE-400 | 2025-11-26 | 2025-11-26 | LPG Pipe | Installation of LPG pipe Dia 3/4" & Valves |  | 1-4,10th floor | OP
|  | 8th floor | QE-401 | 2025-11-26 | 2025-11-26 | Cable | Installation Cable laying |  | 10th floor | OP
|  | 8th floor | QE-402 | 2025-11-26 | 2025-11-26 | pipe installation | Balcony Drain pipe installation |  | 9th floor | OP
|  | 8th floor | QE-403 | 2025-11-26 | 2025-11-26 | Wire | circuit wiring |  | 10th floor | OP
|  | 8th floor | QE-404 | 2025-11-26 | 2025-11-26 | wiring for FAS | Wiring for Fire Alaram System |  | 5 to 7th floor | OP
|  | 8th floor | QE-405 | 2025-11-26 | 2025-11-26 | wiring for PAS | Wiring for Public Adress System |  | 5 to 7th floor | OP
|  | 8th floor | QE-406 | 2025-11-26 | 2025-11-26 | pipe installation | Water Pipe Installation |  | 9th floor Corridor | OP
|  | 8th floor | QE-407 | 2025-11-26 | 2025-11-26 | pipe installation | Drain Pipe Installation |  | GF | OP
|  | 8th floor | QE-408 | 2025-11-26 | 2025-11-26 | UPVC | UPVC Drain Pipe Installation |  | GF Gaming Zone | OP
|  | 8th floor | QE-409 | 2025-11-27 | 2025-11-27 | valves installation | installation of 3/4" ball valves |  |  | OP
|  | 8th floor | QE-410 | 2025-11-27 | 2025-11-27 | valves installation | installation of 1/4" ball valves |  |  | OP
|  | 8th floor | QE-411
|  | 8th floor | QE-412
|  | 8th floor | QE-413
|  | 8th floor | QE-414
|  | 8th floor | QE-415
|  | 8th floor | QE-416
|  | 8th floor | QE-417
|  | 8th floor | QE-418
|  | 8th floor | QE-419
|  | 8th floor | QE-420
|  | 8th floor | QE-421
|  | 8th floor | QE-422
|  | 8th floor | QE-423
|  | 8th floor | QE-424
|  | 8th floor | QE-425
|  | 8th floor | QE-426
|  | 8th floor | QE-427
|  | 8th floor | QE-428
|  | 8th floor | QE-429
|  | 8th floor | QE-430
|  | 8th floor | QE-431
|  | 8th floor | QE-432
|  | 8th floor | QE-433
|  | 8th floor | QE-434
|  | 8th floor | QE-435
|  | 8th floor | QE-436
|  | 8th floor | QE-437
|  | 8th floor | QE-438
|  | 8th floor | QE-439
|  | 8th floor | QE-440
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
8th floor
|  | 8th floor | QE-555 |  |  | pipe installation
|  | 8th floor | QE-556 |  |  | pipe installation
|  | 8th floor | QE-557 |  |  | pipe installation
|  | 8th floor | QE-558 |  |  | pipe installation
|  | 8th floor | QE-559 |  |  | pipe installation
|  | 8th floor | QE-560 |  |  | pipe installation
|  | 8th floor | QE-561 |  |  | pipe installation
|  | 8th floor | QE-562 |  |  | pipe installation
|  | 8th floor | QE-563 |  |  | pipe installation
|  | 8th floor | QE-564 |  |  | pipe installation
|  | 8th floor | QE-565 |  |  | pipe installation
|  | 8th floor | QE-566 |  |  | pipe installation
|  | 8th floor | QE-567 |  |  | pipe installation
|  | 8th floor | QE-568
|  | 8th floor | QE-569
|  | 8th floor | QE-570
|  | 8th floor | QE-571
|  | 8th floor | QE-572
|  | 8th floor | QE-573
|  | 8th floor | QE-574
|  | 8th floor | QE-575
|  | 8th floor | QE-576
|  | 8th floor | QE-577
|  | 8th floor | QE-578
|  | 8th floor | QE-579
|  | 8th floor | QE-580
|  | 8th floor | QE-581
|  | 8th floor | QE-582
|  | 8th floor | QE-583
|  | 8th floor | QE-584
|  | 8th floor | QE-585
|  | 8th floor | QE-586
|  | 8th floor | QE-587
|  | 8th floor | QE-588
|  | 8th floor | QE-589
|  | 8th floor | QE-590
|  | 8th floor | QE-591
|  | 8th floor | QE-592
|  | 8th floor | QE-593
|  | 8th floor | QE-594
|  | 8th floor | QE-595
|  | 8th floor | QE-596
|  | 8th floor | QE-597
|  | 8th floor | QE-598
|  | 8th floor | QE-599
|  | 8th floor | QE-600
|  | 8th floor | QE-601
|  | 8th floor | QE-602
|  | 8th floor | QE-603
|  | 8th floor | QE-604
|  | 8th floor | QE-605
|  | 8th floor | QE-606
|  | 8th floor | QE-607
|  | 8th floor | QE-608
|  | 8th floor | QE-609
|  | 8th floor | QE-610
|  | 8th floor | QE-611
|  | 8th floor | QE-612
|  | 8th floor | QE-613
|  | 8th floor | QE-614
|  | 8th floor | QE-615
|  | 8th floor | QE-616
|  | 8th floor | QE-617
|  | 8th floor | QE-618
|  | 8th floor | QE-619
|  | 8th floor | QE-620
|  | 8th floor | QE-621
|  | 8th floor | QE-622
|  | 8th floor | QE-623
|  | 8th floor | QE-624
|  | 8th floor | QE-625
|  | 8th floor | QE-626
|  | 8th floor | QE-627
|  | 8th floor | QE-628
|  | 8th floor | QE-629
|  | 8th floor | QE-630
|  | 8th floor | QE-631
|  | 8th floor | QE-632
|  | 8th floor | QE-633
|  | 8th floor | QE-634
|  | 8th floor | QE-635
|  | 8th floor | QE-636
|  | 8th floor | QE-637
|  | 8th floor | QE-638
|  | 8th floor | QE-639
|  | 8th floor | QE-640
|  | 8th floor | QE-641
|  | 8th floor | QE-642
|  | 8th floor | QE-643
|  | 8th floor | QE-644
|  | 8th floor | QE-645
|  | 8th floor | QE-646
|  | 8th floor | QE-647
|  | 8th floor | QE-648
|  | 8th floor | QE-649
|  | 8th floor | QE-650
|  | 8th floor | QE-651
|  | 8th floor | QE-652
|  | 8th floor | QE-653
|  | 8th floor | QE-654
|  | 8th floor | QE-655
|  | 8th floor | QE-656
|  | 8th floor | QE-657
|  | 8th floor | QE-658
|  | 8th floor | QE-659
|  | 8th floor | QE-660
|  | 8th floor | QE-661
|  | 8th floor | QE-662
|  | 8th floor | QE-663
|  | 8th floor | QE-664
|  | 8th floor | QE-665
|  | 8th floor | QE-666
|  | 8th floor | QE-667
|  | 8th floor | QE-668
|  | 8th floor | QE-669
|  | 8th floor | QE-670
|  | 8th floor | QE-671
|  | 8th floor | QE-672
|  | 8th floor | QE-673
|  | 8th floor | QE-674
|  | 8th floor | QE-675
|  | 8th floor | QE-676
|  | 8th floor | QE-677
|  | 8th floor | QE-678
|  | 8th floor | QE-679
|  | 8th floor | QE-680
|  | 8th floor | QE-681
|  | 8th floor | QE-682
|  | 8th floor | QE-683
|  | 8th floor | QE-684
|  | 8th floor | QE-685
|  | 8th floor | QE-686
|  | 8th floor | QE-687
|  | 8th floor | QE-688
|  | 8th floor | QE-689
QE-690
QE-691
QE-692
QE-693
QE-694
QE-695
QE-696
QE-697
QE-698
QE-699
QE-700
2023-08-02

## Captive Air I Tower
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 25
[9 empty] | Approved with comments (B) |  | 7
[9 empty] | Rejected ( R) |  | 3
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 35
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | 1st Floor | IT/1 | 2024-10-25 | 2024-10-25 | pipe installation | Installation of MS pipe in corridor |  |  | B | 2024-10-28
2 |  | 2nd floor | IT/2 | 28-Oct+24 | 28-Oct+24 | pipe installation | Check MS pipe in corridor & apartments |  | 201-216 | B | 2024-10-29
3 |  | 3rd floor | IT/3 | 28-Oct+24 | 28-Oct+24 | pipe installation | Check MS pipe in corridor & apartments |  | 301-316 | B | 2024-10-29
4 |  | 4th floor | IT/4 | 2024-10-25 | 2024-10-25 | pipe installation | Check installtion of MS pipe in corridor & apartments |  | 301-316 | B | 2024-10-28
5 |  | 4th floor | IT/5 | 2024-11-20 | 2024-11-20 | pipe installation | Check installtion of MS pipe in corridor & apartments |  | 401-416 | B | 2024-11-21
6 |  | 5th floor | IT/6 | 2024-11-21 | 2024-11-21 | pipe installation | Check MS pipe installation Corridors |  |  |  | 2024-11-21
7 |  | 1st floor | IT/7 | 2024-12-19 | 2024-12-19 | pipe installation | Check MS Pipe installation & pressure test |  |  | B | 2024-12-20
8 |  | 2nd floor | IT/8 | 2024-12-26 | 2024-12-26 | Pipe and Pressure test | Check MS Pipe installation and pressure test |  |  | A | 2024-12-27
9 |  | 3rd floor | IT/9 | 2024-12-26 | 2024-12-26 | Pipe and Pressure test | Check MS Pipe installation and pressure test |  |  | A | 2024-12-27
10 |  | 4th floor | IT/10 | 2024-12-26 | 2024-12-26 | Pipe and Pressure test | Check MS Pipe installation and pressure test |  |  | A | 2024-12-27
11 |  | 6th floor | IT/11 | 2024-12-30 | 2024-12-30 | MS pipe installation | Check MS Pipe installation in corridors |  |  | B | 2024-12-30
12 |  | 5th floor | IT/12 | 2025-01-28 | 2025-01-28 | pipe installation | Check MS Pipe in corridor |  |  | A | 2025-01-30
13 |  | 6th floor | IT/13 | 2025-01-28 | 2025-01-28 | pipe installation | Check MS Pipe in corridor |  |  | A | 2025-01-30
14 |  | 7th floor | IT/14 | 2025-01-28 | 2025-01-28 | pipe installation | Check MS Pipe in corridor |  |  | A | 2025-01-30
15 |  | 8th floor | IT/15 | 2025-01-28 | 2025-01-28 | pipe installation | Check MS Pipe in corridor |  |  | A | 2025-01-30
16 |  | 9th floor | IT/16 | 2025-01-28 | 2025-01-28 | pipe installation | Check MS Pipe in corridor |  |  | A | 2025-01-30
17 |  | Ground floor | IT/17 | 2025-03-13 | 2025-03-13 | pipe installation | Check MS pipe in corridor |  |  | A | 2025-03-15
18 |  | 6th floor | IT/18 | 2025-03-13 | 2025-03-13 | pipe installation | Check MS pipe in corridor & apartments |  |  | A | 2025-03-14
19 |  | 7th floor | IT/19 | 2025-03-13 | 2025-03-13 | pipe installation | Check MS pipe in corridor and apartments |  |  | A | 2025-03-14
20 |  | 8th floor | IT/20 | 2025-05-16 | 2025-05-16 | pipe installation | Check MS pipe in corridor and apartments |  |  | A | 2025-05-20
21 |  | 9th floor | IT/21 | 2025-05-16 | 2025-05-16 | pipe installation | Check MS pipe in corridor and apartments |  |  | A | 2025-05-20
22 |  | 10th floor | IT/22 | 2025-05-16 | 2025-05-16 | pipe installation | Check MS pipe in corridor |  |  | A | 2025-05-20
23 |  | 11th floor | IT/23 | 2025-05-16 | 2025-05-16 | pipe installation | Installation of MS pipe in corridor |  |  | A | 2025-05-20
24 |  | 2nd floor | IT/24 | 2025-05-16 | 2025-05-16 | pipe installation | Installation of MS pipe in corridor |  |  | A | 2025-05-20
25 |  | 1st floor | IT/25 | 2025-05-16 | 2025-05-16 | pipe installation | Installation of MS Pipe & sprinkler in apartments |  |  | A | 2025-05-20
26 |  | 2nd floor | IT/26 | 2025-05-16 | 2025-05-16 | pipe installation | Installation of MS Pipe & sprinkler in apartments |  |  | A | 2025-05-20
27 |  | 3rd floor | IT/27 | 2025-05-16 | 2025-05-16 | pipe installation | Installation of MS Pipe & sprinkler in apartments |  |  | A | 2025-05-20
28 |  | 10th floor | IT/28 | 2025-08-02 | 2025-08-02 | pipe installation | Check installtion of MS pipe in corridor & apartments |  |  | A | 2025-08-04
29 |  | 11th floor | IT/29 | 2025-08-02 | 2025-08-02 | pipe installation | Check installtion of MS pipe in corridor & apartments |  |  | A | 2025-08-04
30 |  | 4th floor | IT/30 | 2025-08-02 | 2025-08-02 | pipe installation | Installation of MS Pipe & sprinkler in apartments |  |  | A | 2025-08-04
31 |  | 5th floor | IT/31 | 2025-08-02 | 2025-08-02 | pipe installation | Installation of MS Pipe & sprinkler in apartments |  |  | A | 2025-08-04
32 |  | 6th floor | IT/32 | 2025-08-02 | 2025-08-02 | pipe installation | Installation of MS Pipe & sprinkler in apartments |  |  | A | 2025-08-04
33 |  | 11th floor | IT/33 | 2025-08-02 | 2025-08-02 | pipe installation | Installation of MS Pipe in Riser from GF to 11th floor |  |  | A | 2025-08-04
34 |  |  | IT/34 | 2025-09-19 | 2025-09-19 | pipe installation | Installation of MS Pipe & nSprinklers in 6th floor |  |  | R | 2025-09-20
35 |  |  | IT/35 | 2025-09-19 | 2025-09-19 | pipe installation | Installation of MS Pipe & nSprinklers in 7th floor |  |  | R | 2025-09-20
36 |  |  | IT/36 | 2025-09-19 | 2025-09-19 | pipe installation | Installation of MS Pipe & nSprinklers in 8th floor |  |  | R | 2025-09-20
37 |  |  | IT/37
38 |  |  | IT/38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
2024-08-15
| Sub Structure | Basement | IT/461
| Sub Structure | Basement | IT/462
| Sub Structure | Basement | IT/463
| Sub Structure | Basement | IT/464
| Sub Structure | Basement | IT/465
| Sub Structure | Basement | IT/466
| Sub Structure | Basement | IT/467
| Sub Structure | Basement | IT/468
| Sub Structure | Basement | IT/469
| Sub Structure | Basement | IT/470
| Sub Structure | Basement | IT/471
| Sub Structure | Basement | IT/472
| Sub Structure | Basement | IT/473
| Sub Structure | Basement | IT/474
| Sub Structure | Basement | IT/475
| Sub Structure | Basement | IT/476
| Sub Structure | Basement | IT/477
| Sub Structure | Basement | IT/478
| Sub Structure | Basement | IT/479
| Sub Structure | Basement | IT/480

## Al Hamd
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower)Al Hamd | [5 empty] | Fully Approved (A) |  | 48
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 2 |  | As of : |  | 2025-12-19
[9 empty] | Open/Pending (OP) |  | 1
[9 empty] | Total |  | 51
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR closing Date | Pour Card No. | Concrete Qty (m3) | Attachment | Remarks
1 | Sub Structure | 1st floor | IR-HVAC/01 | 2025-03-15 | 2025-03-15 | Pipe installation | Installation of refrigerant pipes with expended rubber foam insulation, PVC Type wrapping+control wiring from indoor to |  |  | A | 2025-03-17 |  |  | E:\Soft IRs\IIL\I Tower\1.pdf
2 | Sub Structure | 2nd floor | IR-HVAC/02 | 2025-03-15 | 2025-03-15 | Pipe installation | Installation of refrigerant pipes with expended rubber foam insulation, PVC Type wrapping+control wiring from indoor to |  |  | A | 2025-03-17 |  |  | E:\Soft IRs\IIL\I Tower\2.pdf
3 | Sub Structure | 3rd floor | IR-HVAC/03 | 2025-02-28 | 2025-02-28 | Installation of GI Sheet | Supply, fabrication and installation of GI Sheet metal duct |  |  | A | 2025-03-03 |  |  | E:\Soft IRs\IIL\I Tower\3.pdf
4 | Sub Structure | 4th floor | IR-HVAC/04 | 2025-02-28 | 2025-02-28 | Installation of GI Sheet | Supply, fabrication and installation of GI Sheet metal duct |  |  | A | 2025-03-03 |  |  | E:\Soft IRs\IIL\I Tower\4.pdf
5 | Sub Structure | 3rd floor | IR-HVAC/05 | 2025-03-10 | 2025-03-10 | Installation of GI Sheet | Supply, fabrication and installation of GI Sheet metal duct |  |  | A | 2025-03-11 |  |  | E:\Soft IRs\IIL\I Tower\5.pdf
6 | Sub Structure | 4th floor | IR-HVAC/06 | 2025-03-10 | 2025-03-10 | Installation of GI Sheet | Supply, fabrication and installation of GI Sheet metal duct |  |  | A | 2025-03-11 |  |  | E:\Soft IRs\IIL\I Tower\6.pdf
7 | Sub Structure | 5th floor | IR-HVAC/07 | 2025-03-11 | 2025-03-11 | Installation of GI Sheet | Supply, fabrication and installation of GI Sheet metal duct |  |  | A | 2025-03-13 |  |  | E:\Soft IRs\IIL\I Tower\7.pdf
8 | Sub Structure | 6th floor | IR-HVAC/08 | 2025-03-11 | 2025-03-11 | Installation of GI Sheet | Supply, fabrication and installation of GI Sheet metal duct |  |  | A | 2025-03-13 |  |  | E:\Soft IRs\IIL\I Tower\7A.pdf
9 | Sub Structure | 3rd floor | IR-HVAC/09 | 2025-03-17 | 2025-03-17 | Pipe installation | Installation of refrigerant pipes with expended rubber foam insulation, PVC Type wrapping+control wiring from indoor to |  |  | A |  |  |  | E:\Soft IRs\IIL\I Tower\8.pdf
10 | Sub Structure | 4th floor | IR-HVAC/10 | 2025-03-17 | 2025-03-17 | Pipe installation | Installation of refrigerant pipes with expended rubber foam insulation, PVC Type wrapping+control wiring from indoor to |  |  | A |  |  |  | E:\Soft IRs\IIL\I Tower\9.pdf
11 | Sub Structure | 7th floor | IR-HVAC/11 | 2025-03-17 | 2025-03-17 | GI Sheet Installation | Supply, fabrication and installation of GI Sheet metal duct |  |  | A | 2025-05-19 |  |  | E:\Soft IRs\IIL\I Tower\10.pdf
12 | Sub Structure | 2nd to 9th | IR-HVAC/12 | 2025-03-17 | 2025-03-17 | Pipe installation | Installation of refrigerant pipes with expended rubber foam , insulation, pvc tape wrapping. Control wiring from indoor |  |  | A | 2025-05-20 |  |  | E:\Soft IRs\IIL\I Tower\11.pdf
13 | Sub Structure | Basement | IR-HVAC/13 | 2025-07-15 | 2025-07-15 | Light test | G.I sheet metal duct light test |  |  | A | 2025-07-15 |  |  | E:\Soft IRs\IIL\I Tower\12.pdf
14 | Sub Structure | Basement | IR-HVAC/14 | 2025-07-16 | 2025-07-16 | Light test | G.I sheet metal duct light test |  |  | A | 2025-07-16 |  |  | E:\Soft IRs\IIL\I Tower\13.pdf
15 | Sub Structure | Basement | IR-HVAC/15 | 2025-07-17 | 2025-07-17 | Light test | G.I sheet metal duct light test |  |  | A | 2025-07-17 |  |  | E:\Soft IRs\IIL\I Tower\14.pdf
16 | Sub Structure | Basement | IR-HVAC/16 | 2025-07-18 | 2025-07-18 | Light test | G.I sheet metal duct light test |  |  | A | 2025-07-18 |  |  | E:\14.Soft IRs\IIL\I Tower\15.pdf
17 | Sub Structure | Basement | IR-HVAC/17 | 2025-07-22 | 2025-07-22 | Light test | G.I sheet metal duct light test |  |  | A | 2025-07-22 |  |  | E:\14.Soft IRs\IIL\I Tower\16.pdf
18 | Sub Structure | Basement | IR-HVAC/18 | 2025-07-23 | 2025-07-23 | GI Sheet Installation | Supply, fabrication and installation of GI Sheet metal duct |  |  | A | 2025-07-26 |  |  | E:\14.Soft IRs\IIL\I Tower\17.pdf
19 | Sub Structure | Basement | IR-HVAC/19 | 2025-07-23 | 2025-07-23 | Pipe installation | Installation of refrigerant pipes with expended rubber foam , insulation, pvc tape wrapping. Control wiring from indoor |  |  | A | 2025-07-29 |  |  | E:\14.Soft IRs\IIL\I Tower\18.pdf
20 | Sub Structure | Basement | IR-HVAC/20 | 2025-07-26 | 2025-07-26 | Light test | G.I sheet metal duct light test |  |  | A | 2025-07-26 |  |  | E:\14.Soft IRs\IIL\I Tower\19.pdf
21 | Sub Structure | Basement | IR-HVAC/21 | 2025-08-01 | 2025-08-01 | Light test | G.I sheet metal duct light test |  |  | A | 2025-08-02 |  |  | E:\14.Soft IRs\IIL\I Tower\20.pdf
22 | Sub Structure | Basement | IR-HVAC/22 | 2025-08-12 | 2025-08-12 | Light test | G.I sheet metal duct light test |  |  | A | 2025-08-12 |  |  | E:\14.Soft IRs\IIL\I Tower\21.pdf
23 | Sub Structure | Basement | IR-HVAC/23 | 2025-08-23 | 2025-08-23 | Pressure test | Refrigerent pipe pressure test |  |  | OP | 2025-08-12
24 | Sub Structure | Basement | IR-HVAC/24 | 2025-08-25 | 2025-08-25 | Pipe installation | Installation of refrigerant pipes with expended rubber foam , insulation, pvc tape wrapping. Control wiring from indoor |  |  | A | 2025-08-26
25 | Sub Structure | Basement | IR-HVAC/25 | 2025-09-08 | 2025-09-08 | refrigearant pipr | Installation of refrigerant pipes with expended rubber foam insulation, PVC Type wrapping+control wiring from indoor to | 701-716 |  | A | 2025-09-18
26 | Sub Structure | Basement | IR-HVAC/26 | 2025-09-08 | 2025-09-08 | refrigearant pipr | Installation of refrigerant pipes with expended rubber foam insulation, PVC Type wrapping+control wiring from indoor to | 801-816 |  | A | 2025-09-19
27 | Sub Structure | 9th Floor | IR-HVAC/27 | 2025-09-08 | 2025-09-08 | GI Sheet Installation | Supply, fabrication and installation of GI Sheet metal duct | 9th floor |  | A | 2025-09-22
28 | Sub Structure | Basement | IR-HVAC/28 | 2025-09-08 | 2025-09-08 | Light test | G.I sheet metal duct light test | 9th floor |  | A | 2025-09-11
29 | Sub Structure | Basement | IR-HVAC/29 | 2025-09-10 | 2025-09-10 | Piping | Installation of Copper Piping | 202-206, 208, 213-216 |  | A | 2025-09-11
30 | Sub Structure | Basement | IR-HVAC/30 | 2025-09-10 | 2025-09-10 | Piping | Installation of Copper Piping | 302-305, 307, 309-316 |  | A | 2025-09-11
31 | Sub Structure | Basement | IR-HVAC/31 | 2025-09-10 | 2025-09-10 | Piping | Installation of Copper Piping | 402,404,408-416 |  | A | 2025-09-11
32 | Sub Structure | Basement | IR-HVAC/32 | 2025-09-10 | 2025-09-10 | Piping | Installation of Copper Piping | 502,504,514-516 |  | A | 2025-09-11
33 | Sub Structure | Basement | IR-HVAC/33 | 2025-09-10 | 2025-09-10 | Piping | Installation of Copper Piping | 602-616 |  | A | 2025-09-11
34 | Sub Structure | Basement | IR-HVAC/34 | 2025-09-10 | 2025-09-10 | Piping | Installation of Copper Piping | 702-716 |  | A | 2025-09-11
35 | Sub Structure | Basement | IR-HVAC/35 | 2025-09-10 | 2025-09-10 | Piping | Installation of Copper Piping | 804,809-816 |  | A | 2025-09-11
36 | Sub Structure | Basement | IR-HVAC/36 | 2025-09-16 | 2025-09-16 | Piping | Installation of refrigerant pipes with expended rubber foam , insulation, pvc tape wrapping. Control wiring from indoor | 901-916 |  | A | 2025-09-19
37 | Sub Structure | Basement | IR-HVAC/37 | 2025-10-24 | 2025-10-24 | Piping | Installation of Copper piping | 904-916 |  | A | 2025-10-25
38 | Sub Structure | Basement | IR-HVAC/38 | 2025-10-01 | 2025-10-01 | Light test | G.I sheet metal duct light test | 10th floor corridor |  | A | 2025-10-02
39 | Sub Structure | Basement | IR-HVAC/39 | 2025-10-14 | 2025-10-14 | GI Sheet Installation | Supply, fabrication and installation of GI Sheet metal duct | 10th floor |  | A | 2025-10-14
40 | Sub Structure | Basement | IR-HVAC/40 R01 | 2025-10-23 | 2025-10-23 | Piping | Installation of refrigerant pipes with expended rubber foam , insulation, pvc tape wrapping. Control wiring from indoor | 1001-1016 |  | A | 2025-10-25
41 | Sub Structure | Basement | IR-HVAC/41 R1 | 2025-10-23 | 2025-10-23 | Piping | Installation of refrigerant pipes with expended rubber foam , insulation, pvc tape wrapping. Control wiring from indoor | 101-110 |  | A | 2025-10-25
42 | Sub Structure | Basement | IR-HVAC/42 | 2025-10-18 | 2025-10-18 | Piping | Installation of refrigerant pipes with expended rubber foam , insulation, pvc tape wrapping. Control wiring from indoor | 301-310 |  | R | 2025-10-20
42 | Sub Structure | Basement | IR-HVAC/42 R01 | 2025-10-23 | 2025-10-23 | Piping | Installation of refrigerant pipes with expended rubber foam , insulation, pvc tape wrapping. Control wiring from indoor | 301-310 |  | A | 2025-10-25
43 | Sub Structure | Basement | IR-HVAC/43 | 2025-10-23 | 2025-10-23 | Piping | Installation of refrigerant pipes with expended rubber foam , insulation, pvc tape wrapping. Control wiring from indoor | 201-210 |  | A | 2025-10-25
44 | Sub Structure | Basement | IR-HVAC/44 | 2025-10-23 | 2025-10-23 | Piping | Installation of refrigerant pipes with expended rubber foam , insulation, pvc tape wrapping. Control wiring from indoor | 401-410 |  | A | 2025-10-25
45 | Sub Structure | Basement | IR-HVAC/45 | 2025-10-24 | 2025-10-24 | Light test | G.I sheet metal duct light test | 11th floor |  | A | 2025-10-25
46 | Sub Structure | Basement | IR-HVAC/46 | 2025-10-24 | 2025-10-24 | GI Sheet Installation | Supply, fabrication and installation of GI Sheet metal duct | 11th floor |  | A | 2025-10-25
47 | Sub Structure | Basement | IR-HVAC/47 | 2025-12-10 | 2025-12-10 | GI Sheet Installation | INSTALLATION TESTING & COMMISSIONING OF MS SCH-40 SEAMLESS PIPES | 1TH FLOOR |  | A | 2025-12-12
48 | Sub Structure | Basement | IR-HVAC/48 | 2025-12-11 | 2025-12-11 | Installation | INSTALLATION TESTING & COMMISSIONING OF CI BODY GATE VALUE WITH MATCHING FLANGES | EXTERNAL AREA |  | A | 2025-12-12
49 | Sub Structure | Basement | IR-HVAC/49 | 2025-12-10 | 2025-12-10 | Installation | INSTALLATION TESTING & COMMISSIONING OF MS SCH-40 SEAMLESS PIPES | 2ND FLOOR |  | A | 2025-12-12
50 | Sub Structure | Basement | IR-HVAC/50 | 2025-12-12 | 2025-12-12 | Installation | installation of refrigerent pipes with extended rubber foam insulation ,pvc tape wrapping +control wiring from indoor to outdoor | 10th & 11th floor | 1101-1116 | R | 2025-12-15
51 | Sub Structure | Basement | IR-HVAC/51
52 | Sub Structure | Basement | IR-HVAC/52
53 | Sub Structure | Basement | IR-HVAC/53
54 | Sub Structure | Basement | IR-HVAC/54
55 | Sub Structure | Basement | IR-HVAC/55
56 | Sub Structure | Basement | IR-HVAC/56
57 | Sub Structure | Basement | IR-HVAC/57
58 | Sub Structure | Basement | IR-HVAC/58
59 | Sub Structure | Basement | IR-HVAC/59
60 | Sub Structure | Basement | IR-HVAC/60
61 | Sub Structure | Basement | IR-HVAC/61
62 | Sub Structure | Basement | IR-HVAC/62
63 | Sub Structure | Basement | IR-HVAC/63
64 | Sub Structure | Basement | IR-HVAC/64
65 | Sub Structure | Basement | IR-HVAC/65
66 | Sub Structure | Basement | IR-HVAC/66
67 | Sub Structure | Basement | IR-HVAC/67
68 | Sub Structure | Basement | IR-HVAC/68
69 | Sub Structure | Basement | IR-HVAC/69
70 | I Tower | Ground | IR-HVAC/70
| I Tower | Ground | IR-HVAC/71
72 | I Tower | Ground | IR-HVAC/72
73 | I Tower | Ground | IR-HVAC/73
74 | Sub Structure | Basement | IR-HVAC/74
75 | Sub Structure | Basement | IR-HVAC/75
76 | I Tower | Ground | IR-HVAC/76
77 | I Tower | Ground | IR-HVAC/77
78 | I Tower | Ground | IR-HVAC/78
79 | I Tower | Ground | IR-HVAC/79
80 | I Tower | Ground | IR-HVAC/80
81 | I Tower | Ground | IR-HVAC/81
82 | I Tower | Ground | IR-HVAC/82
83 | I Tower | Ground | IR-HVAC/83
84 | Sub Structure | Basement | IR-HVAC/84
85 | I Tower | Ground | IR-HVAC/85
86 | I Tower | Ground | IR-HVAC/86
87 | I Tower | Ground | IR-HVAC/87
88 | I Tower | Ground | IR-HVAC/88
89 | I Tower | Ground | IR-HVAC/89
90 | I Tower | Ground | IR-HVAC/90
91 | I Tower | Ground | IR-HVAC/91
92 | I Tower | Ground | IR-HVAC/92
93 | I Tower | Ground | IR-HVAC/93
94 | I Tower | Ground | IR-HVAC/94
95 | I Tower | Ground | IR-HVAC/95
96 | I Tower | Ground | IR-HVAC/96
97 | I Tower | Ground | IR-HVAC/97
98 | I Tower | Ground | IR-HVAC/98
99 | I Tower | Ground | IR-HVAC/99
100 | I Tower | Ground | IR-HVAC/100
101 | I Tower | Ground | IR-HVAC/101
102 | I Tower | Ground | IR-HVAC/102
103 | I Tower | Ground | IR-HVAC/103
104 | I Tower | Ground | IR-HVAC/104
105 | I Tower | Ground | IR-HVAC/105
106 | I Tower | Ground | IR-HVAC/106
107 | I Tower | Ground | IR-HVAC/107
108 | I Tower | Ground | IR-HVAC/108
109 | I Tower | Ground | IR-HVAC/109
110 | I Tower | Ground | IR-HVAC/110
111 | I Tower | 1st Floor | IR-HVAC/111
112 | I Tower | 2nd Floor | IR-HVAC/112
113 | I Tower | Ground | IR-HVAC/113
114 | I Tower | Ground | IR-HVAC/114
115 | I Tower | Ground | IR-HVAC/115
116 | I Tower | Ground | IR-HVAC/116
117 | I Tower | 1st Floor | IR-HVAC/117
118 | I Tower | 2nd Floor | IR-HVAC/118
119 | I Tower | 1st Floor | IR-HVAC/119
120 | I Tower | 1st Floor | IR-HVAC/120
121 | I Tower | 2nd Floor | IR-HVAC/121
122 | I Tower | 1st Floor | IR-HVAC/122
123 | I Tower | 1st Floor | IR-HVAC/123
124 | I Tower | 1st Floor | IR-HVAC/124
125 | I Tower | 1st Floor | IR-HVAC/125
126 | I Tower | 1st Floor | IR-HVAC/126
127 | I Tower | 1st Floor | IR-HVAC/127
128 | I Tower | 1st floor | IR-HVAC/128
129 | I Tower | 2nd floor | IR-HVAC/129
130 | I Tower | 2nd floor | IR-HVAC/130
131 | I Tower | 1st floor | IR-HVAC/131
132 | I Tower | 2nd floor | IR-HVAC/132
133 | I Tower | 2nd floor | IR-HVAC/133
134 | I Tower | 2nd floor | IR-HVAC/134
135 | I Tower | 2nd Floor | IR-HVAC/135
136 | I Tower | 2nd Floor | IR-HVAC/136
137 | I Tower | 2nd Floor | IR-HVAC/137
138 | I Tower | 2nd Floor | IR-HVAC/138
139 | I Tower | 2nd Floor | IR-HVAC/139
140 | I Tower | 3rd Floor | IR-HVAC/140
142 | I Tower | 3rd Floor | IR-HVAC/141
143 | I Tower | 3rd Floor | IR-HVAC/142
144 | I Tower | 2nd Floor | IR-HVAC/143
145 | I Tower | 2nd Floor | IR-HVAC/144
146 | I Tower | 3rd Floor | IR-HVAC/145
147 | I Tower | 3rd Floor | IR-HVAC/146
148 | I Tower | 3rd Floor | IR-HVAC/147
149 | I Tower | 3rd Floor | IR-HVAC/148
150 | I Tower | 3rd Floor | IR-HVAC/149
151 | I Tower | 3rd Floor | IR-HVAC/150
152 | I Tower | 3rd Floor | IR-HVAC/151
153 | I Tower | 3rd Floor | IR-HVAC/152
154 | I Tower | 3rd floor | IR-HVAC/153
155 | I Tower | 3rd Floor | IR-HVAC/154
156 | I Tower | 4th floor | IR-HVAC/155
157 | I Tower | 4th floor | IR-HVAC/156
158 | I Tower | 4th floor | IR-HVAC/157
159 | I Tower | 4th floor | IR-HVAC/158
160 | I Tower | 4th floor | IR-HVAC/159
161 | I Tower | 4th floor | IR-HVAC/160
162 | I Tower | 4th floor | IR-HVAC/161
163 | I Tower | 4th floor | IR-HVAC/162
164 | I Tower | 5th Floor | IR-HVAC/163
165 | I Tower | 3rd Floor | IR-HVAC/164
166 | I Tower | 4th floor | IR-HVAC/165
167 | I Tower | 5th Floor | IR-HVAC/166
168 | I Tower | 5th Floor | IR-HVAC/167
169 | I Tower | 5th Floor | IR-HVAC/168
170 | I Tower | 5th Floor | IR-HVAC/169
171 | I Tower | 4th floor | IR-HVAC/170
172 | I Tower | 5th Floor | IR-HVAC/171
173 | I Tower | 6th Floor | IR-HVAC/172
174 | I Tower | 6th floor | IR-HVAC/173
175 | I Tower | 5th Floor | IR-HVAC/174
176 | I Tower | 5th Floor | IR-HVAC/175
177 | I Tower | 5th Floor | IR-HVAC/176
178 | I Tower | 5th Floor | IR-HVAC/177
179 | I Tower | 5th Floor | IR-HVAC/178
180 | I Tower | 5th Floor | IR-HVAC/179
181 | I Tower | Basement | IR-HVAC/180
182 | I Tower | 6th Floor | IR-HVAC/181
183 | I Tower | 6th Floor | IR-HVAC/182
184 | I Tower | 6th Floor | IR-HVAC/183
185 | I Tower | 6th Floor | IR-HVAC/184
186 | I Tower | 6th Floor | IR-HVAC/185
187 | I Tower | Basement | IR-HVAC/186
188 | I Tower | 6th Floor | IR-HVAC/187
189 | I Tower | 6th Floor | IR-HVAC/188
190 | I Tower | 6th Floor | IR-HVAC/189
191 | I Tower | 6th Floor | IR-HVAC/190
192 | I Tower | 6th Floor | IR-HVAC/191
193 | I Tower | 6th Floor | IR-HVAC/192
194 | I Tower | 7th Floor | IR-HVAC/193
195 | I Tower | 7th Floor | IR-HVAC/194
196 | I Tower | 7th Floor | IR-HVAC/195
197 | I Tower | 7th Floor | IR-HVAC/196
198 | I Tower | 7th Floor | IR-HVAC/197
199 | I Tower | 7th floor | IR-HVAC/198
200 | I Tower | 7th Floor | IR-HVAC/199
201 | I Tower | 7th Floor | IR-HVAC/200
202 | I Tower | 8th Floor | IR-HVAC/201
203 | I Tower | 7th Floor | IR-HVAC/202
204 | I Tower | 8th Floor | IR-HVAC/203
205 | I Tower | 8th Floor | IR-HVAC/204
206 | I Tower | 8th Floor | IR-HVAC/205
207 | I Tower | 8th Floor | IR-HVAC/206
208 | I Tower | 8th Floor | IR-HVAC/207
209 | I Tower | 8th Floor | IR-HVAC/208
210 | I Tower | 8th Floor | IR-HVAC/209
211 | I Tower | 8th Floor | IR-HVAC/210
212 | I Tower | 9th Floor | IR-HVAC/211
213 | I Tower | 8th Floor | IR-HVAC/212
214 | I Tower | 9th Floor | IR-HVAC/213
215 | I Tower | 8th Floor | IR-HVAC/214
216 | I Tower | 9th Floor | IR-HVAC/215
217 | I Tower | 9th Floor | IR-HVAC/216
218 | I Tower | 9th Floor | IR-HVAC/217
219 | I Tower | 9th Floor | IR-HVAC/218
220 | I Tower | 9th Floor | IR-HVAC/219
221 | I Tower | 9th Floor | IR-HVAC/220
222 | I Tower | 9th Floor | IR-HVAC/221
223 | I Tower | 9th Floor | IR-HVAC/222
224 | I Tower | 9th Floor | IR-HVAC/223
225 | I Tower | 9th Floor | IR-HVAC/224
226 | I Tower | 9th Floor | IR-HVAC/225
227 | I Tower | 9th Floor | IR-HVAC/226
228 | I Tower | 9th Floor | IR-HVAC/227
229 | I Tower | 10th Floor | IR-HVAC/228
230 | I Tower | 10th Floor | IR-HVAC/229
231 | I Tower | 10th Floor | IR-HVAC/230
232 | I Tower | 10th Floor | IR-HVAC/231
233 | I Tower | 10th Floor | IR-HVAC/232
234 | I Tower | 10th Floor | IR-HVAC/233
235 | I Tower | 10th Floor | IR-HVAC/234
236 | I Tower | 10th Floor | IR-HVAC/235
237 | I Tower | 10th Floor | IR-HVAC/236
238 | I Tower | 10th Floor | IR-HVAC/237
239 | I Tower | 10th Floor | IR-HVAC/238
240 | I Tower | 10th Floor | IR-HVAC/239
241 | I Tower | 11th Floor | IR-HVAC/240
242 | I Tower | 11th Floor | IR-HVAC/241
243 | I Tower | 11th Floor | IR-HVAC/242
244 | I Tower | 11th Floor | IR-HVAC/243
245 | I Tower | 11th Floor | IR-HVAC/244
246 | I Tower | 11th Floor | IR-HVAC/245
247 | I Tower | 11th Floor | IR-HVAC/246
248 | I Tower | 11th Floor | IR-HVAC/247
249 | I Tower | 11th Floor | IR-HVAC/248
250 | I Tower | 11th Floor | IR-HVAC/249
251 | I Tower | 11th Floor | IR-HVAC/250
252 | I Tower | 11th Floor | IR-HVAC/251
253 | I Tower | 11th Floor | IR-HVAC/252
254 | I Tower | 11th Floor | IR-HVAC/253
255 | I Tower | 11th Floor | IR-HVAC/254
256 | I Tower | 11th Floor | IR-HVAC/255
257 | I Tower | 11th Floor | IR-HVAC/256
258 | I Tower | 11th Floor | IR-HVAC/257
259 | I Tower | 11th Floor | IR-HVAC/258
260 | I Tower | 11th Floor | IR-HVAC/259
261 | I Tower | 11th Floor | IR-HVAC/260
| I Tower | 11th Floor | IR-HVAC/261
| I Tower | 11th Floor | IR-HVAC/262
| I Tower | 11th Floor | IR-HVAC/263
| I Tower | 11th Floor | IR-HVAC/264
| I Tower | 11th Floor | IR-HVAC/265
| I Tower | 11th Floor | IR-HVAC/266
| I Tower | 11th Floor | IR-HVAC/267
| I Tower | 11th Floor | IR-HVAC/268
| I Tower | 11th Floor | IR-HVAC/269
| I Tower | 11th Floor | IR-HVAC/270 | [12 empty] | v
| I Tower | 11th Floor | IR-HVAC/271
| I Tower | 11th Floor | IR-HVAC/272
| I Tower | 11th Floor | IR-HVAC/273
| I Tower | 11th Floor | IR-HVAC/274
| I Tower | 11th Floor | IR-HVAC/275
| I Tower | 11th Floor | IR-HVAC/276
| I Tower | 11th Floor | IR-HVAC/277
| I Tower | 11th Floor | IR-HVAC/278
| I Tower | 11th Floor | IR-HVAC/279
| I Tower | 11th Floor | IR-HVAC/280
| I Tower | 11th Floor | IR-HVAC/281
| I Tower | 11th Floor | IR-HVAC/282
| I Tower | 11th Floor | IR-HVAC/283
| I Tower | 11th Floor | IR-HVAC/284
| I Tower | 11th Floor | IR-HVAC/285
IR-HVAC/286
2022-12-19

## Rayyan I tower
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) Jotun | [5 empty] | Fully Approved (A) |  | 121
[9 empty] | Approved with comments (B) |  | 1
[9 empty] | Rejected ( R) |  | 1 |  | As of : | 2025-12-19
[9 empty] | Open/Pending (OP) |  | 9
[9 empty] | Total |  | 132
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR closing Date | Pour Card No. | Concrete Qty (m3) | Remarks
1 | 1st Floor | 1st floor | IT/1 | 2025-02-19 | 2025-01-16 | surface | Surface |  | Grid A-C/1-5 | A
| Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 | primer | Primer
| Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-06 |  | Basem application, application of 03 coats of wall putty
|  | 1st floor | IT/01 R01 | 2025-06-28 |  |  | Basem application, application of 03 coats of wall putty |  | Grid A-C/1-5 | op
4 | Sub Structure | 1st floor | IT/2 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid B-F/1-4 | A
5 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
6 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-06 |  | Basem application, application of 03 coats of wall putty
7 | Sub Structure | 1st floor | IT/3 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid A-C/5-9 | A
9 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
10 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-06 |  | Basem application, application of 03 coats of wall putty
11 | Sub Structure | 1st floor | IT/4 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid C-F/4-9 | A
12 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
13 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-07 |  | Basem application, application of 03 coats of wall putty
14 | Sub Structure | 1st floor | IT/5 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid A-C/10-13 | A
15 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
16 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-07 |  | Basem application, application of 03 coats of wall putty
17 | Sub Structure | 1st floor | IT/6 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid C-F/8-11 | A
18 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
19 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-07 |  | Basem application, application of 03 coats of wall putty
20 | Sub Structure | 1st floor | IT/7 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid A-C/12-15 | A
21 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
22 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-07 |  | Basem application, application of 03 coats of wall putty
23 | Sub Structure | 1st floor | IT/8 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid C-F/10-13 | A
24 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
25 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-07 |  | Basem application, application of 03 coats of wall putty
26 | Sub Structure | 1st floor | IT/9 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid A-C/14-17 | A
27 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
28 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-10 |  | Basem application, application of 03 coats of wall putty
29 | Sub Structure | 1st floor | IT/10 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid C-F/12-15 | A
30 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
31 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-10 |  | Basem application, application of 03 coats of wall putty
32 | Sub Structure | 1st floor | IT/11 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid A-C/18-22 | A
33 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
34 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-10 |  | Basem application, application of 03 coats of wall putty
35 | Sub Structure | 1st floor | IT/12 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid C-F/14-17 | A
36 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
37 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-10 |  | Basem application, application of 03 coats of wall putty
38 | Sub Structure | 1st floor | IT/13 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid A-C/22-26 | A
39 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
40 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-10 |  | Basem application, application of 03 coats of wall putty
41 | Sub Structure | 1st floor | IT/14 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid C-F/16-19 | A
42 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
43 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-11 |  | Basem application, application of 03 coats of wall putty
44 | Sub Structure | 1st floor | IT/15 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid C-F/23-26 | A
45 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
46 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-11 |  | Basem application, application of 03 coats of wall putty
47 | Sub Structure | 1st floor | IT/16 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid C-F/18-23 | A
48 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
49 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-11 |  | Basem application, application of 03 coats of wall putty
50 | Sub Structure | 1st floor | IT/17 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid B-F/1-13 | A
51 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
52 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-12 |  | Basem application, application of 03 coats of wall putty
53 | Sub Structure | 1st floor | IT/18 | 2025-02-19 | 2025-01-16 |  | Surface |  | Grid B-F/13-26 | A
54 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-01-17 |  | Primer
55 | Sub Structure | 1st floor |  | 2025-02-19 | 2025-02-12 |  | Basem application, application of 03 coats of wall putty
56 | Sub Structure | 2nd floor | IT/19 | 2025-02-24 | 2025-01-18 |  | Surface |  | Grid A-C/1-5 | A
57 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-01-20 |  | Primer
58 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-02-10 |  | Base preparation, application of 03 coats of wall putty
59 | Sub Structure | 2nd floor | IT/20 | 2025-02-24 | 2025-01-18 |  | Surface |  | Grid B-F/1-4 | A
60 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-01-20 |  | Primer
61 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-02-10 |  | Base preparation, application of 03 coats of wall putty
62 | Sub Structure | 2nd floor | IT/21 | 2025-02-24 | 2025-01-18 |  | Surface |  | Grid A-C/5-9 | A
63 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-01-20 |  | Primer
64 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-02-10 |  | Base preparation, application of 03 coats of wall putty
65 | Sub Structure | 2nd floor | IT/22 | 2025-02-24 | 2025-01-18 |  | Surface |  | Grid C-F/4-9 | A
66 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-01-20 |  | Primer
67 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-02-10 |  | Base preparation, application of 03 coats of wall putty
68 | Sub Structure | 2nd floor | IT/23 | 2025-02-24 | 2025-01-21 |  | Surface |  | Grid A-C/9-13 | A
69 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-01-22 |  | Primer
70 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-11 |  | Base preparation, application of 03 coats of wall putty
| I Tower | 2nd floor | IT/24 | 2025-02-24 | 2025-01-21 |  | Surface |  | Grid C-F/8-11 | A
72 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-22 |  | Primer
73 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-11 |  | Base preparation, application of 03 coats of wall putty
74 | Sub Structure | 2nd floor | IT/25 | 2025-02-24 | 2025-01-21 |  | Surface |  | Grid A-C/12-15 | A
75 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-01-22 |  | Primer
76 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-11 |  | Base preparation, application of 03 coats of wall putty
77 | I Tower | 2nd floor | IT/26 | 2025-02-24 | 2025-01-21 |  | Surface |  | Grid C-F/10-13 | A
78 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-22 |  | Primer
79 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-11 |  | Base preparation, application of 03 coats of wall putty
80 | I Tower | 2nd floor | IT/27 | 2025-02-24 | 2025-01-22 |  | Surface |  | Grid A-C/14-17 | A
81 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-23 |  | Primer
82 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-12 |  | Base preparation, application of 03 coats of wall putty
83 | I Tower | 2nd floor | IT/28 | 2025-02-24 | 2025-01-22 |  | Surface |  | Grid C-F/12-15 | A
84 | Sub Structure | 2nd floor |  | 2025-02-24 | 2025-01-23 |  | Primer
85 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-12 |  | Base preparation, application of 03 coats of wall putty
86 | I Tower | 2nd floor | IT/29 | 2025-02-24 | 2025-01-22 |  | Surface |  | Grid A-C/18-22 | A
87 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-23 |  | Primer
88 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-12 |  | Base preparation, application of 03 coats of wall putty
89 | I Tower | 2nd floor | IT/30 | 2025-02-24 | 2025-01-22 |  | Surface |  | Grid C-F/14-17 | A
90 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-23 |  | Primer
91 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-12 |  | Base preparation, application of 03 coats of wall putty
92 | I Tower | 2nd floor | IT/31 | 2025-02-24 | 2025-01-23 |  | Surface |  | Grid A-C/22-26 | A
93 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-24 |  | Primer
94 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-13 |  | Base preparation, application of 03 coats of wall putty
95 | I Tower | 2nd floor | IT/32 | 2025-02-24 | 2025-01-23 |  | Surface |  | Grid C-F/16-19 | A
96 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-24 |  | Primer
97 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-13 |  | Base preparation, application of 03 coats of wall putty
98 | I Tower | 2nd floor | IT/33 | 2025-02-24 | 2025-01-23 |  | Surface |  | Grid C-F/23-26 | A
99 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-24 |  | Primer
100 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-13 |  | Base preparation, application of 03 coats of wall putty
101 | I Tower | 2nd floor | IT/34 | 2025-02-24 | 2025-01-23 |  | Surface |  | Grid C-F/18-23 | A
102 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-24 |  | Primer
103 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-13 |  | Base preparation, application of 03 coats of wall putty
106 | I Tower | 2nd floor | IT/35 | 2025-02-24 | 2025-01-24 |  | Surface |  | Grid B-F/1-13 | A
107 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-25 |  | Primer
108 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-15 |  | Base preparation, application of 03 coats of wall putty
109 | I Tower | 2nd floor | IT/36 | 2025-02-24 | 2025-01-24 |  | Surface |  | Grid B-F/13-26 | A
110 | I Tower | 2nd floor |  | 2025-02-24 | 2025-01-25 |  | Primer
111 | I Tower | 2nd floor |  | 2025-02-24 | 2025-02-15 |  | Base preparation, application of 03 coats of wall putty
112 | I Tower | 3rd floor | IT/37 | 2025-02-26 | 2025-01-23 |  | Surface |  | Grid A-C/1-5 | A
113 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-24 |  | Primer
114 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-17 |  | Base preparation, application of 03 coats of wall putty
115 | I Tower | 3rd floor | IT/38 | 2025-02-26 | 2025-01-23 |  | Surface |  | Grid B-F/1-4 | A
116 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-24 |  | Primer
117 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-17 |  | Base preparation, application of 03 coats of wall putty
118 | I Tower | 3rd floor | IT/39 | 2025-02-26 | 2025-01-23 |  | Surface |  | Grid A-C/5-9 | A
119 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-24 |  | Primer
120 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-17 |  | Base preparation, application of 03 coats of wall putty
121 | I Tower | 3rd floor | IT/40 | 2025-02-26 | 2025-01-23 |  | Surface |  | Grid C-F/4-9 | A
122 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-24 |  | Primer
123 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-17 |  | Base preparation, application of 03 coats of wall putty
124 | I Tower | 3rd floor | IT/41 | 2025-02-26 | 2025-01-24 |  | Surface |  | Grid A-C/10-13 | A
125 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-25 |  | Primer
126 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-18 |  | Base preparation, application of 03 coats of wall putty
127 | I Tower | 3rd floor | IT/42 | 2025-02-26 | 2025-01-24 |  | Surface |  | Grid C-F/8-11 | A
128 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-25 |  | Primer
129 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-18 |  | Base preparation, application of 03 coats of wall putty
130 | I Tower | 3rd floor | IT/43 | 2025-02-26 | 2025-01-24 |  | Surface |  | Grid A-C/12-15 | A
131 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-25 |  | Primer
132 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-18 |  | Base preparation, application of 03 coats of wall putty
133 | I Tower | 3rd floor | IT/44 | 2025-02-26 | 2025-01-24 |  | Surface |  | Grid C-F/10-13 | A
134 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-25 |  | Primer
135 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-18 |  | Base preparation, application of 03 coats of wall putty
136 | I Tower | 3rd floor | IT/45 | 2025-02-26 | 2025-01-27 |  | Surface |  | Grid A-C/14-17 | A
137 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-28 |  | Primer
138 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-19 |  | Base preparation, application of 03 coats of wall putty
139 | I Tower | 3rd floor | IT/46 | 2025-02-26 | 2025-01-27 |  | Surface |  | Grid C-F/12-15 | A
140 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-28 |  | Primer
142 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-19 |  | Base preparation, application of 03 coats of wall putty
143 | I Tower | 3rd floor | IT/47 | 2025-02-26 | 2025-01-27 |  | Surface |  | Grid A-C/18-22 | A
144 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-28 |  | Primer
145 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-19 |  | Base preparation, application of 03 coats of wall putty
146 | I Tower | 3rd floor | IT/48 | 2025-02-26 | 2025-01-27 |  | Surface |  | Grid C-F/14-17 | A
147 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-28 |  | Primer
148 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-19 |  | Base preparation, application of 03 coats of wall putty
149 | I Tower | 3rd floor | IT/49 | 2025-02-26 | 2025-01-28 |  | Surface |  | Grid A-C/22-26 | A
150 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-29 |  | Primer
151 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-20 |  | Base preparation, application of 03 coats of wall putty
152 | I Tower | 3rd floor | IT/50 | 2025-02-26 | 2025-01-28 |  | Surface |  | Grid C-F/16-19 | A
153 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-29 |  | Primer
154 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-20 |  | Base preparation, application of 03 coats of wall putty
155 | I Tower | 3rd floor | IT/51 | 2025-02-26 | 2025-01-28 |  | Surface |  | Grid C-F/23-26 | A
156 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-29 |  | Primer
157 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-20 |  | Base preparation, application of 03 coats of wall putty
158 | I Tower | 3rd floor | IT/52 | 2025-02-26 | 2025-01-28 |  | Surface |  | Grid C-F/18-23 | A
159 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-29 |  | Primer
160 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-20 |  | Base preparation, application of 03 coats of wall putty
161 | I Tower | 3rd floor | IT/53 | 2025-02-26 | 2025-01-30 |  | Surface |  | Grid B-F/1-13 | A
162 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-31 |  | Primer
163 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-21 |  | Base preparation, application of 03 coats of wall putty
164 | I Tower | 3rd floor | IT/54 | 2025-02-26 | 2025-01-30 |  | Surface |  | Grid B-F/13-26 | A
165 | I Tower | 3rd floor |  | 2025-02-26 | 2025-01-31 |  | Primer
166 | I Tower | 3rd floor |  | 2025-02-26 | 2025-02-21 |  | Base preparation, application of 03 coats of wall putty
167 | I Tower | 4th floor | IT/055 | 2025-03-04 | 2025-02-03 |  | Surface |  | Grid A-C/1-5 | A
168 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-05 |  | Primer
169 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-24 |  | Base preparation, application of 03 coats of wall putty
170 | I Tower | 4th floor | IT/056 | 2025-03-04 | 2025-02-03 |  | Surface |  | Grid B-F/1-4 | A
171 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-05 |  | Primer
172 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-24 |  | Base preparation, application of 03 coats of wall putty
173 | I Tower | 4th floor | IT/57 | 2025-03-04 | 2025-02-03 |  | Surface |  | Grid A-C/5-9 | A
174 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-05 |  | Primer
175 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-24 |  | Base preparation, application of 03 coats of wall putty
176 | I Tower | 4th floor | IT/58 | 2025-03-04 | 2025-02-03 |  | Surface |  | Grid C-F/4-9 | A
177 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-05 |  | Primer
178 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-24 |  | Base preparation, application of 03 coats of wall putty
179 | I Tower | 4th floor | IT/59 | 2025-03-04 | 2025-02-04 |  | Surface |  |  | A
180 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-06 |  | Primer
181 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-25 |  | Base preparation, application of 03 coats of wall putty
182 | I Tower | 4th floor | IT/60 | 2025-03-04 | 2025-02-04 |  | Surface |  | Grid C-F/8-11 | A
183 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-06 |  | Primer
184 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-25 |  | Base preparation, application of 03 coats of wall putty
185 | I Tower | 4th floor | IT/61 | 2025-03-04 | 2025-02-04 |  | Surface |  | Grid A-C/12-15 | A
186 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-06 |  | Primer
187 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-25 |  | Base preparation, application of 03 coats of wall putty
188 | I Tower | 4th floor | IT/62 | 2025-03-04 | 2025-02-04 |  | Surface |  | Grid C-F/10-13 | A
189 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-06 |  | Primer
190 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-25 |  | Base preparation, application of 03 coats of wall putty
191 | I Tower | 4th floor | IT/63 | 2025-03-04 | 2025-02-05 |  | Surface |  | Grid A-C/14-17 | A
192 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-07 |  | Primer
193 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-26 |  | Base preparation, application of 03 coats of wall putty
194 | I Tower | 4th floor | IT/64 | 2025-03-04 | 2025-02-05 |  | Surface |  | Grid C-F/12-15 | A
195 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-07 |  | Primer
196 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-26 |  | Base preparation, application of 03 coats of wall putty
197 | I Tower | 4th floor | IT/65 | 2025-03-04 | 2025-02-05 |  | Surface |  | Grid A-C/18-22 | A
198 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-07 |  | Primer
199 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-26 |  | Base preparation, application of 03 coats of wall putty
200 | I Tower | 4th floor | IT/66 | 2025-03-04 | 2025-02-05 |  | Surface |  | Grid C-F/14-17 | A
201 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-07 |  | Primer
202 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-26 |  | Base preparation, application of 03 coats of wall putty
203 | I Tower | 4th floor | IT/67 | 2025-03-04 | 2025-02-06 |  | Surface |  | Grid A-C/22-26 | A
204 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-08 |  | Primer
205 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-26 |  | Base preparation, application of 03 coats of wall putty
206 | I Tower | 4th floor | IT/68 | 2025-03-04 | 2025-02-06 |  | Surface |  | Grid C-F/16-19 | A
207 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-08 |  | Primer
208 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-26 |  | Base preparation, application of 03 coats of wall putty
209 | I Tower | 4th floor | IT/69 | 2025-03-04 | 2025-02-06 |  | Surface |  | Grid C-F/23-26 | A
210 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-08 |  | Primer
211 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-26 |  | Base preparation, application of 03 coats of wall putty
212 | I Tower | 4th floor | IT/70 | 2025-03-04 | 2025-02-06 |  | Surface |  | Grid C-F/18-23 | A
213 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-08 |  | Primer
214 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-26 |  | Base preparation, application of 03 coats of wall putty
215 | I Tower | 4th floor | IT/71 | 2025-03-04 | 2025-02-08 |  | Surface |  | Grid B-F/1-13 | A
216 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-10 |  | Primer
217 | I Tower | 4th floor |  | 2025-03-04 | 2025-02-27 |  | Base preparation, application of 03 coats of wall putty
218 | I Tower | 4th floor | IT/72 | 2025-03-04 | 2025-02-08 |  | Surface |  | Grid B-F/13-26 | A
219 | I Tower | 4th floor | IT/217 | 2025-03-04 | 2025-02-10 |  | Primer
220 | I Tower | 4th floor | IT/218 | 2025-03-04 | 2025-02-27 |  | Base preparation, application of 03 coats of wall putty
221 | I Tower | 4th floor | IT/73 | 2025-07-15 | 2025-06-17 |  | Surface |  | 1st Floor(102) | A
222 | I Tower | 4th floor | IT/217 | 2025-07-15 | 2025-06-18 |  | Primer
223 | I Tower | 4th floor | IT/218 | 2025-07-15 | 2025-06-20 |  | Base preparation, application of 03 coats of wall putty
224 | I Tower | 4th floor | IT/74 | 2025-07-15 | 2025-06-17 |  | Surface |  | 1st Floor(103) | A
225 | I Tower | 4th floor | IT/217 | 2025-07-15 | 2025-06-18 |  | Primer
226 | I Tower | 4th floor | IT/218 | 2025-07-15 | 2025-06-20 |  | Base preparation, application of 03 coats of wall putty
227 | I Tower | 9th Floor | IT/75 | 2025-07-15 | 2025-06-17 |  | Surface |  | 1st Floor(104) | A
228 | I Tower | 9th Floor | IT/226 | 2025-07-15 | 2025-06-18 |  | Primer
229 | I Tower | 10th Floor | IT/227 | 2025-07-15 | 2025-06-20 |  | Base preparation, application of 03 coats of wall putty
230 | I Tower | 10th Floor | IT/76 | 2025-07-15 | 2025-06-17 |  | Surface |  | 1st Floor(105) | A
231 | I Tower | 10th Floor | IT/229 | 2025-07-15 | 2025-06-18 |  | Primer
232 | I Tower | 10th Floor | IT/230 | 2025-07-15 | 2025-06-20 |  | Base preparation, application of 03 coats of wall putty
233 | I Tower | 10th Floor | IT/77 | 2025-07-15 | 2025-06-17 |  | Surface |  | 1st Floor(106) | A
234 | I Tower | 10th Floor | IT/232 | 2025-07-15 | 2025-06-18 |  | Primer
235 | I Tower | 10th Floor | IT/233 | 2025-07-15 | 2025-06-21 |  | Base preparation, application of 03 coats of wall putty
236 | I Tower | 10th Floor | IT/78 | 2025-07-15 | 2025-06-17 |  | Surface |  | 1st Floor(107) | A
237 | I Tower | 10th Floor | IT/235 | 2025-07-15 | 2025-06-18 |  | Primer
238 | I Tower | 10th Floor | IT/236 | 2025-07-15 | 2025-06-21 |  | Base preparation, application of 03 coats of wall putty
239 | I Tower | 10th Floor | IT/79 | 2025-07-15 | 2025-06-19 |  | Surface |  | 1st Floor(108) | A
240 | I Tower | 10th Floor | IT/238 | 2025-07-15 | 2025-06-20 |  | Primer
241 | I Tower | 11th Floor | IT/239 | 2025-07-15 | 2025-06-22 |  | Base preparation, application of 03 coats of wall putty
242 | I Tower | 11th Floor | IT/80 | 2025-07-15 | 2025-06-19 |  | Surface |  | 1st Floor(109) | A
243 | I Tower | 11th Floor | IT/241 | 2025-07-15 | 2025-06-20 |  | Primer
244 | I Tower | 11th Floor | IT/242 | 2025-07-15 | 2025-06-22 |  | Base preparation, application of 03 coats of wall putty
245 | I Tower | 11th Floor | IT/81 | 2025-07-15 | 2025-06-19 |  | Surface |  | 1st Floor(110) | A
246 | I Tower | 11th Floor | IT/244 | 2025-07-15 | 2025-06-20 |  | Primer
247 | I Tower | 11th Floor | IT/245 | 2025-07-15 | 2025-06-22 |  | Base preparation, application of 03 coats of wall putty
248 | I Tower | 11th Floor | IT/82 | 2025-07-15 | 2025-06-20 |  | Surface |  | 1st Floor(111) | A
249 | I Tower | 11th Floor | IT/247 | 2025-07-15 | 2025-06-21 |  | Primer
250 | I Tower | 11th Floor | IT/248 | 2025-07-15 | 2025-06-23 |  | Base preparation, application of 03 coats of wall putty
251 | I Tower | 11th Floor | IT/83 | 2025-07-15 | 2025-06-20 |  | Surface |  | 1st Floor(112) | A
252 | I Tower | 11th Floor | IT/250 | 2025-07-15 | 2025-06-21 |  | Primer
253 | I Tower | 11th Floor | IT/251 | 2025-07-15 | 2025-06-23 |  | Base preparation, application of 03 coats of wall putty
254 | I Tower | 11th Floor | IT/84 | 2025-07-15 | 2025-06-20 |  | Surface |  | 1st Floor(113) | A
255 | I Tower | 11th Floor | IT/253 | 2025-07-15 | 2025-06-21 |  | Primer
256 | I Tower | 11th Floor | IT/254 | 2025-07-15 | 2025-06-24 |  | Base preparation, application of 03 coats of wall putty
257 | I Tower | 11th Floor | IT/85 | 2025-07-15 | 2025-06-21 |  | Surface |  | 1st Floor(114) | A
258 | I Tower | 11th Floor | IT/256 | 2025-07-15 | 2025-06-23 |  | Primer
259 | I Tower | 11th Floor | IT/257 | 2025-07-15 | 2025-06-25 |  | Base preparation, application of 03 coats of wall putty
260 | I Tower | 11th Floor | IT/86 | 2025-07-15 | 2025-06-21 |  | Surface |  | 1st Floor(115) | A
261 | I Tower | 11th Floor | IT/259 | 2025-07-15 | 2025-06-23 |  | Primer
| I Tower | 11th Floor | IT/260 | 2025-07-15 | 2025-06-25 |  | Base preparation, application of 03 coats of wall putty
| I Tower | 11th Floor | IT/87 | 2025-07-15 | 2025-06-21 |  | Surface |  | 1st Floor(116) | A
| I Tower | 11th Floor | IT/262 | 2025-07-15 | 2025-06-23 |  | Primer
| I Tower | 11th Floor | IT/263 | 2025-07-15 | 2025-06-25 |  | Base preparation, application of 03 coats of wall putty
| I Tower | 11th Floor | IT/88 | 2025-07-17 | 2025-06-28 |  | Surface |  | 2nd floor (206) | A
| I Tower | 11th Floor | IT/262 | 2025-07-17 | 2025-06-29 |  | Primer
| I Tower | 11th Floor | IT/263 | 2025-07-17 | 2025-07-02 |  | Base preparation, application of 03 coats of wall putty
| I Tower | 11th Floor | IT/89 | 2025-07-17 | 2025-06-28 |  | Surface |  | 2nd floor (211) | A
| I Tower | 11th Floor | IT/268 | 2025-07-17 | 2025-06-29 |  | Primer
| I Tower | 11th Floor | IT/269 | 2025-07-17 | 2025-07-02 |  | Base preparation, application of 03 coats of wall putty | [7 empty] | v
| I Tower | 11th Floor | IT/90 | 2025-07-17 | 2025-06-28 |  | Surface |  | 2nd floor (212) | A
| I Tower | 11th Floor | IT/271 | 2025-07-17 | 2025-06-29 |  | Primer
| I Tower | 11th Floor | IT/272 | 2025-07-17 | 2025-07-02 |  | Base preparation, application of 03 coats of wall putty
| I Tower | 11th Floor | IT/91 | 2025-07-17 | 2025-06-28 |  | Surface |  | 2nd floor (213) | A
| I Tower | 11th Floor | IT/274 | 2025-07-17 | 2025-06-29 |  | Primer
| I Tower | 11th Floor | IT/275 | 2025-07-17 | 2025-07-02 |  | Base preparation, application of 03 coats of wall putty
| I Tower | 11th Floor | IT/92 | 2025-07-17 | 2025-06-28 |  | Surface |  | 2nd floor (214) | A
| I Tower | 11th Floor |  | 2025-07-17 | 2025-06-30 |  | Primer
| I Tower | 11th Floor |  | 2025-07-17 | 2025-07-03 |  | Base preparation, application of 03 coats of wall putty
| I Tower | 11th Floor | IT/93 | 2025-07-17 | 2025-06-29 |  | Surface |  | 2nd floor(215) | A
| I Tower | 11th Floor |  | 2025-07-17 | 2025-06-30 |  | Primer
| I Tower | 11th Floor |  | 2025-07-17 | 2025-07-03 |  | Base preparation, application of 03 coats of wall putty
| I Tower | 11th Floor | IT/94 | 2025-07-17 | 2025-06-30 |  | Surface |  | 2nd floor(216) | A
| I Tower | 11th Floor |  | 2025-07-17 | 2025-07-01 |  | Primer
| I Tower | 11th Floor |  | 2025-07-17 | 2025-07-04 |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/95 | 2025-07-18 | 2025-07-04 |  | Surface |  | 3rd Floor(301) | OP
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/96 | 2025-07-18 |  |  | Surface |  | 3rd Floor(302) | OP
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/97 | 2025-07-18 |  |  | Surface |  | 3rd Floor(303) | OP
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/98 | 2025-07-18 |  |  | Surface |  | 3rd Floor(304) | OP
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/99 | 2025-07-18 |  |  | Surface |  | 3rd Floor(305) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/100 | 2025-07-18 |  |  | Surface |  | 3rd Floor(306) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/101 | 2025-07-18 |  |  | Surface |  | 3rd Floor(307) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/102 | 2025-07-18 |  |  | Surface |  | 3rd Floor(308) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/103 | 2025-07-18 |  |  | Surface |  | 3rd Floor(309) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/104 | 2025-07-18 |  |  | Surface |  | 3rd Floor(310) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/105 | 2025-07-18 |  |  | Surface |  | 3rd Floor(311) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/106 | 2025-07-18 |  |  | Surface |  | 3rd Floor(312) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/107 | 2025-07-18 |  |  | Surface |  | 3rd Floor(313) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/108 | 2025-07-18 |  |  | Surface |  | 3rd Floor(314) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/109 | 2025-07-18 |  |  | Surface |  | 3rd Floor(315) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 3rd floor | IT/110 | 2025-07-18 |  |  | Surface |  | 3rd Floor(316) | A
|  | 3rd floor |  | 2025-07-18 |  |  | Primer
|  | 3rd floor |  | 2025-07-18 |  |  | Base preparation, application of 03 coats of wall putty
|  | 2nd floor | IT/111 | 2025-07-23 |  |  | Surface |  | 2nd Floor(202) | A
|  | 2nd floor |  | 2025-07-23 |  |  | Primer
|  | 2nd floor |  | 2025-07-23 |  |  | Base preparation, application of 03 coats of wall putty
|  | 2nd floor | IT/112 | 2025-07-23 |  |  | Surface |  | 2nd Floor(203) | A
|  | 2nd floor |  | 2025-07-23 |  |  | Primer
|  | 2nd floor |  | 2025-07-23 |  |  | Base preparation, application of 03 coats of wall putty
|  | 2nd floor | IT/113 | 2025-07-23 |  |  | Surface |  | 2nd Floor(204) | A
|  | 2nd floor |  | 2025-07-23 |  |  | Primer
|  | 2nd floor |  | 2025-07-23 |  |  | Base preparation, application of 03 coats of wall putty
|  | 2nd floor | IT/114 | 2025-07-23 |  |  | Surface |  | 2nd Floor(205) | A
|  | 2nd floor |  | 2025-07-23 |  |  | Primer
|  | 2nd floor |  | 2025-07-23 |  |  | Base preparation, application of 03 coats of wall putty
|  | 2nd floor | IT/115 | 2025-07-23 |  |  | Surface |  | 2nd Floor(207) | A
|  | 2nd floor |  | 2025-07-23 |  |  | Primer
|  | 2nd floor |  | 2025-07-23 |  |  | Base preparation, application of 03 coats of wall putty
|  | 2nd floor | IT/116 | 2025-07-23 |  |  | Surface |  | 2nd Floor(208) | A
|  | 2nd floor |  | 2025-07-23 |  |  | Primer
|  | 2nd floor |  | 2025-07-23 |  |  | Base preparation, application of 03 coats of wall putty
|  | 2nd floor | IT/117 | 2025-07-23 |  |  | Surface |  | 2nd Floor(209) | A
|  | 2nd floor |  | 2025-07-23 |  |  | Primer
|  | 2nd floor |  | 2025-07-23 |  |  | Base preparation, application of 03 coats of wall putty
|  | 2nd floor | IT/118 | 2025-07-23 |  |  | Surface |  | 2nd Floor(210) | A
|  | 2nd floor |  | 2025-07-23 |  |  | Primer
|  | 2nd floor |  | 2025-07-23 |  |  | Base preparation, application of 03 coats of wall putty
|  | 1st floor | IT/119 | 2025-10-16 | 2025-10-16 |  | Sanding before 1st Coat of paint |  | 108 | R | 2025-10-18
|  |  | IT/120 | 2025-10-24 | 2025-10-24 |  | Sanding before 1st Coat of paint |  | 106 | A | 2025-10-27 |  |  |  |  | 2025-10-24
|  |  | IT/121 | 2025-10-24 | 2025-10-24 |  | Sanding before 1st Coat of paint |  | 110
|  | 1st floor | IT/122 | 2025-10-27 |  |  | Sanding before 1st coat of paint |  | 1st floor(114) | A | 2025-11-01
|  | 1st floor | IT/123 | 2025-10-27 |  |  | Sanding before 1st coat of paint |  | 1st floor(116) | A | 2025-11-01
|  |  | IT/124 | 2025-11-04 |  |  | Sanding before 1st coat of paint |  | 101 | A | 2025-11-07
|  |  | IT/125 | 2025-11-04 |  |  | Sanding before 1st coat of paint |  | 102 | A | 2025-11-07
|  |  | IT/126 | 2025-11-04 |  |  | Sanding before 1st coat of paint |  | 103 | A | 2025-11-07
|  |  | IT/127 | 2025-11-13 |  |  | Sanding before 1st coat of paint |  | 105
|  |  | IT/128 | 2025-11-13 |  |  | Sanding before 1st coat of paint |  | 107
|  |  | IT/129 | 2025-11-13 |  |  | Sanding before 1st coat of paint |  | 111
|  |  | IT/130 | 2025-11-13 |  |  | Sanding before 1st coat of paint |  | 113
|  |  | IT/131 | 2025-11-13 |  |  | First Coat paint application |  | 101
|  |  | IT/132 | 2025-11-13 |  |  | Primer, 3coat wall putty & Final coat paint on Wardrobe ceilling and wall area |  | 401-416 | A | 2025-11-18
|  |  | IT/133 | 2025-11-13 |  |  | Primer, 3coat wall putty & Final coat paint on Kitchen ceilling and wall area |  | 401-416 | B | 2025-11-18
|  |  | IT/134 | 2025-11-13
|  |  | IT/135 | 2025-11-27 |  |  | 1st coat application |  | 108 | OP
|  |  | IT/136 | 2025-11-27 |  |  | 1st coat application |  | 110 | OP
|  |  | IT/137 | 2025-11-27 |  |  | 1st coat application |  | 114 | OP
|  |  | IT/138 | 2025-11-27 |  |  | 1st coat application |  | 116 | OP
IT/139
IT/140
IT/141
IT/142
IT/143
2025-11-04

## EPN
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) EPN | [5 empty] | Fully Approved (A) |  | 0
[9 empty] | Approved with comments (B) |  | 1
[9 empty] | Rejected ( R) |  | 0 |  | As of : |  | 2025-12-19
[9 empty] | Open/Pending (OP) |  | 1
[9 empty] | Total |  | 2
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR closing Date | Pour Card No. | Concrete Qty (m3) | Attachment | Remarks
1 |  | 1st to 5th floor | IT/01 | 2025-02-21 | 2025-02-21 | cables | 02 core OFC Cable Electric Room to each apartment: 4190 |  |  | B | 2025-03-03
2 | [6 empty] | cat-6 cable from electric room to each camera points: 2385
3 | [6 empty] | cat-6 cable in each apartment for WIFI, TV and telephone: 5435
4 | [6 empty] | RG-6 cable in each apartment for TV: 1790 meter
5 |  | Ground floor | IT/002 | 2025-04-11 | 2025-04-11 | cables | Cable laid OFC, and Cat-6 for Game room, Gym, Lobby and CCTV Cameras, 458M |  |  | OP
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
v
| I Tower | 11th Floor | IT/273
| I Tower | 11th Floor | IT/274
| I Tower | 11th Floor | IT/275
| I Tower | 11th Floor | IT/276
| I Tower | 11th Floor | IT/277
| I Tower | 11th Floor | IT/278
| I Tower | 11th Floor | IT/279
| I Tower | 11th Floor | IT/280
| I Tower | 11th Floor | IT/281
| I Tower | 11th Floor | IT/282
| I Tower | 11th Floor | IT/283
| I Tower | 11th Floor | IT/284
2022-12-19

## Group Star
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) IIL-CSL | [5 empty] | Fully Approved (A) |  | 28
[9 empty] | Approved with comments (B) |  | 7
[9 empty] | Rejected ( R) |  | 4 |  | As of : |  | 2025-12-19
[9 empty] | Open/Pending (OP) |  | 1
[9 empty] | Total |  | 40
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR closing Date | Pour Card No. | Concrete Qty (m3) | Attachment | Remarks
1 | Sub Structure | 1st floor | IT/1 | 2025-03-05 | 2025-03-05 | ceiling | Check POP False ceiling of apartment zone 2 |  |  | B | 2025-03-06 |  |  | E:\Soft IRs\IIL\I Tower\1.pdf
2 | Sub Structure | 3rd floor | IT/2 | 2025-04-18 | 2025-04-18 | ceiling | Check POP false ceiling of apartment no. 110 zone 2 |  | 310 | A | 2025-05-13 |  |  | E:\Soft IRs\IIL\I Tower\2.pdf
3 | Sub Structure | 1st floor | IT/3 | 2025-04-18 | 2025-04-18 | ceiling | Check POP false ceiling of zone 2 |  | 103 | A | 2025-05-13 |  |  | E:\Soft IRs\IIL\I Tower\3.pdf
4 | Sub Structure | 1st floor | IT/4 | 2025-04-18 | 2025-04-18 | ceiling | Check POP false ceiling of zone 2 |  | 109 | A | 2025-05-08 |  |  | E:\Soft IRs\IIL\I Tower\4.pdf
5 | Sub Structure | 1st floor | IT/5 | 2025-04-18 | 2025-04-18 | ceiling | Check POP false ceiling of zone 2 |  | 106 | A | 2025-05-13 |  |  | E:\Soft IRs\IIL\I Tower\5.pdf
6 | Sub Structure | 1st floor | IT/6 | 2025-04-18 | 2025-04-18 | ceiling | Check POP false ceiling of zone 2 |  | 105 | OP |  |  |  | E:\Soft IRs\IIL\I Tower\6.pdf
7 | Sub Structure | 1st floor | IT/7 | 2025-04-28 | 2025-04-28 | ceiling | Check POP false ceiling |  | 108 | A | 2025-05-08 |  |  | E:\Soft IRs\IIL\I Tower\7.pdf
8 | Sub Structure | 1st floor | IT/8 | 2025-04-28 | 2025-04-28 | ceiling | Check POP false ceiling of zone 2 |  | 107 | A | 2025-05-05 |  |  | E:\Soft IRs\IIL\I Tower\7A.pdf
9 | Sub Structure | 1st floor | IT/9 | 2025-04-18 | 2025-04-18 | ceiling | Check POP false ceiling of zone 2 |  | 102 | A | 2025-05-13 |  |  | E:\Soft IRs\IIL\I Tower\8.pdf
10 | Sub Structure | 1st floor | IT/10 | 2025-04-30 | 2025-04-30 | ceiling | Check POP false ceiling of zone 2 |  | 104 | A | 2025-05-08 |  |  | E:\Soft IRs\IIL\I Tower\9.pdf
11 | Sub Structure | 2nd floor | IT/11 R01 | 2025-08-13 | 2025-08-13 | ceiling | Check POP false ceiling of apartment |  | 204 | A | 2025-08-15 |  |  | E:\Soft IRs\IIL\I Tower\10.pdf
12 | Sub Structure | 2nd floor | IT/12 R01 | 2025-08-13 | 2025-08-13 | ceiling | Check POP false ceiling of apartment |  | 206 | A | 2025-08-15 |  |  | E:\Soft IRs\IIL\I Tower\11.pdf
13 | Sub Structure | Basement | IT/13 R01 | 2025-08-13 | 2025-08-13 | ceiling | Check POP false ceiling of apartment |  | 205 | A | 2025-08-15 |  |  | E:\Soft IRs\IIL\I Tower\12.pdf
14 | Sub Structure | Basement | IT/14 R01 | 2025-08-13 | 2025-08-13 | ceiling | Check POP false ceiling of apartment |  | 202 | A | 2025-08-15 |  |  | E:\Soft IRs\IIL\I Tower\13.pdf
15 | Sub Structure | Basement | IT/15 R01 | 2025-08-13 | 2025-08-13 | ceiling | Check POP false ceiling of apartment |  | 210 | A | 2025-08-15 |  |  | E:\Soft IRs\IIL\I Tower\14.pdf
16 | Sub Structure | Basement | IT/16 R01 | 2025-08-13 | 2025-08-13 | ceiling | Check POP false ceiling of apartment |  | 208 | A | 2025-08-15 |  |  | E:\14.Soft IRs\IIL\I Tower\15.pdf
17 | Sub Structure | Basement | IT/17 R01 | 2025-08-13 | 2025-08-13 | ceiling | Check POP false ceiling of apartment |  | 207 | A | 2025-08-15 |  |  | E:\14.Soft IRs\IIL\I Tower\16.pdf
18 | Sub Structure | Basement | IT/18 | 2025-07-15 | 2025-07-15 | ceiling | Check POP false ceiling of apartment |  | 203 | A | 2025-07-21 |  |  | E:\14.Soft IRs\IIL\I Tower\17.pdf
|  |  | IT/18 R01 | 2025-08-13 | 2025-08-13 | ceiling | Check POP false ceiling of apartment |  | 203 | A | 2025-08-15
19 | Sub Structure | Basement | IT/19 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\18.pdf
20 | Sub Structure | Basement | IT/20 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\19.pdf
21 | Sub Structure | Basement | IT/21 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\20.pdf
22 | Sub Structure | Basement | IT/22 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\21.pdf
23 | Sub Structure | Basement | IT/23
24 | Sub Structure | Basement | IT/24
25 | Sub Structure | Basement | IT/25 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 210 | A | 2025-10-28
26 | Sub Structure | Basement | IT/26 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 412 | R | 2025-10-28
27 | Sub Structure | Basement | IT/27 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 407 | R | 2025-10-28
28 | Sub Structure | Basement | IT/28 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 410 | R | 2025-10-28
29 | Sub Structure | Basement | IT/29 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 102 | B | 2025-10-28
30 | Sub Structure | Basement | IT/30 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 103 | A | 2025-10-28
31 | Sub Structure | Basement | IT/31 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 104 | B | 2025-10-28
32 | Sub Structure | Basement | IT/32 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 105 | A | 2025-10-28
33 | Sub Structure | Basement | IT/33 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 106 | A | 2025-10-28
34 | Sub Structure | Basement | IT/34 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 107 | A | 2025-10-28
35 | Sub Structure | Basement | IT/35 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 108 | A | 2025-10-28
36 | Sub Structure | Basement | IT/36 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 109 | A | 2025-10-28
37 | Sub Structure | Basement | IT/37 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 110 | B | 2025-10-28
38 | Sub Structure | Basement | IT/38 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 202 | B | 2025-10-28
39 | Sub Structure | Basement | IT/39 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 203 | A | 2025-10-28
40 | Sub Structure | Basement | IT/40 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 204 | A | 2025-10-28
41 | Sub Structure | Basement | IT/41 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 205 | A | 2025-10-28
42 | Sub Structure | Basement | IT/42 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 206 | A | 2025-10-28
43 | Sub Structure | Basement | IT/43 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 207 | B | 2025-10-28
44 | Sub Structure | Basement | IT/44 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 208 | B | 2025-10-28
45 | Sub Structure | Basement | IT/45 | 2025-10-26 | 2025-10-26 | ceiling | Check POP false ceiling of Balcony |  | 310 | R | 2025-10-28
46 | Sub Structure | Basement | IT/46
47 | Sub Structure | Basement | IT/47
48 | Sub Structure | Basement | IT/48
49 | Sub Structure | Basement | IT/49
50 | Sub Structure | Basement | IT/50
51 | Sub Structure | Basement | IT/51
52 | Sub Structure | Basement | IT/52
53 | Sub Structure | Basement | IT/53
54 | Sub Structure | Basement | IT/54
55 | Sub Structure | Basement | IT/55
56 | Sub Structure | Basement | IT/56
57 | Sub Structure | Basement | IT/57
58 | Sub Structure | Basement | IT/58
59 | Sub Structure | Basement | IT/59
60 | Sub Structure | Basement | IT/60
61 | Sub Structure | Basement | IT/61
62 | Sub Structure | Basement | IT/62
63 | Sub Structure | Basement | IT/63
64 | Sub Structure | Basement | IT/64
65 | Sub Structure | Basement | IT/65
66 | Sub Structure | Basement | IT/66
67 | Sub Structure | Basement | IT/67
68 | Sub Structure | Basement | IT/68
69 | Sub Structure | Basement | IT/69
70 | I Tower | Ground | IT/70
| I Tower | Ground | IT/71
72 | I Tower | Ground | IT/72
73 | I Tower | Ground | IT/73
74 | Sub Structure | Basement | IT/74
75 | Sub Structure | Basement | IT/75
76 | I Tower | Ground | IT/76
77 | I Tower | Ground | IT/77
78 | I Tower | Ground | IT/78
79 | I Tower | Ground | IT/79
80 | I Tower | Ground | IT/80
81 | I Tower | Ground | IT/81
82 | I Tower | Ground | IT/82
83 | I Tower | Ground | IT/83
84 | Sub Structure | Basement | IT/84
85 | I Tower | Ground | IT/85
86 | I Tower | Ground | IT/86
87 | I Tower | Ground | IT/87
88 | I Tower | Ground | IT/88
89 | I Tower | Ground | IT/89
90 | I Tower | Ground | IT/90
91 | I Tower | Ground | IT/91
92 | I Tower | Ground
93 | I Tower | Ground
94 | I Tower | Ground
95 | I Tower | Ground
96 | I Tower | Ground
97 | I Tower | Ground
98 | I Tower | Ground
99 | I Tower | Ground
100 | I Tower | Ground
101 | I Tower | Ground
102 | I Tower | Ground
103 | I Tower | Ground
104 | I Tower | Ground
105 | I Tower | Ground
106 | I Tower | Ground
107 | I Tower | Ground
108 | I Tower | Ground
109 | I Tower | Ground
110 | I Tower | Ground
111 | I Tower | 1st Floor
112 | I Tower | 2nd Floor
113 | I Tower | Ground
114 | I Tower | Ground
115 | I Tower | Ground
116 | I Tower | Ground
117 | I Tower | 1st Floor
118 | I Tower | 2nd Floor
119 | I Tower | 1st Floor
120 | I Tower | 1st Floor
121 | I Tower | 2nd Floor
122 | I Tower | 1st Floor
123 | I Tower | 1st Floor
124 | I Tower | 1st Floor
125 | I Tower | 1st Floor
126 | I Tower | 1st Floor
127 | I Tower | 1st Floor
128 | I Tower | 1st floor
129 | I Tower | 2nd floor
130 | I Tower | 2nd floor
131 | I Tower | 1st floor
132 | I Tower | 2nd floor
133 | I Tower | 2nd floor
134 | I Tower | 2nd floor
135 | I Tower | 2nd Floor
136 | I Tower | 2nd Floor
137 | I Tower | 2nd Floor
138 | I Tower | 2nd Floor
139 | I Tower | 2nd Floor
140 | I Tower | 3rd Floor
142 | I Tower | 3rd Floor
143 | I Tower | 3rd Floor
144 | I Tower | 2nd Floor
145 | I Tower | 2nd Floor
146 | I Tower | 3rd Floor
147 | I Tower | 3rd Floor
148 | I Tower | 3rd Floor
149 | I Tower | 3rd Floor
150 | I Tower | 3rd Floor
151 | I Tower | 3rd Floor
152 | I Tower | 3rd Floor
153 | I Tower | 3rd Floor
154 | I Tower | 3rd floor
155 | I Tower | 3rd Floor
156 | I Tower | 4th floor
157 | I Tower | 4th floor
158 | I Tower | 4th floor
159 | I Tower | 4th floor
160 | I Tower | 4th floor
161 | I Tower | 4th floor
162 | I Tower | 4th floor
163 | I Tower | 4th floor
164 | I Tower | 5th Floor
165 | I Tower | 3rd Floor
166 | I Tower | 4th floor
167 | I Tower | 5th Floor
168 | I Tower | 5th Floor
169 | I Tower | 5th Floor
170 | I Tower | 5th Floor
171 | I Tower | 4th floor
172 | I Tower | 5th Floor
173 | I Tower | 6th Floor
174 | I Tower | 6th floor
175 | I Tower | 5th Floor
176 | I Tower | 5th Floor
177 | I Tower | 5th Floor
178 | I Tower | 5th Floor
179 | I Tower | 5th Floor
180 | I Tower | 5th Floor
181 | I Tower | Basement
182 | I Tower | 6th Floor
183 | I Tower | 6th Floor
184 | I Tower | 6th Floor
185 | I Tower | 6th Floor
186 | I Tower | 6th Floor
187 | I Tower | Basement
188 | I Tower | 6th Floor
189 | I Tower | 6th Floor
190 | I Tower | 6th Floor
191 | I Tower | 6th Floor
192 | I Tower | 6th Floor
193 | I Tower | 6th Floor
194 | I Tower | 7th Floor
195 | I Tower | 7th Floor
196 | I Tower | 7th Floor
197 | I Tower | 7th Floor
198 | I Tower | 7th Floor
199 | I Tower | 7th floor
200 | I Tower | 7th Floor
201 | I Tower | 7th Floor
202 | I Tower | 8th Floor
203 | I Tower | 7th Floor
204 | I Tower | 8th Floor
205 | I Tower | 8th Floor
206 | I Tower | 8th Floor
207 | I Tower | 8th Floor
208 | I Tower | 8th Floor
209 | I Tower | 8th Floor
210 | I Tower | 8th Floor
211 | I Tower | 8th Floor
212 | I Tower | 9th Floor
213 | I Tower | 8th Floor
214 | I Tower | 9th Floor
215 | I Tower | 8th Floor
216 | I Tower | 9th Floor
217 | I Tower | 9th Floor
218 | I Tower | 9th Floor
219 | I Tower | 9th Floor
220 | I Tower | 9th Floor
221 | I Tower | 9th Floor
222 | I Tower | 9th Floor
223 | I Tower | 9th Floor
224 | I Tower | 9th Floor
225 | I Tower | 9th Floor
226 | I Tower | 9th Floor
227 | I Tower | 9th Floor
228 | I Tower | 9th Floor
229 | I Tower | 10th Floor
230 | I Tower | 10th Floor
231 | I Tower | 10th Floor
232 | I Tower | 10th Floor
233 | I Tower | 10th Floor
234 | I Tower | 10th Floor
235 | I Tower | 10th Floor
236 | I Tower | 10th Floor
237 | I Tower | 10th Floor
238 | I Tower | 10th Floor
239 | I Tower | 10th Floor
240 | I Tower | 10th Floor
241 | I Tower | 11th Floor
242 | I Tower | 11th Floor
243 | I Tower | 11th Floor
244 | I Tower | 11th Floor
245 | I Tower | 11th Floor
246 | I Tower | 11th Floor
247 | I Tower | 11th Floor
248 | I Tower | 11th Floor
249 | I Tower | 11th Floor
250 | I Tower | 11th Floor
251 | I Tower | 11th Floor
252 | I Tower | 11th Floor
253 | I Tower | 11th Floor
254 | I Tower | 11th Floor
255 | I Tower | 11th Floor
256 | I Tower | 11th Floor
257 | I Tower | 11th Floor
258 | I Tower | 11th Floor
259 | I Tower | 11th Floor
260 | I Tower | 11th Floor
261 | I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor | [13 empty] | v
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
| I Tower | 11th Floor
2022-12-19

## Buildko
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) IIL-CSL | [5 empty] | Fully Approved (A) |  | 8
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 0 |  | As of : |  | 2025-12-19
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 8
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR closing Date | Pour Card No. | Concrete Qty (m3) | Attachment | Remarks
1 | Sub Structure | 1st floor | IT/1 | 2025-03-05 | 2025-03-06 | ceiling | Check ceiling of apartment No. 112 without balcony |  |  | A | 2025-03-06 |  |  | E:\Soft IRs\IIL\I Tower\1.pdf
2 | Sub Structure | 2nd floor | IT/2 | 2025-03-07 | 2025-03-07 | ceiling | Check ceiling of apartment No. 211 without balcony |  |  | A | 2025-03-07 |  |  | E:\Soft IRs\IIL\I Tower\2.pdf
3 | Sub Structure | 2nd floor | IT/3 | 2025-03-07 | 2025-03-07 | ceiling | Check ceiling of apartment No. 212 without balcony |  |  | A | 2025-03-07 |  |  | E:\Soft IRs\IIL\I Tower\3.pdf
4 | Sub Structure | 2nd floor | IT/4 | 2025-03-07 | 2025-03-07 | ceiling | Check ceiling of apartment No. 215 without balcony |  |  | A | 2025-03-07 |  |  | E:\Soft IRs\IIL\I Tower\4.pdf
5 | Sub Structure | 2nd floor | IT/5 | 2025-03-07 | 2025-03-07 | ceiling | Check ceiling of apartment No. 216 without balcony |  |  | A | 2025-03-07 |  |  | E:\Soft IRs\IIL\I Tower\5.pdf
6 | Sub Structure | 2nd floor | IT/6 | 2025-04-21 | 2025-04-21 | ceiling | Check ceiling of apartment No. 209 without balcony |  |  | A | 2025-05-08 |  |  | E:\Soft IRs\IIL\I Tower\6.pdf
7 | Sub Structure | 2nd floor | IT/7 | 2025-04-21 | 2025-04-21 | ceiling | Check ceiling of apartment No. 214 without balcony |  |  | A | 2025-05-05 |  |  | E:\Soft IRs\IIL\I Tower\7.pdf
9 | Sub Structure | 2nd floor | IT/8 | 2025-04-21 | 2025-04-21 | ceiling | Check ceiling of apartment No. 213 without balcony |  |  | A | 2025-05-08 |  |  | E:\Soft IRs\IIL\I Tower\8.pdf
10 | Sub Structure | Basement | IT/9 | [10 empty] | E:\Soft IRs\IIL\I Tower\9.pdf
11 | Sub Structure | Basement | IT/10 | [10 empty] | E:\Soft IRs\IIL\I Tower\10.pdf
12 | Sub Structure | Basement | IT/11 | [10 empty] | E:\Soft IRs\IIL\I Tower\11.pdf
13 | Sub Structure | Basement | IT/12 | [10 empty] | E:\Soft IRs\IIL\I Tower\12.pdf
14 | Sub Structure | Basement | IT/13 | [10 empty] | E:\Soft IRs\IIL\I Tower\13.pdf
15 | Sub Structure | Basement | IT/14 | [10 empty] | E:\Soft IRs\IIL\I Tower\14.pdf
16 | Sub Structure | Basement | IT/15 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\15.pdf
17 | Sub Structure | Basement | IT/16 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\16.pdf
18 | Sub Structure | Basement | IT/17 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\17.pdf
19 | Sub Structure | Basement | IT/18 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\18.pdf
20 | Sub Structure | Basement | IT/19 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\19.pdf
21 | Sub Structure | Basement | IT/20 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\20.pdf
22 | Sub Structure | Basement | IT/21 | [10 empty] | E:\14.Soft IRs\IIL\I Tower\21.pdf
23 | Sub Structure | Basement | IT/22
24 | Sub Structure | Basement | IT/23
25 | Sub Structure | Basement | IT/24
26 | Sub Structure | Basement | IT/25
27 | Sub Structure | Basement | IT/26
28 | Sub Structure | Basement | IT/27
29 | Sub Structure | Basement | IT/28
30 | Sub Structure | Basement | IT/29
31 | Sub Structure | Basement | IT/30
32 | Sub Structure | Basement | IT/31
33 | Sub Structure | Basement | IT/32
34 | Sub Structure | Basement | IT/33
35 | Sub Structure | Basement | IT/34
36 | Sub Structure | Basement | IT/35
37 | Sub Structure | Basement | IT/36
38 | Sub Structure | Basement | IT/37
39 | Sub Structure | Basement | IT/38
40 | Sub Structure | Basement | IT/39
41 | Sub Structure | Basement | IT/40
42 | Sub Structure | Basement | IT/41
43 | Sub Structure | Basement | IT/42
44 | Sub Structure | Basement | IT/43
45 | Sub Structure | Basement | IT/44
46 | Sub Structure | Basement | IT/45
47 | Sub Structure | Basement | IT/46
48 | Sub Structure | Basement | IT/47
49 | Sub Structure | Basement | IT/48
50 | Sub Structure | Basement | IT/49
51 | Sub Structure | Basement | IT/50
52 | Sub Structure | Basement | IT/51
53 | Sub Structure | Basement | IT/52
54 | Sub Structure | Basement | IT/53
55 | Sub Structure | Basement | IT/54
56 | Sub Structure | Basement | IT/55
57 | Sub Structure | Basement | IT/56
58 | Sub Structure | Basement | IT/57
59 | Sub Structure | Basement | IT/58
60 | Sub Structure | Basement | IT/59
61 | Sub Structure | Basement | IT/60
62 | Sub Structure | Basement | IT/61
63 | Sub Structure | Basement | IT/62
64 | Sub Structure | Basement | IT/63
65 | Sub Structure | Basement | IT/64
66 | Sub Structure | Basement | IT/65
67 | Sub Structure | Basement | IT/66
68 | Sub Structure | Basement | IT/67
69 | Sub Structure | Basement | IT/68
70 | I Tower | Ground | IT/69
| I Tower | Ground | IT/70 A
72 | I Tower | Ground | IT/71
73 | I Tower | Ground | IT/72
74 | Sub Structure | Basement | IT/73
75 | Sub Structure | Basement | IT/74
76 | I Tower | Ground | IT/75
77 | I Tower | Ground | IT/76
78 | I Tower | Ground | IT/77
79 | I Tower | Ground | IT/78
80 | I Tower | Ground | IT/79
81 | I Tower | Ground | IT/80
82 | I Tower | Ground | IT/81
83 | I Tower | Ground | IT/82
84 | Sub Structure | Basement | IT/83
85 | I Tower | Ground | IT/84
86 | I Tower | Ground | IT/85
87 | I Tower | Ground | IT/86
88 | I Tower | Ground | IT/87
89 | I Tower | Ground | IT/88
90 | I Tower | Ground | IT/89
91 | I Tower | Ground | IT/90
92 | I Tower | Ground | IT/91
93 | I Tower | Ground | IT/92
94 | I Tower | Ground | IT/93
95 | I Tower | Ground | IT/94
96 | I Tower | Ground | IT/95
97 | I Tower | Ground | IT/96
98 | I Tower | Ground | IT/97
99 | I Tower | Ground | IT/98
100 | I Tower | Ground | IT/99
101 | I Tower | Ground | IT/100
102 | I Tower | Ground | IT/101
103 | I Tower | Ground | IT/102
104 | I Tower | Ground | IT/103
105 | I Tower | Ground | IT/104
106 | I Tower | Ground | IT/105
107 | I Tower | Ground | IT/106
108 | I Tower | Ground | IT/107
109 | I Tower | Ground | IT/108
110 | I Tower | Ground | IT/109
111 | I Tower | 1st Floor | IT/110
112 | I Tower | 2nd Floor | IT/111
113 | I Tower | Ground | IT/112
114 | I Tower | Ground | IT/113
115 | I Tower | Ground | IT/114
116 | I Tower | Ground | IT/115
117 | I Tower | 1st Floor | IT/116
118 | I Tower | 2nd Floor | IT/117
119 | I Tower | 1st Floor | IT/118
120 | I Tower | 1st Floor | IT/119
121 | I Tower | 2nd Floor | IT/120
122 | I Tower | 1st Floor | IT/121
123 | I Tower | 1st Floor | IT/122
124 | I Tower | 1st Floor | IT/123
125 | I Tower | 1st Floor | IT/124
126 | I Tower | 1st Floor | IT/125
127 | I Tower | 1st Floor | IT/126
128 | I Tower | 1st floor | IT/127
129 | I Tower | 2nd floor | IT/128
130 | I Tower | 2nd floor | IT/129
131 | I Tower | 1st floor | IT/130
132 | I Tower | 2nd floor | IT/131
133 | I Tower | 2nd floor | IT/132
134 | I Tower | 2nd floor | IT/133
135 | I Tower | 2nd Floor | IT/134
136 | I Tower | 2nd Floor | IT/135
137 | I Tower | 2nd Floor | IT/136
138 | I Tower | 2nd Floor | IT/137
139 | I Tower | 2nd Floor | IT/138
140 | I Tower | 3rd Floor | IT/139
142 | I Tower | 3rd Floor | IT/140
143 | I Tower | 3rd Floor | IT/141
144 | I Tower | 2nd Floor | IT/142
145 | I Tower | 2nd Floor | IT/143
146 | I Tower | 3rd Floor | IT/144
147 | I Tower | 3rd Floor | IT/145
148 | I Tower | 3rd Floor | IT/146
149 | I Tower | 3rd Floor | IT/147
150 | I Tower | 3rd Floor | IT/148
151 | I Tower | 3rd Floor | IT/149
152 | I Tower | 3rd Floor | IT/150
153 | I Tower | 3rd Floor | IT/151
154 | I Tower | 3rd floor | IT/152
155 | I Tower | 3rd Floor | IT/153
156 | I Tower | 4th floor | IT/154
157 | I Tower | 4th floor | IT/155
158 | I Tower | 4th floor | IT/156
159 | I Tower | 4th floor | IT/157
160 | I Tower | 4th floor | IT/158
161 | I Tower | 4th floor | IT/159
162 | I Tower | 4th floor | IT/160
163 | I Tower | 4th floor | IT/161
164 | I Tower | 5th Floor | IT/162
165 | I Tower | 3rd Floor | IT/163
166 | I Tower | 4th floor | IT/164
167 | I Tower | 5th Floor | IT/165
168 | I Tower | 5th Floor | IT/166
169 | I Tower | 5th Floor | IT/167
170 | I Tower | 5th Floor | IT/168
171 | I Tower | 4th floor | IT/169
172 | I Tower | 5th Floor | IT/170
173 | I Tower | 6th Floor | IT/171
174 | I Tower | 6th floor | IT/172
175 | I Tower | 5th Floor | IT/173
176 | I Tower | 5th Floor | IT/174
177 | I Tower | 5th Floor | IT/175
178 | I Tower | 5th Floor | IT/176
179 | I Tower | 5th Floor | IT/177
180 | I Tower | 5th Floor | IT/178
181 | I Tower | Basement | IT/179
182 | I Tower | 6th Floor | IT/180
183 | I Tower | 6th Floor | IT/181
184 | I Tower | 6th Floor | IT/182
185 | I Tower | 6th Floor | IT/183
186 | I Tower | 6th Floor | IT/184
187 | I Tower | Basement | IT/185
188 | I Tower | 6th Floor | IT/186
189 | I Tower | 6th Floor | IT/187
190 | I Tower | 6th Floor | IT/188
191 | I Tower | 6th Floor | IT/189
192 | I Tower | 6th Floor | IT/190
193 | I Tower | 6th Floor | IT/191
194 | I Tower | 7th Floor | IT/192
195 | I Tower | 7th Floor | IT/193
196 | I Tower | 7th Floor | IT/194
197 | I Tower | 7th Floor | IT/195
198 | I Tower | 7th Floor | IT/196
199 | I Tower | 7th floor | IT/197
200 | I Tower | 7th Floor | IT/198
201 | I Tower | 7th Floor | IT/199
202 | I Tower | 8th Floor | IT/200
203 | I Tower | 7th Floor | IT/201
204 | I Tower | 8th Floor | IT/202
205 | I Tower | 8th Floor | IT/203
206 | I Tower | 8th Floor | IT/204
207 | I Tower | 8th Floor | IT/205
208 | I Tower | 8th Floor | IT/206
209 | I Tower | 8th Floor | IT/207
210 | I Tower | 8th Floor | IT/208
211 | I Tower | 8th Floor | IT/209
212 | I Tower | 9th Floor | IT/210
213 | I Tower | 8th Floor | IT/211
214 | I Tower | 9th Floor | IT/212
215 | I Tower | 8th Floor | IT/213
216 | I Tower | 9th Floor | IT/214
217 | I Tower | 9th Floor | IT/215
218 | I Tower | 9th Floor | IT/216
219 | I Tower | 9th Floor | IT/217
220 | I Tower | 9th Floor | IT/218
221 | I Tower | 9th Floor | IT/219
222 | I Tower | 9th Floor | IT/220
223 | I Tower | 9th Floor | IT/221
224 | I Tower | 9th Floor | IT/222
225 | I Tower | 9th Floor | IT/223
226 | I Tower | 9th Floor | IT/224
227 | I Tower | 9th Floor | IT/225
228 | I Tower | 9th Floor | IT/226
229 | I Tower | 10th Floor | IT/227
230 | I Tower | 10th Floor | IT/228
231 | I Tower | 10th Floor | IT/229
232 | I Tower | 10th Floor | IT/230
233 | I Tower | 10th Floor | IT/231
234 | I Tower | 10th Floor | IT/232
235 | I Tower | 10th Floor | IT/233
236 | I Tower | 10th Floor | IT/234
237 | I Tower | 10th Floor | IT/235
238 | I Tower | 10th Floor | IT/236
239 | I Tower | 10th Floor | IT/237
240 | I Tower | 10th Floor | IT/238
241 | I Tower | 11th Floor | IT/239
242 | I Tower | 11th Floor | IT/240
243 | I Tower | 11th Floor | IT/241
244 | I Tower | 11th Floor | IT/242
245 | I Tower | 11th Floor | IT/243
246 | I Tower | 11th Floor | IT/244
247 | I Tower | 11th Floor | IT/245
248 | I Tower | 11th Floor | IT/246
249 | I Tower | 11th Floor | IT/247
250 | I Tower | 11th Floor | IT/248
251 | I Tower | 11th Floor | IT/249
252 | I Tower | 11th Floor | IT/250
253 | I Tower | 11th Floor | IT/251
254 | I Tower | 11th Floor | IT/252
255 | I Tower | 11th Floor | IT/253
256 | I Tower | 11th Floor | IT/254
257 | I Tower | 11th Floor | IT/255
258 | I Tower | 11th Floor | IT/256
259 | I Tower | 11th Floor | IT/257
260 | I Tower | 11th Floor | IT/258
261 | I Tower | 11th Floor | IT/259
| I Tower | 11th Floor | IT/260
| I Tower | 11th Floor | IT/261
| I Tower | 11th Floor | IT/262
| I Tower | 11th Floor | IT/263
| I Tower | 11th Floor | IT/264
| I Tower | 11th Floor | IT/265
| I Tower | 11th Floor | IT/266
| I Tower | 11th Floor | IT/267
| I Tower | 11th Floor | IT/268
| I Tower | 11th Floor | IT/269 | [12 empty] | v
| I Tower | 11th Floor | IT/270
| I Tower | 11th Floor | IT/271
| I Tower | 11th Floor | IT/272
| I Tower | 11th Floor | IT/273
| I Tower | 11th Floor | IT/274
| I Tower | 11th Floor | IT/275
| I Tower | 11th Floor | IT/276
| I Tower | 11th Floor | IT/277
| I Tower | 11th Floor | IT/278
| I Tower | 11th Floor | IT/279
| I Tower | 11th Floor | IT/280
| I Tower | 11th Floor | IT/281
| I Tower | 11th Floor | IT/282
| I Tower | 11th Floor | IT/283
| I Tower | 11th Floor | IT/284
2022-12-19

## Rock Stone
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 214
[9 empty] | Approved with comments (B) |  | 155
[9 empty] | Rejected ( R) |  | 96
[9 empty] | Open/Pending (OP) |  | 19
[9 empty] | Total |  | 484
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | 1st to 2nd lfoor | IT/1 | 2025-03-20 | 2025-03-20 | travertine | Check travertine (clading) work inside the rear side column |  | 1A to 25A | OP
2 | Sub Structure | 1st, 5th floor | IT/2 | 2025-03-20 | 2025-03-21 | China verona | Check china verona (Window sill) work of rear side |  | 1A to 25A | R | 22-3-25
3 | Sub Structure | 1st floor | IT/3 | 2025-03-20 | 2025-03-20 | travertine | Check travertine (Wall cladding) work of rear side lift wall |  | 9A-11A & 16A-18A | A | 22-3-25
4 | Sub Structure | 1st to 2nd lfoor | IT/4 | 2025-03-20 | 2025-03-20 | travertine | Check travertine (cladding) work inside the fron side columns |  | 1E to 25E | B | 22-3-25
5 | Sub Structure | 1st , 5th floor | IT/5 | 2025-03-20 | 2025-03-20 | China verona | Check china verona (Window sill) work of rear side |  | 1E to 25E, 1E to 1C | R | 22-3-25
6 | Sub Structure |  | IT/6 | 2025-03-20 | 2025-03-20 | travertine | Check travertine (cladding) work fron side column of Tower 2 |  | U/26 | R | 22-3-25
7 | Sub Structure | 1st to Top | IT/7 | 2025-03-20 | 2025-03-20 | travertine | Check travertine (cladding) work fron side column |  | 9E to 17E | R | 22-3-25
8 | Sub Structure | Top floor | IT/8 | 2025-03-20 | 2025-03-20 | travertine | Check travertine (cladding) work fron side column |  | 10E to 17E | R | 22-3-25
9 | Sub Structure |  | IT/9 | 2025-03-20 | 2025-03-20 | travertine | Check travertine (cladding) work fron side columns of tower 2 |  | 10E to 17E | R | 22-3-25
10 | Sub Structure |  | IT/10 | 2025-03-20 | 2025-03-20 | travertine | Check travertine (cladding) work fron side columns of tower 2 |  | U/26 | OP
11 | Sub Structure |  | IT/11 | 2025-03-20 | 2025-03-20 | travertine | Check travertine (cladding) work front side of side columns |  | 1C to 1E | A | 22-3-25
12 | Sub Structure |  | IT/12 | 2025-03-20 | 2025-03-20 | travertine | Check travertine (cladding) work beam of side columns |  | 1C to 1E | OP
13 | Sub Structure | 9th floor | IT/13 | 2025-05-16 | 2025-05-16 | travertine | Check travertine (Cladding) work fron side columns |  | L & R Side | A | 2025-05-16
14 | Sub Structure | 10th floor | IT/14 | 2025-05-16 | 2025-05-16 | travertine | Check travertine (Cladding) work fron side columns |  | L & R Side | A | 2025-05-16
15 | Sub Structure | 1st to 11th | IT/15 | 2025-05-16 | 2025-05-16 | travertine | Check travertine (Cladding) work fron side columns |  | L & R Side | A | 2025-05-16
16 | Sub Structure | 1st to 12 | IT/16 | 2025-05-16 | 2025-05-16 | travertine | Check travertine (Cladding) work fron side columns |  | L & R Side | A | 2025-05-16
17 | Sub Structure | 1st to 13th floor | IT/17 | 2025-05-16 | 2025-05-16 | travertine | Check travertine (Cladding) work fron side columns |  | L & R Side | A | 2025-05-16
18 | Sub Structure | 1st to 14th | IT/18 | 2025-05-16 | 2025-05-16 | travertine | Check travertine (Cladding) work fron side columns |  | L & R Side | A | 2025-05-16
19 | Sub Structure | 1st to 15th floor | IT/19 | 2025-05-16 | 2025-05-16 | travertine | Check travertine (Cladding) work fron side columns |  | L & R Side | A | 2025-05-16
20 | Sub Structure | 1st to 16th | IT/20 | 2025-05-16 | 2025-05-16 | travertine | Check travertine (Cladding) work fron side columns |  | L & R Side | A | 2025-05-16
21 | Sub Structure | 1st to 17th | IT/21 | 2025-05-16 | 2025-05-16 | travertine | Check travertine (Cladding) work fron side columns |  | L & R Side | A | 2025-05-16
22 | Sub Structure | 1st floor | IT/22 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-101 | B | 2025-05-12
23 | Sub Structure | 1st floor | IT/23 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-103 | B | 2025-05-12
24 | Sub Structure | 1st floor | IT/24 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-105 | B | 2025-05-12
25 | Sub Structure | 1st floor | IT/25 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-107 | B | 2025-05-12
26 | Sub Structure | 1st floor | IT/26 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-109 | B | 2025-05-12
27 | Sub Structure | 1st floor | IT/27 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-111 | B | 2025-05-12
28 | Sub Structure | 1st floor | IT/28 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-113 | OP | 2025-05-12
29 | Sub Structure | 1st floor | IT/29 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-102 | B | 2025-05-12
30 | Sub Structure | 1st floor | IT/30 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-104 | B | 2025-05-12
31 | Sub Structure | 1st floor | IT/31 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-106 | B | 2025-05-12
32 | Sub Structure | 1st floor | IT/32 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-108 | B | 2025-05-12
33 | Sub Structure | 1st floor | IT/33 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-110 | B | 2025-05-12
34 | Sub Structure | 1st floor | IT/34 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-112 | B | 2025-05-12
35 | Sub Structure | 1st floor | IT/35 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-114 | B | 2025-05-12
36 | Sub Structure | 1st floor | IT/36 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-116 | B | 2025-05-12
37 | Sub Structure | 1st floor | IT/37 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-115 | B | 2025-05-12
38 | Sub Structure | 2nd floor | IT/38 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-201 | B | 2025-05-12
39 | Sub Structure | 2nd floor | IT/39 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-203 | B | 2025-05-12
40 | Sub Structure | 2nd floor | IT/40 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-205 | B | 2025-05-12
41 | Sub Structure | 2nd floor | IT/41 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-207 | B | 2025-05-12
42 | Sub Structure | 2nd floor | IT/42 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-209 | B | 2025-05-12
43 | Sub Structure | 2nd floor | IT/43 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-211 | B | 2025-05-12
44 | Sub Structure | 2nd floor | IT/44 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-213 | B | 2025-05-12
45 | Sub Structure | 2nd floor | IT/45 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-202 | B | 2025-05-12
46 | Sub Structure | 2nd floor | IT/46 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-204 | B | 2025-05-12
47 | Sub Structure | 2nd floor | IT/47 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-206 | B | 2025-05-12
48 | Sub Structure | 2nd floor | IT/48 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-208 | B | 2025-05-12
49 | Sub Structure | 2nd floor | IT/49 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-210 | B | 2025-05-12
50 | Sub Structure | 2nd floor | IT/50 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-212 | B | 2025-05-12
51 | Sub Structure | 2nd floor | IT/51 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-214 | B | 2025-05-12
52 | Sub Structure | 2nd floor | IT/52 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-216 | B | 2025-05-12
53 | Sub Structure | 2nd floor | IT/53 | 2025-05-08 | 2025-05-09 | verona | Check china verona (Window sill) of rear side |  | T1-215 | B | 2025-05-12
54 | Sub Structure | 1st to 2nd | IT/54 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) front side of columns |  | 1A | B | 2025-05-22
55 | Sub Structure | 5th, 8th, 12th floor | IT/55 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) left side beam |  | 1A-1E | A | 2025-05-22
56 | Sub Structure | 1st to top floor | IT/56 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) front side of columns |  | L& R Side | B | 2025-05-21
57 | Sub Structure | 1st to top floor | IT/57 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) front side of columns |  | 8F | B | 2025-05-21
58 | Sub Structure | 1st to top floor | IT/58 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) front side of columns |  | 18F | B | 2025-05-21
59 | Sub Structure | 1st to top floor | IT/59 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) front side of columns |  | L& R Side | B | 2025-05-21
60 | Sub Structure | 1st to top floor | IT/60 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) front side of columns |  | L& R Side | B | 2025-05-20
61 | Sub Structure | 5th, 8th, 12th floor | IT/61 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) front side of beam |  | 12F-13F | B | 2025-05-20
62 | Sub Structure | 1st to 4th floor | IT/62 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) front side of beam zone 3 |  | 26F to 26G | B | 2025-05-20
63 | Sub Structure | 1st floor | IT/63 | 2025-05-19 | 2025-05-19 | verona | Check china verona (Window sill) work of rear side |  | 101-116 | A | 2025-05-20
64 | Sub Structure | 1st floor | IT/64 | 2025-05-19 | 2025-05-19 | verona | Check china verona (Window sill) work of rear side |  | 101-116 | A | 2025-05-22
65 | Sub Structure | 3rd floor | IT/65 | 2025-05-19 | 2025-05-19 | verona | Check china verona (Window sill) work of rear and front side |  | 301-316 | B | 2025-05-21
66 | Sub Structure | 4th floor | IT/66 | 2025-05-19 | 2025-05-19 | verona | Check china verona (Window sill) work of rear and front side |  | 401-416 | B | 2025-05-21
67 | Sub Structure | 5th floor | IT/67 | 2025-05-19 | 2025-05-19 | verona | Check china verona (Window sill) work of rear and front side |  | 501-516 | B | 2025-05-20
68 | Sub Structure | 1st floor | IT/68 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) work inner side of column rear & fron side |  |  | B | 2025-05-20
69 | Sub Structure | 2nd floor | IT/69 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) work inner side of column rear & fron side |  |  | B | 2025-05-19
70 | Sub Structure | 5th, 8th, 12th floor | IT/70 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) work fron beam of L Tower 2 |  | 18U-26U | A | 2025-05-19
71 | Sub Structure | 1st floor to top floor | IT/71 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) work fron side column |  | 16U-26U | A | 2025-05-19
72 | Sub Structure | 1st floor to top floor | IT/72 | 2025-05-19 | 2025-05-19 | travertine | check travertine (cladding) work fron beam of I Tower |  | 6F-18F | B | 2025-05-19
73 | Sub Structure | 1st floor to top floor | IT/73 | 2025-06-02 | 2025-06-03 | travertine | check travertine (cladding) back column |  | 16M-17M | B | 2025-06-04
74 | Sub Structure | 1st floor | IT/74 | 2025-06-02 | 2025-06-03 | verona | check china verona (Window sill) fron side |  | 102-116 | A | 2025-06-04
75 | Sub Structure | 2nd floor | IT/75 | 2025-06-02 | 2025-06-03 | verona | check china verona (Window sill) fron side |  | 202-216 | A | 2025-06-04
76 | Sub Structure | 3rd floor | IT/76 | 2025-06-02 | 2025-06-03 | verona | check china verona (Window sill) fron side |  | 302-316 | A | 2025-06-04
77 | Sub Structure | 4th floor | IT/77 | 2025-06-02 | 2025-06-03 | verona | check china verona (Window sill) fron side |  | 402-416 | B | 2025-06-04
78 | Sub Structure | 5th floor | IT/78 | 2025-06-02 | 2025-06-03 | verona | check china verona (Window sill) fron side |  | 502-516 | B | 2025-06-04
79 | Sub Structure | 6th floor | IT/79 | 2025-06-02 | 2025-06-03 | verona | check china verona (Window sill) fron side |  | 602-616 | B | 2025-06-04
80 | Sub Structure | 7th floor | IT/80 | 2025-06-02 | 2025-06-03 | verona | check china verona (Window sill) fron side |  | 702-716 | B | 2025-06-04
81 | Sub Structure | 8th floor | IT/81 | 2025-06-02 | 2025-06-03 | verona | check china verona (Window sill) fron side |  | 802-816 | B | 2025-06-04
82 | Sub Structure | 9th floor | IT/82 | 2025-06-02 | 2025-06-03 | verona | check china verona (Window sill) fron side |  | 902-916 | R | 2025-06-04
83 | Sub Structure | Wall | IT/83 | 2025-06-02 | 2025-06-03 | travertine | check travertine (cladding) work front wall zone 3 |  | 23f-26f | B | 2025-06-04
|  |  | IT/83 R01 | 2025-08-26 | 2025-08-26 | travertine | check travertine (cladding) work front wall zone 3 |  | 23f-26f | B | 2025-08-28
|  |  | IT/83 R02 | 2025-09-14 | 2025-09-14 | travertine | check travertine (cladding) work front wall zone 3 |  | 23f-26f | A | 2025-09-23
84 | Sub Structure | elevation | IT/84 | 2025-06-19 | 2025-06-19 | travertine | Check travertine cladding work to allow the work |  |  | A | 2025-06-19
85 | Sub Structure | elevation | IT/85 | 2025-06-19 | 2025-06-19 | travertine | allow to start the work of travertine |  |  | A | 2025-06-20
86 | Sub Structure | Ground floor | IT/86 | 2025-06-19 | 2025-06-19 | China verona | Allow to start the fixing work of china veronaq & botticina on floor |  |  | A | 2025-06-19
87 | Sub Structure | elevation | IT/87 | 2025-06-20 | 2025-06-20 | travertine | allow to start the work of travertine on backside |  |  | A | 2025-06-20
88 | Sub Structure | Ground floor | IT/88 | 2025-06-23 | 2025-06-23 | sardinia marble | check sardinia marble/stone sample cladding on column |  | back side I Tower | R | 2025-06-23
89 | Sub Structure | 1st Floor | IT/89 | 2025-07-22 | 2025-07-22 | Window sill | Check 13ft window sills |  | 7th floor | R | 2025-06-26
90 | Sub Structure | 5th Floor | IT/90
91 | Sub Structure | 5th Floor | IT/91
92 | Sub Structure | 5th Floor | IT/92
93 | Sub Structure | 8th floor | IT/93 | 2025-07-22 | 2025-07-22 | Window sill | Check 13ft window sills |  | 8th floor | OP
94 | Sub Structure | 9th floor | IT/94 | 2025-07-22 | 2025-07-22 | Window sill | Check 13ft window sills |  | 9th floor | OP
95 | Sub Structure | 5th Floor | IT/95
96 | Sub Structure | 5th Floor | IT/96 | 2025-07-17 | 2025-07-17 | sardinia marble | check sardinia marble/stone sample cladding on column |  | GF | A | 2025-06-21
97 | Sub Structure | 8th floor | IT/97 | 2025-07-22 | 2025-07-22 | Window sill | Check 13ft window sills |  | 8th floor | R | 2025-06-26
98 | Sub Structure | 9th floor | IT/98 | 2025-07-22 | 2025-07-22 | Window sill | Check 13ft window sills |  | 9th floor | R | 2025-06-26
99 | Sub Structure | 5th Floor | IT/99 | 2025-07-24 | 2025-07-24 | travertine | allow to start the work of travertine(1/2") fixing of column |  | 1st floor | A | 2025-06-26
100 | Sub Structure | 5th Floor | IT/100 | 2025-07-24 | 2025-07-24 | cladding | Check cladding work of sardina marble on the gf columns |  | GF | A | 2025-06-26
101 | Sub Structure | 2nd Floor | IT/101 | 2025-07-24 | 2025-07-24 | travertine | allow to start the work of travertine(1/2") fixing of column |  | 1st floor | A | 2025-06-30
102 | Sub Structure | 5th Floor | IT/102 | 2025-07-24 | 2025-07-24 | travertine | allow to start the work of travertine(1/2") fixing |  | 1st floor | A | 2025-06-30
103 | Sub Structure | 6th Floor | IT/103 | 2025-07-24 | 2025-07-24 | travertine | allow to start the work of travertine(1/2") fixing of column |  | 3rd floor | A | 2025-06-30
104 | Sub Structure | GF Plan | IT/104 | 2025-07-25 | 2025-07-25 | China verona | allow to start the work of gf lobby fixing of china verona |  | GF | A | 2025-06-26
105 | Sub Structure | 7th Floor | IT/105 | 2025-07-28 | 2025-07-28 | travertine | allow to start the work of travertine(3/4") fixing of gf column |  | GF | A | 2025-06-30
106 | Sub Structure | GF Plan | IT/106 | 2025-07-03 | 2025-07-03 | travertine | Check the travertine (3/4')fixingwork of ground floor |  | GF | A | 2025-08-06
107 | Sub Structure | 3rd floor | IT/107 | 2025-08-01 | 2025-08-01 | travertine | Check cladding work of sardina marble on the gf columns inner side |  | 3rd floor | B | 2025-08-12
|  |  | IT/107 R01 | 2025-08-26 | 2025-08-26 | travertine | Check cladding work of sardina marble on the gf columns inner side |  | 3rd floor | B | 2025-08-28
|  |  | IT/107 R02 | 2025-09-14 | 2025-09-14 | travertine | Check cladding work of sardina marble on the gf columns inner side |  | 3rd floor | A | 2025-09-23
108 | Sub Structure | 2nd floor | IT/108 | 2025-07-31 | 2025-07-31 | travertine | Check cladding work of sardina marble on the gf columns inner side |  | 2nd floor | B | 2025-08-08
|  |  | IT/108 R01 | 2025-08-26 | 2025-08-26 | travertine | Check cladding work of sardina marble on the gf columns inner side |  | 2nd floor | B | 2025-08-28
|  |  | IT/108 R02 | 2025-09-14 | 2025-09-14 | travertine | Check cladding work of sardina marble on the gf columns inner side |  | 2nd floor | A | 2025-09-18
109 | Sub Structure | 1st floor | IT/109 | 2025-07-31 | 2025-07-31 | travertine | Check cladding work of sardina marble on the gf columns inner side |  | 1st floor | B | 2025-08-08
|  |  | IT/109 R01 | 2025-08-26 | 2025-08-26 | travertine | Check cladding work of sardina marble on the gf columns inner side |  | 1st floor | B | 2025-08-28
|  |  | IT/109 R02 | 2025-09-14 | 2025-09-14 | travertine | Check cladding work of sardina marble on the gf columns inner side |  | 1st floor | A | 2025-09-18
110 | Sub Structure | 1st floor | IT/110 | 2025-07-31 | 2025-07-31 | Window sill | Check 13' window sill work 1st front side of tower |  | 1st floor | A | 2025-08-06
111 | Sub Structure | 1st floor | IT/111 | 2025-07-31 | 2025-07-31 | Window sill | Check 13' window sill work 1st back side of tower |  | 1st floor | A | 2025-08-06
112 | Sub Structure | 2nd floor | IT/112 | 2025-07-31 | 2025-07-31 | Window sill | Check 13' window sill work 2nd front side of tower |  | 2nd floor | R | 2025-08-06
113 | Sub Structure | 2nd floor | IT/113 | 2025-07-31 | 2025-07-31 | Window sill | Check 13' window sill work 2nd back side of tower |  | 2nd floor | R | 2025-08-06
114 | Sub Structure | 3rd floor | IT/114 | 2025-07-31 | 2025-07-31 | Window sill | Check 13' window sill work 3rd front side of tower |  | 3rd floor | R | 2025-08-06
115 | Sub Structure | 3rd floor | IT/115 | 2025-07-31 | 2025-07-31 | Window sill | Check 13' window sill work 3rd back side of tower |  | 3rd floor | R | 2025-08-06
116 | Sub Structure | 4th floor | IT/116 | 2025-07-31 | 2025-07-31 | Window sill | Check 13' window sill work 4th front side of tower |  | 4th floor | R | 2025-08-06
117 | Sub Structure | 4th floor | IT/117 | 2025-07-31 | 2025-07-31 | Window sill | Check 13' window sill work 4th back side of tower |  | 4th floor | R | 2025-08-06
118 | Sub Structure | 5th floor | IT/118 | 2025-07-31 | 2025-07-31 | Window sill | Check 13' window sill work 5th front side of tower |  | 5th floor | R | 2025-08-06
119 | Sub Structure | 5th floor | IT/119 | 2025-07-31 | 2025-07-31 | Window sill | Check 13' window sill work 5th back side of tower |  | 5th floor | A | 2025-08-06
120 | Sub Structure | 6th floor | IT/120 | 2025-08-01 | 2025-08-01 | Window sill | Check 13' window sill work 6th front side of tower |  | 6th floor | R | 2025-08-06
121 | Sub Structure | 6th floor | IT/121 | 2025-08-01 | 2025-08-01 | Window sill | Check 13' window sill work 6th back side of tower |  | 6th floor | R | 2025-08-06
122 | Sub Structure | 1st floor | IT/122 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work1st floor front side of tower |  | 1st floor | R | 2025-08-06
123 | Sub Structure | 2nd floor | IT/123 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work 2nd floor front side of tower |  | 2nd floor | R | 2025-08-06
124 | Sub Structure | 3rd floor | IT/124 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work 3rd floor front side of tower |  | 3rd floor | R | 2025-08-06
125 | Sub Structure | 4th floor | IT/125 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work 4th floor front side of tower |  | 4th floor | R | 2025-08-06
126 | Sub Structure | 5th floor | IT/126 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work 5th floor front side of tower |  | 5th floor | R | 2025-08-06
127 | Sub Structure | 6th floor | IT/127 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work 6th floor front side of tower |  | 6th floor | R | 2025-08-06
128 | Sub Structure | Empty plot side | IT/128 | 2025-08-01 | 2025-08-01 | travertine | allow to start the work of travertine(1/2") fixing of column |  | empty plot side | A | 2025-08-08
129 | Sub Structure | Rear Elevation | IT/129 | 2025-08-01 | 2025-08-01 | travertine | allow to start the work of travertine(1/2") fixing of column |  | Rear Elevation | B | 2025-08-08
|  |  | IT/129 R01 | 2025-08-26 | 2025-08-26 | travertine | allow to start the work of travertine(1/2") fixing of column |  | Rear Elevation | B | 2025-08-28
|  |  | IT/129 R02 | 2025-09-14 | 2025-09-14 | travertine | allow to start the work of travertine(1/2") fixing of column |  | Rear Elevation | A | 2025-09-23
|  |  | IT/129 R03 | 2025-11-17 | 2025-11-17 | travertine | allow to start the work of travertine(1/2") fixing of column |  | Rear Elevation | A | 2025-11-18
130 | Sub Structure | 1st floor | IT/130 | 2025-08-01 | 2025-08-01 | Window sill | Check to mark the outer plaster level and give approval to start bedroom 7' window sill |  | 1st floor | R | 2025-08-08
131 | Sub Structure | 7th Floor | IT/131 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work 7th floor front side of tower |  | 7th floor | R | 2025-08-04
132 | Sub Structure | 8th floor | IT/132 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work 8th floor front side of tower |  | 8th floor | R | 2025-08-04
133 | Sub Structure | 9th floor | IT/133 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work 9th floor front side of tower |  | 9th floor | R | 2025-08-04
| Sub Structure | 10th floor | IT/134 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work 10th floor front side of tower |  | 10th floor | R | 2025-08-04
| Sub Structure | 11th floor | IT/135 | 2025-08-01 | 2025-08-01 | Window sill | Check 7'' window sill work 11th floor front side of tower |  | 11th floor | R | 2025-08-04
| Sub Structure | 3rd Floor | IT/136 | 2025-08-02 | 2025-08-02 | plaster surface | Check the plaster surface and plaster surface level and allow to start tracertine |  | Grid A/8-11 | A | 2025-08-08
| Sub Structure | 4th floor | IT/137 | 2025-08-16 | 2025-08-16 | travertine | allow to start the work of travertine(1/2") fixing of column |  | Grid A/13-14 | A
| Sub Structure | 3rd Floor | IT/138 | 2025-08-16 | 2025-08-16 | sardinia marble | Check the fixing of Saridina Marble |  | Grid D/13-14 | R
| Sub Structure | GF Plan | IT/138 R1 | 2025-10-16 | 2025-10-16 | sardinia marble | Check the fixing of Saridina Marble |  | Grid D/13-14 | B | 2025-10-18
| Sub Structure | GF Plan | IT/138 R2 | 2025-10-31 | 2025-10-31 | sardinia marble | Check the fixing of Saridina Marble |  | Grid D/13-14 | R | 2025-11-06
| Sub Structure | GF Plan | IT/138 R3 | 2025-11-07 | 2025-11-07 | sardinia marble | Check the fixing of Saridina Marble |  | Grid D/13-14 | A | 2025-11-10
| Sub Structure | 2nd floor | IT/139 | 2025-08-18 | 2025-08-18 | sardinia marble | Check the fixing of Saridina Marble |  | Grid F/12-15 | B
| Sub Structure | 4th Floor | IT/140 | 2025-09-13 | 2025-09-13 | sardinia marble | Allow to start the work of Marble |  | GF 3rd floor | R | 2025-09-17
| Sub Structure | 3rd Floor | IT/141 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 101 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 101 | A | 2025-08-29
| Sub Structure | 2nd floor | IT/142 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 102 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 102 | B | 2025-08-29
| Sub Structure | 2nd floor | IT/142 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 102 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 102 | B | 2025-11-10
| Sub Structure | 2nd floor | IT/143 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 103 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 103 | B | 2025-08-29
| Sub Structure | 2nd floor | IT/143 R1 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 103 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 103 | A | 2025-11-10
| Sub Structure | 6th Floor | IT/144 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 104 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 104 | B | 2025-08-29
| Sub Structure | 6th Floor | IT/144 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 104 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 104 | B | 2025-11-10
| Sub Structure | 7th Floor | IT/145 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 105 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 105 | A | 2025-08-29
| Sub Structure | 4th Floor | IT/146 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 106 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 106 | B | 2025-08-29
| Sub Structure | 4th Floor | IT/146 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 106 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 106 | R | 2025-11-11
| Sub Structure | 3rd floor | IT/147 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 107 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 107 | A | 2025-08-29
| Sub Structure | 5th Floor | IT/148 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 108 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 108 | A | 2025-08-29
| Sub Structure | 4th Floor | IT/149 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 109 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 109 | A | 2025-09-04
| Sub Structure | 2nd floor | IT/150 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 110 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 110 | A | 2025-09-04
| Sub Structure | 5th Floor | IT/151 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 111 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 111 | A | 2025-08-29
| Sub Structure | 3rd Floor | IT/152 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 112 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 112 | A | 2025-09-03
| Sub Structure | 3rd Floor | IT/153 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 113 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 113 | A | 2025-08-29
| Sub Structure | 3rd Floor | IT/154 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 114 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 114 | A | 2025-08-29
| Sub Structure | 7th Floor | IT/155 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 115 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 115 | B | 2025-08-29
| Sub Structure | 7th Floor | IT/155 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 115 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 115 | B | 2025-11-10
| Sub Structure | 7th Floor | IT/156 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 116 on 1st Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 1st Floor Aparment No. 116 | A | 2025-08-29
| Sub Structure | 5th Floor | IT/157 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 201 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 201 | R | 2025-08-29
| Sub Structure | 5th Floor | IT/157 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 201 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 201 | A | 2025-11-12
| Sub Structure | 5th floor | IT/158 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 202 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 202 | B | 2025-08-29
| Sub Structure | 5th floor | IT/158 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 202 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 202 | R | 2025-11-12
| Sub Structure | 4th Floor | IT/159 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 203 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 203 | A | 2025-08-29
| Sub Structure | 2nd Floor | IT/160 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 204 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 204 | B | 2025-08-29
| Sub Structure | 2nd Floor | IT/160 R01 | 2025-11-10 | 11\/10/2025 | Window sill | Please visit the site and check the work of window sills at Apartment No. 204 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 204 | R | 2025-11-12
| Sub Structure | 3rd Floor | IT/161 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 205 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 205 | B | 2025-08-29
| Sub Structure | 3rd Floor | IT/161 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 205 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 205 | A | 2025-11-12
| Sub Structure | 3rd Floor | IT/162 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 206 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 206 | B | 2025-08-29
| Sub Structure | 3rd Floor | IT/162 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 206 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 206 | R | 2025-11-12
| Sub Structure | 3rd Floor | IT/163 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 207 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 207 | B | 2025-08-29
| Sub Structure | 3rd Floor | IT/163 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 207 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 207 | A | 2025-11-12
| Sub Structure | 3rd Floor | IT/164 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 208 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 208 | B | 2025-08-29
| Sub Structure | 3rd Floor | IT/164 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 208 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 208 | A | 2025-11-12
| Sub Structure | 6th Floor | IT/165 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 209 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 209 | A | 2025-08-29
| Sub Structure | 3rd Floor | IT/166 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 210 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 210 | A | 2025-08-29
| Sub Structure | 3rd Floor | IT/167 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 211 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 211 | B | 2025-08-29
| Sub Structure | 3rd Floor | IT/167 R1 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 211 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 211 | A | 2025-11-12
| Sub Structure | 8th Floor | IT/168 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 212 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 212 | B | 2025-08-29
| Sub Structure | 8th Floor | IT/168 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 212 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 212 | R | 2025-11-12
| Sub Structure | 8th Floor | IT/169 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 213 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 213 | A | 2025-08-29
| Sub Structure | 4th Floor | IT/170 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 214 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 214 | B | 2025-08-29
| Sub Structure | 4th Floor | IT/170 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 214 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 214 | A | 2025-11-12
| Sub Structure | 4th Floor | IT/171 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 215 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 215 | B | 2025-08-29
| Sub Structure | 4th Floor | IT/171 R1 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 215 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 215 | R | 2025-11-12
| Sub Structure | 8th Floor | IT/172 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 216 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 216 | B | 2025-08-29
| Sub Structure | 8th Floor | IT/172 R1 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 216 on 2nd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 2nd Floor Aparment No. 216 | R | 2025-11-12
| Sub Structure | Basement | IT/173 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 301 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 301 | A | 2025-08-29
| Sub Structure | 3rd Floor | IT/174 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 302 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 302 | B | 2025-08-29
| Sub Structure | 3rd Floor | IT/174 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 302 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 302 | A | 2025-11-14
| Sub Structure | 6th Floor | IT/175 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 303 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 303 | B | 2025-08-29
| Sub Structure | 6th Floor | IT/175 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 303 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 303 | A | 2025-11-14
| Sub Structure | 5th Floor | IT/176 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 304 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 304 | R | 2025-08-29
| Sub Structure | 5th Floor | IT/176 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 304 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 304 | B | 2025-11-14
| Sub Structure | 8th Floor | IT/177 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 305 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 305 | R | 2025-08-29
| Sub Structure | 8th Floor | IT/177 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 305 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 305 | B | 2025-11-14
| Sub Structure | 8th Floor | IT/178 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 306 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 306 | B | 2025-08-29
| Sub Structure | 8th Floor | IT/178 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 306 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 306 | R | 2025-11-14
| Sub Structure | 4th Floor | IT/179 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 307 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 307 | B | 2025-08-29
| Sub Structure | 4th Floor | IT/179 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 307 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 307 | A | 2025-11-14
| Sub Structure | 4th Floor | IT/180 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 308 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 308 | A | 2025-08-29
| Sub Structure | 8th Floor | IT/181 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 309 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 309 | B | 2025-08-29
| Sub Structure | 8th Floor | IT/181 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 309 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 309 | A | 2025-11-14
| Sub Structure | 8th Floor | IT/182 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 310 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 310 | A | 2025-08-29
| Sub Structure | 1st floor | IT/183 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 311 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 311 | R | 2025-08-29
| Sub Structure | 1st floor | IT/183 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 311 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 311 | R | 2025-11-14
| Sub Structure | 2nd floor | IT/184 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 312 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 312 | B | 2025-08-29
| Sub Structure | 2nd floor | IT/184 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 312 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 312 | B | 2025-11-14
| Sub Structure | 4th Floor | IT/185 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 313 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 313 | B | 2025-08-29
| Sub Structure | 4th Floor | IT/185 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 313 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 313 | A | 2025-11-14
| Sub Structure | 4th Floor | IT/186 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 314 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 314 | A | 2025-08-29
| Sub Structure | 5th Floor | IT/187 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 315 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 315 | R | 2025-08-29
| Sub Structure | 5th Floor | IT/187 R1 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 315 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 315 | A | 2025-11-14
| Sub Structure | 5th Floor | IT/188 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 316 on 3rd Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 3rd Floor Aparment No. 316 | A | 2025-08-29
| Sub Structure | Basement | IT/189 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 401 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 401 | A | 2025-08-29
| Sub Structure | 6th Floor | IT/190 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 402 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 402 | B | 2025-08-29
| Sub Structure | 6th Floor | IT/190 R 01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 402 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 402 | B | 2025-11-10
| Sub Structure | 6th Floor | IT/191 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 403 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 403 | A | 2025-08-29
| Sub Structure | Basement | IT/192 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 404 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 404 | B | 2025-08-29
| Sub Structure | Basement | IT/192 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 404 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 404 | A | 2025-11-10
| Sub Structure | 8th Floor | IT/193 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 405 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 405 | A | 2025-08-29
| Sub Structure | 8th Floor | IT/194 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 406 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 406 | B | 2025-08-29
| Sub Structure | 8th Floor | IT/194 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 406 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 406 | A | 2025-11-10
| Sub Structure | 9th Floor | IT/195 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 407 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 407 | A | 2025-08-29
| Sub Structure | 9th Floor | IT/196 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 408 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 408 | B | 2025-08-29
| Sub Structure | 9th Floor | IT/196 r01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 408 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 408 | A | 2025-11-10
| Sub Structure | 5th floor | IT/197 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 409 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 409 | A | 2025-08-29
| Sub Structure | 5th Floor | IT/198 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 410 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 410 | B | 2025-08-29
| Sub Structure | 5th Floor | IT/198 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 410 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 410 | A | 2025-11-10
| Sub Structure | 9th Floor | IT/199 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 411 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 411 | A | 2025-08-29
| Sub Structure | 9th Floor | IT/200 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 412 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 412 | A | 2025-08-29
| Sub Structure | 5th Floor | IT/201 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 413 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 413 | A | 2025-08-29
| Sub Structure | 5th Floor | IT/202 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 414 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 414 | A | 2025-08-29
| Sub Structure | 8th floor | IT/203 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 415 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 415 | B | 2025-08-29
| Sub Structure | 8th floor | IT/203 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 415 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 415 | A | 2025-11-10
| Sub Structure | 8th Floor | IT/204 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 416 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 416 | B | 2025-08-29
| Sub Structure | 8th Floor | IT/204 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 416 on 4th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 4th Floor Aparment No. 416 | A | 2025-11-10
| Sub Structure | 3rd Floor | IT/205 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 501 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 501 | B | 2025-09-03
| Sub Structure | 3rd Floor | IT/205 R1 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 501 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 501 | R | 2025-11-11
| Sub Structure | 4th Floor | IT/206 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 502 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 502 | R | 2025-09-03
| Sub Structure | 4th Floor | IT/206 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 502 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 502 | R | 2025-11-11
| Sub Structure | 5th Floor | IT/207 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 503 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 503 | A | 2025-09-03
| Sub Structure | 10th Floor | IT/208 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 504 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 504 | R | 2025-09-03
| Sub Structure | 10th Floor | IT/208 R1 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 504 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 504 | B | 2025-11-11
| Sub Structure | 10th Floor | IT/209 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 505 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 505 | A | 2025-09-03
| Sub Structure | Basement | IT/210 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 506 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 506 | R | 2025-09-03
| Sub Structure | Basement | IT/210 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 506 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 506 | B | 2025-11-11
| Sub Structure | 6th floor | IT/211 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 507 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 507 | A | 2025-09-03
| Sub Structure | 6th floor | IT/212 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 508 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 508 | A | 2025-09-03
| Sub Structure | 5th Floor | IT/213 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 509 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 509 | A | 2025-09-03
| Sub Structure | 5th Floor | IT/214 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 510 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 510 | R | 2025-09-03
| Sub Structure | 5th Floor | IT/214 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 510 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 510 | A | 2025-11-11
| Sub Structure | 7th Floor | IT/215 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 511 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 511 | A | 2025-09-03
| Sub Structure | 8th Floor | IT/216 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 512 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 512 | R | 2025-09-03
| Sub Structure | 8th Floor | IT/216 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 512 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 512 | R | 2025-11-11
| Sub Structure | 8th Floor | IT/217 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 513 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 513 | A | 2025-09-03
| Sub Structure | 5th floor | IT/218 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 514 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 514 | A | 2025-09-03
| Sub Structure | Ground floor | IT/219 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 515 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 515 | R | 2025-09-02
| Sub Structure | Ground floor | IT/219 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 515 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 515 | B | 2025-11-11
| Sub Structure | 7th Floor | IT/220 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 516 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 516 | R | 2025-09-02
| Sub Structure | 7th Floor | IT/220 R1 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 516 on 5th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 5th Floor Aparment No. 516 | A | 2025-11-11
| Sub Structure | 7th Floor | IT/221 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 601 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 601 | R | 2025-09-02
| Sub Structure | 7th Floor | IT/221 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 601 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 601 | A | 2025-11-12
| Sub Structure | 7th Floor | IT/222 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 602 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 602 | R | 2025-09-02
| Sub Structure | 7th Floor | IT/222 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 602 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 602 | B | 2025-11-12
| Sub Structure | 8th Floor | IT/223 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 603 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 603 | B | 2025-09-02
| Sub Structure | 8th Floor | IT/223 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 603 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 603 | A | 2025-11-12
| Sub Structure | 8th Floor | IT/224 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 604 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 604 | R | 2025-09-03
| Sub Structure | 8th Floor | IT/224 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 604 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 604 | A | 2025-11-12
| Sub Structure | 8th Floor | IT/225 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 605 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 605 | R | 2025-09-02
| Sub Structure | 8th Floor | IT/225 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 605 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 605 | A | 2025-11-12
| Sub Structure | 8th Floor | IT/226 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 606 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 606 | B | 2025-09-02
| Sub Structure | 8th Floor | IT/226 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 606 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 606 | A | 2025-11-12
| Sub Structure | 6th floor | IT/227 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 607 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 607 | R | 2025-09-02
| Sub Structure | 6th floor | IT/227 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 607 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 607 | A | 2025-11-12
| Sub Structure | 8th floor | IT/228 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 608 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 608 | A | 2025-09-02
| Sub Structure | 6th Floor | IT/229 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 609 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 609 | B | 2025-09-02
| Sub Structure | 6th Floor | IT/229 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 609 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 609 | A | 2025-11-12
| Sub Structure | 6th Floor | IT/230 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 610 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 610 | A | 2025-09-02
| Sub Structure | 8th Floor | IT/231 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 611 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 611 | A | 2025-09-02
| Sub Structure | 7th Floor | IT/232 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 612 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 612 | A | 2025-09-02
| Sub Structure | 10th Floor | IT/233 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 613 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 613 | A | 2025-09-02
| Sub Structure | Basement | IT/234 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 614 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 614 | R | 2025-09-02
| Sub Structure | Basement | IT/234 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 614 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 614 | A | 2025-11-12
| Sub Structure | 11th floor | IT/235 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 615 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 615 | R | 2025-09-02
| Sub Structure | 11th floor | IT/235 R1 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 615 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 615 | A | 2025-11-12
| Sub Structure | 11th floor | IT/236 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 616 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 616 | R | 2025-09-02
| Sub Structure | 11th floor | IT/236 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 616 on 6th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 6th Floor Aparment No. 616 | A | 2025-11-12
| Sub Structure | 8th floor | IT/237 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 702 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 702 | R | 2025-08-28
| Sub Structure | 8th floor | IT/237 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 702 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 702 | B | 2025-11-14
| Sub Structure | 8th floor | IT/238 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 704 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 704 | R | 2025-08-28
| Sub Structure | 8th floor | IT/238 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 704 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 704 | B | 2025-11-14
| Sub Structure | 7th floor | IT/239 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 706 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 706 | B | 2025-08-28
| Sub Structure | 7th floor | IT/239 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 706 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 706 | B | 2025-11-14
| Sub Structure | 7th floor | IT/240 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 708 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 708 | A | 2025-08-28
| Sub Structure | 7th floor | IT/241 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 710 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 710 | B | 2025-08-28
| Sub Structure | 7th floor | IT/241 R1 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 710 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 710 | A | 2025-11-10
| Sub Structure | basement | IT/242 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 712 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 712 | B | 2025-08-28
| Sub Structure | basement | IT/242 R1 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 712 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 712 | A | 2025-11-10
| Sub Structure | 11th floor | IT/243 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 714 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 714 | B | 2025-08-28
| Sub Structure | 11th floor | IT/243 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 714 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 714 | A | 2025-11-10
| Sub Structure | 5th floor | IT/244 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 716 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 716 | B | 2025-08-28
| Sub Structure | 5th floor | IT/244 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 716 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 716 | A | 2025-11-10
| Sub Structure | 6th floor | IT/245 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 715 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 715 | R | 2025-08-28
| Sub Structure | 6th floor | IT/245 R01 | 2025-11-06 | 2025-11-06 | Window sill | Please visit the site and check the work of window sills at Apartment No. 715 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 7th Floor Aparment No. 715 | A | 2025-11-10
| Sub Structure | 7th floor | IT/246 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 802 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 802 | R | 2025-08-28
| Sub Structure | 7th floor | IT/246 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 802 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 802 | B | 2025-11-12
| Sub Structure | GF | IT/247 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 804 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 804 | B | 2025-08-28
| Sub Structure | GF | IT/247 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 804 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 804 | B | 2025-11-12
| Sub Structure | GF | IT/248 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 8026on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 806 | B | 2025-08-28
| Sub Structure | GF | IT/248 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 8026on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 806 | A | 2025-11-12
| Sub Structure | 8th Floor | IT/249 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 808 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 808 | B | 2025-08-28
| Sub Structure | 8th Floor | IT/249 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 808 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 808 | A | 2025-11-12
| Sub Structure | 8th Floor | IT/250 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 810 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 810 | B | 2025-08-28
| Sub Structure | 8th Floor | IT/250 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 810 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 810 | A | 2025-11-12
| Sub Structure | 8th Floor | IT/251 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 812 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 812 | R | 2025-08-28
| Sub Structure | 8th Floor | IT/251 R1 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 812 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 812 | A | 2025-11-12
| Sub Structure | 9th Floor | IT/252 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 814 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 814 | B | 2025-08-28
| Sub Structure | 9th Floor | IT/252 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 814 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 814 | A | 2025-11-12
| Sub Structure | 9th Floor | IT/253 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 816 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 816 | B | 2025-08-28
| Sub Structure | 9th Floor | IT/253 R01 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 816 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 816 | A | 2025-11-12
| Sub Structure | 7th floor | IT/254 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 815 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 815 | R | 2025-08-28
| Sub Structure | 7th floor | IT/254 R1 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 815 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 8th Floor Aparment No. 815 | R | 2025-11-12
| Sub Structure | 8th floor | IT/255 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 902 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 902 | R | 2025-08-28
| Sub Structure | 8th floor | IT/255 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 902 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 902 | B | 2025-11-14
| Sub Structure | GF | IT/256 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 904 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 904 | B | 2025-08-28
| Sub Structure | GF | IT/256 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 904 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 904 | A | 2025-11-14
| Sub Structure | GF | IT/257 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 906 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 906 | B | 2025-08-28
| Sub Structure | GF | IT/257 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 906 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 906 | B | 2025-11-14
| Sub Structure | 8th floor | IT/258 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 908 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 908 | B | 2025-08-28
| Sub Structure | 8th floor | IT/258 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 908 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 908 | R | 2025-11-14
| Sub Structure | 9th floor | IT/259 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 910 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 910 | B | 2025-08-28
| Sub Structure | 9th floor | IT/259 R01 | 2025-11-11 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 910 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 910 | A | 2025-11-14
| Sub Structure | 9th floor | IT/260 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 912 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 912 | B | 2025-08-28
| Sub Structure | 9th floor | IT/260 R1 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 912 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 912 | A | 2025-11-14
| Sub Structure | 9th floor | IT/261 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 914 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 914 | B | 2025-08-28
| Sub Structure | 9th floor | IT/261 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 914 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 914 | A | 2025-11-14
| Sub Structure | 9th floor | IT/262 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 916 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 916 | B | 2025-08-28
| Sub Structure | 9th floor | IT/262 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 916 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 916 | A | 2025-11-14
| Sub Structure | 9th floor | IT/263 | 2025-08-26 | 2025-08-26 | Window sill | Please visit the site and check the work of window sills at Apartment No. 915 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 915 | R | 2025-08-28
| Sub Structure | 9th floor | IT/263 R01 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 915 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  | I Tower 9th Floor Aparment No. 915 | B | 2025-11-14
| Sub Structure | 8th floor | IT/264 | 2025-08-26 | 2025-08-26 | travertine | Check travertine (1/2") fixing at the horizental & vertical band of front elevation |  | Grid F-G/06-21 | B | 2025-08-28
| Sub Structure | 8th floor | IT/264 R01 | 2025-09-14 | 2025-09-14 | travertine | Check travertine (1/2") fixing at the horizental & vertical band of front elevation |  | Grid F-G/06-21 | A | 2025-09-23
| Sub Structure | 8th floor | IT/265 | 2025-08-26 | 2025-08-26 | travertine | Check travertine (1/2") fixing at the horizental & vertical band at umt side |  | Grid A-E/01 | B | 2025-08-28
| Sub Structure | 8th floor | IT/265 R01 | 2025-09-14 | 2025-09-14 | travertine | Check travertine (1/2") fixing at the horizental & vertical band at umt side |  | Grid A-E/01 | A | 2025-09-23
| Sub Structure | 9th floor | IT/266 | 2025-08-26 | 2025-08-26 | travertine | Check travertine (1/2") fixing work of columns/vertical band of the rear elevation |  | Grid A/15-16 | B | 2025-08-28
| Sub Structure | 9th floor | IT/266 R01 | 2025-09-14 | 2025-09-14 | travertine | Check travertine (1/2") fixing work of columns/vertical band of the rear elevation |  | Grid A/15-16 | A | 2025-09-23
| Sub Structure | 9th floor | IT/267 | 2025-09-22 | 2025-09-22 | travertine | Check travertine (1/2") fixing work of columns/vertical band of the rear elevation |  | Rear Elevation | A | 2025-09-29
| Sub Structure | 2nd floor | IT/268 | 2025-10-07 | 2025-10-07 | travertine | Check travertine (1/2") fixing work of columns/vertical band of the rear elevation |  | Grid A/13-14 | A | 2025-10-09
| Sub Structure | 1st floor | IT/269 | 2025-10-08 | 2025-10-08 | travertine | Check travertine (1/2") fixing at the horizental & vertical band of the rear elevation |  | Grid A/11-12 | A | 2025-10-09
| Sub Structure | 1st floor | IT/270 | 2025-10-16 | 2025-10-16 | Marble | Check the installation work of marble at GF lobby |  | GF Lobby | B | 2025-10-18
| Sub Structure | 1st floor | IT/270 R01 | 2025-10-28 | 2025-10-28 | Marble | Check the installation work of marble at GF lobby |  | GF Lobby | A | 2025-10-31
| Sub Structure | 1st floor | IT/271 | 2025-10-16 | 2025-10-16 | sardinia marble | Check the fixing of Saridina Marble AT columns of ground floor lobby |  | GF Lobby | B | 2025-10-18
| Sub Structure | 8th floor | IT/272 | 2025-10-21 | 2025-10-21 | travertine | Visit the site and allow us to start work of travertine(1/2") on the back column |  | Rear Elevation | A | 2025-10-23
| Sub Structure | 8th floor | IT/273 | 2025-10-21 | 2025-10-21 | travertine | Visit the site and allow us to start work of travertine(1/2") on the back column |  | Back boundary wall | A | 2025-10-23
| Sub Structure | 8th floor | IT/274 | 2025-10-21 | 2025-10-21 | China Verona | Visit the site and allow us to start work of China verona (1/2") on the back column |  | Zone 2 Emergency stair | A | 2025-10-23
| Sub Structure | 1st floor | IT/275 | 2025-10-21 | 2025-10-21 | travertine | Visit the site and allow us to start work of travertine(1/2") on the back column |  | Rear Elevation | A | 2025-11-01
| Sub Structure | 1st floor | IT/276 | 2025-10-22 | 2025-10-22 | travertine | Visit the site and allow us to start work of travertine(1/2") on the back column |  |  | B | 2025-11-06
| Sub Structure | 1st floor | IT/276 R01 | 2025-11-03 | 2025-11-03 | travertine | Visit the site and allow us to start work of travertine(1/2") on the back column |  |  | B | 2025-11-06
| Sub Structure | 1st floor | IT/276 R02 | 2025-11-12 | 2025-11-12 | travertine | Visit the site and allow us to start work of travertine(1/2") on the back column |  |  | A | 2025-11-18
| Sub Structure | 1st floor | IT/277 | 2025-10-28 | 2025-10-28 | travertine | Visit the site and allow us to start work of travertine(1/2") fixing work at the horizental and vertical band |  | Rear Elevation | A | 2025-11-01
| Sub Structure | 7th floor | IT/278 | 2025-10-28 | 2025-10-28 | travertine | Visit the site and allow us to start work of travertine(3/4") fixing work at wall, GF rear elevation |  | Rear Elevation | A | 2025-11-01
| Sub Structure | 1st Floor | IT/279 | 2025-10-28 | 2025-10-28 | travertine | Visit the site and allow us to start work of travertine(3/4") fixing work at wall, GF rear elevation |  | Rear Elevation | A | 2025-11-01
| Sub Structure | 8th floor | IT/280 | 2025-10-31 | 2025-10-31 | sardinia marble | visit thye site and allow us to start work of sardinia marble |  | Wall ground floor | A | 2025-11-06
| Sub Structure | 8th floor | IT/281 | 2025-10-31 | 2025-10-31 | Marble | visit thye site and allow us to start work of sardinia marble |  | Lift Ground floor | A | 2025-11-07
| Sub Structure | Basement | IT/282 | 2025-10-31 | 2025-10-31
| Sub Structure | 9th floor | IT/283 | 2025-11-03 | 2025-11-03 | travertine | please visit the site and check the travertine(3/4") fixing work at the boundary wall |  | boundary wall I tower | A | 2025-11-06
| Sub Structure | 9th floor | IT/283 R01 | 2025-11-24 | 2025-11-24 | travertine | please visit the site and check the travertine(3/4") fixing work at the boundary wall |  | boundary wall I tower | A | 2025-11-26
| Sub Structure | 10th floor | IT/284 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 401 | A | 2025-11-05
| Sub Structure | 2nd floor | IT/285 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 403 | A | 2025-11-05
| Sub Structure | 2nd floor | IT/286 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 404 | A | 2025-11-05
| Sub Structure | 10th floor | IT/287 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 405 | A | 2025-11-05
| Sub Structure | 9th floor | IT/288 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 406 | A | 2025-11-05
| Sub Structure | 7th floor | IT/289 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 407 | A | 2025-11-05
| Sub Structure | 2nd floor | IT/290 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 408 | A | 2025-11-05
| Sub Structure | 10th floor | IT/291 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 409 | A | 2025-11-05
| Sub Structure | 10th floor | IT/292 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 410 | A | 2025-11-05
| Sub Structure | 2nd floor | IT/293 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 411 | A | 2025-11-05
| Sub Structure | 2nd floor | IT/294 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 412 | A | 2025-11-05
| Sub Structure | 10th floor | IT/295 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 413 | A | 2025-11-05
| Sub Structure | 10th floor | IT/296 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 414 | A | 2025-11-05
| Sub Structure | 10th floor | IT/297 | 2025-11-03 | 2025-11-03 | travertine | Check the internal work of travertine(1/2") fixing at vertical bend |  | 416 | B | 2025-11-05
| Sub Structure | 9th floor | IT/298 | 2025-11-04 | 2025-11-04 | travertine | Visit the site and allow us to start work of travertine(3/4") fixing work at wall, GF rear elevation |  | Parking area | A | 2025-11-06
| Sub Structure | 2nd floor | IT/299 | 2025-11-06 | 2025-11-06 | travertine | Check the work of travertine(1/2") fixing at the horizental & vertical bendd of the rear Elevation |  | Grid A/19-21 | A | 2025-11-10
| Sub Structure | 2nd floor | IT/300 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 701 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 11th floor | IT/301 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 703 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 11th floor | IT/302 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 705 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 11th floor | IT/303 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 707 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 11th floor | IT/304 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 709 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 1st Floor | IT/305 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 711 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 11th floor | IT/306 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 713 on 7th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 9th floor | IT/307 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 801 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 2nd floor | IT/308 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 803 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 11th floor | IT/309 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 805 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 11th floor | IT/310 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 807 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | B | 2025-11-12
| Sub Structure | 10th floor | IT/311 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 809 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 10th floor | IT/312 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 811 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 2nd floor | IT/313 | 2025-11-10 | 2025-11-10 | Window sill | Please visit the site and check the work of window sills at Apartment No. 813 on 8th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-12
| Sub Structure | 2nd floor | IT/314 |  |  | Window sill
| Sub Structure | 1st floor | IT/315 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at Stair GF |  | Zone 1 Emergency stair | B | 2025-11-11
| Sub Structure | 10th floor | IT/316 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at Stair 1st Floor |  | Zone 1 Emergency stair | B | 2025-11-11
| Sub Structure | 11th floor | IT/317 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at Stair 2nd Floor |  | Zone 1 Emergency stair | B | 2025-11-11
| Sub Structure | 11th floor | IT/318 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 3rdFloor |  | Zone 1 Emergency stair | B | 2025-11-11
| Sub Structure | Basement | IT/319 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 4th Floor |  | Zone 1 Emergency stair | R | 2025-11-10
| Sub Structure | Basement | IT/319 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 4th Floor |  | Zone 1 Emergency stair | OP
| Sub Structure | Basement | IT/319 R02 | 2025-11-18 | 2025-11-18 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 4th Floor |  | Zone 1 Emergency stair | A | 2025-11-21
| Sub Structure | 9th floor | IT/320 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 5th Floor |  | Zone 1 Emergency stair | R | 2025-11-10
| Sub Structure | 9th floor | IT/320 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 5th Floor |  | Zone 1 Emergency stair | OP
| Sub Structure | 9th floor | IT/320 R02 | 2025-11-18 | 2025-11-18 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 5th Floor |  | Zone 1 Emergency stair | A | 2025-11-21
| Sub Structure | 10th floor | IT/321 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 6th Floor |  | Zone 1 Emergency stair | R | 2025-11-10
| Sub Structure | 10th floor | IT/321 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 6th Floor |  | Zone 1 Emergency stair | OP
| Sub Structure | 10th floor | IT/321 R02 | 2025-11-18 | 2025-11-18 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 6th Floor |  | Zone 1 Emergency stair | A | 2025-11-21
| Sub Structure | 9th floor | IT/322 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 7th Floor |  | Zone 1 Emergency stair | R | 2025-11-11
| Sub Structure | 9th floor | IT/322 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 7th Floor |  | Zone 1 Emergency stair | OP
| Sub Structure | 9th floor | IT/322 R02 | 2025-11-15 | 2025-11-15 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 7th Floor |  | Zone 1 Emergency stair | A | 2025-11-21
| Sub Structure | 10th floor | IT/323 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 8th Floor |  | Zone 1 Emergency stair | R | 2025-11-11
| Sub Structure | 10th floor | IT/323 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 8th Floor |  | Zone 1 Emergency stair | OP
| Sub Structure | 10th floor | IT/323 R02 | 2025-11-18 | 2025-11-18 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 8th Floor |  | Zone 1 Emergency stair | A | 2025-11-21
| Sub Structure | 8th floor | IT/324 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 9th Floor |  | Zone 1 Emergency stair | R | 2025-11-11
| Sub Structure | 8th floor | IT/324 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 9th Floor |  | Zone 1 Emergency stair | OP
| Sub Structure | 8th floor | IT/324 R02 | 2025-11-18 | 2025-11-18 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 9th Floor |  | Zone 1 Emergency stair | A | 2025-11-21
| Sub Structure | 9th floor | IT/325 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 10th Floor |  | Zone 1 Emergency stair | R | 2025-11-11
| Sub Structure | 9th floor | IT/325 R02 | 2025-11-18 | 2025-11-18 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 10th Floor |  | Zone 1 Emergency stair | R | 2025-11-21
| Sub Structure | 9th floor | IT/326 | 2025-11-07 | 2025-11-07
| Sub Structure | 3rd floor | IT/327 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at Stair GF |  | Zone 3 Public stair | B | 2025-11-11
| Sub Structure | 3rd floor | IT/328 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" 1st Stair GF |  | Zone 3 Public stair | B | 2025-11-11
| Sub Structure | 3rd floor | IT/329 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at Stair 2nd Floor |  | Zone 3 Public stair | B | 2025-11-11
| Sub Structure | 6th floor | IT/330 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 3rdFloor |  | Zone 3 Public stair | B | 2025-11-11
| Sub Structure | 7th floor | IT/331 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 4th Floor |  | Zone 3 Public stair | R | 2025-11-10
| Sub Structure | 7th floor | IT/331 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 4th Floor |  | Zone 3 Public stair | OP
| Sub Structure | 8th floor | IT/332 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 5th Floor |  | Zone 3 Public stair | R | 2025-11-10
| Sub Structure | 8th floor | IT/332 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 5th Floor |  | Zone 3 Public stair | OP
| Sub Structure | 8th floor | IT/333 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 6th Floor |  | Zone 3 Public stair | R | 2025-11-10
| Sub Structure | 8th floor | IT/333 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 6th Floor |  | Zone 3 Public stair | OP
| Sub Structure | 8th floor | IT/333 R02 | 2025-11-18 | 2025-11-18 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 6th Floor |  | Zone 3 Public stair | A | 2025-11-21
| Sub Structure | 8th floor | IT/334 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 7th Floor |  | Zone 3 Public stair | B | 2025-11-11
| Sub Structure | 8th floor | IT/335 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 8th Floor |  | Zone 3 Public stair | R | 2025-11-11 |  |  |  | 2024-08-15
| Sub Structure | 10th floor | IT/336 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 9th Floor |  | Zone 3 Public stair | R | 2025-11-11
| Sub Structure | 10th floor | IT/336 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 9th Floor |  | Zone 3 Public stair | OP
| Sub Structure | 10th floor | IT/336 R02 | 2025-11-18 | 2025-11-18 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 9th Floor |  | Zone 3 Public stair | A | 2025-11-21
| Sub Structure | 10th floor | IT/337 | 2025-11-07 | 2025-11-07 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 10th Floor |  | Zone 3 Public stair | R | 2025-11-11
| Sub Structure | 10th floor | IT/337 R01 | 2025-11-13 | 2025-11-13 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 10th Floor |  | Zone 3 Public stair | OP
| Sub Structure | 10th floor | IT/337 R03 | 2025-11-21 | 2025-11-21 | China Verona | Visit the Site and verify work of China Verona marble 3/4" at 10th Floor |  | Zone 3 Public stair | A | 2025-11-24
| Sub Structure | 3rd floor | IT/338 | 2025-11-07 | 2025-11-07 | Cmor White Marble | Visit the Site and verify work of cmor White marble 3/4" |  | GF Kitchen(101-105) | R | 2025-11-11
| Sub Structure | 3rd floor | IT/338 R01 | 2025-11-13 | 2025-11-13 | Cmor White Marble | Visit the Site and verify work of cmor White marble 3/4" |  | GF Kitchen(101-105) | OP
| Sub Structure | 3rd floor | IT/338 R02 | 2025-11-18 | 2025-11-18 | Cmor White Marble | Visit the Site and verify work of cmor White marble 3/4" |  | GF Kitchen(101-105) | A | 2025-11-20
| Sub Structure | 3rd floor | IT/339 | 2025-11-07 | 2025-11-07 | Cmor White Marble | Visit the Site and verify work of cmor White marble 3/4" |  | GF Kitchen(106-110) | R | 2025-11-11
| Sub Structure | 3rd floor | IT/339 R01 | 2025-11-13 | 2025-11-13 | Cmor White Marble | Visit the Site and verify work of cmor White marble 3/4" |  | GF Kitchen(106-110) | OP
| Sub Structure | 3rd floor | IT/339 R02 | 2025-11-18 | 2025-11-18 | Cmor White Marble | Visit the Site and verify work of cmor White marble 3/4" |  | GF Kitchen(106-110) | A | 2025-11-20
| Sub Structure | 11th floor | IT/340 | 2025-11-07 | 2025-11-07 | Cmor White Marble | Visit the Site and verify work of cmor White marble 3/4" |  | GF Kitchen(111, 114-116) | R | 2025-11-11
| Sub Structure | 11th floor | IT/340 R01 | 2025-11-13 | 2025-11-13 | Cmor White Marble | Visit the Site and verify work of cmor White marble 3/4" |  | GF Kitchen(111, 114-116) | R | 2025-11-18
| Sub Structure | 11th floor | IT/340 R02 | 2025-11-18 | 2025-11-18 | Cmor White Marble | Visit the Site and verify work of cmor White marble 3/4" |  | GF Kitchen(111, 114-116) | B | 2025-11-18
| Sub Structure | 3rd floor | IT/341 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 901 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-14
| Sub Structure | 3rd floor | IT/342 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 903 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-14
| Sub Structure | 9th floor | IT/343 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 905 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-14
| Sub Structure | 9th floor | IT/344 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 907 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-14
| Sub Structure | 11th floor | IT/345 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 909 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-14
| Sub Structure | 11th floor | IT/346 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 911 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-14
| Sub Structure | 11th floor | IT/347 | 2025-11-11 | 2025-11-11 | Window sill | Please visit the site and check the work of window sills at Apartment No. 913 on 9th Floor of I Tower, including the bedroom (W15) and living room (W6) window sills. |  |  | A | 2025-11-14
| Sub Structure | 11th floor | IT/348 | 2025-11-13 | 2025-11-13 | travertine | Check the work of travertine(1/2") fixing at the horizental & vertical bendd of the rear Elevation |  |  | A | 2025-11-18
| Sub Structure | 4th floor | IT/349 | 2025-11-15 | 2025-11-15 | China Verona | Visit the site and verify work of China Verona marble (3/4")at Grounf floor only stair step or riser |  | Zone 3 (GF\Floor) | A | 2025-11-19
| Sub Structure | 4th floor | IT/350 | 2025-11-15 | 2025-11-15 | China Verona | Visit the site and verify work of China Verona marble (3/4")at 1st floor only stair step or riser |  | Zone 3 (1st Floor) | A | 2025-11-19
| Sub Structure | 10th floor | IT/351 | 2025-11-15 | 2025-11-15 | China Verona | Visit the site and verify work of China Verona marble (3/4")at 2nd floor only stair step or riser |  | Zone 3 (2nd Floor) | A | 2025-11-19
| Sub Structure | 10th floor | IT/352 | 2025-11-17 | 2025-11-17 | China Verona | Visit the site and verify work of China Verona marble (3/4")at 3rd floor only stair step or riser |  | Zone 3 (3rd Floor) | A | 2025-11-19
| Sub Structure | 4th floor | IT/353 R01 | 2025-11-18 | 2025-11-18 | China Verona | Visit the site and verify work of China Verona marble (3/4")at 3rd floor only stair step or riser |  | Zone 3 (3th Floor) | A | 2025-11-21
| Sub Structure | 4th floor | IT/354 | 2025-11-15 | 2025-11-15 | China Verona | Visit the site and verify work of China Verona marble (3/4")at 5th floor only stair step or riser |  | Zone 3 (5th Floor) | A | 2025-11-18
| Sub Structure | 4th floor | IT/355 | 2025-11-15 | 2025-11-15 | China Verona | Visit the site and verify work of China Verona marble (3/4")at 6th floor only stair step or riser |  | Zone 3 (6th Floor) | A | 2025-11-18
| Sub Structure | 3rd floor | IT/356 | 2025-11-15 | 2025-11-15 | China Verona | Visit the site and verify work of China Verona marble (3/4")at 7th floor only stair step or riser |  | Zone 3 (7th Floor) | A | 2025-11-18
| Sub Structure | 3rd floor | IT/357 | 2025-11-15 | 2025-11-15 | China Verona | Visit the site and verify work of China Verona marble (3/4")at 8th floor only stair step or riser |  | Zone 3 (8th Floor) | A | 2025-11-18
| Sub Structure | 3rd floor | IT/358
| Sub Structure | 3rd floor | IT/359 | 2025-11-17 | 2025-11-17 | travertine | Check the travertine (3/4')fixingwork of ground floor |  |  | A | 2025-11-18
| Sub Structure | 4th floor | IT/360 | 2025-11-17 | 2025-11-17 | travertine | Check the travertine (3/4')fixingwork of ground floor |  | GF Parking area | A | 2025-11-18
| Sub Structure | 11th floor | IT/361
| Sub Structure | 4th floor | IT/362
| Sub Structure | 4th floor | IT/363
| Sub Structure | 11th floor | IT/364
| Sub Structure | 4th floor | IT/365
| Sub Structure | 4th floor | IT/366
| Sub Structure | 4th floor | IT/367
| Sub Structure | 4th floor | IT/368
| Sub Structure | 1st floor | IT/369
| Sub Structure | 1st floor | IT/370 | 2025-12-06 | 2025-12-10 | MARBLE | CHECK THE WORK TURKISH WHITE MARBLE AT KITCHEN SLAB |  | BOUNDRY WALL | R | 2025-12-10
| Sub Structure | 1st floor | IT/371 | 2025-12-10 | 2025-12-10 | travertine | Check the travertine (3/4')fixingwork of ground floor |  | EXTERNAL WALL | B | 2025-12-18
| Sub Structure | 1st floor | IT/372 | 2025-12-08 | 2025-12-09 | MARBLE | CHECK THE WORK TURKISH WHITE MARBLE AT KITCHEN SLAB |  | 2ND FLOOR | A | 2025-12-09
| Sub Structure | 1st floor | IT/373 | 2025-12-08 | 2025-12-09 | MARBLE | CHECK THE WORK TURKISH WHITE MARBLE AT KITCHEN SLAB |  | 1ND FLOOR | A | 2025-12-09
| Sub Structure | 1st floor | IT/374 | 2025-12-15 | 2025-12-15 | China Verona | check the window still china verona (3/4) on the l1 tpwer and please verify work |  | 101-102-103-104-108
| Sub Structure | Top floor | IT/375 | 2025-12-15 | 2025-12-15 | China Verona | check the window still china verona (3/4) on the l1 tpwer and please verify work |  | 201-210
| Sub Structure | 11th floor | IT/376 | 2025-12-15 | 2025-12-15 | China Verona | check the window still china verona (3/4) on the l1 tpwer and please verify work |  | 301to 305-307-310
| Sub Structure | 5th floor | IT/377 | 2025-12-15 | 2025-12-15 | China Verona | check the window still china verona (3/4) on the l1 tpwer and please verify work |  | 403to 407-409-410
| Sub Structure | 5th floor | IT/378
| Sub Structure | 1st floor | IT/379
| Sub Structure | 1st floor | IT/380
| Sub Structure | 2nd floor | IT/381
| Sub Structure | 11th floor | IT/382
| Sub Structure | Basement | IT/383
| Sub Structure | 1st floor | IT/384
| Sub Structure | Top floor | IT/385
| Sub Structure | 1st floor | IT/386
| Sub Structure | 5th floor | IT/387
| Sub Structure | 9th floor | IT/388
| Sub Structure | 10th floor | IT/389
| Sub Structure | 2nd floor | IT/390
| Sub Structure | top floor | IT/391
| Sub Structure | top floor | IT/392
| Sub Structure | 1st floor | IT/393
| Sub Structure | 2nd floor | IT/394
| Sub Structure | 1st floor | IT/395
| Sub Structure | 4th floor | IT/396
| Sub Structure | 2nd floor | IT/397
| Sub Structure | 2nd floor | IT/398
| Sub Structure | 2nd floor | IT/399
| Sub Structure | 2nd floor | IT/400
| Sub Structure | 5th floor | IT/401
| Sub Structure | 5th floor | IT/402
| Sub Structure | 2nd floor | IT/403
| Sub Structure | 2nd floor | IT/404
| Sub Structure | 5th floor | IT/405
| Sub Structure | 2nd floor | IT/406
| Sub Structure | 2nd floor | IT/407
| Sub Structure | 2nd floor | IT/408
| Sub Structure | 2nd floor | IT/409
| Sub Structure | 2nd floor | IT/410
| Sub Structure | 5th floor | IT/411
| Sub Structure | 5th floor | IT/412
| Sub Structure | top floor | IT/413
| Sub Structure | 5th floor | IT/414
| Sub Structure | 3rd floor | IT/415
| Sub Structure | 3rd floor | IT/416
| Sub Structure | Top roof | IT/417
| Sub Structure | 3rd floor | IT/418
| Sub Structure | 11th floor | IT/419
| Sub Structure | 3rd floor | IT/420
| Sub Structure | Top floor | IT/421
| Sub Structure | 3rd floor | IT/422
| Sub Structure | 6th floor | IT/423
| Sub Structure | 3rd floor | IT/424
| Sub Structure | 11th floor | IT/425
| Sub Structure | Basement | IT/426
| Sub Structure | 3rd floor | IT/427
| Sub Structure | 3rd floor | IT/428
| Sub Structure | 6th floor | IT/429
| Sub Structure | 6th floor | IT/430
| Sub Structure | 3rd floor | IT/431
| Sub Structure | 3rd floor | IT/432
| Sub Structure | 6th floor | IT/433
| Sub Structure | 6th floor | IT/434
| Sub Structure | top floor | IT/435
| Sub Structure | 6th floor | IT/436
| Sub Structure | 3rd floor | IT/437
| Sub Structure | 3rd floor | IT/438
| Sub Structure | 6th floor | IT/439
| Sub Structure | top floor | IT/440
| Sub Structure | Top floor | IT/441
| Sub Structure | 4th floor | IT/442
| Sub Structure | 4th floor | IT/443
| Sub Structure | 3rd floor | IT/444
| Sub Structure | top floor | IT/445
| Sub Structure | 6th floor | IT/446
| Sub Structure | 7th floor | IT/447
| Sub Structure | 2nd floor | IT/448
| Sub Structure | 7th floor | IT/449
| Sub Structure | 4th floor | IT/450
| Sub Structure | 7th floor | IT/451
| Sub Structure | 7th floor | IT/452
| Sub Structure | 4th floor | IT/453
| Sub Structure | 4th floor | IT/454
| Sub Structure | 7th floor | IT/455
| Sub Structure | top floor | IT/456
| Sub Structure | 4th floor | IT/457
| Sub Structure | 7th floor | IT/458
| Sub Structure | 4th floor | IT/459
| Sub Structure | Top floor | IT/460
| Sub Structure | 7th floor | IT/461
| Sub Structure | 1st floor | IT/462
| Sub Structure | 4th floor | IT/463
| Sub Structure | 7th floor | IT/464
| Sub Structure | top floor | IT/465
| Sub Structure | 4th floor | IT/466
| Sub Structure | 4th floor | IT/467
| Sub Structure | 7th floor | IT/468
| Sub Structure | top floor | IT/469
| Sub Structure | 8th floor | IT/470
| Sub Structure | 8th floor | IT/471
| Sub Structure | 8th floor | IT/472
| Sub Structure | Top floor | IT/473
| Sub Structure | 5th floor | IT/474
| Sub Structure | 5th floor | IT/475
| Sub Structure | 5th floor | IT/476
| Sub Structure | 2nd floor | IT/477
| Sub Structure | 1st floor | IT/478
| Sub Structure | 8th floor | IT/479
| Sub Structure | 8th floor | IT/480
| Sub Structure | 8th floor | IT/481
| Sub Structure | 9th floor | IT/482
| Sub Structure | 5th floor | IT/483
| Sub Structure | 1st floor | IT/484
| Sub Structure | 5th floor | IT/485
| Sub Structure | 5th floor | IT/486
| Sub Structure | 5th floor | IT/487
| Sub Structure | 2nd floor | IT/488
| Sub Structure | 8th floor | IT/489
| Sub Structure | 8th floor | IT/490
| Sub Structure |  | IT/491
| Sub Structure | 9th floor | IT/492
| Sub Structure | Top floor | IT/493
| Sub Structure | 5th floor | IT/494
| Sub Structure | 2nd floor | IT/495
| Sub Structure | 5th floor | IT/496
| Sub Structure | 2nd floor | IT/497
| Sub Structure | 5th floor | IT/498
| Sub Structure | 5th floor | IT/499
| Sub Structure |  | IT/500
| Sub Structure | 9th floor | IT/501
| Sub Structure | 5th floor | IT/502
| Sub Structure | 8th floor | IT/503
| Sub Structure | 5th floor | IT/504
| Sub Structure | 11th floor | IT/505
| Sub Structure | 8th floor | IT/506
| Sub Structure | 8th floor | IT/507
| Sub Structure | 5th floor | IT/508
| Sub Structure | 5th floor | IT/509
| Sub Structure | 8th floor | IT/510
| Sub Structure | 8th floor | IT/511
| Sub Structure | 9th floor | IT/512
| Sub Structure | 2nd floor | IT/513
| Sub Structure | 3rd floor | IT/514
| Sub Structure | 6th floor | IT/515
| Sub Structure | 2nd floor | IT/516
| Sub Structure | 5th floor | IT/517
| Sub Structure | 5th floor | IT/518
| Sub Structure | 3rd floor | IT/519
| Sub Structure | 6th floor | IT/520
| Sub Structure | 8th floor | IT/521
| Sub Structure | 6th floor | IT/521
| Sub Structure | 6th floor | IT/522
| Sub Structure | 6th floor | IT/523
| Sub Structure | 3rd floor | IT/524
| Sub Structure | 9th floor | IT/525
| Sub Structure | 6th floor | IT/526
| Sub Structure | 6th floor | IT/527
| Sub Structure | 6th floor | IT/528
| Sub Structure | 6th floor | IT/529
| Sub Structure | 6th floor | IT/530
| Sub Structure | 9th floor | IT/531
| Sub Structure | 6th floor | IT/532
| Sub Structure | 9th floor | IT/533
| Sub Structure | Mummty floor | IT/534
| Sub Structure | 9th floor | IT/535
| Sub Structure | 9th floor | IT/536
| Sub Structure | 6th floor | IT/537
| Sub Structure | 3rd floor | IT/538
| Sub Structure | 4th floor | IT/539
| Sub Structure | 6th floor | IT/540
| Sub Structure | top floor | IT/541
| Sub Structure | 6th floor | IT/542
| Sub Structure | 9th floor | IT/543
| Sub Structure | 4th floor | IT/544
| Sub Structure | 9th floor | IT/545
| Sub Structure | 8th floor | IT/546
| Sub Structure | 6th floor | IT/547
| Sub Structure |  | IT/548
| Sub Structure | 4th floor | IT/549
| Sub Structure | 6th floor | IT/550
| Sub Structure | 5th floor | IT/551
| Sub Structure | 6th floor | IT/552
| Sub Structure | 5th floor | IT/553
| Sub Structure | 5th floor | IT/554
| Sub Structure | 9th floor | IT/555
| Sub Structure | 7th floor | IT/556
| Sub Structure | 7th floor | IT/557
| Sub Structure | 6th floor | IT/558
| Sub Structure | 6th floor | IT/559
| Sub Structure | 6th floor | IT/560
| Sub Structure | 7th floor | IT/561
| Sub Structure | top roof mummty | IT/562
| Sub Structure | 7th floor | IT/563
| Sub Structure | top floor | IT/564
| Sub Structure | 7th floor | IT/565
| Sub Structure | 7th floor | IT/566
| Sub Structure | 7th floor | IT/567
| Sub Structure | 7th floor | IT/568
| Sub Structure | 7th floor | IT/569
| Sub Structure | 3rd floor | IT/570
| Sub Structure | 7th floor | IT/571
| Sub Structure | 7th floor | IT/572
| Sub Structure | 7th floor | IT/573
| Sub Structure | 7th floor | IT/574
| Sub Structure | 7th flor | IT/575
| Sub Structure | 7th floor | IT/576
| Sub Structure | 7th floor | IT/577
| Sub Structure | 1st to 2nd floor | IT/578
| Sub Structure |  | IT/579
| Sub Structure | 1st floor | IT/580
| Sub Structure | 7th floor | IT/581
| Sub Structure | 7th floor | IT/582
| Sub Structure | 8th floor | IT/583
| Sub Structure | 8th floor | IT/584
| Sub Structure | 7th floor | IT/585
| Sub Structure | 7th floor | IT/586
| Sub Structure | 7th floor | IT/587
| Sub Structure | 8th floor | IT/588
| Sub Structure | 8th floor | IT/589
| Sub Structure | 8th floor | IT/590
| Sub Structure | GF | IT/591
| Sub Structure | 3rd floor | IT/592
| Sub Structure | 9th floor | IT/593
| Sub Structure | 8th floor | IT/594
| Sub Structure | 8th floor | IT/595
| Sub Structure | 8th floor | IT/596
| Sub Structure | 9th floor | IT/597
| Sub Structure | 9th floor | IT/598
| Sub Structure | 8th floor | IT/599
| Sub Structure | 8th floor | IT/600
| Sub Structure | 8th floor | IT/601
| Sub Structure | 8th floor | IT/602
| Sub Structure | 8th floor | IT/603
| Sub Structure | Top floor | IT/604
| Sub Structure | 2nd floor | IT/605
| Sub Structure | 9th floor | IT/606
| Sub Structure | 9th floor | IT/607
| Sub Structure | 8th floor | IT/608
| Sub Structure | 10th floor | IT/609
| Sub Structure | 4th floor | IT/610
| Sub Structure | 8th floor | IT/611
| Sub Structure | 8th floor | IT/612
| Sub Structure | 8th floor | IT/613
| Sub Structure | 10th floor | IT/614
| Sub Structure | 8th floor | IT/615
| Sub Structure | 8th floor | IT/616
| Sub Structure | 8th floor | IT/617
| Sub Structure | Mummty floor | IT/618
| Sub Structure | top floor | IT/619
| Sub Structure | 9th floor | IT/620
| Sub Structure | 9th floor | IT/621
| Sub Structure | 9th floor | IT/622
| Sub Structure | 9th floor | IT/623
| Sub Structure | 10th floor | IT/624
| Sub Structure | 8th floor | IT/625
| Sub Structure | 9th floor | IT/626
| Sub Structure | 5th floor | IT/627
| Sub Structure | 8th floor | IT/628
| Sub Structure | 8th floor | IT/629
| Sub Structure | 9th floor | IT/630
| Sub Structure | 10th floor | IT/631
| Sub Structure | 8th floor | IT/632
| Sub Structure | 9th floor | IT/633
| Sub Structure | 9th floor | IT/634
| Sub Structure | 5th floor | IT/635
| Sub Structure | 9th floor | IT/636
| Sub Structure | 9th floor | IT/637
| Sub Structure | Top floor | IT/638
| Sub Structure | 10th flooor | IT/639
| Sub Structure | 10th floor | IT/640
| Sub Structure | 11th floor | IT/641
| Sub Structure | 4th floor | IT/642
| Sub Structure | 9th floor | IT/643
| Sub Structure | 9th floor | IT/644
| Sub Structure | 10th floor | IT/645
| Sub Structure | 10th floor | IT/646
| Sub Structure | 1st floor to top floor | IT/647
| Sub Structure | 10th floor | IT/648
| Sub Structure | top floor | IT/649
| Sub Structure |  | IT/650
| Sub Structure | 11th floor | IT/651
| Sub Structure | 9th floor | IT/652
| Sub Structure | 4th floor | IT/653
| Sub Structure | 10th floor | IT/654
| Sub Structure | 10th floor | IT/655
| Sub Structure | 10th floor | IT/656
| Sub Structure | 9th floor | IT/657
| Sub Structure | top floor | IT/658
| Sub Structure | 10th floor | IT/659
| Sub Structure | top floor | IT/660
| Sub Structure | 10th floor | IT/661
| Sub Structure | 10th floor | IT/662
| Sub Structure | 10th floor | IT/663
| Sub Structure | 10th floor | IT/664
| Sub Structure | Mummty floor | IT/665
| Sub Structure | 10th floor | IT/666
| Sub Structure | 10th floor | IT/667
| Sub Structure | 10th floor | IT/668
| Sub Structure | 10th floor | IT/669
| Sub Structure | 10th floor | IT/670
| Sub Structure | 11th floor | IT/671
| Sub Structure | 10th floor | IT/672
| Sub Structure | 5th floor | IT/673
| Sub Structure | 5th floor | IT/674
| Sub Structure | 5th floor | IT/675
| Sub Structure | 11th floor | IT/676
| Sub Structure | 11th floor | IT/677
| Sub Structure | 11th floor | IT/678
| Sub Structure | 11th floor | IT/679
| Sub Structure | 11th floor | IT/680
| Sub Structure | 11th floor | IT/681
| Sub Structure | 11th floor | IT/682
| Sub Structure | 11th floor | IT/683
| Sub Structure | 11th floor | IT/684
| Sub Structure | 11th floor | IT/685
| Sub Structure | 11th floor | IT/686
| Sub Structure | top floor | IT/687
| Sub Structure | top floor | IT/688
| Sub Structure | Top floor | IT/689
| Sub Structure | top floor | IT/690
| Sub Structure | 11th floor | IT/691
| Sub Structure | 11th floor | IT/692
| Sub Structure | 11th floor | IT/693
| Sub Structure | 11th floor | IT/694
| Sub Structure | top floor | IT/695
| Sub Structure | top floor | IT/696
| Sub Structure | 11th floor | IT/697
| Sub Structure | 5th floor | IT/698
| Sub Structure | 11th floor | IT/699
| Sub Structure | top floor | IT/700
| Sub Structure | Top floor | IT/701
| Sub Structure | 11th floor | IT/702
| Sub Structure | top floor | IT/703
| Sub Structure | Ground floor | IT/704
| Sub Structure | Top floor | IT/705
| Sub Structure | 5th floor | IT/706
| Sub Structure | Top floor | IT/707
| Sub Structure | 6th floor | IT/708
| Sub Structure | 3rd floor | IT/709
| Sub Structure | 4th floor | IT/710
| Sub Structure | 5th floor | IT/711
| Sub Structure | 6th floor | IT/712
| Sub Structure | 6th floor | IT/713
| Sub Structure | Top floor | IT/714
| Sub Structure | Top floor | IT/715
| Sub Structure | 7th floor | IT/716
| Sub Structure | Top floor | IT/717
| Sub Structure | Top floor | IT/718
| Sub Structure | 7th floor | IT/719
| Sub Structure | 7th floor | IT/720
| Sub Structure | Ground floor | IT/721
| Sub Structure | Top floor | IT/722
| Sub Structure | 8th floor | IT/723
| Sub Structure | Top floor | IT/724
| Sub Structure | top floor | IT/725
| Sub Structure | top floor | IT/726
| Sub Structure | Ground floor | IT/727
| Sub Structure | top floor | IT/728
| Sub Structure | 9th floor | IT/729
| Sub Structure | 9th floor | IT/730
| Sub Structure | top floor | IT/731
| Sub Structure | top floor | IT/732
| Sub Structure | top floor | IT/733
| Sub Structure | top floor | IT/734
| Sub Structure | top floor | IT/735
| Sub Structure | top floor | IT/736
| Sub Structure | top floor | IT/737
| Sub Structure | top floor | IT/738

## Rock stone L2
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 29
[9 empty] | Approved with comments (B) |  | 5
[9 empty] | Rejected ( R) |  | 1
[9 empty] | Open/Pending (OP) |  | 2
[9 empty] | Total |  | 37
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
|  |  | L2/01 | 2025-08-06 | 2025-08-06 | travertine | Check travertine on the front elevation of courtyard |  | Grid U/11-12 | A | 2025-08-08
2 |  |  | L2/02 | 2025-08-06 | 2025-08-06 | travertine | Check travertine at the elevation columns vertical band of courtyard side |  | Grid M-N/10-12 | R | 2025-08-08
3 |  |  | L2/03 | 2025-08-16 | 2025-08-16 | travertine | Allow to start the work of travertine fixing |  | Grid M-N/11-12 | A | 2025-09-01
4 |  |  | L2/04 | 2025-08-16 | 2025-08-16 | travertine | Check travertine at the elevation columns vertical band |  | Grid U/11-12 | A | 2025-09-01
5 |  |  | L2/05 | 2025-08-16 | 2025-08-16 | travertine | Allow to start the work of travertine fixing |  | Grid U/8-9 | A | 2025-09-01
6 |  |  | L2/06 | 2025-08-18 | 2025-08-18 | travertine | Allow to start the work of travertine fixing |  | Grid H-K/7-8 | A | 2025-09-01
7 |  |  | L2/07 | 2025-08-20 | 2025-08-20 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  | Grid U/10-11 | A | 2025-08-23
8 |  |  | L2/08 | 2025-08-22 | 2025-08-22 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  | Grid U/04-06 | A | 2025-08-25
9 |  |  | L2/09
10 |  |  | L2/10 | 2025-08-26 | 2025-08-26 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  | Grid U/8-9 | B | 2025-08-28
|  |  | L2/10 R01 | 2025-09-02 | 2025-09-02 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  | Grid U/8-9 | A | 2025-09-11
11 |  |  | L2/11 | 2025-08-26 | 2025-08-26 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  | Grid H-K/7-8 | B | 2025-08-28
|  |  | L2/11 R01 | 2025-09-02 | 2025-09-02 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  | Grid H-K/7-8 | A | 2025-09-12
12 |  |  | L2/12 | 2025-08-28 | 2025-08-28 | travertine | Allow to start the work of travertine fixing |  | front elevation | A | 2025-09-01
13 |  |  | L2/13 | 2025-08-28 | 2025-08-28 | travertine | Allow to start the work of travertine fixing |  | UMT side | A | 2025-09-01
14 |  |  | L2/14 | 2025-09-16 | 2025-09-16 | travertine | Allow to start the work of travertine fixing |  |  | A | 2025-09-18
15 |  |  | L2/15 | 2025-09-16 | 2025-09-16 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  |  | A | 2025-09-19
16 |  |  | L2/16 | 2025-09-18 | 2025-09-18 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  |  | B | 2025-09-20
16 |  |  | L2/16 R01 | 2025-09-24 | 2025-09-24 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  |  | A | 2025-09-30
17 |  |  | L2/17 | 2025-09-22 | 2025-09-22 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  |  | A | 2025-09-30
18 |  |  | L2/18 | 2025-09-22 | 2025-09-22 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  |  | A | 2025-09-30
19 |  |  | L2/19 | 2025-09-29 | 2025-09-29 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of the courtyard side |  |  | A | 2025-09-30
20 |  |  | L2/20 | 2025-09-29 | 2025-09-29 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of the UMT side |  |  | A | 2025-09-30
21 |  |  | L2/21 | 2025-09-29 | 2025-09-29 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of the courtyard side |  |  | A | 2025-09-30
22 |  |  | L2/22 | 2025-10-08 | 2025-10-08 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 |  | UMT side (M-P/01) | A | 2025-10-09
23 |  |  | L2/23 | 2025-10-08 | 2025-10-08 | travertine | Allow to start the work of travertine fixing |  | UMT side (R-T/01) | A | 2025-10-09
24 |  |  | L2/24 | 2025-10-08 | 2025-10-08 | travertine | Allow to start the work of travertine fixing |  | G/1-3, G-J/01 | A | 2025-10-09
25 |  |  | L2/25 | 2025-10-16 | 2025-10-16 | travertine | Check the work of travertine fixing (1/2") at the elevation columns/vertical band of L2 |  | Courtyard side | A | 2025-10-17
25 |  |  | L2/25 R01 | 2025-11-12 | 2025-11-12 | travertine | Check the work of travertine fixing (1/2") at the elevation columns/vertical band of L2 |  | Courtyard side | A | 2025-11-14
26 |  |  | L2/26 | 2025-10-22 | 2025-10-22 | travertine | Check the complete marble fixing work of travertine(1/2") on the back column |  | P-M | OP
27 |  |  | L2/27 | 2025-10-22 | 2025-10-22 | travertine | Check the complete marble fixing work of travertine(1/2") on the back Beam\ |  | N-Q | OP
28 |  |  | L2/28 | 2025-10-23 | 2025-10-23 | travertine | visit the sitre and allow to start work of travertine on the L2 tower |  | Stair cass area | A | 2025-10-23
29 |  |  | L2/29 | 2025-11-12 | 2025-11-12 | travertine | Visit the site and check the work of travertine(1/2") fixing the horizental & vertical bend |  | UMT Side | A | 2025-11-14
30 |  |  | L2/30 | 2025-10-28 | 2025-10-28 | travertine | Visit the site and allow us to start work of travertine(3/4") fixing work at wall, GF rear elevation |  |  | A | 2025-10-31
31 |  |  | L2/31 | 2025-11-03 | 2025-11-03 | travertine | Visit the site and check the work of travertine(1/2") fixing the horizental & vertical bend |  |  | B | 2025-11-05
31 |  |  | L2/31 R01 | 2025-11-20 | 2025-11-20 | travertine | Visit the site and check the work of travertine(1/2") fixing the horizental & vertical bend |  |  | A | 2025-11-21
32 |  |  | L2/32 | 2025-11-04 | 2025-11-04 | travertine | Check the travertine 3/4" fixing work at boundary wall |  |  | B | 2025-11-06
32 |  |  | L2/32 R01 | 2025-11-13 | 2025-11-13 | travertine | Check the travertine 3/4" fixing work at boundary wall |  |  | A | 2025-11-15
33 |  |  | L2/33
34 |  |  | L2/34
35 |  |  | L2/35
36 |  |  | L2/36
37 |  |  | L2/37
38 |  |  | L2/38
39 |  |  | L2/39
40 |  |  | L2/40
41 |  |  | L2/41
42 |  |  | L2/42
43 |  |  | L2/43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
2024-08-15
IT/795
IT/796
IT/806
IT/807
IT/808
IT/809
IT/810
IT/811
IT/812
IT/813
IT/814
IT/815
IT/816
IT/817
IT/818
IT/819
IT/820
IT/821
IT/822
IT/823
IT/824
IT/825
IT/826
IT/827
IT/828
IT/829
IT/830
IT/831
IT/832
IT/833
IT/834
IT/835
IT/836
IT/837
IT/838
IT/839
IT/840
IT/841
IT/842
IT/843
IT/844
IT/845
IT/846
IT/847
IT/848
IT/849
IT/850
IT/851
IT/852
IT/853

## Rock stone L1
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 17
[9 empty] | Approved with comments (B) |  | 5
[9 empty] | Rejected ( R) |  | 2
[9 empty] | Open/Pending (OP) |  | 1
[9 empty] | Total |  | 25
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
2 |  |  | L1/02 | 2025-07-24 | 2025-07-24 | travertine | Check travertine on the front elevation of courtyard |  |  | R | 2025-07-30
|  |  | L1/02 | 2025-08-09 | 2025-08-09 | travertine | Check travertine on the front elevation of courtyard |  |  | B | 2025-08-12
|  |  | L1/02 R02 | 2025-08-26 | 2025-08-26 | travertine | Check travertine on the front elevation of courtyard |  |  | B | 2025-08-28
|  |  | L1/02 R03 | 2025-09-16 | 2025-09-16 | travertine | Check travertine on the front elevation of courtyard |  |  | A | 2025-09-20
3 |  |  | L1/03 | 2025-08-01 | 2025-08-01 | travertine | Check travertin (1/2") fixing work of columns/vertical bend of the side elevation of I tower |  |  | A | 2025-08-23
4 |  |  | L1/04 | 2025-08-16 | 2025-08-16 | travertine | Check travertin (1/2") fixing work of columns/vertical bend of the side elevation of I tower |  |  | A | 2025-09-01
4 |  |  | L1/04 R01 | 2025-09-16 | 2025-09-16 | travertine | Check travertin (1/2") fixing work of columns/vertical bend of the side elevation of I tower |  |  | B | 2025-09-18
5 |  |  | L1/05 | 2025-08-18 | 2025-08-18 | travertine | Check travertin (1/2") fixing work of columns/vertical bend of the side elevation of I tower |  |  | A | 2025-09-01
6 |  |  | L1/06 | 2025-08-26 | 2025-08-26 | travertine | Check the work of travertine (1/2")fixing at the horizental & vertical band of road side elevation |  |  | B | 2025-08-28
|  |  | L1/06 R01 | 2025-09-16 | 2025-09-16 | travertine | Check the work of travertine (1/2")fixing at the horizental & vertical band of road side elevation |  |  | A | 2025-09-20
7 |  |  | L1/07 | 2025-09-16 | 2025-09-16 | travertine | Alloe to start work of travertine |  |  | A | 2025-09-17
8 |  |  | L1/08 | 2025-09-22 | 2025-09-22 | travertine | Alloe to start work of travertine |  |  | R | 2025-09-23
|  |  | L1/08 R01 | 2025-09-26 | 2025-09-26 | travertine | Alloe to start work of travertine |  |  | A | 2025-09-29
|  |  | L1/09 | 2025-09-25 | 2025-09-25 | travertine | Check the work of travertine (1/2")fixing at the horizental & vertical band of road side elevation |  |  | A | 2025-09-29
9 |  |  | L1/10 | 2025-10-08 | 2025-10-08 | travertine | Check the work of travertine (1/2")fixing at the Core-wall |  |  | A | 2025-10-09
9 |  |  | L1/10 R01 | 2025-11-03 | 2025-11-03 | travertine | Check the work of travertine (1/2")fixing at the Core-wall |  |  | A | 2025-11-05
9 |  |  | L1/10 R02 | 2025-11-10 | 2025-11-10 | travertine | Check the work of travertine (1/2")fixing at the Core-wall |  |  | A | 2025-11-12
10 |  |  | L1/11 | 2025-10-28 | 2025-10-28 | travertine | Visit the site and allow us to start work of travertine(3/4") fixing work at wall, GF rear elevation |  |  | A | 2025-10-29
10 |  |  | L1/11 R01 | 2025-11-04 | 2025-11-04 | travertine | Visit the site and allow us to start work of travertine(3/4") fixing work at wall, GF rear elevation |  |  | A | 2025-11-07
11 |  |  | L1/12 | 2025-10-28 | 2025-10-28 | travertine | Visit the site and allow us to start work of travertine(3/4") fixing work at wall, GF rear elevation |  |  | A | 2025-11-01
12 |  |  | L1/13 | 2025-11-03 | 2025-11-03 | travertine | Check the work of travertine (3/4") fixing at the stairwall of L1 Tower |  |  | A | 2025-11-05
12 |  |  | L1/13 R1 | 2025-11-10 | 2025-11-10 | travertine | Check the work of travertine (3/4") fixing at the stairwall of L1 Tower |  |  | A | 2025-11-12
13 |  |  | L1/14 | 2025-11-04 | 2025-11-04 | travertine | Check the work of travertine (3/4") fixing at the stairwall of L1 Tower Boundary wall |  |  | B | 2025-11-06
13 |  |  | L1/14 R01 | 2025-11-13 | 2025-11-13 | travertine | Check the work of travertine (3/4") fixing at the stairwall of L1 Tower Boundary wall |  |  | A | 2025-11-15
14 |  |  | L1/15 | 2025-11-27 | 2025-11-27 | window sill | Check the level and allow to start fixing work of window sills w6 w15 |  |  | OP
15 |  |  | L1/16
16 |  |  | L1/17
17 |  |  | L1/18
18 |  |  | L1/19
19 |  |  | L1/20
20 |  |  | L1/21
21 |  |  | L1/22
22 |  |  | L1/23
23 |  |  | L1/24
24 |  |  | L1/25
25 |  |  | L1/26
26 |  |  | L1/27
27 |  |  | L1/28
28 |  |  | L1/29
29 |  |  | L1/30
30 |  |  | L1/31
31 |  |  | L1/32
32 |  |  | L1/33
33 |  |  | L1/34
34 |  |  | L1/35
35 |  |  | L1/36
36 |  |  | L1/37
37 |  |  | L1/38
38 |  |  | L1/39
39 |  |  | L1/40
40 |  |  | L1/41
41 |  |  | L1/42
42 |  |  | L1/43
43 |  |  | L1/44
44 |  |  | L1/45
45 |  |  | L1/46
46 |  |  | L1/47
47 |  |  | L1/48
48 |  |  | L1/49
49 |  |  | L1/50
50 |  |  | L1/51
51 |  |  | L1/52
52 |  |  | L1/53
53 |  |  | L1/54
54 |  |  | L1/55
55 |  |  | L1/56
56 |  |  | L1/57
57 |  |  | L1/58
58 |  |  | L1/59
59 |  |  | L1/60
60 |  |  | L1/61
61 |  |  | L1/62
62 |  |  | L1/63
63 |  |  | L1/64
64 |  |  | L1/65
65 |  |  | L1/66
66 |  |  | L1/67
67 |  |  | L1/68
68 |  |  | L1/69
69 |  |  | L1/70
70 |  |  | L1/71
71 |  |  | L1/72
72 |  |  | L1/73
73 |  |  | L1/74
74 |  |  | L1/75
75 |  |  | L1/76
76 |  |  | L1/77
77 |  |  | L1/78
78 |  |  | L1/79
79 |  |  | L1/80
80 |  |  | L1/81
81 |  |  | L1/82
82 |  |  | L1/83
83 |  |  | L1/84
84 |  |  | L1/85
85 |  |  | L1/86
86 |  |  | L1/87
87 |  |  | L1/88
88 |  |  | L1/89
89 |  |  | L1/90
90 |  |  | L1/91
91 |  |  | L1/92
92 |  |  | L1/93
93 |  |  | L1/94
94 |  |  | L1/95
95 |  |  | L1/96
96 |  |  | L1/97
97 |  |  | L1/98
98 |  |  | L1/99
99 |  |  | L1/100
100 |  |  | L1/101
101 |  |  | L1/102
102 |  |  | L1/103
103 |  |  | L1/104
104 |  |  | L1/105
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
2024-08-15
IT/795
IT/796
IT/806
IT/807
IT/808
IT/809
IT/810
IT/811
IT/812
IT/813
IT/814
IT/815
IT/816
IT/817
IT/818
IT/819
IT/820
IT/821
IT/822
IT/823
IT/824
IT/825
IT/826
IT/827
IT/828
IT/829
IT/830
IT/831
IT/832
IT/833
IT/834
IT/835
IT/836
IT/837
IT/838
IT/839
IT/840
IT/841
IT/842
IT/843
IT/844
IT/845
IT/846
IT/847
IT/848
IT/849
IT/850
IT/851
IT/852
IT/853

## Elegant Engineering
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG I Tower) | [5 empty] | Fully Approved (A) |  | 17
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 9
[9 empty] | Open/Pending (OP) |  | 6
[9 empty] | Total |  | 32
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | 3rd floor | IT/01 | 2025-04-09 | 2025-04-10 | ceiling | check False ceiling of apartment no. 01 |  | 301 | A | 2025-05-01
2 | Sub Structure | 1st floor | IT/02 | 2025-04-23 | 2025-04-23 | ceiling | Check false ceiling of apartment No. 11 |  | 111 | OP
3 | Sub Structure | 1st floor | IT/03 | 2025-04-23 | 2025-04-23 | ceiling | Check false ceiling of apartment No. 13 |  | 13 | OP
4 | Sub Structure | 1st floor | IT/04 | 2025-04-23 | 2025-04-23 | ceiling | Check false ceiling of apartment No. 14 |  | 14 | OP
5 | Sub Structure | 1st floor | IT/05 | 2025-04-23 | 2025-04-23 | ceiling | Check false ceiling of apartment No. 15 |  | 15 | OP
6 | Sub Structure | 1st floor | IT/06 | 2025-04-23 | 2025-04-23 | ceiling | Check false ceiling of apartment No. 16 |  | 16 | OP
7 | Sub Structure | 3rd floor | IT/07 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 303 |  | 303 | A | 2025-05-30
8 | Sub Structure | 3rd floor | IT/08 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 304 |  | 304 | A | 2025-05-30
9 | Sub Structure | 3rd floor | IT/09 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 305 |  | 305 | A | 2025-05-30
10 | Sub Structure | 3rd floor | IT/10 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 307 |  | 307 | A | 2025-05-30
11 | Sub Structure | 3rd floor | IT/11 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 308 |  | 308 | A | 2025-05-30
12 | Sub Structure | 3rd floor | IT/12 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 309 |  | 309 | A | 2025-05-30
13 | Sub Structure | 3rd floor | IT/13 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 311 |  | 311 | A | 2025-05-30
14 | Sub Structure | 3rd floor | IT/14 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 312 |  | 312 | A | 2025-05-30
15 | Sub Structure | 3rd floor | IT/15 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 313 |  | 313 | A | 2025-05-30
16 | Sub Structure | 3rd floor | IT/16 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 314 |  | 314 | A | 2025-05-30
17 | Sub Structure | 3rd floor | IT/17 | 2025-05-26 | 2025-05-26 | ceiling | check false ceiling of apartment No. 316 |  | 316 | A | 2025-05-30
18 | Sub Structure | 3rd floor | IT/18 | 2025-06-30 | 2025-06-30 | ceiling | check false ceiling of apartment No. 2 |  | 2 | A | 2025-07-26
19 | Sub Structure | 3rd floor | IT/19 | 2025-07-02 | 2025-07-02 | ceiling | check false ceiling of apartment No. 6 |  | 306 | A | 2025-07-26
20 | Sub Structure | 3rd floor | IT/20 | 2025-07-04 | 2025-07-04 | ceiling | check false ceiling of apartment No. 15 |  | 315 | A | 2025-07-26
21 | Sub Structure | 4th floor | IT/21 | 2025-08-26 | 2025-08-26 | ceiling | Design Approval of false ceiling pulmit of Appartment no 14 |  | 414 | A | 2025-09-09
22 | Sub Structure | 4th floor | IT/22 R02 | 2025-11-13 | 2025-11-13 | ceiling | Installation of falso ceiling |  | 4th Floor (2) | R | 2025-11-15 | Saqib
23 | Sub Structure | 4th floor | IT/23 R02 | 2025-11-13 | 2025-11-13 | ceiling | Installation of falso ceiling |  | 4th Floor (4) | R | 2025-11-15 | Saqib
24 | Sub Structure | 4th floor | IT/24 R01 | 2025-10-07 | 2025-10-07 | ceiling | Installation of falso ceiling |  | 4th Floor (14) | R | 2025-10-11 | Saqib
25 | Sub Structure | 1st floor | IT/25 R01 | 2025-10-07 | 2025-10-07 | ceiling | Installation of Balcony falso ceiling |  | 1st Floor (11) | R | 2025-10-11 | Asad Butt
26 | Sub Structure | 1st floor | IT/26 R01 | 2025-10-07 | 2025-10-07 | ceiling | Installation of Balcony falso ceiling |  | 1st Floor (13) | R | 2025-10-11 | Asad Butt
27 | Sub Structure | 1st floor | IT/27R01 | 2025-10-07 | 2025-10-07 | ceiling | Installation of Balcony falso ceiling |  | 1st Floor (14) | R | 2025-10-11 | Asad Butt
28 | Sub Structure | 1st floor | IT/28 R01 | 2025-10-07 | 2025-10-07 | ceiling | Installation of Balcony falso ceiling |  | 1st Floor (15) | R | 2025-10-11 | Asad Butt
29 | Sub Structure | 1st floor | IT/29 R01 | 2025-10-07 | 2025-10-07 | ceiling | Installation of Balcony falso ceiling |  | 1st Floor (16) | R | 2025-10-11 | Asad Butt
30 | Sub Structure | 3rd floor | IT/30 R01 | 2025-10-07 | 2025-10-07 | ceiling | Installation of Balcony falso ceiling |  | 12 | A | 2025-10-09
31 | Sub Structure | 1st 'floor | IT/31 | 2025-10-27 | 2025-10-27 | ceiling | Installation of Pulment false ceiling |  | 11 | OP
32 | Sub Structure | 1st 'floor | IT/32 | 2025-10-31 | 2025-10-31 | ceiling | Installation of Pulment false ceiling |  | 13 | R | 2025-11-01
33 | Sub Structure
34 | Sub Structure
35 | Sub Structure
36 | Sub Structure
37 | Sub Structure
38 | Sub Structure
39 | Sub Structure
40 | Sub Structure
41 | Sub Structure
42 | Sub Structure
43 | Sub Structure
44 | Sub Structure
Sub Structure
45 | Sub Structure
46 | Sub Structure
47 | Sub Structure
48 | Sub Structure
49 | Sub Structure
50 | Sub Structure
51 | Sub Structure
52 | Sub Structure
53 | Sub Structure
54 | Sub Structure
55 | Sub Structure
56 | Sub Structure
57 | Sub Structure
58 | Sub Structure
59 | Sub Structure
60 | Sub Structure
61 | Sub Structure
62 | Sub Structure
63 | Sub Structure
64 | Sub Structure
65 | Sub Structure
66 | Sub Structure
67 | Sub Structure
68 | Sub Structure
69 | Sub Structure
70 | Sub Structure
71 | Sub Structure
72 | Sub Structure
73 | Sub Structure
74 | Sub Structure
75 | Sub Structure
76 | Sub Structure
77 | Sub Structure
78 | Sub Structure
79 | Sub Structure
80 | Sub Structure
81 | Sub Structure
82 | Sub Structure
83 | Sub Structure
84 | Sub Structure
85 | Sub Structure
86 | Sub Structure
87 | Sub Structure
88 | Sub Structure
89 | Sub Structure
90 | Sub Structure
91 | Sub Structure
92 | Sub Structure
93 | Sub Structure
94 | Sub Structure
95 | Sub Structure
96 | Sub Structure
97 | Sub Structure
98 | Sub Structure
99 | Sub Structure
100 | Sub Structure
101 | Sub Structure
102 | Sub Structure
103 | Sub Structure
104 | Sub Structure
105 | Sub Structure
106 | Sub Structure
107 | Sub Structure
108 | Sub Structure
109 | Sub Structure
110 | Sub Structure
111 | Sub Structure
112 | Sub Structure
113 | Sub Structure
114 | Sub Structure
115 | Sub Structure
116 | Sub Structure
117 | Sub Structure
118 | Sub Structure
119 | Sub Structure
120 | Sub Structure
121 | Sub Structure
122 | Sub Structure
123 | Sub Structure
124 | Sub Structure
125 | Sub Structure
126 | Sub Structure
127 | Sub Structure
128 | Sub Structure
129 | Sub Structure
130 | Sub Structure
131 | Sub Structure
132 | Sub Structure
133 | Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
| Sub Structure |  | LT-1-329
| Sub Structure |  | LT-1-330
| Sub Structure |  | LT-1-331
| Sub Structure |  | LT-1-332
| Sub Structure |  | LT-1-333
| Sub Structure |  | LT-1-334
| Sub Structure |  | LT-1-335
| Sub Structure |  | LT-1-336
| Sub Structure |  | LT-1-337
| Sub Structure |  | LT-1-338
| Sub Structure |  | LT-1-339
| Sub Structure |  | LT-1-340
LT-1-341
LT-1-342
LT-1-343
LT-1-344
LT-1-345
LT-1-346
LT-1-347
LT-1-348
LT-1-349
LT-1-350
2025-03-19

## Aizdi
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) IIL-CSL | [5 empty] | Fully Approved (A) |  | 1
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 0 |  | As of : |  | 2025-12-19
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 1
Sr. | Work Package | Floor | IR No. | Submission Date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR closing Date | Pour Card No. | Concrete Qty (m3) | Attachment | Remarks
1 | Sub Structure | Basement | IT/1 | 2025-04-24 | 2025-04-24 | sleeves | Check OHWT Sleeves installation |  | T1,T2, T3 | A | 2025-04-24 |  |  | E:\Soft IRs\IIL\I Tower\1.pdf
2 | Sub Structure | Basement | IT/2 | 2022-09-26 | [9 empty] | E:\Soft IRs\IIL\I Tower\2.pdf
3 | Sub Structure | Basement | IT/3 | 2022-09-27 | [9 empty] | E:\Soft IRs\IIL\I Tower\3.pdf
4 | Sub Structure | Basement | IT/4 | 2022-09-30 | [9 empty] | E:\Soft IRs\IIL\I Tower\4.pdf
5 | Sub Structure | Basement | IT/5 | 2022-09-30 | [9 empty] | E:\Soft IRs\IIL\I Tower\5.pdf
6 | Sub Structure | Basement | IT/6 | 2022-10-04 | [9 empty] | E:\Soft IRs\IIL\I Tower\6.pdf
7 | Sub Structure | Basement | IT/7 | 2022-10-04 | [9 empty] | E:\Soft IRs\IIL\I Tower\7.pdf
8 | Sub Structure | Basement | IT/7A | 2022-10-07 | [9 empty] | E:\Soft IRs\IIL\I Tower\7A.pdf
9 | Sub Structure | Basement | IT/8 | 2022-10-08 | [9 empty] | E:\Soft IRs\IIL\I Tower\8.pdf
10 | Sub Structure | Basement | IT/9 | 2022-10-09 | [9 empty] | E:\Soft IRs\IIL\I Tower\9.pdf
11 | Sub Structure | Basement | IT/10 | 2022-10-09 | [9 empty] | E:\Soft IRs\IIL\I Tower\10.pdf
12 | Sub Structure | Basement | IT/11 | 2022-10-10 | [9 empty] | E:\Soft IRs\IIL\I Tower\11.pdf
13 | Sub Structure | Basement | IT/12 | 2022-10-15 | [9 empty] | E:\Soft IRs\IIL\I Tower\12.pdf
14 | Sub Structure | Basement | IT/13 | 2022-10-17 | [9 empty] | E:\Soft IRs\IIL\I Tower\13.pdf
15 | Sub Structure | Basement | IT/14 | 2022-10-19 | [9 empty] | E:\Soft IRs\IIL\I Tower\14.pdf
16 | Sub Structure | Basement | IT/15 | 2022-10-21 | [9 empty] | E:\14.Soft IRs\IIL\I Tower\15.pdf
17 | Sub Structure | Basement | IT/16 | 2022-10-26 | [9 empty] | E:\14.Soft IRs\IIL\I Tower\16.pdf
18 | Sub Structure | Basement | IT/17 | 2022-10-28 | [9 empty] | E:\14.Soft IRs\IIL\I Tower\17.pdf
19 | Sub Structure | Basement | IT/18 | 2022-10-31 | [9 empty] | E:\14.Soft IRs\IIL\I Tower\18.pdf
20 | Sub Structure | Basement | IT/19 | 2022-10-31 | [9 empty] | E:\14.Soft IRs\IIL\I Tower\19.pdf
21 | Sub Structure | Basement | IT/20 | 2022-11-01 | [9 empty] | E:\14.Soft IRs\IIL\I Tower\20.pdf
22 | Sub Structure | Basement | IT/21 | 2022-11-01 | [9 empty] | E:\14.Soft IRs\IIL\I Tower\21.pdf
23 | Sub Structure | Basement | IT/22 | 2022-11-02
24 | Sub Structure | Basement | IT/23 | 2022-11-07
25 | Sub Structure | Basement | IT/24 | 2022-11-07
26 | Sub Structure | Basement | IT/25 | 2022-11-08
27 | Sub Structure | Basement | IT/26 | 2022-11-08
28 | Sub Structure | Basement | IT/27 | 2022-11-08
29 | Sub Structure | Basement | IT/28 | 2022-11-09
30 | Sub Structure | Basement | IT/29 | 2022-11-09
31 | Sub Structure | Basement | IT/30 | 2022-11-14
32 | Sub Structure | Basement | IT/31 | 2022-11-15
33 | Sub Structure | Basement | IT/32 | 2022-11-19
34 | Sub Structure | Basement | IT/33 | 2022-11-21
35 | Sub Structure | Basement | IT/34 | 2022-11-21
36 | Sub Structure | Basement | IT/35 | 2022-11-22
37 | Sub Structure | Basement | IT/36 | 2022-11-23
38 | Sub Structure | Basement | IT/37 | 2022-11-25
39 | Sub Structure | Basement | IT/38 | 2023-06-21
40 | Sub Structure | Basement | IT/39 | 2022-11-25
41 | Sub Structure | Basement | IT/40 | 2022-11-29
42 | Sub Structure | Basement | IT/41 | 2022-11-26
43 | Sub Structure | Basement | IT/42 | 2022-12-01
44 | Sub Structure | Basement | IT/43 | 2022-12-02
45 | Sub Structure | Basement | IT/44 | 2022-12-02
46 | Sub Structure | Basement | IT/45 | 2022-12-03
47 | Sub Structure | Basement | IT/46
48 | Sub Structure | Basement | IT/47 | 2022-12-03
49 | Sub Structure | Basement | IT/48 | 2022-12-03
50 | Sub Structure | Basement | IT/49 | 2022-12-05
51 | Sub Structure | Basement | IT/50 | 2022-12-05
52 | Sub Structure | Basement | IT/51 | 2022-12-05
53 | Sub Structure | Basement | IT/52 | 2022-12-07
54 | Sub Structure | Basement | IT/53 | 2022-12-08
55 | Sub Structure | Basement | IT/54 | 2022-12-08
56 | Sub Structure | Basement | IT/55 | 2022-12-10
57 | Sub Structure | Basement | IT/56 | 2022-12-09
58 | Sub Structure | Basement | IT/57 | 2022-12-10
59 | Sub Structure | Basement | IT/58 | 2022-12-11
60 | Sub Structure | Basement | IT/59 | 2022-12-12
61 | Sub Structure | Basement | IT/60 | 2022-12-12
62 | Sub Structure | Basement | IT/61 | 2022-12-13
63 | Sub Structure | Basement | IT/62 | 2022-12-13
64 | Sub Structure | Basement | IT/63 | 2022-12-14
65 | Sub Structure | Basement | IT/64 | 2022-12-16
66 | Sub Structure | Basement | IT/65 | 2022-12-16
67 | Sub Structure | Basement | IT/66 | 2022-12-17
68 | Sub Structure | Basement | IT/67 | 2022-12-17
69 | Sub Structure | Basement | IT/68 | 2022-12-18
70 | I Tower | Ground | IT/69 | 2022-12-18
| I Tower | Ground | IT/70 A | 2022-12-18
72 | I Tower | Ground | IT/71 | 2022-12-19
73 | I Tower | Ground | IT/72 | 2022-12-19
74 | Sub Structure | Basement | IT/73 | 2022-12-20
75 | Sub Structure | Basement | IT/74 | 2022-12-20
76 | I Tower | Ground | IT/75 | 2022-12-21
77 | I Tower | Ground | IT/76 | 2022-12-21
78 | I Tower | Ground | IT/77 | 2022-12-22
79 | I Tower | Ground | IT/78 | 2022-12-22
80 | I Tower | Ground | IT/79 | 2022-12-23
81 | I Tower | Ground | IT/80 | 2022-12-23
82 | I Tower | Ground | IT/81 | 2022-12-23
83 | I Tower | Ground | IT/82 | 2022-12-23
84 | Sub Structure | Basement | IT/83 | 2022-12-23
85 | I Tower | Ground | IT/84 | 2022-12-26
86 | I Tower | Ground | IT/85 | 2022-12-26
87 | I Tower | Ground | IT/86 | 2022-12-26
88 | I Tower | Ground | IT/87 | 2022-12-28
89 | I Tower | Ground | IT/88 | 2022-12-28
90 | I Tower | Ground | IT/89 | 2022-12-30
91 | I Tower | Ground | IT/90 | 2022-12-30
92 | I Tower | Ground | IT/91
93 | I Tower | Ground | IT/92 | 2022-12-30
94 | I Tower | Ground | IT/93
95 | I Tower | Ground | IT/94 | 2023-01-01
96 | I Tower | Ground | IT/95
97 | I Tower | Ground | IT/96 | 2023-01-01
98 | I Tower | Ground | IT/97
99 | I Tower | Ground | IT/98 | 2023-01-02
100 | I Tower | Ground | IT/99
101 | I Tower | Ground | IT/100 | 2023-01-03
102 | I Tower | Ground | IT/101
103 | I Tower | Ground | IT/102 | 2023-01-05
104 | I Tower | Ground | IT/103 | 2023-01-05
105 | I Tower | Ground | IT/104 | 2023-01-05
106 | I Tower | Ground | IT/105 | 2023-01-06
107 | I Tower | Ground | IT/106 | 2023-01-07
108 | I Tower | Ground | IT/107 | 2023-01-09
109 | I Tower | Ground | IT/108 | 2023-01-10
110 | I Tower | Ground | IT/109 | 2023-01-14
111 | I Tower | 1st Floor | IT/110 | 2023-01-16
112 | I Tower | 2nd Floor | IT/111 | 2023-01-19
113 | I Tower | Ground | IT/112 | 2023-01-21
114 | I Tower | Ground | IT/113 | 2023-01-21
115 | I Tower | Ground | IT/114 | 2023-01-26
116 | I Tower | Ground | IT/115 | 2023-01-26
117 | I Tower | 1st Floor | IT/116 | 2023-01-26
118 | I Tower | 2nd Floor | IT/117 | 2023-01-27
119 | I Tower | 1st Floor | IT/118 | 2023-02-04
120 | I Tower | 1st Floor | IT/119 | 2023-02-04
121 | I Tower | 2nd Floor | IT/120 | 2023-02-04
122 | I Tower | 1st Floor | IT/121 | 2023-02-07
123 | I Tower | 1st Floor | IT/122 | 2023-02-10
124 | I Tower | 1st Floor | IT/123 | 2023-02-10
125 | I Tower | 1st Floor | IT/124 | 2023-02-13
126 | I Tower | 1st Floor | IT/125 | 2023-02-13
127 | I Tower | 1st Floor | IT/126 | 2023-02-16
128 | I Tower | 1st floor | IT/127 | 2023-02-17
129 | I Tower | 2nd floor | IT/128 | 2023-02-17
130 | I Tower | 2nd floor | IT/129 | 2023-02-18
131 | I Tower | 1st floor | IT/130 | 2023-02-18
132 | I Tower | 2nd floor | IT/131 | 2023-02-20
133 | I Tower | 2nd floor | IT/132 | 2023-02-20
134 | I Tower | 2nd floor | IT/133 | 2023-02-23
135 | I Tower | 2nd Floor | IT/134 | 2023-02-27
136 | I Tower | 2nd Floor | IT/135 | 2023-02-27
137 | I Tower | 2nd Floor | IT/136 | 2023-02-27
138 | I Tower | 2nd Floor | IT/137 | 2023-03-01
139 | I Tower | 2nd Floor | IT/138 | 2023-03-03
140 | I Tower | 3rd Floor | IT/139 | 2023-03-06
142 | I Tower | 3rd Floor | IT/140 | 2023-03-06
143 | I Tower | 3rd Floor | IT/141 | 2023-03-06
144 | I Tower | 2nd Floor | IT/142 | 2023-03-06
145 | I Tower | 2nd Floor | IT/143 | 2023-03-07
146 | I Tower | 3rd Floor | IT/144 | 2023-03-09
147 | I Tower | 3rd Floor | IT/145 | 2023-03-11
148 | I Tower | 3rd Floor | IT/146 | 2023-03-09
149 | I Tower | 3rd Floor | IT/147 | 2023-03-10
150 | I Tower | 3rd Floor | IT/148 | 2023-03-11
151 | I Tower | 3rd Floor | IT/149 | 2023-03-13
152 | I Tower | 3rd Floor | IT/150 | 2023-03-14
153 | I Tower | 3rd Floor | IT/151 | 2023-03-14
154 | I Tower | 3rd floor | IT/152 | 2023-03-17
155 | I Tower | 3rd Floor | IT/153 | 2023-03-18
156 | I Tower | 4th floor | IT/154 | 2023-03-18
157 | I Tower | 4th floor | IT/155 | 2023-03-21
158 | I Tower | 4th floor | IT/156 | 2023-03-22
159 | I Tower | 4th floor | IT/157 | 2023-03-22
160 | I Tower | 4th floor | IT/158 | 2023-03-22
161 | I Tower | 4th floor | IT/159 | 2023-03-25
162 | I Tower | 4th floor | IT/160 | 2023-03-28
163 | I Tower | 4th floor | IT/161 | 2023-03-28
164 | I Tower | 5th Floor | IT/162 | 2023-03-30
165 | I Tower | 3rd Floor | IT/163 | 2023-03-31
166 | I Tower | 4th floor | IT/164 | 2023-03-31
167 | I Tower | 5th Floor | IT/165 | 2023-04-07
168 | I Tower | 5th Floor | IT/166 | 2023-04-07
169 | I Tower | 5th Floor | IT/167 | 2023-04-07
170 | I Tower | 5th Floor | IT/168 | 2023-04-10
171 | I Tower | 4th floor | IT/169
172 | I Tower | 5th Floor | IT/170 | 2023-04-13
173 | I Tower | 6th Floor | IT/171 | 2023-04-16
174 | I Tower | 6th floor | IT/172 | 2023-04-29
175 | I Tower | 5th Floor | IT/173 | 2023-04-30
176 | I Tower | 5th Floor | IT/174 | 2023-05-01
177 | I Tower | 5th Floor | IT/175 | 2023-05-01
178 | I Tower | 5th Floor | IT/176 | 2023-05-02
179 | I Tower | 5th Floor | IT/177 | 2023-05-06
180 | I Tower | 5th Floor | IT/178 | 2023-05-06
181 | I Tower | Basement | IT/179 | 2023-05-06
182 | I Tower | 6th Floor | IT/180 | 2023-05-07
183 | I Tower | 6th Floor | IT/181 | 2023-05-09
184 | I Tower | 6th Floor | IT/182 | 2023-05-13
185 | I Tower | 6th Floor | IT/183 | 2023-05-13
186 | I Tower | 6th Floor | IT/184 | 2023-05-14
187 | I Tower | Basement | IT/185 | 2023-05-15
188 | I Tower | 6th Floor | IT/186 | 2023-05-17
189 | I Tower | 6th Floor | IT/187 | 2023-05-19
190 | I Tower | 6th Floor | IT/188 | 2023-05-22
191 | I Tower | 6th Floor | IT/189 | 2023-05-22
192 | I Tower | 6th Floor | IT/190 | 2023-05-29
193 | I Tower | 6th Floor | IT/191 | 2023-05-29
194 | I Tower | 7th Floor | IT/192 | 2023-06-08
195 | I Tower | 7th Floor | IT/193 | 2023-06-12
196 | I Tower | 7th Floor | IT/194 | 2023-06-13
197 | I Tower | 7th Floor | IT/195 | 2023-06-15
198 | I Tower | 7th Floor | IT/196 | 2023-07-03
199 | I Tower | 7th floor | IT/197 | 2023-07-12
200 | I Tower | 7th Floor | IT/198 | 2023-07-12
201 | I Tower | 7th Floor | IT/199 | 2023-05-15
202 | I Tower | 8th Floor | IT/200 | 2023-07-18
203 | I Tower | 7th Floor | IT/201 | 2023-07-21
204 | I Tower | 8th Floor | IT/202 | 2023-07-24
205 | I Tower | 8th Floor | IT/203 | 2023-07-31
206 | I Tower | 8th Floor | IT/204 | 2023-07-31
207 | I Tower | 8th Floor | IT/205 | 2023-07-31
208 | I Tower | 8th Floor | IT/206 | 2023-08-03
209 | I Tower | 8th Floor | IT/207 | 2023-08-07
210 | I Tower | 8th Floor | IT/208 | 2023-08-07
211 | I Tower | 8th Floor | IT/209 | 2023-08-09
212 | I Tower | 9th Floor | IT/210 | 2023-08-12
213 | I Tower | 8th Floor | IT/211 | 2023-08-12
214 | I Tower | 9th Floor | IT/212 | 2023-08-15
215 | I Tower | 8th Floor | IT/213 | 2023-08-17
216 | I Tower | 9th Floor | IT/214 | 2023-08-18
217 | I Tower | 9th Floor | IT/215 | 2023-08-21
218 | I Tower | 9th Floor | IT/216 | 2023-08-22
219 | I Tower | 9th Floor | IT/217 | 2023-08-22
220 | I Tower | 9th Floor | IT/218 | 2023-08-23
221 | I Tower | 9th Floor | IT/219 | 2023-08-23
222 | I Tower | 9th Floor | IT/220 | 2023-08-31
223 | I Tower | 9th Floor | IT/221 | 2023-09-01
224 | I Tower | 9th Floor | IT/222 | 2023-09-02
225 | I Tower | 9th Floor | IT/223 | 2023-09-03
226 | I Tower | 9th Floor | IT/224 | 2023-09-04
227 | I Tower | 9th Floor | IT/225 | 2023-09-06
228 | I Tower | 9th Floor | IT/226 | 2023-09-10
229 | I Tower | 10th Floor | IT/227 | 2023-09-12
230 | I Tower | 10th Floor | IT/228 | 2023-09-14
231 | I Tower | 10th Floor | IT/229 | 2023-09-18
232 | I Tower | 10th Floor | IT/230 | 2023-09-20
233 | I Tower | 10th Floor | IT/231 | 2023-09-21
234 | I Tower | 10th Floor | IT/232 | 2023-09-21
235 | I Tower | 10th Floor | IT/233 | 2023-09-22
236 | I Tower | 10th Floor | IT/234 | 2023-09-23
237 | I Tower | 10th Floor | IT/235 | 2023-09-25
238 | I Tower | 10th Floor | IT/236 | 2023-09-25
239 | I Tower | 10th Floor | IT/237 | 2023-09-26
240 | I Tower | 10th Floor | IT/238 | 2023-10-03
241 | I Tower | 11th Floor | IT/239 | 2023-11-18 | 2023-11-19
242 | I Tower | 11th Floor | IT/240 | 2023-11-20 | 2023-11-20
243 | I Tower | 11th Floor | IT/241 | 2023-11-24 | 2023-11-25
244 | I Tower | 11th Floor | IT/242 | 2023-11-25 | 2023-11-25
245 | I Tower | 11th Floor | IT/243 | 2023-11-27 | 2023-11-27
246 | I Tower | 11th Floor | IT/244 | 2023-11-27 | 2023-11-27
247 | I Tower | 11th Floor | IT/245 | 2023-11-28 | 2023-11-28
248 | I Tower | 11th Floor | IT/246 | 2023-11-29 | 2023-11-29
249 | I Tower | 11th Floor | IT/247 | 2023-11-29 | 2023-11-29
250 | I Tower | 11th Floor | IT/248 | 2023-11-29 | 2023-11-30
251 | I Tower | 11th Floor | IT/249 | 2023-11-30 | 2023-11-30
252 | I Tower | 11th Floor | IT/250 | 2023-12-01 | 2023-12-01
253 | I Tower | 11th Floor | IT/251 | 2023-12-02 | 2023-12-02
254 | I Tower | 11th Floor | IT/252 | 2023-12-04 | 2023-12-04
255 | I Tower | 11th Floor | IT/253 | 2023-12-05 | 2023-12-05
256 | I Tower | 11th Floor | IT/254 | 2023-12-07 | 2023-12-07
257 | I Tower | 11th Floor | IT/255 | 2023-12-11 | 2023-12-11
258 | I Tower | 11th Floor | IT/256 | 2023-12-11 | 2023-12-12
259 | I Tower | 11th Floor | IT/257 | 2023-12-12 | 2023-12-12
260 | I Tower | 11th Floor | IT/258 | 2023-12-26 | 2023-12-26
261 | I Tower | 11th Floor | IT/259 | 2023-12-28 | 2023-12-28
| I Tower | 11th Floor | IT/260 | 2024-01-01 | 2024-01-01
| I Tower | 11th Floor | IT/261 | 2024-01-01 | 2024-01-02
| I Tower | 11th Floor | IT/262 | 2023-01-02 | 2023-01-02
| I Tower | 11th Floor | IT/263 | 2024-01-04 | 2024-01-04
| I Tower | 11th Floor | IT/264 | 2024-01-04 | 2024-01-05
| I Tower | 11th Floor | IT/265 | 2024-01-08 | 2024-01-07
| I Tower | 11th Floor | IT/266 | 2024-01-09 | 2024-01-10
| I Tower | 11th Floor | IT/267 | 2024-01-15 | 2024-01-16
| I Tower | 11th Floor | IT/268 | 2024-02-14 | 2024-02-15
| I Tower | 11th Floor | IT/269 | 2024-02-23 | 2024-02-23 | [10 empty] | v
| I Tower | 11th Floor | IT/270 | 2024-02-29 | 2024-02-29
| I Tower | 11th Floor | IT/271 | 2024-03-09 | 2024-03-10
| I Tower | 11th Floor | IT/272 | 2024-03-20 | 2024-03-20
| I Tower | 11th Floor | IT/273
| I Tower | 11th Floor | IT/274
| I Tower | 11th Floor | IT/275
| I Tower | 11th Floor | IT/276
| I Tower | 11th Floor | IT/277
| I Tower | 11th Floor | IT/278
| I Tower | 11th Floor | IT/279
| I Tower | 11th Floor | IT/280
| I Tower | 11th Floor | IT/281
| I Tower | 11th Floor | IT/282
| I Tower | 11th Floor | IT/283
| I Tower | 11th Floor | IT/284
2022-12-19

## Archtive IT
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 57
[9 empty] | Approved with comments (B) |  | 41
[9 empty] | Rejected ( R) |  | 4
[9 empty] | Open/Pending (OP) |  | 4
[9 empty] | Total |  | 106
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | 3rd floor | IT/1 | 2025-04-30 | 2025-04-30 | plaster work | Check plaster work for tile |  | 307310312 | A | 2025-05-08
2 | Sub Structure | 3RD FLOOR | IT/2 | 2025-05-02 | 2025-05-02 | level | Check level and plaster preparation for tile |  | 305306308314316 | A | 2025-05-08
|  | 3RD FLOOR | IT/2 A | 2025-05-20 | 2025-05-20 | layout | check tile layout and installation tile work permission for apartment |  | 311313314315316 | A | 2025-05-21
3 | Sub Structure | 3rd floor | IT/3 | 2025-05-03 | 2025-05-03 | level | Check level and preparation of plaster work for tiles |  |  | A | 2025-05-08
|  | 3rd floor | IT/3A | 2025-05-22 | 2025-05-22 | layout | check tile layout and installation tile work permission for apartment |  | 301302303304306 | A | 2025-05-30
4 | Sub Structure | 3rd floor | IT/4 | 2025-05-05 | 2025-05-05 | level | Check level and preparation of plaster work for tiles |  |  | A | 2025-05-08
5 | Sub Structure | 4th floor | IT/5 | 2025-05-05 | 2025-05-05 | level | Check level and preparation of plaster work for tiles |  |  | A | 2025-05-08
6 | Sub Structure | 4th floor | IT/6 | 2025-05-13 | 2025-05-13 | level | Check level and preparation of plaster work for tiles |  | 402404406414415 | A | 2025-05-14
7 | Sub Structure | 3rd floor | IT/7 | 2025-05-24 | 2025-05-24 | cleaning | check floor tile cleaning |  |  | A | 2025-05-26
8 | Sub Structure | 3rd floor | IT/8 | 2025-05-23 | 2025-05-23 | layout | check layout of tile and installation tile work |  |  | A | 2025-05-24
9 | Sub Structure | 3rd floor | IT/9 | 2025-05-27 | 2025-05-27 | cleaning | check floor tile cleaning |  |  | A | 2025-05-30
10 | Sub Structure | 3rd floor | IT/10 | 2025-05-30 | 2025-05-30 | cleaning | check floor tile cleaning |  |  | OP
11 | Sub Structure | 3rd floor | IT/11 | 2025-06-02 | 2025-06-02 | cleaning | check floor tile cleaning |  | 311313314 | OP
12 | Sub Structure | 4th floor | IT/12 | 2025-06-18 | 2025-06-18 | layout | check layout of tile and installation of tile work permission for apartments |  | 401-406 | A | 2025-06-18
13 | Sub Structure | 4th floor | IT/13 | 2025-06-21 | 2025-06-21 | layout | check layout of tile and installation tile work permission |  | 407-412 | A | 2025-06-21
14 | Sub Structure | 4th floor | IT/14 | 2025-06-21 | 2025-06-21 | cleaning | check cleaning of bedrooms area & approved tile grouting permission |  | 401-406 | A | 2025-06-21
15 | Sub Structure | 4th floor | IT/15 | 2025-06-23 | 2025-06-23 | cleaning | check bedrooms area cleaning and approved tile grouting permission |  | 407-412 | A | 2025-06-26
16 | Sub Structure | 6th Floor | IT/16 | 2025-06-23 | 2025-06-23 | layout | check layout of tile and installation tile work permission |  | 413-416 | A | 2025-06-26
17 | Sub Structure | 4th floor | IT/17 | 2025-06-25 | 2025-06-25 | cleaning | check bedrooms area cleaning & aproved tile grouting |  | 413-416 | A | 2025-06-26
18 | Sub Structure | 3rd floor | IT/18 | 2025-06-25 | 2025-06-25 | dismantling | check allow for dismantling of pcc WASHROOMS, pwd & laundary leveling |  | 301-304 | A | 2025-06-26
19 | Sub Structure | 4th floor | IT/19 | 2025-07-14 | 2025-07-14 | layout | check layout of tile and installation tile work permission |  | 401-406 | A | 2025-07-19
20 | Sub Structure | 4th floor | IT/20 | 2025-07-18 | 2025-07-18 | layout | Check layoout washroom Wall tile |  | 407-412 | A | 2025-07-19
21 | Sub Structure | 1st Floor | IT/21 | 2025-07-18 | 2025-07-18 | cleaning | Check clearing of living area and approved thr grouting permission |  | 401-406 | OP
22 | Sub Structure | 1st Floor | IT/22 | 2025-07-19 | 2025-07-19 | layout | check layout of tile and installation tile work permission |  | 407-416 | A | 2025-07-19
23 | Sub Structure | 7th Floor | IT/23 | 2025-07-19 | 2025-07-19 | layout | check layout of tile and installation tile work permission |  | 301-308 | A | 2025-07-19
24 | Sub Structure | 8th Floor | IT/24 | 2025-07-21 | 2025-07-21 | layout | Check layout of washrooms tiles and installation tile permission |  | 413-416 | OP
25 | Sub Structure | 2nd Floor | IT/25 | 2025-07-29 | 2025-07-29 | layout | Check layout of Washrooms floor tile and installation tile permission |  | 301-308 | A | 2025-07-30
26 | Sub Structure | 3rd floor | IT/26 | 2025-08-01 | 2025-08-01 | layout | Check layout of Washrooms floor tile and installation tile permission |  | 309-316 | A | 2025-08-05
27 | Sub Structure | 3rd floor | IT/27 | 2025-08-01 | 2025-08-01 | tile grouting | Check the cleaning of Washrooms floor tiles and approved tile grouting permission |  | 301-308 | A | 2025-08-05
28 | Sub Structure | 3rd floor | IT/28 | 2025-08-08 | 2025-08-08 | tile grouting | Check the cleaning of Washrooms floor tiles and approved tile grouting permission |  | 309-316 | R | 2025-08-12
29 | Sub Structure | 4th floor | IT/29 | 2025-08-08 | 2025-08-08 | plaster work | Check allow to start plaster work of balcony |  | 406-413 | A | 2025-08-12
30 | Sub Structure | 4th floor | IT/30 | 2025-08-11 | 2025-08-11 | layout | Check layout of Washrooms floor tile and installation tile permission |  | 409-416 | A | 2025-08-15
31 | Sub Structure | 4th Floor | IT/31 | 2025-08-12 | 2025-08-12 | plaster work | Sllowed to start plaster work of balcony for tiles |  | 401-405, 414-416 | A | 2025-08-15
32 | Sub Structure | 4th floor | IT/32 | 2025-08-13 | 2025-08-13 | layout | Check the layout of balcony tiles and allow to permissionfor tile work |  | 406-413 | A | 2025-08-15
33 | Sub Structure | 4th floor | IT/33 | 2025-08-20 | 2025-08-20 | layout | Check the layout of balcony tiles and allow to permissionfor tile work |  | 401-405, 414-416 | R | 2025-09-09
34 | Sub Structure | 2nd Floor | IT/34 | 2025-08-22 | 2025-08-22 | plaster work | allowed to start plaster work of balcony for tile |  | 303-308,310,314 | A | 2025-08-25
35 | Sub Structure | 2nd Floor | IT/35 | 2025-08-22 | 2025-08-22 | tile work | Check the final tile work |  | 301-316 | R | 2025-08-24
36 | Sub Structure | 2nd Floor | IT/36 | 2025-08-22 | 2025-08-22 | tile work | Check the final tile work |  | 401-416 | R | 2025-08-24
37 | Sub Structure | 1st Floor | IT/37 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 303 | B | 2025-09-05
|  | 1st Floor | IT/37 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 303 | A | 2025-10-09
38 | Sub Structure | 1st floor | IT/38 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 304 | B | 2025-09-05
|  | 1st floor | IT/38 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 304 | A | 2025-10-09
39 | Sub Structure | 1st Floor | IT/39 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 305 | B | 2025-09-05
|  | 1st Floor | IT/39 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 305 | A | 2025-10-09
40 | Sub Structure | 1st floor | IT/40 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 306 | B | 2025-09-05
|  | 1st floor | IT/40 R1 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 306 | A | 2025-10-09
41 | Sub Structure | 1st Floor | IT/41 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 307 | B | 2025-09-05
|  |  | IT/41 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 307 | A | 2025-10-09
42 | Sub Structure | 1st Floor | IT/42 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 308 | B | 2025-09-05
|  |  | IT/42 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 308 | A | 2025-10-09
43 | Sub Structure | 2nd Floor | IT/43 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 309 | B | 2025-09-05
|  |  | IT/43 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 309 | B | 2025-10-09
44 | Sub Structure | 2nd Floor | IT/44 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 310 | B | 2025-09-05
|  |  | IT/44 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 310 | B | 2025-10-09
45 | Sub Structure | 3rd Floor | IT/45 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 311 | B | 2025-09-05
|  |  | IT/45 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 311 | B | 2025-10-09
46 | Sub Structure | 5th Floor | IT/46 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 312 | B | 2025-09-05
|  |  | IT/46 R1 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 312 | B | 2025-10-09
47 | Sub Structure | 6th Floor | IT/47 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 313 | B | 2025-09-05
|  |  | IT/47 R1 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 313 | B | 2025-10-09
48 | Sub Structure | 7th Flor | IT/48 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 314 | B | 2025-09-05
|  |  | IT/48 R | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 314 | B | 2025-10-09
49 | Sub Structure | 2nd Floor | IT/49 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 315 | B | 2025-09-05
|  |  | IT/49 R1 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 315 | B | 2025-10-09
50 | Sub Structure | 2nd Floor | IT/50 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 316 | B | 2025-09-05
|  |  | IT/50 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 316 | B | 2025-10-09
51 | Sub Structure | 10th Floor | IT/51 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 401 | B | 2025-09-05
|  |  | IT/51 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 401 | A | 2025-10-10
52 | Sub Structure | 3rd Floor | IT/52 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 402 | B | 2025-09-05
|  |  | IT/52 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 402 | A | 2025-10-10
53 | Sub Structure | 3rd Floor | IT/53 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 403 | B | 2025-09-05
|  |  | IT/53 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 403 | A | 2025-10-10
54 | Sub Structure | 3rd Floor | IT/54 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 404 | B | 2025-09-05
|  |  | IT/54 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 404 | A | 2025-10-10
55 | Sub Structure | 4th Floor | IT/55 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 405 | B | 2025-09-05
|  |  | IT/55 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 405 | A | 2025-10-10
56 | Sub Structure | 4th Floor | IT/56 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 406 | B | 2025-09-05
|  |  | IT/56 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 406 | A | 2025-10-10
57 | Sub Structure | 8th Floor | IT/57 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 407 | B | 2025-09-05
|  |  | IT/57 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 407 | A | 2025-10-10
58 | Sub Structure | 9th Floor | IT/58 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 408 | B | 2025-09-05
|  |  | IT/58 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 408 | A | 2025-10-10
59 | Sub Structure | 3rd floor | IT/59 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 409 | B | 2025-09-05
|  |  | IT/59 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 409 | A | 2025-10-10
60 | Sub Structure | 3rd Floor | IT/60 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 410 | B | 2025-09-05
|  |  | IT/60 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 410 | A | 2025-10-10
61 | Sub Structure | 4th Floor | IT/61 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 411 | B | 2025-09-04
|  |  | IT/61 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 411 | A | 2025-10-10
62 | Sub Structure | 4th Floor | IT/62 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 412 | B | 2025-09-04
|  |  | IT/62 R1 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 412 | A | 2025-10-10
63 | Sub Structure | 11th Floor | IT/63 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 413 | B | 2025-09-05
|  |  | IT/63 R1 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 413 | A | 2025-10-10
64 | Sub Structure | 3rd Floor | IT/64 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 414 | B | 2025-09-05
|  |  | IT/64R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 414 | A | 2025-10-10
65 | Sub Structure | 3rd Floor | IT/65 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 415 | B | 2025-09-05
|  |  | IT/65 R1 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 415 | A | 2025-10-10
66 | Sub Structure | 5th Floor | IT/66 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 416 | B | 2025-09-05
|  |  | IT/66 R1 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 416 | A | 2025-10-10
67 | Sub Structure | 4th Floor | IT/67 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 301 | B | 2025-09-05
|  | 4th Floor | IT/67 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 301 | A | 2025-10-09
68 | Sub Structure | 4th Floor | IT/68 | 2025-08-27 | 2025-08-27 | tile work | Check the final tile work without balcony |  | 302 | B | 2025-09-05
|  | 4th Floor | IT/68 R01 | 2025-09-30 | 2025-09-30 | tile work | Check the final tile work without balcony |  | 302 | A | 2025-10-09
69 | Sub Structure | 3rd floor | IT/69 | 2025-09-05 | 2025-09-05 | tile work | Check the final tile work of powder bath |  | 302 | B | 2025-09-15
70 | Sub Structure | 3rd floor | IT/70 | 2025-09-05 | 2025-09-05 | plaster work | Allow to start plaster work of balcony for tile |  | 301-302,309-316 | A | 2025-09-12
71 | Sub Structure | 5th Floor | IT/71 | 2025-09-05 | 2025-09-05 | layout | Check layout of balcony tiles and allowed to permission for tile work |  | 303-308,310,314 | A | 2025-09-11
72 | Sub Structure | 5th Floor | IT/72 | 2025-09-05 | 2025-09-05 | layout | Check layout of balcony tiles and allowed to permission for tile work |  | 301-302,309-316 | A | 2025-09-16
73 | Sub Structure | 4th Floor | IT/73
74 | Sub Structure | 10ht Floor | IT/74
75 | Sub Structure | 5th Floor | IT/75
76 | Sub Structure | 5th Floor | IT/76
77 | Sub Structure | 5th Floor | IT/77
78 | Sub Structure | 5th Floor | IT/78
79 | Sub Structure | 4th Floor | IT/79
80 | Sub Structure | 5th Floor | IT/80
81 | Sub Structure | 1st Floor | IT/81
82 | Sub Structure | 5th Floor | IT/82
83 | Sub Structure | 5th Floor | IT/83
84 | Sub Structure | 5th Floor | IT/84
85 | Sub Structure | 5th Floor | IT/85
86 | Sub Structure | 5th Floor | IT/86
87 | Sub Structure | 4th Floor | IT/87
88 | Sub Structure | 1st Floor | IT/88
89 | Sub Structure | 1st Floor | IT/89
90 | Sub Structure | 5th Floor | IT/90
91 | Sub Structure | 5th Floor | IT/91
92 | Sub Structure | 5th Floor | IT/92
93 | Sub Structure | 6th Floor | IT/93
94 | Sub Structure | 6ht Floor | IT/94
95 | Sub Structure | 5th Floor | IT/95
96 | Sub Structure | 5th Floor | IT/96
97 | Sub Structure | 6ht Floor | IT/97
98 | Sub Structure | 6th Floor | IT/98
99 | Sub Structure | 5th Floor | IT/99
100 | Sub Structure | 5th Floor | IT/100
101 | Sub Structure | 2nd Floor | IT/101
102 | Sub Structure | 5th Floor | IT/102
103 | Sub Structure | 6th Floor | IT/103
104 | Sub Structure | 7th Floor | IT/104
105 | Sub Structure | 7th Floor | IT/105
106 | Sub Structure | 7th Floor | IT/106
107 | Sub Structure | 6th Floor | IT/107
108 | Sub Structure | 6th Floor | IT/108
109 | Sub Structure | 7th Floor | IT/109
110 | Sub Structure | 7th Floor | IT/110
111 | Sub Structure | 7th Floor | IT/111
112 | Sub Structure | 7th Floor | IT/112
113 | Sub Structure | 6th Floor | IT/113
114 | Sub Structure | 5th Floor | IT/114
115 | Sub Structure | 6th Floor | IT/114A
116 | Sub Structure | 2nd floor | IT/115
117 | Sub Structure | 7th Floor | IT/116
118 | Sub Structure | 7th Floor | IT/117
119 | Sub Structure | 1st Floor | IT/118
120 | Sub Structure | 2nd Floor | IT/119
121 | Sub Structure | 1st floor | IT/120
122 | Sub Structure | 1st floor | IT/121
123 | Sub Structure | 1st Floor | IT/122
124 | Sub Structure | 2nd Floor | IT/123
125 | Sub Structure | 11th Floor | IT/124
126 | Sub Structure | 1st Floor | IT/125
127 | Sub Structure | 1st Floor | IT/126
128 | Sub Structure | 1st Floor | IT/127
129 | Sub Structure | 2nd Floor | IT/128
130 | Sub Structure | 2nd Floor | IT/129
131 | Sub Structure | 2nd Floor | IT/130
132 | Sub Structure | 2nd floor | IT/131
133 | Sub Structure | 3rd floor | IT/132
| Sub Structure | 2nd Floor | IT/133
| Sub Structure | 3rd Floor | IT/134
| Sub Structure | 3rd Floor | IT/135
| Sub Structure | 4th floor | IT/136
| Sub Structure | 3rd Floor | IT/137
| Sub Structure | 2nd floor | IT/138
| Sub Structure | 4th Floor | IT/139
| Sub Structure | 3rd Floor | IT/140
| Sub Structure | 2nd floor | IT/141
| Sub Structure | 2nd floor | IT/142
| Sub Structure | 6th Floor | IT/143
| Sub Structure | 7th Floor | IT/144
| Sub Structure | 4th Floor | IT/145
| Sub Structure | 3rd floor | IT/146
| Sub Structure | 5th Floor | IT/147
| Sub Structure | 4th Floor | IT/148
| Sub Structure | 2nd floor | IT/149
| Sub Structure | 5th Floor | IT/150
| Sub Structure | 3rd Floor | IT/151
| Sub Structure | 3rd Floor | IT/152
| Sub Structure | 3rd Floor | IT/153
| Sub Structure | 7th Floor | IT/154
| Sub Structure | 7th Floor | IT/155
| Sub Structure | 5th Floor | IT/156
| Sub Structure | 5th floor | IT/157
| Sub Structure | 4th Floor | IT/158
| Sub Structure | 2nd Floor | IT/159
| Sub Structure | 3rd Floor | IT/160
| Sub Structure | 3rd Floor | IT/161
| Sub Structure | 3rd Floor | IT/162
| Sub Structure | 3rd Floor | IT/163
| Sub Structure | 6th Floor | IT/164
| Sub Structure | 3rd Floor | IT/165
| Sub Structure | 3rd Floor | IT/166
| Sub Structure | 8th Floor | IT/167
| Sub Structure | 8th Floor | IT/168
| Sub Structure | 4th Floor | IT/169
| Sub Structure | 4th Floor | IT/170
| Sub Structure | 8th Floor | IT/171
| Sub Structure | Basement | IT/172
| Sub Structure | 3rd Floor | IT/173
| Sub Structure | 6th Floor | IT/174
| Sub Structure | 5th Floor | IT/175
| Sub Structure | 8th Floor | IT/176
| Sub Structure | 8th Floor | IT/177
| Sub Structure | 4th Floor | IT/178
| Sub Structure | 4th Floor | IT/179
| Sub Structure | 8th Floor | IT/180
| Sub Structure | 8th Floor | IT/181
| Sub Structure | 1st floor | IT/182
| Sub Structure | 2nd floor | IT/183
| Sub Structure | 4th Floor | IT/184
| Sub Structure | 4th Floor | IT/185
| Sub Structure | 5th Floor | IT/186
| Sub Structure | 5th Floor | IT/187
| Sub Structure | Basement | IT/188
| Sub Structure | 6th Floor | IT/189
| Sub Structure | 6th Floor | IT/190
| Sub Structure | Basement | IT/191
| Sub Structure | 8th Floor | IT/192
| Sub Structure | 8th Floor | IT/193
| Sub Structure | 9th Floor | IT/194
| Sub Structure | 9th Floor | IT/195
| Sub Structure | 5th floor | IT/196
| Sub Structure | 5th Floor | IT/197
| Sub Structure | 9th Floor | IT/198
| Sub Structure | 9th Floor | IT/199
| Sub Structure | 5th Floor | IT/200
| Sub Structure | 5th Floor | IT/201
| Sub Structure | 8th floor | IT/202
| Sub Structure | 8th Floor | IT/203
| Sub Structure | 3rd Floor | IT/204
| Sub Structure | 4th Floor | IT/205
| Sub Structure | 5th Floor | IT/206
| Sub Structure | 10th Floor | IT/207
| Sub Structure | 10th Floor | IT/208
| Sub Structure | Basement | IT/209
| Sub Structure | 6th floor | IT/210
| Sub Structure | 6th floor | IT/211
| Sub Structure | 5th Floor | IT/212
| Sub Structure | 5th Floor | IT/213
| Sub Structure | 7th Floor | IT/214
| Sub Structure | 8th Floor | IT/215
| Sub Structure | 8th Floor | IT/216
| Sub Structure | 5th floor | IT/217
| Sub Structure | Ground floor | IT/218
| Sub Structure | 7th Floor | IT/219
| Sub Structure | 7th Floor | IT/220
| Sub Structure | 7th Floor | IT/221
| Sub Structure | 8th Floor | IT/222
| Sub Structure | 8th Floor | IT/223
| Sub Structure | 8th Floor | IT/224
| Sub Structure | 8th Floor | IT/225
| Sub Structure | 6th floor | IT/226
| Sub Structure | 8th floor | IT/227
| Sub Structure | 6th Floor | IT/228
| Sub Structure | 6th Floor | IT/229
| Sub Structure | 8th Floor | IT/230
| Sub Structure | 7th Floor | IT/231
| Sub Structure | 10th Floor | IT/232
| Sub Structure | Basement | IT/233
| Sub Structure | 11th floor | IT/234
| Sub Structure | 11th floor | IT/235
| Sub Structure | 8th floor | IT/236
| Sub Structure | 8th floor | IT/237
| Sub Structure | 7th floor | IT/238
| Sub Structure | 7th floor | IT/239
| Sub Structure | 7th floor | IT/240
| Sub Structure | basement | IT/241
| Sub Structure | 11th floor | IT/242
| Sub Structure | 5th floor | IT/243
| Sub Structure | 6th floor | IT/244
| Sub Structure | 7th floor | IT/245
| Sub Structure | GF | IT/246
| Sub Structure | GF | IT/247
| Sub Structure | 8th Floor | IT/248
| Sub Structure | 8th Floor | IT/249
| Sub Structure | 8th Floor | IT/250
| Sub Structure | 9th Floor | IT/251
| Sub Structure | 9th Floor | IT/252
| Sub Structure | 7th floor | IT/253
| Sub Structure | 8th floor | IT/254
| Sub Structure | GF | IT/255
| Sub Structure | GF | IT/256
| Sub Structure | 8th floor | IT/257
| Sub Structure | 9th floor | IT/258
| Sub Structure | 9th floor | IT/259
| Sub Structure | 9th floor | IT/260
| Sub Structure | 9th floor | IT/261
| Sub Structure | 9th floor | IT/262
| Sub Structure | 8th floor | IT/263
| Sub Structure | 8th floor | IT/264
| Sub Structure | 9th floor | IT/265
| Sub Structure | 9th floor | IT/266
| Sub Structure | 2nd floor | IT/267
| Sub Structure | 1st floor | IT/268
| Sub Structure | 1st floor | IT/269
| Sub Structure | 1st floor | IT/270
| Sub Structure | 8th floor | IT/271
| Sub Structure | 8th floor | IT/272
| Sub Structure | 8th floor | IT/273
| Sub Structure | 1st floor | IT/274
| Sub Structure | 1st floor | IT/275
| Sub Structure | 1st floor | IT/276
| Sub Structure | 7th floor | IT/277
| Sub Structure | 1st Floor | IT/278
| Sub Structure | 8th floor | IT/279
| Sub Structure | 8th floor | IT/280
| Sub Structure | Basement | IT/281
| Sub Structure | 9th floor | IT/282
| Sub Structure | 10th floor | IT/283
| Sub Structure | 2nd floor | IT/284
| Sub Structure | 2nd floor | IT/285
| Sub Structure | 10th floor | IT/286
| Sub Structure | 9th floor | IT/287
| Sub Structure | 7th floor | IT/288
| Sub Structure | 2nd floor | IT/289
| Sub Structure | 10th floor | IT/290
| Sub Structure | 10th floor | IT/291
| Sub Structure | 2nd floor | IT/292
| Sub Structure | 2nd floor | IT/293
| Sub Structure | 10th floor | IT/294
| Sub Structure | 10th floor | IT/295
| Sub Structure | 10th floor | IT/296
| Sub Structure | 9th floor | IT/297
| Sub Structure | 2nd floor | IT/298
| Sub Structure | 2nd floor | IT/299
| Sub Structure | 11th floor | IT/300
| Sub Structure | 11th floor | IT/301
| Sub Structure | 11th floor | IT/302
| Sub Structure | 11th floor | IT/303
| Sub Structure | 1st Floor | IT/304
| Sub Structure | 11th floor | IT/305
| Sub Structure | 9th floor | IT/306
| Sub Structure | 2nd floor | IT/307
| Sub Structure | 11th floor | IT/308
| Sub Structure | 11th floor | IT/309
| Sub Structure | 10th floor | IT/310
| Sub Structure | 10th floor | IT/311
| Sub Structure | 2nd floor | IT/312
| Sub Structure | 2nd floor | IT/313
| Sub Structure | 1st floor | IT/314
| Sub Structure | 10th floor | IT/315
| Sub Structure | 11th floor | IT/316
| Sub Structure | 11th floor | IT/317
| Sub Structure | Basement | IT/318
| Sub Structure | 9th floor | IT/319
| Sub Structure | 10th floor | IT/320
| Sub Structure | 9th floor | IT/321
| Sub Structure | 10th floor | IT/322
| Sub Structure | 8th floor | IT/323
| Sub Structure | 9th floor | IT/324
| Sub Structure | 9th floor | IT/325
| Sub Structure | 3rd floor | IT/326
| Sub Structure | 3rd floor | IT/327
| Sub Structure | 3rd floor | IT/328
| Sub Structure | 6th floor | IT/329
| Sub Structure | 7th floor | IT/330
| Sub Structure | 8th floor | IT/331
| Sub Structure | 8th floor | IT/332
| Sub Structure | 8th floor | IT/333
| Sub Structure | 8th floor | IT/334 | [11 empty] | 2024-08-15
| Sub Structure | 10th floor | IT/335
| Sub Structure | 10th floor | IT/336
| Sub Structure | 3rd floor | IT/337
| Sub Structure | 3rd floor | IT/338
| Sub Structure | 11th floor | IT/339
| Sub Structure | 3rd floor | IT/340
| Sub Structure | 3rd floor | IT/341
| Sub Structure | 9th floor | IT/342
| Sub Structure | 9th floor | IT/343
| Sub Structure | 11th floor | IT/344
| Sub Structure | 11th floor | IT/345
| Sub Structure | 11th floor | IT/346
| Sub Structure | 11th floor | IT/347
| Sub Structure | 4th floor | IT/348
| Sub Structure | 4th floor | IT/349
| Sub Structure | 10th floor | IT/350
| Sub Structure | 10th floor | IT/351
| Sub Structure | 4th floor | IT/352
| Sub Structure | 4th floor | IT/353
| Sub Structure | 4th floor | IT/354
| Sub Structure | 3rd floor | IT/355
| Sub Structure | 3rd floor | IT/356
| Sub Structure | 3rd floor | IT/357
| Sub Structure | 3rd floor | IT/358
| Sub Structure | 4th floor | IT/359
| Sub Structure | 11th floor | IT/360
| Sub Structure | 4th floor | IT/361
| Sub Structure | 4th floor | IT/362
| Sub Structure | 11th floor | IT/363
| Sub Structure | 4th floor | IT/364
| Sub Structure | 4th floor | IT/365
| Sub Structure | 4th floor | IT/366
| Sub Structure | 4th floor | IT/367
| Sub Structure | 1st floor | IT/368
| Sub Structure | 1st floor | IT/369
| Sub Structure | 1st floor | IT/370
| Sub Structure | 1st floor | IT/371
| Sub Structure | 1st floor | IT/372
| Sub Structure | 1st floor | IT/373
| Sub Structure | Top floor | IT/374
| Sub Structure | 11th floor | IT/375
| Sub Structure | 5th floor | IT/376
| Sub Structure | 5th floor | IT/377
| Sub Structure | 1st floor | IT/378
| Sub Structure | 1st floor | IT/379
| Sub Structure | 2nd floor | IT/380
| Sub Structure | 11th floor | IT/381
| Sub Structure | Basement | IT/382
| Sub Structure | 1st floor | IT/383
| Sub Structure | Top floor | IT/384
| Sub Structure | 1st floor | IT/385
| Sub Structure | 5th floor | IT/386
| Sub Structure | 9th floor | IT/387
| Sub Structure | 10th floor | IT/388
| Sub Structure | 2nd floor | IT/389
| Sub Structure | top floor | IT/390
| Sub Structure | top floor | IT/391
| Sub Structure | 1st floor | IT/392
| Sub Structure | 2nd floor | IT/393
| Sub Structure | 1st floor | IT/394
| Sub Structure | 4th floor | IT/395
| Sub Structure | 2nd floor | IT/396
| Sub Structure | 2nd floor | IT/397
| Sub Structure | 2nd floor | IT/398
| Sub Structure | 2nd floor | IT/399
| Sub Structure | 5th floor | IT/400
| Sub Structure | 5th floor | IT/401
| Sub Structure | 2nd floor | IT/402
| Sub Structure | 2nd floor | IT/403
| Sub Structure | 5th floor | IT/404
| Sub Structure | 2nd floor | IT/405
| Sub Structure | 2nd floor | IT/406
| Sub Structure | 2nd floor | IT/407
| Sub Structure | 2nd floor | IT/408
| Sub Structure | 2nd floor | IT/409
| Sub Structure | 5th floor | IT/410
| Sub Structure | 5th floor | IT/411
| Sub Structure | top floor | IT/412
| Sub Structure | 5th floor | IT/413
| Sub Structure | 3rd floor | IT/414
| Sub Structure | 3rd floor | IT/415
| Sub Structure | Top roof | IT/416
| Sub Structure | 3rd floor | IT/417
| Sub Structure | 11th floor | IT/418
| Sub Structure | 3rd floor | IT/419
| Sub Structure | Top floor | IT/420
| Sub Structure | 3rd floor | IT/421
| Sub Structure | 6th floor | IT/422
| Sub Structure | 3rd floor | IT/423
| Sub Structure | 11th floor | IT/424
| Sub Structure | Basement | IT/425
| Sub Structure | 3rd floor | IT/426
| Sub Structure | 3rd floor | IT/427
| Sub Structure | 6th floor | IT/428
| Sub Structure | 6th floor | IT/429
| Sub Structure | 3rd floor | IT/430
| Sub Structure | 3rd floor | IT/431
| Sub Structure | 6th floor | IT/432
| Sub Structure | 6th floor | IT/433
| Sub Structure | top floor | IT/434
| Sub Structure | 6th floor | IT/435
| Sub Structure | 3rd floor | IT/436
| Sub Structure | 3rd floor | IT/437
| Sub Structure | 6th floor | IT/438
| Sub Structure | top floor | IT/439
| Sub Structure | Top floor | IT/440
| Sub Structure | 4th floor | IT/441
| Sub Structure | 4th floor | IT/442
| Sub Structure | 3rd floor | IT/443
| Sub Structure | top floor | IT/444
| Sub Structure | 6th floor | IT/445
| Sub Structure | 7th floor | IT/446
| Sub Structure | 2nd floor | IT/447
| Sub Structure | 7th floor | IT/448
| Sub Structure | 4th floor | IT/449
| Sub Structure | 7th floor | IT/450
| Sub Structure | 7th floor | IT/451
| Sub Structure | 4th floor | IT/452
| Sub Structure | 4th floor | IT/453
| Sub Structure | 7th floor | IT/454
| Sub Structure | top floor | IT/455
| Sub Structure | 4th floor | IT/456
| Sub Structure | 7th floor | IT/457
| Sub Structure | 4th floor | IT/458
| Sub Structure | Top floor | IT/459
| Sub Structure | 7th floor | IT/460
| Sub Structure | 1st floor | IT/461
| Sub Structure | 4th floor | IT/462
| Sub Structure | 7th floor | IT/463
| Sub Structure | top floor | IT/464
| Sub Structure | 4th floor | IT/465
| Sub Structure | 4th floor | IT/466
| Sub Structure | 7th floor | IT/467
| Sub Structure | top floor | IT/468
| Sub Structure | 8th floor | IT/469
| Sub Structure | 8th floor | IT/470
| Sub Structure | 8th floor | IT/471
| Sub Structure | Top floor | IT/472
| Sub Structure | 5th floor | IT/473
| Sub Structure | 5th floor | IT/474
| Sub Structure | 5th floor | IT/475
| Sub Structure | 2nd floor | IT/476
| Sub Structure | 1st floor | IT/477
| Sub Structure | 8th floor | IT/478
| Sub Structure | 8th floor | IT/479
| Sub Structure | 8th floor | IT/480
| Sub Structure | 9th floor | IT/481
| Sub Structure | 5th floor | IT/482
| Sub Structure | 1st floor | IT/483
| Sub Structure | 5th floor | IT/484
| Sub Structure | 5th floor | IT/485
| Sub Structure | 5th floor | IT/486
| Sub Structure | 2nd floor | IT/487
| Sub Structure | 8th floor | IT/488
| Sub Structure | 8th floor | IT/489
| Sub Structure |  | IT/490
| Sub Structure | 9th floor | IT/491
| Sub Structure | Top floor | IT/492
| Sub Structure | 5th floor | IT/493
| Sub Structure | 2nd floor | IT/494
| Sub Structure | 5th floor | IT/495
| Sub Structure | 2nd floor | IT/496
| Sub Structure | 5th floor | IT/497
| Sub Structure | 5th floor | IT/498
| Sub Structure |  | IT/499
| Sub Structure | 9th floor | IT/500
| Sub Structure | 5th floor | IT/501
| Sub Structure | 8th floor | IT/502
| Sub Structure | 5th floor | IT/503
| Sub Structure | 11th floor | IT/504
| Sub Structure | 8th floor | IT/505
| Sub Structure | 8th floor | IT/506
| Sub Structure | 5th floor | IT/507
| Sub Structure | 5th floor | IT/508
| Sub Structure | 8th floor | IT/509
| Sub Structure | 8th floor | IT/510
| Sub Structure | 9th floor | IT/511
| Sub Structure | 2nd floor | IT/512
| Sub Structure | 3rd floor | IT/513
| Sub Structure | 6th floor | IT/514
| Sub Structure | 2nd floor | IT/515
| Sub Structure | 5th floor | IT/516
| Sub Structure | 5th floor | IT/517
| Sub Structure | 3rd floor | IT/518
| Sub Structure | 6th floor | IT/519
| Sub Structure | 8th floor | IT/520
| Sub Structure | 6th floor | IT/521
| Sub Structure | 6th floor | IT/522
| Sub Structure | 6th floor | IT/523
| Sub Structure | 3rd floor | IT/524
| Sub Structure | 9th floor | IT/525
| Sub Structure | 6th floor | IT/526
| Sub Structure | 6th floor | IT/527
| Sub Structure | 6th floor | IT/528
| Sub Structure | 6th floor | IT/529
| Sub Structure | 6th floor | IT/530
| Sub Structure | 9th floor | IT/531
| Sub Structure | 6th floor | IT/532
| Sub Structure | 9th floor | IT/533
| Sub Structure | Mummty floor | IT/534
| Sub Structure | 9th floor | IT/535
| Sub Structure | 9th floor | IT/536
| Sub Structure | 6th floor | IT/537
| Sub Structure | 3rd floor | IT/538
| Sub Structure | 4th floor | IT/539
| Sub Structure | 6th floor | IT/540
| Sub Structure | top floor | IT/541
| Sub Structure | 6th floor | IT/542
| Sub Structure | 9th floor | IT/543
| Sub Structure | 4th floor | IT/544
| Sub Structure | 9th floor | IT/545
| Sub Structure | 8th floor | IT/546
| Sub Structure | 6th floor | IT/547
| Sub Structure |  | IT/548
| Sub Structure | 4th floor | IT/549
| Sub Structure | 6th floor | IT/550
| Sub Structure | 5th floor | IT/551
| Sub Structure | 6th floor | IT/552
| Sub Structure | 5th floor | IT/553
| Sub Structure | 5th floor | IT/554
| Sub Structure | 9th floor | IT/555
| Sub Structure | 7th floor | IT/556
| Sub Structure | 7th floor | IT/557
| Sub Structure | 6th floor | IT/558
| Sub Structure | 6th floor | IT/559
| Sub Structure | 6th floor | IT/560
| Sub Structure | 7th floor | IT/561
| Sub Structure | top roof mummty | IT/562
| Sub Structure | 7th floor | IT/563
| Sub Structure | top floor | IT/564
| Sub Structure | 7th floor | IT/565
| Sub Structure | 7th floor | IT/566
| Sub Structure | 7th floor | IT/567
| Sub Structure | 7th floor | IT/568
| Sub Structure | 7th floor | IT/569
| Sub Structure | 3rd floor | IT/570
| Sub Structure | 7th floor | IT/571
| Sub Structure | 7th floor | IT/572
| Sub Structure | 7th floor | IT/573
| Sub Structure | 7th floor | IT/574
| Sub Structure | 7th flor | IT/575
| Sub Structure | 7th floor | IT/576
| Sub Structure | 7th floor | IT/577
| Sub Structure | 1st to 2nd floor | IT/578
| Sub Structure |  | IT/579
| Sub Structure | 1st floor | IT/580
| Sub Structure | 7th floor | IT/581
| Sub Structure | 7th floor | IT/582
| Sub Structure | 8th floor | IT/583
| Sub Structure | 8th floor | IT/584
| Sub Structure | 7th floor | IT/585
| Sub Structure | 7th floor | IT/586
| Sub Structure | 7th floor | IT/587
| Sub Structure | 8th floor | IT/588
| Sub Structure | 8th floor | IT/589
| Sub Structure | 8th floor | IT/590
| Sub Structure | GF | IT/591
| Sub Structure | 3rd floor | IT/592
| Sub Structure | 9th floor | IT/593
| Sub Structure | 8th floor | IT/594
| Sub Structure | 8th floor | IT/595
| Sub Structure | 8th floor | IT/596
| Sub Structure | 9th floor | IT/597
| Sub Structure | 9th floor | IT/598
| Sub Structure | 8th floor | IT/599
| Sub Structure | 8th floor | IT/600
| Sub Structure | 8th floor | IT/601
| Sub Structure | 8th floor | IT/602
| Sub Structure | 8th floor | IT/603
| Sub Structure | Top floor | IT/604
| Sub Structure | 2nd floor | IT/605
| Sub Structure | 9th floor | IT/606
| Sub Structure | 9th floor | IT/607
| Sub Structure | 8th floor | IT/608
| Sub Structure | 10th floor | IT/609
| Sub Structure | 4th floor | IT/610
| Sub Structure | 8th floor | IT/611
| Sub Structure | 8th floor | IT/612
| Sub Structure | 8th floor | IT/613
| Sub Structure | 10th floor | IT/614
| Sub Structure | 8th floor | IT/615
| Sub Structure | 8th floor | IT/616
| Sub Structure | 8th floor | IT/617
| Sub Structure | Mummty floor | IT/618
| Sub Structure | top floor | IT/619
| Sub Structure | 9th floor | IT/620
| Sub Structure | 9th floor | IT/621
| Sub Structure | 9th floor | IT/622
| Sub Structure | 9th floor | IT/623
| Sub Structure | 10th floor | IT/624
| Sub Structure | 8th floor | IT/625
| Sub Structure | 9th floor | IT/626
| Sub Structure | 5th floor | IT/627
| Sub Structure | 8th floor | IT/628
| Sub Structure | 8th floor | IT/629
| Sub Structure | 9th floor | IT/630
| Sub Structure | 10th floor | IT/631
| Sub Structure | 8th floor | IT/632
| Sub Structure | 9th floor | IT/633
| Sub Structure | 9th floor | IT/634
| Sub Structure | 5th floor | IT/635
| Sub Structure | 9th floor | IT/636
| Sub Structure | 9th floor | IT/637
| Sub Structure | Top floor | IT/638
| Sub Structure | 10th flooor | IT/639
| Sub Structure | 10th floor | IT/640
| Sub Structure | 11th floor | IT/641
| Sub Structure | 4th floor | IT/642
| Sub Structure | 9th floor | IT/643
| Sub Structure | 9th floor | IT/644
| Sub Structure | 10th floor | IT/645
| Sub Structure | 10th floor | IT/646
| Sub Structure | 1st floor to top floor | IT/647
| Sub Structure | 10th floor | IT/648
| Sub Structure | top floor | IT/649
| Sub Structure |  | IT/650
| Sub Structure | 11th floor | IT/651
| Sub Structure | 9th floor | IT/652
| Sub Structure | 4th floor | IT/653
| Sub Structure | 10th floor | IT/654
| Sub Structure | 10th floor | IT/655
| Sub Structure | 10th floor | IT/656
| Sub Structure | 9th floor | IT/657
| Sub Structure | top floor | IT/658
| Sub Structure | 10th floor | IT/659
| Sub Structure | top floor | IT/660
| Sub Structure | 10th floor | IT/661
| Sub Structure | 10th floor | IT/662
| Sub Structure | 10th floor | IT/663
| Sub Structure | 10th floor | IT/664
| Sub Structure | Mummty floor | IT/665
| Sub Structure | 10th floor | IT/666
| Sub Structure | 10th floor | IT/667
| Sub Structure | 10th floor | IT/668
| Sub Structure | 10th floor | IT/669
| Sub Structure | 10th floor | IT/670
| Sub Structure | 11th floor | IT/671
| Sub Structure | 10th floor | IT/672
| Sub Structure | 5th floor | IT/673
| Sub Structure | 5th floor | IT/674
| Sub Structure | 5th floor | IT/675
| Sub Structure | 11th floor | IT/676
| Sub Structure | 11th floor | IT/677
| Sub Structure | 11th floor | IT/678
| Sub Structure | 11th floor | IT/679
| Sub Structure | 11th floor | IT/680
| Sub Structure | 11th floor | IT/681
| Sub Structure | 11th floor | IT/682
| Sub Structure | 11th floor | IT/683
| Sub Structure | 11th floor | IT/684
| Sub Structure | 11th floor | IT/685
| Sub Structure | 11th floor | IT/686
| Sub Structure | Top floor | IT/687
| Sub Structure | top floor | IT/688
| Sub Structure | Top floor | IT/689
| Sub Structure | top floor | IT/690
| Sub Structure | 11th floor | IT/691
| Sub Structure | 11th floor | IT/692
| Sub Structure | 11th floor | IT/693
| Sub Structure | 11th floor | IT/694
| Sub Structure | top floor | IT/695
| Sub Structure | top floor | IT/696
| Sub Structure | 11th floor | IT/697
| Sub Structure | 5th floor | IT/698
| Sub Structure | 11th floor | IT/699
| Sub Structure | top floor | IT/700
| Sub Structure | Top floor | IT/701
| Sub Structure | 11th floor | IT/702
| Sub Structure | top floor | IT/703
| Sub Structure | Ground floor | IT/704
| Sub Structure | Top floor | IT/705
| Sub Structure | 5th floor | IT/706
| Sub Structure | Top floor | IT/707
| Sub Structure | 6th floor | IT/708
| Sub Structure | 3rd floor | IT/709
| Sub Structure | 4th floor | IT/710
| Sub Structure | 5th floor | IT/711
| Sub Structure | 6th floor | IT/712
| Sub Structure | 6th floor | IT/713
| Sub Structure | Top floor | IT/714
| Sub Structure | Top floor | IT/715
| Sub Structure | 7th floor | IT/716
| Sub Structure | Top floor | IT/717
| Sub Structure | Top floor | IT/718
| Sub Structure | 7th floor | IT/719
| Sub Structure | 7th floor | IT/720
| Sub Structure | Ground floor | IT/721
| Sub Structure | Top floor | IT/722
| Sub Structure | 8th floor | IT/723
| Sub Structure | Top floor | IT/724
| Sub Structure | 8th floor | IT/725
| Sub Structure | 8th floor | IT/726
| Sub Structure | Ground floor | IT/727
| Sub Structure | 9th floor | IT/728
| Sub Structure | 9th floor | IT/729
| Sub Structure | 9th floor | IT/730
| Sub Structure | 10th floor | IT/731
| Sub Structure | 10th floor | IT/732
| Sub Structure | 10th floor | IT/733
| Sub Structure | 8th floor | IT/734
| Sub Structure | 11th floor | IT/735
| Sub Structure | 11th floor | IT/736
| Sub Structure | 11th floor | IT/737
| Sub Structure | Ground floor | IT/738
| Sub Structure | 5th floor | IT/739
| Sub Structure | 2nd floor | IT/740
| Sub Structure | Top floor | IT/741
| Sub Structure | 1st to floor to top | IT/742
| Sub Structure | 10th floor | IT/743
| Sub Structure | 11th floor | IT/744
| Sub Structure | Top floor | IT/745
| Sub Structure | 1st floor | IT/746
| Sub Structure | 11th floor | IT/747
| Sub Structure | 10th floor | IT/748
| Sub Structure | 11th floor | IT/749
| Sub Structure | 1st floor | IT/750
| Sub Structure | 10th floor | IT/751
| Sub Structure | 1st floor | IT/752
| Sub Structure | Top floor | IT/753
| Sub Structure | 1st floor | IT/754
| Sub Structure | 2nd floor | IT/755
| Sub Structure |  | IT/756
| Sub Structure |  | IT/757
| Sub Structure |  | IT/758
| Sub Structure |  | IT/759
| Sub Structure |  | IT/760
| Sub Structure | 2nd floor | IT/761
| Sub Structure | 5th floor | IT/762
| Sub Structure | Top floor | IT/763
| Sub Structure | 5th floor | IT/764
| Sub Structure | 10th floor | IT/765
| Sub Structure |  | IT/766
| Sub Structure |  | IT/767
| Sub Structure |  | IT/768
| Sub Structure |  | IT/769
| Sub Structure |  | IT/770
| Sub Structure |  | IT/771
| Sub Structure |  | IT/772
| Sub Structure |  | IT/773
| Sub Structure |  | IT/774
| Sub Structure |  | IT/775
| Sub Structure |  | IT/776
IT/777
IT/778
IT/779
IT/780
IT/781
IT/782
IT/783
IT/784
IT/785
IT/786
IT/787
IT/788
IT/789
IT/790
IT/791
IT/792
IT/793

## Cybersol L1 Tower
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 26
[9 empty] | Approved with comments (B) |  | 1
[9 empty] | Rejected ( R) |  | 10
[9 empty] | Open/Pending (OP) |  | 33
[9 empty] | Total |  | 70
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | 1st Floor | IT/1 | 2025-05-23 | 2025-05-23 | CPVC Pipe installation | Check CPVC & LPG installation |  | 101 | OP
2 | Sub Structure | 1st Floor | IT/2 | 2025-05-23 | 2025-05-23 | CPVC Pipe installation | Check CPVC & LPG installation |  | 102 | OP
3 | Sub Structure | 1st Floor | IT/3 | 2025-05-23 | 2025-05-23 | CPVC Pipe installation | Check CPVC & LPG installation |  | 103 | OP
4 | Sub Structure | 1st Floor | IT/4 | 2025-05-23 | 2025-05-23 | CPVC Pipe installation | Check CPVC & LPG installation |  | 104 | OP
5 | Sub Structure | 1st Floor | IT/5 | 2025-05-23 | 2025-05-23 | CPVC Pipe installation | Check CPVC & LPG installation |  | 105 | OP
6 | Sub Structure | 1st Floor | IT/6 | 2025-05-23 | 2025-05-23 | CPVC Pipe installation | Check CPVC & LPG installation |  | 106 | OP
7 | Sub Structure | 1st Floor | IT/7 | 2025-05-23 | 2025-05-23 | CPVC Pipe installation | Check CPVC & LPG installation |  | 107 | OP
8 | Sub Structure | 1st Floor | IT/8 | 2025-05-23 | 2025-05-23 | CPVC Pipe installation | Check CPVC & LPG installation |  | 108 | OP
9 | Sub Structure | 1st Floor | IT/9 | 2025-05-23 | 2025-05-23 | CPVC Pipe installation | Check CPVC & LPG installation |  | 109 | OP
10 | Sub Structure | 1st Floor | IT/10 | 2025-05-23 | 2025-05-23 | CPVC Pipe installation | Check CPVC & LPG installation |  | 110 | OP
11 | Sub Structure | 1st Floor | IT/11 | 2025-05-23 | 2025-05-23 | UPVC Pipe installation | Check CPVC & LPG installation |  | 101 | OP
12 | Sub Structure | 1st Floor | IT/12 | 2025-05-23 | 2025-05-23 | UPVC Pipe installation | Check CPVC & LPG installation |  | 102 | OP
13 | Sub Structure | 1st Floor | IT/13 | 2025-05-23 | 2025-05-23 | UPVC Pipe installation | Check CPVC & LPG installation |  | 103 | OP
14 | Sub Structure | 1st Floor | IT/14 | 2025-05-23 | 2025-05-23 | UPVC Pipe installation | Check CPVC & LPG installation |  | 104 | OP
15 | Sub Structure | 1st Floor | IT/15 | 2025-05-23 | 2025-05-23 | UPVC Pipe installation | Check CPVC & LPG installation |  | 105 | OP
16 | Sub Structure | 1st Floor | IT/16 | 2025-05-23 | 2025-05-23 | UPVC Pipe installation | Check CPVC & LPG installation |  | 106 | OP
17 | Sub Structure | 1st Floor | IT/17 | 2025-05-23 | 2025-05-23 | UPVC Pipe installation | Check CPVC & LPG installation |  | 107 | OP
18 | Sub Structure | 1st Floor | IT/18 | 2025-05-23 | 2025-05-23 | UPVC Pipe installation | Check CPVC & LPG installation |  | 108 | OP
19 | Sub Structure | 1st Floor | IT/19 | 2025-05-23 | 2025-05-23 | UPVC Pipe installation | Check CPVC & LPG installation |  | 109 | OP
20 | Sub Structure | 1st Floor | IT/20 | 2025-05-23 | 2025-05-23 | UPVC Pipe installation | Check CPVC & LPG installation |  | 110 | OP
21 | Sub Structure | 1st Floor | IT/21 | 2025-05-23 | 2025-05-23 | conduit/back box | electrical conduit/back box |  |  | OP
22 | Sub Structure | 2nd floor | IT/22 | 2025-05-23 | 2025-05-23 | conduit/back box | electrical conduit/back box |  |  | OP
23 | Sub Structure | 3rd floor | IT/23 | 2025-05-23 | 2025-05-23 | conduit/back box | electrical conduit/back box |  |  | OP
24 |  |  | IT/24
25 |  | 2nd floor | IT/25 | 2025-07-18 | 2025-07-18 | Exhaust pipe | Check Exhaust pipe installation |  | 2nd floor | A | 2025-07-23
26 |  | 3rd floor | IT/26 | 2025-07-18 | 2025-07-18 | Exhaust pipe | Check Exhaust pipe installation |  |  | A | 2025-07-23
27 |  | 4th Floor | IT/27 | 2025-07-18 | 2025-07-18 | Exhaust pipe | Check Exhaust pipe installation |  |  | A | 2025-07-23
28 | Sub Structure | 5th Floor | IT/28 | 2025-07-18 | 2025-07-18 | Exhaust pipe | Check Exhaust pipe installation |  |  | A | 2025-07-23
29 | Sub Structure | 6th Floor | IT/29 | 2025-07-18 | 2025-07-18 | Exhaust pipe | Check Exhaust pipe installation |  |  | A | 2025-07-23
30 | Sub Structure | 2nd floor | IT/30 | 2025-07-18 | 2025-07-18 | LPG pipe | Check LPG pipe installation |  |  | A | 2025-07-22
31 | Sub Structure | 3rd floor | IT/31 | 2025-07-18 | 2025-07-18 | LPG pipe | Check LPG pipe installation |  |  | A | 2025-07-22
32 | Sub Structure | 4th Floor | IT/32 | 2025-07-18 | 2025-07-18 | LPG pipe | Check LPG pipe installation |  |  | A | 2025-07-22
33 | Sub Structure | 2nd Floor | IT/33 | 2025-08-15 | 2025-08-15 | conduit/back box | electrical conduit/back box |  | 4th floor | A | 2025-08-16
34 | Sub Structure | 2nd Floor | IT/34 | 2025-08-15 | 2025-08-15 | conduit/back box | electrical conduit/back box |  | 5th floor | A | 2025-08-16
35 | Sub Structure | 2nd Floor | IT/35 | 2025-08-15 | 2025-08-15 | conduit/back box | electrical conduit/back box |  | 6th floor | A | 2025-08-16
36 | Sub Structure | 2nd Floor | IT/36 | 2025-08-16 | 2025-08-16 | UPVC Pipe installation | Check UPVC/ Exhaust pipr installation |  | 2nd floor | A | 2025-08-20
37 | Sub Structure | 1st Floor | IT/37 | 2025-08-16 | 2025-08-16 | UPVC Pipe installation | Check CPVC & LPG installation |  | 2nd floor | A | 2025-08-20
38 | Sub Structure | 1st floor | IT/38 | 2025-09-22 | 2025-09-22 | LPG pipe | Check LPG pipe installation |  | 1st to 9th floor | OP
39 | Sub Structure | 1st Floor | IT/39 | 2025-09-22 | 2025-09-22 | UPVC Pipe installation | UPVC Pipe Installation |  | 5th floor | OP
40 | Sub Structure | 1st floor | IT/40 | 2025-09-22 | 2025-09-22 | AC Drain Piping | AC Drain piping |  | 3rd to 6th floor | OP
41 | Sub Structure | 1st Floor | IT/41 | 2025-09-22 | 2025-09-22 | Core Cutting | Core Cutting |  | 2nd, 3rd & 6th | OP
42 | Sub Structure | 1st Floor | IT/42 | 2025-09-22 | 2025-09-22 | Exhaust pipe | Check Exhaust pipe installation |  | 3rd to 5th | OP
43 | Sub Structure | 2nd Floor | IT/43 | 2025-09-22 | 2025-09-22 | CPVC Pipe installation | Check CPVC installation |  | 3rd to 6th floor | OP
44 | Sub Structure | 2nd Floor | IT/44 | 2025-09-22 | 2025-09-22 | UPVC Pipe installation | UPVC Pipe Installation |  | 3rd floor | OP
45 | Sub Structure | 3rd Floor | IT/45 | 2025-09-23 | 2025-09-23 | conduit/back box | electrical conduit/back box |  | 8th floor | OP
46 | Sub Structure | 5th Floor | IT/46 | 2025-09-23 | 2025-09-23 | conduit/back box | electrical conduit/back box |  | 7th floor | OP
47 | Sub Structure | 6th Floor | IT/47 | 2025-09-23 | 2025-09-23 | Pipe Installation | Balcony Drainand Rain water Pipe Installation |  | 1st to 9th floor | OP
48 | Sub Structure | 7th Flor | IT/48 | 2025-10-09 | 2025-10-09 | lights | Façade Lights |  | ground & 8th Floor | A
49 | Sub Structure | 2nd Floor | IT/49 | 2025-10-20 | 2025-10-20 | conduit/back box | electrical conduit/back box |  | 9th floor | A | 2025-10-21
50 | Sub Structure | 2nd Floor | IT/50 | 2025-10-20 | 2025-10-20 | conduit/back box | electrical conduit/back box |  | 110407507607 | A | 2025-10-21
51 | Sub Structure | 10th Floor | IT/51 | 2025-10-20 | 2025-10-20 | UPVC Pipe installation | UPVC/Exhaust pipe installation |  | 6th floor | R | 2025-10-21
51 | Sub Structure | 10th Floor | IT/51 R01 | 2025-10-22 | 2025-10-22 | UPVC Pipe installation | UPVC/Exhaust pipe installation |  | 6th floor | A | 2025-10-29
52 | Sub Structure | 3rd Floor | IT/52 | 2025-10-20 | 2025-10-20 | UPVC Pipe installation | UPVC Pipe installation |  | 6th floor | R | 2025-10-21
52 | Sub Structure | 3rd Floor | IT/52 R01 | 2025-10-22 | 2025-10-22 | UPVC Pipe installation | UPVC Pipe installation |  | 6th floor | A | 2025-10-29
53 | Sub Structure | 3rd Floor | IT/53 | 2025-10-22 | 2025-10-22 | CPVC Pipe installation | CPVC Pipe install |  | 3rd floor | R | 2025-10-23
53 | Sub Structure | 3rd Floor | IT/53 R01 | 2025-10-24 | 2025-10-24 | CPVC Pipe installation | CPVC Pipe install |  | 3rd floor | R | 2025-10-27
53 | Sub Structure | 3rd Floor | IT/53 R02 | 2025-10-28 | 2025-10-28 | CPVC Pipe installation | CPVC Pipe install |  | 3rd floor | A | 2025-10-29
54 | Sub Structure | 3rd Floor | IT/54 | 2025-10-22 | 2025-10-22 | CPVC Pipe installation | CPVC Pipe install |  | 4th floor | R | 2025-10-23
54 | Sub Structure | 3rd Floor | IT/54 R01 | 2025-10-24 | 2025-10-24 | CPVC Pipe installation | CPVC Pipe install |  | 4th floor | R | 2025-10-27
54 | Sub Structure | 3rd Floor | IT/54 R02 | 2025-10-28 | 2025-10-28 | CPVC Pipe installation | CPVC Pipe install |  | 4th floor | A | 2025-10-29
55 | Sub Structure | 4th Floor | IT/55 | 2025-10-22 | 2025-10-22 | Cable Containment | Cable Containment |  | 1-4 floor | R | 2025-10-23
55 | Sub Structure | 4th Floor | IT/55 R01 | 2025-10-24 | 2025-10-24 | Cable Containment | Cable Containment |  | 1-4 floor | R | 2025-10-27
55 | Sub Structure | 4th Floor | IT/55 R02 | 2025-10-28 | 2025-10-28 | Cable Containment | Cable Containment |  | 1-4 floor | A | 2025-10-29
56 | Sub Structure | 4th Floor | IT/56 | 2025-10-24 | 2025-10-24 | CPVC Pipe installation | CPVC Pipe install |  | 6th floor | R | 2025-10-27
56 | Sub Structure | 4th Floor | IT/56 R01 | 2025-10-28 | 2025-10-28 | CPVC Pipe installation | CPVC Pipe install |  | 6th floor | A | 2025-10-29
57 | Sub Structure | 8th Floor | IT/57 | 2025-10-24 | 2025-10-24 | conduit/back box | electrical conduit/back box |  | 10th floor | R | 2025-10-27
57 | Sub Structure | 8th Floor | IT/57 R01 | 2025-10-28 | 2025-10-28 | conduit/back box | electrical conduit/back box |  | 10th floor | A | 2025-10-29
58 | Sub Structure | 9th Floor | IT/58 | 2025-10-30 | 2025-10-30 | UPVC Pipe installation | UPVC Pipe installation |  | 7th floor | A | 2025-10-30
59 | Sub Structure | 3rd floor | IT/59
60 | Sub Structure | 3rd Floor | IT/60
61 | Sub Structure | 4th Floor | IT/61
62 | Sub Structure | 4th Floor | IT/62
63 | Sub Structure | 11th Floor | IT/63
64 | Sub Structure | 3rd Floor | IT/64
65 | Sub Structure | 3rd Floor | IT/65
66 | Sub Structure | 5th Floor | IT/66 | 2025-12-06 | 2025-12-06 | AC Drain Piping | AC Drain piping |  | 7TH TO 9TH FLOOR | A | 2025-12-06
67 | Sub Structure | 4th Floor | IT/67 | 2025-12-06 | 2025-12-06 | Cable Containment | Cable Containment |  | 5TH TO 7TH FLOOR | A | 2025-12-06
68 | Sub Structure | 4th Floor | IT/68 | 2025-12-06 | 2025-12-06 | ELECTRIC CABLING | ELECTRIC CABLING |  | 3TH FLOOR | B | 2025-12-06
69 | Sub Structure | 3rd floor | IT/69
70 | Sub Structure | 3rd floor | IT/70
71 | Sub Structure | 5th Floor | IT/71
72 | Sub Structure | 5th Floor | IT/72
73 | Sub Structure | 4th Floor | IT/73
74 | Sub Structure | 10ht Floor | IT/74
75 | Sub Structure | 5th Floor | IT/75
76 | Sub Structure | 5th Floor | IT/76
77 | Sub Structure | 5th Floor | IT/77
78 | Sub Structure | 5th Floor | IT/78
79 | Sub Structure | 4th Floor | IT/79
80 | Sub Structure | 5th Floor | IT/80
81 | Sub Structure | 1st Floor | IT/81
82 | Sub Structure | 5th Floor | IT/82
83 | Sub Structure | 5th Floor | IT/83
84 | Sub Structure | 5th Floor | IT/84
85 | Sub Structure | 5th Floor | IT/85
86 | Sub Structure | 5th Floor | IT/86
87 | Sub Structure | 4th Floor | IT/87
88 | Sub Structure | 1st Floor | IT/88
89 | Sub Structure | 1st Floor | IT/89
90 | Sub Structure | 5th Floor | IT/90
91 | Sub Structure | 5th Floor | IT/91
92 | Sub Structure | 5th Floor | IT/92
93 | Sub Structure | 6th Floor | IT/93
94 | Sub Structure | 6ht Floor | IT/94
95 | Sub Structure | 5th Floor | IT/95
96 | Sub Structure | 5th Floor | IT/96
97 | Sub Structure | 6ht Floor | IT/97
98 | Sub Structure | 6th Floor | IT/98
99 | Sub Structure | 5th Floor | IT/99
100 | Sub Structure | 5th Floor | IT/100
101 | Sub Structure | 2nd Floor | IT/101
102 | Sub Structure | 5th Floor | IT/102
103 | Sub Structure | 6th Floor | IT/103
104 | Sub Structure | 7th Floor | IT/104
105 | Sub Structure | 7th Floor | IT/105
106 | Sub Structure | 7th Floor | IT/106
107 | Sub Structure | 6th Floor | IT/107
108 | Sub Structure | 6th Floor | IT/108
109 | Sub Structure | 7th Floor | IT/109
110 | Sub Structure | 7th Floor | IT/110
111 | Sub Structure | 7th Floor | IT/111
112 | Sub Structure | 7th Floor | IT/112
113 | Sub Structure | 6th Floor | IT/113
114 | Sub Structure | 5th Floor | IT/114
115 | Sub Structure | 6th Floor | IT/114A
116 | Sub Structure | 2nd floor | IT/115
117 | Sub Structure | 7th Floor | IT/116
118 | Sub Structure | 7th Floor | IT/117
119 | Sub Structure | 1st Floor | IT/118
120 | Sub Structure | 2nd Floor | IT/119
121 | Sub Structure | 1st floor | IT/120
122 | Sub Structure | 1st floor | IT/121
123 | Sub Structure | 1st Floor | IT/122
124 | Sub Structure | 2nd Floor | IT/123
125 | Sub Structure | 11th Floor | IT/124
126 | Sub Structure | 1st Floor | IT/125
127 | Sub Structure | 1st Floor | IT/126
128 | Sub Structure | 1st Floor | IT/127
129 | Sub Structure | 2nd Floor | IT/128
130 | Sub Structure | 2nd Floor | IT/129
131 | Sub Structure | 2nd Floor | IT/130
132 | Sub Structure | 2nd floor | IT/131
133 | Sub Structure | 3rd floor | IT/132
| Sub Structure | 2nd Floor | IT/133
| Sub Structure | 3rd Floor | IT/134
| Sub Structure | 3rd Floor | IT/135
| Sub Structure | 4th floor | IT/136
| Sub Structure | 3rd Floor | IT/137
| Sub Structure | 2nd floor | IT/138
| Sub Structure | 4th Floor | IT/139
| Sub Structure | 3rd Floor | IT/140
| Sub Structure | 2nd floor | IT/141
| Sub Structure | 2nd floor | IT/142
| Sub Structure | 6th Floor | IT/143
| Sub Structure | 7th Floor | IT/144
| Sub Structure | 4th Floor | IT/145
| Sub Structure | 3rd floor | IT/146
| Sub Structure | 5th Floor | IT/147
| Sub Structure | 4th Floor | IT/148
| Sub Structure | 2nd floor | IT/149
| Sub Structure | 5th Floor | IT/150
| Sub Structure | 3rd Floor | IT/151
| Sub Structure | 3rd Floor | IT/152
| Sub Structure | 3rd Floor | IT/153
| Sub Structure | 7th Floor | IT/154
| Sub Structure | 7th Floor | IT/155
| Sub Structure | 5th Floor | IT/156
| Sub Structure | 5th floor | IT/157
| Sub Structure | 4th Floor | IT/158
| Sub Structure | 2nd Floor | IT/159
| Sub Structure | 3rd Floor | IT/160
| Sub Structure | 3rd Floor | IT/161
| Sub Structure | 3rd Floor | IT/162
| Sub Structure | 3rd Floor | IT/163
| Sub Structure | 6th Floor | IT/164
| Sub Structure | 3rd Floor | IT/165
| Sub Structure | 3rd Floor | IT/166
| Sub Structure | 8th Floor | IT/167
| Sub Structure | 8th Floor | IT/168
| Sub Structure | 4th Floor | IT/169
| Sub Structure | 4th Floor | IT/170
| Sub Structure | 8th Floor | IT/171
| Sub Structure | Basement | IT/172
| Sub Structure | 3rd Floor | IT/173
| Sub Structure | 6th Floor | IT/174
| Sub Structure | 5th Floor | IT/175
| Sub Structure | 8th Floor | IT/176
| Sub Structure | 8th Floor | IT/177
| Sub Structure | 4th Floor | IT/178
| Sub Structure | 4th Floor | IT/179
| Sub Structure | 8th Floor | IT/180
| Sub Structure | 8th Floor | IT/181
| Sub Structure | 1st floor | IT/182
| Sub Structure | 2nd floor | IT/183
| Sub Structure | 4th Floor | IT/184
| Sub Structure | 4th Floor | IT/185
| Sub Structure | 5th Floor | IT/186
| Sub Structure | 5th Floor | IT/187
| Sub Structure | Basement | IT/188
| Sub Structure | 6th Floor | IT/189
| Sub Structure | 6th Floor | IT/190
| Sub Structure | Basement | IT/191
| Sub Structure | 8th Floor | IT/192
| Sub Structure | 8th Floor | IT/193
| Sub Structure | 9th Floor | IT/194
| Sub Structure | 9th Floor | IT/195
| Sub Structure | 5th floor | IT/196
| Sub Structure | 5th Floor | IT/197
| Sub Structure | 9th Floor | IT/198
| Sub Structure | 9th Floor | IT/199
| Sub Structure | 5th Floor | IT/200
| Sub Structure | 5th Floor | IT/201
| Sub Structure | 8th floor | IT/202
| Sub Structure | 8th Floor | IT/203
| Sub Structure | 3rd Floor | IT/204
| Sub Structure | 4th Floor | IT/205
| Sub Structure | 5th Floor | IT/206
| Sub Structure | 10th Floor | IT/207
| Sub Structure | 10th Floor | IT/208
| Sub Structure | Basement | IT/209
| Sub Structure | 6th floor | IT/210
| Sub Structure | 6th floor | IT/211
| Sub Structure | 5th Floor | IT/212
| Sub Structure | 5th Floor | IT/213
| Sub Structure | 7th Floor | IT/214
| Sub Structure | 8th Floor | IT/215
| Sub Structure | 8th Floor | IT/216
| Sub Structure | 5th floor | IT/217
| Sub Structure | Ground floor | IT/218
| Sub Structure | 7th Floor | IT/219
| Sub Structure | 7th Floor | IT/220
| Sub Structure | 7th Floor | IT/221
| Sub Structure | 8th Floor | IT/222
| Sub Structure | 8th Floor | IT/223
| Sub Structure | 8th Floor | IT/224
| Sub Structure | 8th Floor | IT/225
| Sub Structure | 6th floor | IT/226
| Sub Structure | 8th floor | IT/227
| Sub Structure | 6th Floor | IT/228
| Sub Structure | 6th Floor | IT/229
| Sub Structure | 8th Floor | IT/230
| Sub Structure | 7th Floor | IT/231
| Sub Structure | 10th Floor | IT/232
| Sub Structure | Basement | IT/233
| Sub Structure | 11th floor | IT/234
| Sub Structure | 11th floor | IT/235
| Sub Structure | 8th floor | IT/236
| Sub Structure | 8th floor | IT/237
| Sub Structure | 7th floor | IT/238
| Sub Structure | 7th floor | IT/239
| Sub Structure | 7th floor | IT/240
| Sub Structure | basement | IT/241
| Sub Structure | 11th floor | IT/242
| Sub Structure | 5th floor | IT/243
| Sub Structure | 6th floor | IT/244
| Sub Structure | 7th floor | IT/245
| Sub Structure | GF | IT/246
| Sub Structure | GF | IT/247
| Sub Structure | 8th Floor | IT/248
| Sub Structure | 8th Floor | IT/249
| Sub Structure | 8th Floor | IT/250
| Sub Structure | 9th Floor | IT/251
| Sub Structure | 9th Floor | IT/252
| Sub Structure | 7th floor | IT/253
| Sub Structure | 8th floor | IT/254
| Sub Structure | GF | IT/255
| Sub Structure | GF | IT/256
| Sub Structure | 8th floor | IT/257
| Sub Structure | 9th floor | IT/258
| Sub Structure | 9th floor | IT/259
| Sub Structure | 9th floor | IT/260
| Sub Structure | 9th floor | IT/261
| Sub Structure | 9th floor | IT/262
| Sub Structure | 8th floor | IT/263
| Sub Structure | 8th floor | IT/264
| Sub Structure | 9th floor | IT/265
| Sub Structure | 9th floor | IT/266
| Sub Structure | 2nd floor | IT/267
| Sub Structure | 1st floor | IT/268
| Sub Structure | 1st floor | IT/269
| Sub Structure | 1st floor | IT/270
| Sub Structure | 8th floor | IT/271
| Sub Structure | 8th floor | IT/272
| Sub Structure | 8th floor | IT/273
| Sub Structure | 1st floor | IT/274
| Sub Structure | 1st floor | IT/275
| Sub Structure | 1st floor | IT/276
| Sub Structure | 7th floor | IT/277
| Sub Structure | 1st Floor | IT/278
| Sub Structure | 8th floor | IT/279
| Sub Structure | 8th floor | IT/280
| Sub Structure | Basement | IT/281
| Sub Structure | 9th floor | IT/282
| Sub Structure | 10th floor | IT/283
| Sub Structure | 2nd floor | IT/284
| Sub Structure | 2nd floor | IT/285
| Sub Structure | 10th floor | IT/286
| Sub Structure | 9th floor | IT/287
| Sub Structure | 7th floor | IT/288
| Sub Structure | 2nd floor | IT/289
| Sub Structure | 10th floor | IT/290
| Sub Structure | 10th floor | IT/291
| Sub Structure | 2nd floor | IT/292
| Sub Structure | 2nd floor | IT/293
| Sub Structure | 10th floor | IT/294
| Sub Structure | 10th floor | IT/295
| Sub Structure | 10th floor | IT/296
| Sub Structure | 9th floor | IT/297
| Sub Structure | 2nd floor | IT/298
| Sub Structure | 2nd floor | IT/299
| Sub Structure | 11th floor | IT/300
| Sub Structure | 11th floor | IT/301
| Sub Structure | 11th floor | IT/302
| Sub Structure | 11th floor | IT/303
| Sub Structure | 1st Floor | IT/304
| Sub Structure | 11th floor | IT/305
| Sub Structure | 9th floor | IT/306
| Sub Structure | 2nd floor | IT/307
| Sub Structure | 11th floor | IT/308
| Sub Structure | 11th floor | IT/309
| Sub Structure | 10th floor | IT/310
| Sub Structure | 10th floor | IT/311
| Sub Structure | 2nd floor | IT/312
| Sub Structure | 2nd floor | IT/313
| Sub Structure | 1st floor | IT/314
| Sub Structure | 10th floor | IT/315
| Sub Structure | 11th floor | IT/316
| Sub Structure | 11th floor | IT/317
| Sub Structure | Basement | IT/318
| Sub Structure | 9th floor | IT/319
| Sub Structure | 10th floor | IT/320
| Sub Structure | 9th floor | IT/321
| Sub Structure | 10th floor | IT/322
| Sub Structure | 8th floor | IT/323
| Sub Structure | 9th floor | IT/324
| Sub Structure | 9th floor | IT/325
| Sub Structure | 3rd floor | IT/326
| Sub Structure | 3rd floor | IT/327
| Sub Structure | 3rd floor | IT/328
| Sub Structure | 6th floor | IT/329
| Sub Structure | 7th floor | IT/330
| Sub Structure | 8th floor | IT/331
| Sub Structure | 8th floor | IT/332
| Sub Structure | 8th floor | IT/333
| Sub Structure | 8th floor | IT/334 | [11 empty] | 2024-08-15
| Sub Structure | 10th floor | IT/335
| Sub Structure | 10th floor | IT/336
| Sub Structure | 3rd floor | IT/337
| Sub Structure | 3rd floor | IT/338
| Sub Structure | 11th floor | IT/339
| Sub Structure | 3rd floor | IT/340
| Sub Structure | 3rd floor | IT/341
| Sub Structure | 9th floor | IT/342
| Sub Structure | 9th floor | IT/343
| Sub Structure | 11th floor | IT/344
| Sub Structure | 11th floor | IT/345
| Sub Structure | 11th floor | IT/346
| Sub Structure | 11th floor | IT/347
| Sub Structure | 4th floor | IT/348
| Sub Structure | 4th floor | IT/349
| Sub Structure | 10th floor | IT/350
| Sub Structure | 10th floor | IT/351
| Sub Structure | 4th floor | IT/352
| Sub Structure | 4th floor | IT/353
| Sub Structure | 4th floor | IT/354
| Sub Structure | 3rd floor | IT/355
| Sub Structure | 3rd floor | IT/356
| Sub Structure | 3rd floor | IT/357
| Sub Structure | 3rd floor | IT/358
| Sub Structure | 4th floor | IT/359
| Sub Structure | 11th floor | IT/360
| Sub Structure | 4th floor | IT/361
| Sub Structure | 4th floor | IT/362
| Sub Structure | 11th floor | IT/363
| Sub Structure | 4th floor | IT/364
| Sub Structure | 4th floor | IT/365
| Sub Structure | 4th floor | IT/366
| Sub Structure | 4th floor | IT/367
| Sub Structure | 1st floor | IT/368
| Sub Structure | 1st floor | IT/369
| Sub Structure | 1st floor | IT/370
| Sub Structure | 1st floor | IT/371
| Sub Structure | 1st floor | IT/372
| Sub Structure | 1st floor | IT/373
| Sub Structure | Top floor | IT/374
| Sub Structure | 11th floor | IT/375
| Sub Structure | 5th floor | IT/376
| Sub Structure | 5th floor | IT/377
| Sub Structure | 1st floor | IT/378
| Sub Structure | 1st floor | IT/379
| Sub Structure | 2nd floor | IT/380
| Sub Structure | 11th floor | IT/381
| Sub Structure | Basement | IT/382
| Sub Structure | 1st floor | IT/383
| Sub Structure | Top floor | IT/384
| Sub Structure | 1st floor | IT/385
| Sub Structure | 5th floor | IT/386
| Sub Structure | 9th floor | IT/387
| Sub Structure | 10th floor | IT/388
| Sub Structure | 2nd floor | IT/389
| Sub Structure | top floor | IT/390
| Sub Structure | top floor | IT/391
| Sub Structure | 1st floor | IT/392
| Sub Structure | 2nd floor | IT/393
| Sub Structure | 1st floor | IT/394
| Sub Structure | 4th floor | IT/395
| Sub Structure | 2nd floor | IT/396
| Sub Structure | 2nd floor | IT/397
| Sub Structure | 2nd floor | IT/398
| Sub Structure | 2nd floor | IT/399
| Sub Structure | 5th floor | IT/400
| Sub Structure | 5th floor | IT/401
| Sub Structure | 2nd floor | IT/402
| Sub Structure | 2nd floor | IT/403
| Sub Structure | 5th floor | IT/404
| Sub Structure | 2nd floor | IT/405
| Sub Structure | 2nd floor | IT/406
| Sub Structure | 2nd floor | IT/407
| Sub Structure | 2nd floor | IT/408
| Sub Structure | 2nd floor | IT/409
| Sub Structure | 5th floor | IT/410
| Sub Structure | 5th floor | IT/411
| Sub Structure | top floor | IT/412
| Sub Structure | 5th floor | IT/413
| Sub Structure | 3rd floor | IT/414
| Sub Structure | 3rd floor | IT/415
| Sub Structure | Top roof | IT/416
| Sub Structure | 3rd floor | IT/417
| Sub Structure | 11th floor | IT/418
| Sub Structure | 3rd floor | IT/419
| Sub Structure | Top floor | IT/420
| Sub Structure | 3rd floor | IT/421
| Sub Structure | 6th floor | IT/422
| Sub Structure | 3rd floor | IT/423
| Sub Structure | 11th floor | IT/424
| Sub Structure | Basement | IT/425
| Sub Structure | 3rd floor | IT/426
| Sub Structure | 3rd floor | IT/427
| Sub Structure | 6th floor | IT/428
| Sub Structure | 6th floor | IT/429
| Sub Structure | 3rd floor | IT/430
| Sub Structure | 3rd floor | IT/431
| Sub Structure | 6th floor | IT/432
| Sub Structure | 6th floor | IT/433
| Sub Structure | top floor | IT/434
| Sub Structure | 6th floor | IT/435
| Sub Structure | 3rd floor | IT/436
| Sub Structure | 3rd floor | IT/437
| Sub Structure | 6th floor | IT/438
| Sub Structure | top floor | IT/439
| Sub Structure | Top floor | IT/440
| Sub Structure | 4th floor | IT/441
| Sub Structure | 4th floor | IT/442
| Sub Structure | 3rd floor | IT/443
| Sub Structure | top floor | IT/444
| Sub Structure | 6th floor | IT/445
| Sub Structure | 7th floor | IT/446
| Sub Structure | 2nd floor | IT/447
| Sub Structure | 7th floor | IT/448
| Sub Structure | 4th floor | IT/449
| Sub Structure | 7th floor | IT/450
| Sub Structure | 7th floor | IT/451
| Sub Structure | 4th floor | IT/452
| Sub Structure | 4th floor | IT/453
| Sub Structure | 7th floor | IT/454
| Sub Structure | top floor | IT/455
| Sub Structure | 4th floor | IT/456
| Sub Structure | 7th floor | IT/457
| Sub Structure | 4th floor | IT/458
| Sub Structure | Top floor | IT/459
| Sub Structure | 7th floor | IT/460
| Sub Structure | 1st floor | IT/461
| Sub Structure | 4th floor | IT/462
| Sub Structure | 7th floor | IT/463
| Sub Structure | top floor | IT/464
| Sub Structure | 4th floor | IT/465
| Sub Structure | 4th floor | IT/466
| Sub Structure | 7th floor | IT/467
| Sub Structure | top floor | IT/468
| Sub Structure | 8th floor | IT/469
| Sub Structure | 8th floor | IT/470
| Sub Structure | 8th floor | IT/471
| Sub Structure | Top floor | IT/472
| Sub Structure | 5th floor | IT/473
| Sub Structure | 5th floor | IT/474
| Sub Structure | 5th floor | IT/475
| Sub Structure | 2nd floor | IT/476
| Sub Structure | 1st floor | IT/477
| Sub Structure | 8th floor | IT/478
| Sub Structure | 8th floor | IT/479
| Sub Structure | 8th floor | IT/480
| Sub Structure | 9th floor | IT/481
| Sub Structure | 5th floor | IT/482
| Sub Structure | 1st floor | IT/483
| Sub Structure | 5th floor | IT/484
| Sub Structure | 5th floor | IT/485
| Sub Structure | 5th floor | IT/486
| Sub Structure | 2nd floor | IT/487
| Sub Structure | 8th floor | IT/488
| Sub Structure | 8th floor | IT/489
| Sub Structure |  | IT/490
| Sub Structure | 9th floor | IT/491
| Sub Structure | Top floor | IT/492
| Sub Structure | 5th floor | IT/493
| Sub Structure | 2nd floor | IT/494
| Sub Structure | 5th floor | IT/495
| Sub Structure | 2nd floor | IT/496
| Sub Structure | 5th floor | IT/497
| Sub Structure | 5th floor | IT/498
| Sub Structure |  | IT/499
| Sub Structure | 9th floor | IT/500
| Sub Structure | 5th floor | IT/501
| Sub Structure | 8th floor | IT/502
| Sub Structure | 5th floor | IT/503
| Sub Structure | 11th floor | IT/504
| Sub Structure | 8th floor | IT/505
| Sub Structure | 8th floor | IT/506
| Sub Structure | 5th floor | IT/507
| Sub Structure | 5th floor | IT/508
| Sub Structure | 8th floor | IT/509
| Sub Structure | 8th floor | IT/510
| Sub Structure | 9th floor | IT/511
| Sub Structure | 2nd floor | IT/512
| Sub Structure | 3rd floor | IT/513
| Sub Structure | 6th floor | IT/514
| Sub Structure | 2nd floor | IT/515
| Sub Structure | 5th floor | IT/516
| Sub Structure | 5th floor | IT/517
| Sub Structure | 3rd floor | IT/518
| Sub Structure | 6th floor | IT/519
| Sub Structure | 8th floor | IT/520
| Sub Structure | 6th floor | IT/521
| Sub Structure | 6th floor | IT/522
| Sub Structure | 6th floor | IT/523
| Sub Structure | 3rd floor | IT/524
| Sub Structure | 9th floor | IT/525
| Sub Structure | 6th floor | IT/526
| Sub Structure | 6th floor | IT/527
| Sub Structure | 6th floor | IT/528
| Sub Structure | 6th floor | IT/529
| Sub Structure | 6th floor | IT/530
| Sub Structure | 9th floor | IT/531
| Sub Structure | 6th floor | IT/532
| Sub Structure | 9th floor | IT/533
| Sub Structure | Mummty floor | IT/534
| Sub Structure | 9th floor | IT/535
| Sub Structure | 9th floor | IT/536
| Sub Structure | 6th floor | IT/537
| Sub Structure | 3rd floor | IT/538
| Sub Structure | 4th floor | IT/539
| Sub Structure | 6th floor | IT/540
| Sub Structure | top floor | IT/541
| Sub Structure | 6th floor | IT/542
| Sub Structure | 9th floor | IT/543
| Sub Structure | 4th floor | IT/544
| Sub Structure | 9th floor | IT/545
| Sub Structure | 8th floor | IT/546
| Sub Structure | 6th floor | IT/547
| Sub Structure |  | IT/548
| Sub Structure | 4th floor | IT/549
| Sub Structure | 6th floor | IT/550
| Sub Structure | 5th floor | IT/551
| Sub Structure | 6th floor | IT/552
| Sub Structure | 5th floor | IT/553
| Sub Structure | 5th floor | IT/554
| Sub Structure | 9th floor | IT/555
| Sub Structure | 7th floor | IT/556
| Sub Structure | 7th floor | IT/557
| Sub Structure | 6th floor | IT/558
| Sub Structure | 6th floor | IT/559
| Sub Structure | 6th floor | IT/560
| Sub Structure | 7th floor | IT/561
| Sub Structure | top roof mummty | IT/562
| Sub Structure | 7th floor | IT/563
| Sub Structure | top floor | IT/564
| Sub Structure | 7th floor | IT/565
| Sub Structure | 7th floor | IT/566
| Sub Structure | 7th floor | IT/567
| Sub Structure | 7th floor | IT/568
| Sub Structure | 7th floor | IT/569
| Sub Structure | 3rd floor | IT/570
| Sub Structure | 7th floor | IT/571
| Sub Structure | 7th floor | IT/572
| Sub Structure | 7th floor | IT/573
| Sub Structure | 7th floor | IT/574
| Sub Structure | 7th flor | IT/575
| Sub Structure | 7th floor | IT/576
| Sub Structure | 7th floor | IT/577
| Sub Structure | 1st to 2nd floor | IT/578
| Sub Structure |  | IT/579
| Sub Structure | 1st floor | IT/580
| Sub Structure | 7th floor | IT/581
| Sub Structure | 7th floor | IT/582
| Sub Structure | 8th floor | IT/583
| Sub Structure | 8th floor | IT/584
| Sub Structure | 7th floor | IT/585
| Sub Structure | 7th floor | IT/586
| Sub Structure | 7th floor | IT/587
| Sub Structure | 8th floor | IT/588
| Sub Structure | 8th floor | IT/589
| Sub Structure | 8th floor | IT/590
| Sub Structure | GF | IT/591
| Sub Structure | 3rd floor | IT/592
| Sub Structure | 9th floor | IT/593
| Sub Structure | 8th floor | IT/594
| Sub Structure | 8th floor | IT/595
| Sub Structure | 8th floor | IT/596
| Sub Structure | 9th floor | IT/597
| Sub Structure | 9th floor | IT/598
| Sub Structure | 8th floor | IT/599
| Sub Structure | 8th floor | IT/600
| Sub Structure | 8th floor | IT/601
| Sub Structure | 8th floor | IT/602
| Sub Structure | 8th floor | IT/603
| Sub Structure | Top floor | IT/604
| Sub Structure | 2nd floor | IT/605
| Sub Structure | 9th floor | IT/606
| Sub Structure | 9th floor | IT/607
| Sub Structure | 8th floor | IT/608
| Sub Structure | 10th floor | IT/609
| Sub Structure | 4th floor | IT/610
| Sub Structure | 8th floor | IT/611
| Sub Structure | 8th floor | IT/612
| Sub Structure | 8th floor | IT/613
| Sub Structure | 10th floor | IT/614
| Sub Structure | 8th floor | IT/615
| Sub Structure | 8th floor | IT/616
| Sub Structure | 8th floor | IT/617
| Sub Structure | Mummty floor | IT/618
| Sub Structure | top floor | IT/619
| Sub Structure | 9th floor | IT/620
| Sub Structure | 9th floor | IT/621
| Sub Structure | 9th floor | IT/622
| Sub Structure | 9th floor | IT/623
| Sub Structure | 10th floor | IT/624
| Sub Structure | 8th floor | IT/625
| Sub Structure | 9th floor | IT/626
| Sub Structure | 5th floor | IT/627
| Sub Structure | 8th floor | IT/628
| Sub Structure | 8th floor | IT/629
| Sub Structure | 9th floor | IT/630
| Sub Structure | 10th floor | IT/631
| Sub Structure | 8th floor | IT/632
| Sub Structure | 9th floor | IT/633
| Sub Structure | 9th floor | IT/634
| Sub Structure | 5th floor | IT/635
| Sub Structure | 9th floor | IT/636
| Sub Structure | 9th floor | IT/637
| Sub Structure | Top floor | IT/638
| Sub Structure | 10th flooor | IT/639
| Sub Structure | 10th floor | IT/640
| Sub Structure | 11th floor | IT/641
| Sub Structure | 4th floor | IT/642
| Sub Structure | 9th floor | IT/643
| Sub Structure | 9th floor | IT/644
| Sub Structure | 10th floor | IT/645
| Sub Structure | 10th floor | IT/646
| Sub Structure | 1st floor to top floor | IT/647
| Sub Structure | 10th floor | IT/648
| Sub Structure | top floor | IT/649
| Sub Structure |  | IT/650
| Sub Structure | 11th floor | IT/651
| Sub Structure | 9th floor | IT/652
| Sub Structure | 4th floor | IT/653
| Sub Structure | 10th floor | IT/654
| Sub Structure | 10th floor | IT/655
| Sub Structure | 10th floor | IT/656
| Sub Structure | 9th floor | IT/657
| Sub Structure | top floor | IT/658
| Sub Structure | 10th floor | IT/659
| Sub Structure | top floor | IT/660
| Sub Structure | 10th floor | IT/661
| Sub Structure | 10th floor | IT/662
| Sub Structure | 10th floor | IT/663
| Sub Structure | 10th floor | IT/664
| Sub Structure | Mummty floor | IT/665
| Sub Structure | 10th floor | IT/666
| Sub Structure | 10th floor | IT/667
| Sub Structure | 10th floor | IT/668
| Sub Structure | 10th floor | IT/669
| Sub Structure | 10th floor | IT/670
| Sub Structure | 11th floor | IT/671
| Sub Structure | 10th floor | IT/672
| Sub Structure | 5th floor | IT/673
| Sub Structure | 5th floor | IT/674
| Sub Structure | 5th floor | IT/675
| Sub Structure | 11th floor | IT/676
| Sub Structure | 11th floor | IT/677
| Sub Structure | 11th floor | IT/678
| Sub Structure | 11th floor | IT/679
| Sub Structure | 11th floor | IT/680
| Sub Structure | 11th floor | IT/681
| Sub Structure | 11th floor | IT/682
| Sub Structure | 11th floor | IT/683
| Sub Structure | 11th floor | IT/684
| Sub Structure | 11th floor | IT/685
| Sub Structure | 11th floor | IT/686
| Sub Structure | Top floor | IT/687
| Sub Structure | top floor | IT/688
| Sub Structure | Top floor | IT/689
| Sub Structure | top floor | IT/690
| Sub Structure | 11th floor | IT/691
| Sub Structure | 11th floor | IT/692
| Sub Structure | 11th floor | IT/693
| Sub Structure | 11th floor | IT/694
| Sub Structure | top floor | IT/695
| Sub Structure | top floor | IT/696
| Sub Structure | 11th floor | IT/697
| Sub Structure | 5th floor | IT/698
| Sub Structure | 11th floor | IT/699
| Sub Structure | top floor | IT/700
| Sub Structure | Top floor | IT/701
| Sub Structure | 11th floor | IT/702
| Sub Structure | top floor | IT/703
| Sub Structure | Ground floor | IT/704
| Sub Structure | Top floor | IT/705
| Sub Structure | 5th floor | IT/706
| Sub Structure | Top floor | IT/707
| Sub Structure | 6th floor | IT/708
| Sub Structure | 3rd floor | IT/709
| Sub Structure | 4th floor | IT/710
| Sub Structure | 5th floor | IT/711
| Sub Structure | 6th floor | IT/712
| Sub Structure | 6th floor | IT/713
| Sub Structure | Top floor | IT/714
| Sub Structure | Top floor | IT/715
| Sub Structure | 7th floor | IT/716
| Sub Structure | Top floor | IT/717
| Sub Structure | Top floor | IT/718
| Sub Structure | 7th floor | IT/719
| Sub Structure | 7th floor | IT/720
| Sub Structure | Ground floor | IT/721
| Sub Structure | Top floor | IT/722
| Sub Structure | 8th floor | IT/723
| Sub Structure | Top floor | IT/724
| Sub Structure | 8th floor | IT/725
| Sub Structure | 8th floor | IT/726
| Sub Structure | Ground floor | IT/727
| Sub Structure | 9th floor | IT/728
| Sub Structure | 9th floor | IT/729
| Sub Structure | 9th floor | IT/730
| Sub Structure | 10th floor | IT/731
| Sub Structure | 10th floor | IT/732
| Sub Structure | 10th floor | IT/733
| Sub Structure | 8th floor | IT/734
| Sub Structure | 11th floor | IT/735
| Sub Structure | 11th floor | IT/736
| Sub Structure | 11th floor | IT/737
| Sub Structure | Ground floor | IT/738
| Sub Structure | 5th floor | IT/739
| Sub Structure | 2nd floor | IT/740
| Sub Structure | Top floor | IT/741
| Sub Structure | 1st to floor to top | IT/742
| Sub Structure | 10th floor | IT/743
| Sub Structure | 11th floor | IT/744
| Sub Structure | Top floor | IT/745
| Sub Structure | 1st floor | IT/746
| Sub Structure | 11th floor | IT/747
| Sub Structure | 10th floor | IT/748
| Sub Structure | 11th floor | IT/749
| Sub Structure | 1st floor | IT/750
| Sub Structure | 10th floor | IT/751
| Sub Structure | 1st floor | IT/752
| Sub Structure | Top floor | IT/753
| Sub Structure | 1st floor | IT/754
| Sub Structure | 2nd floor | IT/755
| Sub Structure | 2nd floor | IT/756
| Sub Structure | 1st floor | IT/757
| Sub Structure | Top floor | IT/758
| Sub Structure | Top floor | IT/759
| Sub Structure | 2nd floor | IT/760
| Sub Structure | 2nd floor | IT/761
| Sub Structure | 5th floor | IT/762
| Sub Structure | Top floor | IT/763
| Sub Structure | 5th floor | IT/764
| Sub Structure | 10th floor | IT/765
| Sub Structure | 1st floor | IT/766
| Sub Structure | 2nd floor | IT/767
| Sub Structure | Top floor | IT/768
| Sub Structure | Top floor | IT/769
| Sub Structure | Top floor | IT/770
| Sub Structure | 6th floor | IT/771
| Sub Structure | 5th floor | IT/772
| Sub Structure | 1st floor | IT/773
| Sub Structure | 1st floor | IT/774
| Sub Structure | 1st floor | IT/775
| Sub Structure | 1st floor | IT/776
|  | 1st floor | IT/777
|  | 10th floor | IT/778
|  | 10th floor | IT/779
|  | top floor | IT/780
|  | 10th floor | IT/781
|  | 10th floor | IT/782
IT/783
IT/784
|  | 2nd floor | IT/785
|  | 2nd floor | IT/786
|  | 2nd floor | IT/787
|  | Top floor | IT/788
|  | 10th floor | IT/789
|  | 10th floor | IT/790
|  | 1st floor | IT/791
|  | 2nd floor | IT/792
|  | Top floor | IT/793

## Rex Engg Chiseling
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 4
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 2
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 6
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 |  | Ground floor | L1/01 | 2025-05-27 | 2025-05-26 | chiseling | check chiseling work backside |  | Grid A/8-11 | A | 2025-05-27
2 |  | 1st floor to 11th floor | L1/02 | 2025-07-23 | 2025-07-23 | chiseling | check chiseling work at SOG side |  | Grid H-N/15-20 | R | 2025-07-30
2 |  | 1st floor to 11th floor | L1/02 R01 | 2025-10-14 | 2025-10-14 | chiseling | check chiseling work at SOG side |  | Grid H-N/15-20 | A | 2025-10-18
3 |  |  | L1/03
4 |  |  | L1/04
5 |  |  | L1/05
6 |  |  | L1/06
7 |  | 2nd floor | I.T/07 | 2025-08-13 | 2025-08-13 | chiseling | Check Chiseling work at 2nd floor to top floor |  | Grid A/17-18 | R | 2025-08-15
8 |  |  | I.T/07 R01 | 2025-09-12 | 2025-09-12 | chiseling | Check Chiseling work at 2nd floor to top floor |  | Grid A/17-18 | A | 2025-09-12 | Bilal
9 |  |  | I.T/08 | 2025-10-27 | 2025-10-27 | Lift pit | Chek the dismantling and removing at lift pit basement |  | Grid A-B/09-10 | A | 2025-10-31
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
2024-08-15
IT/795
IT/796
IT/806
IT/807
IT/808
IT/809
IT/810
IT/811
IT/812
IT/813
IT/814
IT/815
IT/816
IT/817
IT/818
IT/819
IT/820
IT/821
IT/822
IT/823
IT/824
IT/825
IT/826
IT/827
IT/828
IT/829
IT/830
IT/831
IT/832
IT/833
IT/834
IT/835
IT/836
IT/837
IT/838
IT/839
IT/840
IT/841
IT/842
IT/843
IT/844
IT/845
IT/846
IT/847
IT/848
IT/849
IT/850
IT/851
IT/852
IT/853

## Rayan
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 4
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 0
[9 empty] | Open/Pending (OP) |  | 1
[9 empty] | Total |  | 5
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1
2 |  |  | IT/02 | 2025-07-01 | 2025-07-01 | Wall putty | check Primer,03 coat wall putty & 03 coat paint on wardrobe |  | 102-116 | A | 2025-07-09
3 |  |  | IT/03 | 2025-07-26 | 2025-07-26 | Wall putty | check Primer,03 coat wall putty & 03 coat paint on wardrobe |  | 202-216 | A | 2025-07-30
4 |  |  | IT/04 | 2025-07-26 | 2025-07-26 | Wall putty | check Primer,03 coat wall putty & 03 coat paint on wardrobe |  | 202-216 | OP
5 |  |  | IT/05 | 2025-07-26 | 2025-07-26 | Wall putty | check Primer,03 coat wall putty & 03 coat paint on wardrobe |  | 202-216 | A | 2025-07-30
6 |  |  | IT/06 | 2025-07-26 | 2025-07-26 | Wall putty | check Primer,03 coat wall putty & 03 coat paint on wardrobe |  | 301-316 | A | 2025-07-30
7 |  |  | IT/07
8 |  |  | IT/08
9 |  |  | IT/09
10 |  |  | IT/10
11 |  |  | IT/11
12 |  |  | IT/12
13 |  |  | IT/13
14 |  |  | IT/14
15 |  |  | IT/15
16 |  |  | IT/16
17 |  |  | IT/17
18 |  |  | IT/18
19 |  |  | IT/19
20 |  |  | IT/20
21 |  |  | IT/21
22 |  |  | IT/22
23 |  |  | IT/23
24 |  |  | IT/24
25 |  |  | IT/25
26 |  |  | IT/26
27 |  |  | IT/27
28 |  |  | IT/28
29 |  |  | IT/29
30 |  |  | IT/30
31 |  |  | IT/31
32 |  |  | IT/32
33 |  |  | IT/33
34 |  |  | IT/34
35 |  |  | IT/35
36 |  |  | IT/36
37 |  |  | IT/37
38 |  |  | IT/38
39 |  |  | IT/39
40 |  |  | IT/40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
2024-08-15
IT/795
IT/796
IT/806
IT/807
IT/808
IT/809
IT/810
IT/811
IT/812
IT/813
IT/814
IT/815
IT/816
IT/817
IT/818
IT/819
IT/820
IT/821
IT/822
IT/823
IT/824
IT/825
IT/826
IT/827
IT/828
IT/829
IT/830
IT/831
IT/832
IT/833
IT/834
IT/835
IT/836
IT/837
IT/838
IT/839
IT/840
IT/841
IT/842
IT/843
IT/844
IT/845
IT/846
IT/847
IT/848
IT/849
IT/850
IT/851
IT/852
IT/853

## Rock Shield
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 1
[9 empty] | Approved with comments (B) |  | 1
[9 empty] | Rejected ( R) |  | 1
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 3
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 |  |  | IT/01 | 2025-07-12 | 2025-07-12 | paint | Check Externsl psint base work of I tower |  |  | B | 2025-07-26
2 |  |  | L2/02 | 2025-09-23 | 2025-09-23 | paint | Check Externsl psint base work of L2 tower |  |  | R | 2025-09-25 | Asad Jaweed
3 |  |  | L1/02 R01 | 2025-10-03 | 2025-10-03 | paint | Check Externsl psint base work of L1 tower |  |  | A | 2025-10-08
4
5
6
7 |  |  | IT/07
8 |  |  | IT/08
9 |  |  | IT/09
10 |  |  | IT/10
11 |  |  | IT/11
12 |  |  | IT/12
13 |  |  | IT/13
14 |  |  | IT/14
15 |  |  | IT/15
16 |  |  | IT/16
17 |  |  | IT/17
18 |  |  | IT/18
19 |  |  | IT/19
20 |  |  | IT/20
21 |  |  | IT/21
22 |  |  | IT/22
23 |  |  | IT/23
24 |  |  | IT/24
25 |  |  | IT/25
26 |  |  | IT/26
27 |  |  | IT/27
28 |  |  | IT/28
29 |  |  | IT/29
30 |  |  | IT/30
31 |  |  | IT/31
32 |  |  | IT/32
33 |  |  | IT/33
34 |  |  | IT/34
35 |  |  | IT/35
36 |  |  | IT/36
37 |  |  | IT/37
38 |  |  | IT/38
39 |  |  | IT/39
40 |  |  | IT/40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
2024-08-15
IT/795
IT/796
IT/806
IT/807
IT/808
IT/809
IT/810
IT/811
IT/812
IT/813
IT/814
IT/815
IT/816
IT/817
IT/818
IT/819
IT/820
IT/821
IT/822
IT/823
IT/824
IT/825
IT/826
IT/827
IT/828
IT/829
IT/830
IT/831
IT/832
IT/833
IT/834
IT/835
IT/836
IT/837
IT/838
IT/839
IT/840
IT/841
IT/842
IT/843
IT/844
IT/845
IT/846
IT/847
IT/848
IT/849
IT/850
IT/851
IT/852
IT/853

## Chawla Aluminium
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 47
[9 empty] | Approved with comments (B) |  | 21
[9 empty] | Rejected ( R) |  | 3
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 71
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 |  |  | 1 | 2025-07-17 | 2025-07-17 | Aluminimun | Check only Aluminium Window fitting | Level 01 |  | A | 2025-07-22
2 |  |  | 2 | 2025-07-17 | 2025-07-17 | Aluminimun | Check only Aluminium Window fitting | Level 02 |  | A | 2025-07-22
3 |  |  | 3 | 2025-07-17 | 2025-07-17 | Aluminimun | Check only Aluminium Window fitting | Level 03 |  | A | 2025-07-22
4 |  |  | 4 | 2025-07-17 | 2025-07-17 | Aluminimun | Check only Aluminium Window fitting | Level 04 |  | A | 2025-07-22
5 |  |  | 5 | 2025-07-17 | 2025-07-17 | Aluminimun | Check only Aluminium Window fitting | Level 05 |  | A | 2025-07-22
6 |  |  | 6 | 2025-07-17 | 2025-07-17 | Aluminimun | Check only Aluminium Window fitting | Level 06 |  | A | 2025-07-22
7 |  |  | 7 | 2025-07-17 | 2025-07-17 | Aluminimun | Check only Aluminium Window fitting | Level 07 |  | A | 2025-07-22
8 |  |  | 8 | 2025-07-17 | 2025-07-17 | Aluminimun | Check only Aluminium Window fitting | Level 08 |  | A | 2025-07-22
9 |  |  | 9 | 2025-07-17 | 2025-07-17 | Aluminimun | Check only Aluminium Window fitting | Level 09 |  | A | 2025-07-22
10 |  |  | IT/10 | 2025-08-15 | 2025-08-15 | Aluminimun | Check only Aluminium Window fitting | Level 01 |  | B | 2025-08-24
11 |  |  | IT/11 | 2025-08-15 | 2025-08-15 | Aluminimun | Check only Aluminium Window fitting | Level 02 |  | B | 2025-08-24
12 |  |  | IT/12 | 2025-08-15 | 2025-08-15 | Aluminimun | Check only Aluminium Window fitting | Level 03 |  | B | 2025-08-24
13 |  |  | IT/13 | 2025-08-15 | 2025-08-15 | Aluminimun | Check only Aluminium Window fitting | Level 04 |  | B | 2025-09-01
14 |  |  | IT/14 | 2025-08-15 | 2025-08-15 | Aluminimun | Check only Aluminium Window fitting | Level 05 |  | B | 2025-09-01
15 |  |  | IT/15 | 2025-08-15 | 2025-08-15 | Aluminimun | Check only Aluminium Window fitting | Level 07 |  | B | 2025-09-01
16 |  |  | IT/16 | 2025-08-15 | 2025-08-15 | Aluminimun | Check only Aluminium Window fitting | Level 08 |  | B | 2025-09-01
17 |  |  | IT/17 | 2025-08-15 | 2025-08-15 | Aluminimun | Check only Aluminium Window fitting | Level 09 |  | B | 2025-09-01
18 |  |  | IT/18 | 2025-08-15 | 2025-08-15 | Glass | Check Fixing of Glass | Level 02 |  | B | 2025-08-24
19 |  |  | IT/19 | 2025-08-15 | 2025-08-15 | Glass | Check Fixing of Glass | Level 01 |  | B | 2025-08-24
20 |  |  | IT/20 | 2025-08-15 | 2025-08-15 | Glass | Check Fixing of Glass | Level 03 |  | B | 2025-09-01
21 |  |  | IT/21 | 2025-08-15 | 2025-08-15 | Glass | Check Fixing of Glass | Level 04 |  | B | 2025-09-01
22 |  |  | IT/22 | 2025-08-15 | 2025-08-15 | Glass | Check Fixing of Glass | Level 05 |  | B | 2025-09-01
23 |  |  | IT/23 | 2025-08-15 | 2025-08-15 | Glass | Check Fixing of Glass | Level 06 |  | B | 2025-09-01
24 |  |  | IT/24 | 2025-09-24 | 2025-09-24 | Glass | Check Fixing of Glass | Level 07 |  | R | 2025-09-26
25 |  |  | IT/25 | 2025-09-24 | 2025-09-24 | Glass | Check Fixing of Glass | Level 08 |  | R | 2025-09-26
26 |  |  | IT/26 | 2025-09-24 | 2025-09-24 | Glass | Check Fixing of Glass | Level 09 |  | R | 2025-09-26
27 |  |  | IT/27 | 2025-10-09 | 2025-10-09 | Aluminimun | Check only Aluminium Window fitting | Level 01 |  | A | 2025-10-09
28 |  |  | IT/28 | 2025-10-09 | 2025-10-09 | Aluminimun | Check only Aluminium Window fitting | Level 02 |  | A | 2025-10-09
29 |  |  | IT/29 | 2025-10-09 | 2025-10-09 | Aluminimun | Check only Aluminium Window fitting | Level 03 |  | A | 2025-10-09
30 |  |  | IT/30 | 2025-10-03 | 2025-10-03 | Aluminimun | Check only Aluminium Window fitting | Level 04 |  | B | 2025-10-07
30 |  |  | IT/30 R01 | 2025-10-09 | 2025-10-09 | Aluminimun | Check only Aluminium Window fitting | Level 04 |  | A | 2025-10-10
31 |  |  | IT/31 | 2025-10-03 | 2025-10-03 | Aluminimun | Check only Aluminium Window fitting | Level 05 |  | B | 2025-10-07
|  |  | IT/31 R01 | 2025-10-09 | 2025-10-09 | Aluminimun | Check only Aluminium Window fitting | Level 05 |  | A | 2025-10-10
32 |  |  | IT/32 | 2025-10-03 | 2025-10-03 | Aluminimun | Check only Aluminium Window fitting | Level 06 |  | B | 2025-10-07
|  |  | IT/32 R01 | 2025-10-09 | 2025-10-09 | Aluminimun | Check only Aluminium Window fitting | Level 06 |  | A | 2025-10-10
33 |  |  | IT/038 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 02 |  | A | 2025-12-06
34 |  |  | IT/055 | 2025-12-02 | 2025-12-03 | Aluminimun | Check only Aluminium Window fitting | Level 07 |  | A | 2025-12-06
35 |  |  | IT/054 | 2025-12-02 | 2025-12-03 | Aluminimun | Check only Aluminium Window fitting | Level 07 |  | A | 2025-12-06
36 |  |  | IT/037 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 02 |  | A | 2025-12-06
37 |  |  | IT/036 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 01 |  | A | 2025-12-06
38 |  |  | IT/040 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 02 |  | A | 2025-12-06
39 |  |  | IT/058 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 01 |  | A | 2025-12-06
40 |  |  | IT/057 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 01 |  | A | 2025-12-06
41 |  |  | IT/056 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 01 |  | A | 2025-12-06
42 |  |  | IT/035 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 01 |  | A | 2025-12-06
43 |  |  | IT/036 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 01 |  | A | 2025-12-06
44 |  |  | IT/060 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 02 |  | A | 2025-12-06
45 |  |  | IT/059 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 02 |  | A | 2025-12-06
46 |  |  | IT/039 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 03 |  | A | 2025-12-06
47 |  |  | IT/041 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 03 |  | A | 2025-12-06
48 |  |  | IT/042 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 03 |  | A | 2025-12-06
49 |  |  | IT/063 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 03 |  | A | 2025-12-06
50 |  |  | IT062 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 03 |  | A | 2025-12-06
51 |  |  | IT/061 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 03 |  | A | 2025-12-06
52 |  |  | IT/051 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 06 |  | B | 2025-12-06
53 |  |  | IT/069 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 06 |  | A | 2025-12-06
54 |  |  | IT/048 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 05 |  | B | 2025-12-06
55 |  |  | IT/066 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 05 |  | A | 2025-12-06
56 |  |  | IT/045 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 04 |  | A | 2025-12-06
57 |  |  | IT/053 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 04 |  | A | 2025-12-06
58 |  |  | IT/044 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 04 |  | A | 2025-12-06
59 |  |  | IT/052 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 04 |  | A | 2025-12-06
60 |  |  | IT/043 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 04 |  | A | 2025-12-06
61 |  |  | IT/068 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 05 |  | A | 2025-12-06
62 |  |  | IT/050 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 06 |  | B | 2025-12-06
63 |  |  | IT/067 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 06 |  | A | 2025-12-06
64 |  |  | IT/049 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 06 |  | B | 2025-12-06
65 |  |  | IT/065 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 05 |  | A | 2025-12-06
66 |  |  | IT/047 | 2025-12-02 | 2025-12-05 | Glass | Check Fixing of Glass | Level 05 |  | A | 2025-12-06
67 |  |  | IT/064 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 05 |  | A | 2025-12-06
68 |  |  | IT/046 | 2025-12-02 | 2025-12-05 | Aluminimun | Check only Aluminium Window fitting | Level 05 |  | A | 2025-12-06
69 |  |  | IT/40
70 |  |  | IT/40
71 |  |  | IT/40
72 |  |  | IT/40
73 |  |  | IT/40
74 |  |  | IT/40
75 |  |  | IT/40
76 |  |  | IT/40
77 |  |  | IT/40
78 |  |  | IT/40
79 |  |  | IT/40
80 |  |  | IT/40
81 |  |  | IT/40
82 |  |  | IT/40
83 |  |  | IT/40
84 |  |  | IT/40
85 |  |  | IT/40
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
2024-08-15
IT/795
IT/796
IT/806
IT/807
IT/808
IT/809
IT/810
IT/811
IT/812
IT/813
IT/814
IT/815
IT/816
IT/817
IT/818
IT/819
IT/820
IT/821
IT/822
IT/823
IT/824
IT/825
IT/826
IT/827
IT/828
IT/829
IT/830
IT/831
IT/832
IT/833
IT/834
IT/835
IT/836
IT/837
IT/838
IT/839
IT/840
IT/841
IT/842
IT/843
IT/844
IT/845
IT/846
IT/847
IT/848
IT/849
IT/850
IT/851
IT/852
IT/853

## Rex engg L1
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 1
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 0
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 1
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1
2 |  | 1st floor to 11th floor | L1/02 | 2025-07-23 | 2025-07-23 | chiseling | check chiseling work at SOG side |  | (+19.00 to +131.00) | A | 2025-07-30
3 |  |  | L1/03
4 |  |  | L1/04
5 |  |  | L1/05
6 |  |  | L1/06
7 |  |  | L1/07
8 |  |  | L1/08
9 |  |  | L1/09
10 |  |  | L1/10
11 |  |  | L1/11
12 |  |  | L1/12
13 |  |  | L1/13
14 |  |  | L1/14
15 |  |  | L1/15
16 |  |  | L1/16
17 |  |  | L1/17
18 |  |  | L1/18
19 |  |  | L1/19
20 |  |  | L1/20
21 |  |  | L1/21
22 |  |  | L1/22
23 |  |  | L1/23
24 |  |  | L1/24
25 |  |  | L1/25
26 |  |  | L1/26
27 |  |  | L1/27
28 |  |  | L1/28
29 |  |  | L1/29
30 |  |  | L1/30
31 |  |  | L1/31
32 |  |  | L1/32
33 |  |  | L1/33
34 |  |  | L1/34
35 |  |  | L1/35
36 |  |  | L1/36
37 |  |  | L1/37
38 |  |  | L1/38
39 |  |  | L1/39
40 |  |  | L1/40
41 |  |  | L1/41
42 |  |  | L1/42
43 |  |  | L1/43
44 |  |  | L1/44
45 |  |  | L1/45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
2024-08-15
IT/795
IT/796
IT/806
IT/807
IT/808
IT/809
IT/810
IT/811
IT/812
IT/813
IT/814
IT/815
IT/816
IT/817
IT/818
IT/819
IT/820
IT/821
IT/822
IT/823
IT/824
IT/825
IT/826
IT/827
IT/828
IT/829
IT/830
IT/831
IT/832
IT/833
IT/834
IT/835
IT/836
IT/837
IT/838
IT/839
IT/840
IT/841
IT/842
IT/843
IT/844
IT/845
IT/846
IT/847
IT/848
IT/849
IT/850
IT/851
IT/852
IT/853

## Mecatech
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 19
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 0
[9 empty] | Open/Pending (OP) |  | 4
[9 empty] | Total |  | 23
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 |  |  | 1 | 2025-09-05 | 2025-09-05 | Insulation | Check duct insulation work 1st Floor | Level 01 |  | A | 2025-09-08
2 |  |  | 2 | 2025-09-05 | 2025-09-05 | Insulation | Check duct insulation work 2nd Floor | Level 02 |  | A | 2025-09-08
3 |  |  | 3 | 2025-09-05 | 2025-09-05 | Insulation | Check duct insulation work 3rd Floor | Level 03 |  | A | 2025-09-08
4 |  |  | 4 | 2025-09-05 | 2025-09-05 | Insulation | Check duct insulation work 4th Floor | Level 04 |  | A | 2025-09-08
5 |  |  | 5 | 2025-09-05 | 2025-09-05 | Insulation | Check duct insulation work 5th Floor | Level 05 |  | A | 2025-09-08
6 |  |  | 6 | 2025-09-05 | 2025-09-05 | Insulation | Check duct insulation work 6th Floor | Level 06 |  | A | 2025-09-08
7 |  |  | 7 | 2025-09-05 | 2025-09-05 | Insulation | Check duct insulation work 7th Floor | Level 07 |  | A | 2025-09-08
8 |  |  | 8 | 2025-09-05 | 2025-09-05 | Insulation | Check duct insulation work 8th Floor | Level 08 |  | A | 2025-09-08
9 |  |  | 9 | 2025-09-08 | 2025-09-08 | VRF | Check Copper pipe VRF |  |  | OP
10 |  |  | 10 | 2025-09-16 | 2025-09-16 | PIPE | Control Wire with Conduit Pipe For VRF |  |  | A | 2025-09-20
11 |  |  | 11 | 2025-09-16 | 2025-09-16 | VRF | VRF Shop drwing |  |  | A | 2025-09-20
12 |  |  | 12 | 2025-09-17 | 2025-09-17 | VRF | VRF Y-joints | 1 to 5 floor |  | A | 2025-09-20
13 |  |  | 13 | 2025-09-17 | 2025-09-17 | Duct | Duct installation at 9th floor | 9th floor |  | A | 2025-09-20
14 |  |  | 14 | 2025-10-07 | 2025-10-07 | Drain Pipe | Drain Pipe with Insulation | 1st to 11th floor |  | A | 2025-10-09
15 |  |  | 15 | 2025-10-14 | 2025-10-14 | Duct | Duct installation at 10th floor | 10TH floor |  | OP
16 |  |  | 16 | 2025-10-14 | 2025-10-14 | Pipes | Installation Copper pipe | 6th to 11th |  | OP
17 |  |  | 17 | 2025-10-14 | 2025-10-14 | Y-Branches | Installation Y-Branches | 6th to 11th |  | OP
18 |  |  | 18 | 2025-11-15 | 2025-11-15
19 |  |  | 19 | 2025-11-15 | 2025-11-15 | Upvc | Drain Pipe UPVC | 11th to 6th |  | A | 2025-11-18
20 |  |  | 20 | 2025-11-15 | 2025-11-15 | VRF System | Contro; Wire With conduit pipe for VRF System | 1 to 11th Floor |  | A | 2025-11-18
21 |  |  | 21 | 2025-11-21 | 2025-11-21 | VRF | Indour and outdoor Units of VRF Panasonic | 1 to 11th Floor |  | A | 2025-11-24
|  |  | 22 | 2025-12-05 | 2025-12-05 | Y-Branches | DUCT INSULATION | 11TH FLOOR |  | A | 2025-12-13
23 |  |  | 23 | 2025-12-05 | 2025-12-05 | ITEMS | CHECK THE ITEMS & ACTIVITY TO BE INSPECYED | 11TH FLOOR |  | A | 2025-12-13
24 |  |  | IT/24 | 2025-12-05 | 2025-12-05 | VRF | INSULATION OF VRF INDOOR UNITS | 1 to 11th Floor |  | A | 2025-12-13
25 |  |  | IT/25
26 |  |  | IT/26
27 |  |  | IT/27
28 |  |  | IT/28
29 |  |  | IT/29
30 |  |  | IT/30
31 |  |  | IT/31
32 |  |  | IT/32
33 |  |  | IT/33
34 |  |  | IT/34
35 |  |  | IT/35
36 |  |  | IT/36
37 |  |  | IT/37
38 |  |  | IT/38
39 |  |  | IT/39
40 |  |  | IT/40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
2024-08-15
IT/795
IT/796
IT/806
IT/807
IT/808
IT/809
IT/810
IT/811
IT/812
IT/813
IT/814
IT/815
IT/816
IT/817
IT/818
IT/819
IT/820
IT/821
IT/822
IT/823
IT/824
IT/825
IT/826
IT/827
IT/828
IT/829
IT/830
IT/831
IT/832
IT/833
IT/834
IT/835
IT/836
IT/837
IT/838
IT/839
IT/840
IT/841
IT/842
IT/843
IT/844
IT/845
IT/846
IT/847
IT/848
IT/849
IT/850
IT/851
IT/852
IT/853

## Sheet1 (hidden)
GE I-Tower
IT/924 | 2025-08-30 | 2025-08-30 | tile work | Check the final inspection of living room tile work | Grid A-B/10-13 | B | 2025-09-05
IT/926 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bed rooms & living room tile work | Grid A-C/05-09 | OP
IT/927 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bed rooms & living room tile work | Grid A-F/04-13 | OP
IT/928 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work | Grid A-F/09-15 | OP
IT/929 | 2025-08-30 | 2025-08-30 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work | Grid A-F/12-22 | A | 2025-09-10
IT/930 | 2025-08-30 | 2025-08-30 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work | Grid A-F/16-26 | B | 2025-09-09
IT/932 | 2025-09-03 | 2025-09-03 | tile work | Check the final inspection of Bed rooms & living room tile work | Grid A-B/10-14 | OP
IT/933 | 2025-09-03 | 2025-09-03 | tile work | Check the final inspection of Bed rooms & living room tile work | Grid C-F/13-18 | OP
IT/935 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work | Grid C-F/11-12 | A | 2025-09-10
IT/936 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work | Grid C-F/11-12 | B | 2025-09-11
IT/937 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work | Grid C-F/15-16 | R | 2025-09-12
IT/938 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work | Grid C-F/17-18 | B | 2025-09-12
IT/939 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work | Grid C-F/19-22 | B | 2025-09-12
IT/940 | 2025-09-04 | 2025-09-04 | ceiling work | Check the final inspection of ceiling work | Grid C-F/19-22 | R | 2025-09-12
IT/943 | 2025-09-05 | 2025-09-05 | brick work | Check the complete kitchen pad brickwork | Grid A-F/1-26 | A | 2025-09-12
IT/944 | 2025-09-05 | 2025-09-05 | brick work | Check the complete kitchen pad brickwork | Grid A-F/1-26 | A | 2025-09-13
IT/945 | 2025-09-05 | 2025-09-05 | brick work | Check the complete brickwork(dressing and bed room wardrobe) | Grid A-F/1-26 | B | 2025-09-16
IT/946 | 2025-09-05 | 2025-09-05 | brick work | Check the complete brickwork(dressing and bed room wardrobe) | Grid A-F/1-26 | A | 2025-09-13
IT/947 | 2025-09-05 | 2025-09-05 | dummy wall | Check the complete dummy wall (vanity wall) | Grid A-F/1-26 | A | 2025-09-13
IT/948 | 2025-09-05 | 2025-09-05 | dummy wall | Check the complete dummy wall (vanity wall) | Grid A-F/1-26 | A | 2025-09-14
IT/949 | 2025-09-05 | 2025-09-05 | dummy wall | Check the complete dummy wall (vanity wall) | Grid A-F/1-26 | A | 2025-09-12
IT/950 | 2025-09-08 | 2025-09-08 | dummy wall | Check the complete dummy wall (vanity wall) | Grid A-F/1-26 | A | 2025-09-13
IT/951 | 2025-09-08 | 2025-09-08 | dummy wall | Check the complete dummy wall (vanity wall) | Grid A-F/1-26 | A | 2025-09-10
IT/952 | 2025-09-08 | 2025-09-08 | dummy wall | Check the complete dummy wall (vanity wall) | Grid A-F/1-26 | A | 2025-09-13
IT/953 R01 | 2025-09-09 | 2025-09-09 | reinforcement & formwork | Check reinforcement and formwork of horizentalband and allow to start concrete | Grid A/21-23 | A | 2025-09-10
IT/954 | 2025-09-11 | 2025-09-11 | brickwork | Check complete Brickwork at GF | Grid A-F/01-26 | A | 2025-09-13
IT/955 | 2025-09-11 | 2025-09-11 | reinforcement & formwork | Check reinforcement and formwork of horizentalband and allow to start concrete | Grid A-C/26 | A | 2025-09-13
IT/956 | 2025-09-11 | 2025-09-11 | ceiling work | Check the final inspection of ceiling work | Grid A-C/01-04 | A | 2025-09-13
IT/957 | 2025-09-11 | 2025-09-11 | ceiling work | Check the final inspection of ceiling work | Grid A-C/05-08 | B | 2025-09-13
IT/958 | 2025-09-11 | 2025-09-11 | ceiling work | Check the final inspection of ceiling work | Grid A-C/01-04 | R | 2025-09-12
IT/959 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work | Grid C-F/01-04 | R | 2025-09-15
IT/960 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work | Grid A-C/04-06 | R | 2025-09-15
IT/962 R01 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of Bath rooms & PWR/LND room wall tile work | Grid A-B/13-06 | R | 2025-09-15
IT/963 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work | 103, 104 | R | 2025-09-13
IT/964 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work | 105108 | R | 2025-09-15
IT/965 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work | 107 , 110 | R | 2025-09-15
IT/966 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work | 114, 116 | R | 2025-09-15
IT/967 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work | 109, 111 | B | 2025-09-15
IT/968 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work | 101, 106 | R | 2025-09-15
IT/969 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work | 102, 115 | R | 2025-09-15
IT/970 | 2025-09-12 | 2025-09-12 | tile work | Check the inspection of Balcony tile work | 113 | R | 2025-09-15
IT/971 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of living room tile work | 212 | OP
IT/972 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of bath Tiles | 212 | OP
IT/973 | 2025-09-13 | 2025-09-13 | tile work | Check the final inspection of bath Tiles | 202 | OP
IT/898 | 2025-09-04 | 2025-09-04 | Ceiling work | Check the final inspection of ceiling work | Grid A-C/05-09 | R | 2025-09-10
IT/899 | 2025-09-04 | 2025-09-04 | Ceiling work | Check the final inspection of ceiling work | Grid C-F/04-08 | R | 2025-09-14
IT/900 | 2025-09-04 | 2025-09-04 | Ceiling work | Check the final inspection of ceiling work | Grid A-E/11-13 | R | 2025-09-10
IT/901 | 2025-09-04 | 2025-09-04 | Ceiling work | Check the final inspection of ceiling work | Grid A-C/15-17 | B | 2025-09-10
GE L1-Tower
LT-1-569 R01 | 2025-09-04 | 2025-09-04 | level | Check level points, corner beads & chicken mesh | Grid R/16-23, K-l/24-26 | A | 2025-09-12
LT-1-570 | 2025-09-04 | 2025-09-04 | plaster work | Check external façade plaster work | Grid P-S/15 | R | 2025-09-15
LT-1-571 | 2025-09-04 | 2025-09-04 | level | Check level points, chicken mesh | Grid G/24-26 | A | 2025-09-08
LT-1-572 | 2025-09-05 | 2025-09-05 | plaster work | Chech complete façade (vertical band) plaster work | Grid R-T/26 | B | 2025-09-07
LT-1-573 R01 | 2025-09-10 | 2025-09-10 | plaster work | Check the Final inspection of plaster work | Grid Q-U/23-26 | R | 2025-09-13
LT-1-574 R01 | 2025-09-10 | 2025-09-10 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room | Grid N-U/15-18 | R | 2025-09-13
LT-1-575 R01 | 2025-09-10 | 2025-09-10 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room | Grid N-U/17-20 | B | 2025-09-13
LT-1-576 R01 | 2025-09-10 | 2025-09-10 | plaster work | Check the Final inspection of plaster work | Grid G-K/20-23 | R | 2025-09-16
LT-1-577 | 2025-09-05 | 2025-09-05 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room | Grid N-U/17-20 | A | 2025-09-10
LT-1-578 | 2025-09-05 | 2025-09-05 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room | Grid L-N/20-26 | A | 2025-09-15
LT-1-579 | 2025-09-05 | 2025-09-05 | plaster work | Check the Final inspection of Bathrooms & PWD/LND room | Grid J-P/23-26 | A | 2025-09-15
LT-1-580 | 2025-09-08 | 2025-09-08 | plaster work | Check complete plaster work on External side | Grid G-M/26 | B | 2025-09-12
LT-1-581 | 2025-09-08 | 2025-09-08 | plaster work | Check complete plaster work on External side | Grid M-T/26 | A | 2025-09-11
LT-1-582 | 2025-09-09 | 2025-09-09 | level | Check the level of screed flooring | Grid G-R/20-26 | A | 2025-09-11
LT-1-583 | 2025-09-09 | 2025-09-09 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | Grid G/24-26 | A | 2025-09-15
LT-1-584 | 2025-09-09 | 2025-09-09 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | Grid M-Q/23-26 | A | 2025-09-11
LT-1-585 | 2025-09-09 | 2025-09-09 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | Grid R-U/17-24 | OP
LT-1-586 | 2025-09-10 | 2025-09-10 | level | Check the level of screed flooring | Grid M-U/20-26, R/15-23 | A | 2025-09-10
LT-1-587 | 2025-09-10 | 2025-09-10 | level | Check the level of screed flooring | Grid R-U/12-24 | R | 2025-09-13
LT-1-589 | 2025-09-11 | 2025-09-11 | Tie columns | Check Tie Columns work 11th floor |  | B | 2025-09-11
LT-1-590 | 2025-09-11 | 2025-09-11 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | Grid R-U/12-17 | R | 2025-09-13
LT-1-591 | 2025-09-12 | 2025-09-12 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | Grid M-U/13-24 | R | 2025-09-13
GE-L2-Tower
LT-2-686 | 2025-09-09 | 2025-09-09 | brick work | Check internal brickwork of horizental band | Grid K-T/01 | A | 2025-09-11
LT-2-687 | 2025-09-09 | 2025-09-09 | brick work | Check internal brickwork of horizental band | Grid H-M/07-12 | A | 2025-09-12
LT-2-688 | 2025-09-09 | 2025-09-09 | brick work | Check internal brickwork of horizental band |  | A | 2025-09-11
LT-2-689 | 2025-09-10 | 2025-09-10 | layout | Check layout and allow to brick masnory | Grid N-U/3-9 | A | 2025-09-11
LT-2-690 | 2025-09-10 | 2025-09-10 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | Grid U/11-12 | A | 2025-09-12
LT-2-691 | 2025-09-10 | 2025-09-10 | brick work | Check internal brickwork of horizental band | Grid K-T/01 | A | 2025-09-16
LT-2-692 | 2025-09-10 | 2025-09-10 | brick work | Check internal brickwork of horizental band | Grid K-T/01 | A | 2025-09-16
LT-2-693 | 2025-09-11 | 2025-09-11 | level | Check level points, corner beads & chicken mesh and allow to start plaster work | Grid U/11-12 | A | 2025-09-15
Ezymix
IT/222 | 2025-09-04 | 2025-09-04 | plaster work | Check plaster work at MEP Duct | 101113 | A | 2025-09-13
IT/223 | 2025-09-04 | 2025-09-04 | plaster work | Check plaster work at MEP Duct | 201213 | B | 2025-09-12
IT/224 | 2025-09-04 | 2025-09-04 | plaster work | Check plaster work at MEP Duct | 301313 | A | 2025-09-12
IT/225 | 2025-09-04 | 2025-09-04 | plaster work | Check plaster work at MEP Duct | 401413 | R | 2025-09-16
IT/226 | 2025-09-09 | 2025-09-09 | Corner bead | Check the left and right bed rooms pre-prepration corner bead complete with all recpect | 1011 | A | 2025-09-13
IT/227 | 2025-09-09 | 2025-09-09 | plaster work | Check the plaster work of standing wall and zone 1 stair door wall |  | A | 2025-09-12
IT/228 | 2025-09-10 | 2025-09-10 | plaster work | Check the beam plaster | 501-516 | B | 2025-09-12
IT/229 | 2025-09-10 | 2025-09-10 | plaster work | Check ladge wall plaster | 501-516 | B | 2025-09-12
IT/230 | 2025-09-10 | 2025-09-10 | plaster work | Check ladge wall plaster | 601-616 | R | 2025-09-16
Elegent
IT/25 | 2025-08-29 | 2025-08-29 | ceiling | Installation of Balcony falso ceiling | 11 | R | 2025-09-15
IT/26 | 2025-08-29 | 2025-08-29 | ceiling | Installation of Balcony falso ceiling | 15 | R | 2025-09-15
IT/27 | 2025-08-29 | 2025-08-29 | ceiling | Installation of Balcony falso ceiling | 14 | R | 2025-09-15
IT/28 | 2025-08-29 | 2025-08-29 | ceiling | Installation of Balcony falso ceiling | 15 | R | 2025-09-15
IT/29 | 2025-08-29 | 2025-08-29 | ceiling | Installation of Balcony falso ceiling | 16 | R | 2025-09-15
IT/30 | 2025-08-29 | 2025-08-29 | ceiling | Installation of Balcony falso ceiling | 12 | R | 2025-09-15
Architive
IT/69 | 2025-09-05 | 2025-09-05 | tile work | Check the final tile work of powder bath | 302 | B | 2025-09-15
IT/70 | 2025-09-05 | 2025-09-05 | plaster work | Allow to start plaster work of balcony for tile | 301-302,309-316 | A | 2025-09-12
IT/71 | 2025-09-05 | 2025-09-05 | layout | Check layout of balcony tiles and allowed to permission for tile work | 303-308,310,314 | A | 2025-09-11
IT/72 | 2025-09-05 | 2025-09-05 | layout | Check layout of balcony tiles and allowed to permission for tile work | 301-302,309-316 | A | 2025-09-16
Rock stone
L2/10 R01 | 2025-09-02 | 2025-09-02 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 | Grid U/8-9 | A | 2025-09-11
L2/11 R01 | 2025-09-02 | 2025-09-02 | travertine | Check the work of travertine fixing (1/2") at the front elevation columns/vertical band of L2 | Grid H-K/7-8 | A | 2025-09-12

## Sheet2
IR STATUS
[7 empty] | Fully Approved (A) |  | 0
[7 empty] | Approved with comments (B) |  | 1
| Pending IR's Status | [5 empty] | Rejected ( R) |  | 0
[7 empty] | Open/Pending (OP) |  | 2
[7 empty] | Total |  | 3
Work Package | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
GE I-Tower
| IT/1096 | 2025-10-17 | 2025-10-17 | ceiling work | Check the Ceiling work |  | 601 | OP | saqib
| IT/1097 | 2025-10-17 | 2025-10-17 | ceiling work | Check the Ceiling work Bed room and Living Pelmet |  | 602 | OP | saqib
| IT/1231 | 2025-12-01 | 2025-12-02 | ceiling work | Check the Ceiling work |  | 608 | B | saqib
2024-08-15
IT/795
IT/796
IT/806
IT/807
IT/808
IT/809
IT/810
IT/811
IT/812
IT/813
IT/814
IT/815
IT/816
IT/817
IT/818
IT/819
IT/820
IT/821
IT/822
IT/823
IT/824
IT/825
IT/826
IT/827
IT/828
IT/829
IT/830
IT/831
IT/832
IT/833
IT/834
IT/835
IT/836
IT/837
IT/838
IT/839
IT/840
IT/841
IT/842
IT/843
IT/844
IT/845
IT/846
IT/847
IT/848
IT/849
IT/850
IT/851
IT/852
IT/853

## Architive IT TOWER
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 1
[9 empty] | Approved with comments (B) |  | 3
[9 empty] | Rejected ( R) |  | 0
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 4
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3)
I TOWER
1 | Sub Structure | 3rd floor | IT/1 | 2025-04-30 | 2025-04-30 | plaster work | Check plaster work for tile |  | 307310312 | A | 2025-05-08
2 | Sub Structure | I tower | it/01 | 2025-12-12 | 2025-12-12 | Farming work | check the farming work & allow to install cladding sheets |  | GROUND FLOOR | B | 2025-12-18
| Sub Structure | I tower | it/01 | 2025-12-12 | 2025-12-12 | Farming work | check the farming work & allow to install cladding sheets |  | GROUND FLOOR | B | 2025-12-18
3 | Sub Structure | I tower | it/01 | 2025-12-12 | 2025-12-12 | Farming work | check the farming work & allow to install cladding sheets |  | GROUND FLOOR | B | 2025-12-18
Sub Structure
4 | Sub Structure
5 | Sub Structure
6 | Sub Structure
7 | Sub Structure
8 | Sub Structure
9 | Sub Structure
10 | Sub Structure
11 | Sub Structure
12 | Sub Structure
13 | Sub Structure
14 | Sub Structure
15 | Sub Structure
16 | Sub Structure
17 | Sub Structure
18 | Sub Structure
19 | Sub Structure
20 | Sub Structure
21 | Sub Structure
22 | Sub Structure
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59

## GE SOG
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 13
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 0
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 13
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | SOG | SOG/01
2 | Sub Structure | SOG | SOG/02
3 | Sub Structure | SOG | SOG/03
4 | Sub Structure | SOG | SOG/04
| Sub Structure | SOG | SOG/05
5 | Sub Structure | SOG | SOG/06
6 | Sub Structure | SOG | SOG/07
7 | Sub Structure | SOG | SOG/08
8 | Sub Structure | SOG | SOG/09
9 | Sub Structure | SOG | SOG/10
10 | Sub Structure | SOG | SOG/11
11 | Sub Structure | SOG | SOG/12
12 | Sub Structure | SOG | SOG/13
13 | Sub Structure | SOG | SOG/14
14 | Sub Structure | SOG | SOG/15
15 | Sub Structure | SOG | SOG/16 | 2025-11-29 | 2025-11-29 | GHASSU | CHECK THE GHASSU (3') FILLING AT SOG |  |  | A | 2025-12-02
16 | Sub Structure | SOG | SOG/17 | 2025-11-29 | 2025-11-29 | LEVEL POINT | CHECK THE LEVEL POINT AND ALLOW TO START CONCRETE OF PLANTER AT SOG SLAB UMT SIDE |  |  | A | 2025-12-02
17 | Sub Structure | SOG | SOG/18 | 2025-12-01 | 2025-12-05 | GHASSU | CHECK THE GHASSU (3') FILLING AT SOG |  |  | A | 2025-12-05
18 | Sub Structure | SOG | SOG/19 | 2025-12-01 | 2025-12-02 | LEVEL POINT | CHECK THE LEVEL POINT AND ALLOW TO START CONCRETE AT SOG SLAB UMT SIDE | L2- TOWER |  | A | 2025-12-02
19 | Sub Structure | SOG | SOG/20 | 2025-12-02 | 2025-12-05 | GHASSU | CHECK THE GHASSU (3') FILLING AT SOG |  |  | A | 2025-12-05
20 | Sub Structure | SOG | SOG/21 | 2025-12-01 | 2025-12-02 | LEVEL POINT | CHECK THE LEVEL POINT AND ALLOW TO START CONCRETE AT SOG SLAB |  |  | A | 2025-12-02 |  |  | 2025-12-02
21 | Sub Structure | SOG | SOG/22 | 2025-12-04 | 2025-12-05 | GHASSU | CHECK THE GHASSU (9') FILLING AT SOG |  |  | A | 2025-12-05
22 | Sub Structure | SOG | SOG/23 | 2025-12-04 | 2025-12-05 | LEVEL POINT | CHECK THE LEVEL POINT AND ALLOW TO START CONCRETE AT PODIUM SOG SLAB |  |  | A | 2025-12-05
23 | Sub Structure | SOG | SOG/24
24 | Sub Structure | SOG | SOG/25 | 2025-12-05 | 2025-12-05 | LEVEL POINT | CHECK THE LEVEL POINT AND ALLOW TO START CONCRETE AT SOG SLAB |  |  | A | 2025-12-05
25 | Sub Structure | SOG | SOG/26 | 2025-12-05 | 2025-12-05 | LAYOUT | CHECK THE LAYOUT AND ALLOW TO START LEAN CONCRETE OF PLANTER WALL AREA AT SOG SLAB |  |  | A | 2025-12-05
26 | Sub Structure | SOG | SOG/27 | 2025-12-09 | 2025-12-10 | GHASSU | CHECK THE GHASSU (3) FILLING AT SOG | L2- TOWER |  | A | 2025-12-18
27 | Sub Structure | SOG | SOG/28 | 2025-12-08 | 2025-12-09 | LEVEL POINT | CHECK THE LEVEL POINT AND ALLOW TO START CONCRETE AT SOG SLAB | L2- TOWER |  | A | 2025-12-09
28 | Sub Structure | SOG | SOG/29 | 2025-12-09 | 2025-12-10 | LAYOUT | CHECK THE LAYOUT AND ALLOW TO START BRICK WORK OF PLANTER WALL AREA AT SOG SLAB |  |  | A | 2025-12-10
31 | Sub Structure | SOG | SOG/30 | 2025-12-13 | 2025-12-13 | GHASSU | CHECK THE GHASSU (605) FILLING AT SOG | I TOWER
32 | Sub Structure | SOG | SOG/31
33 | Sub Structure | SOG | SOG/32
34 | Sub Structure | SOG | SOG/33
35 | Sub Structure | SOG | SOG/34
36 | Sub Structure | SOG | SOG/35
37 | Sub Structure | SOG | SOG/36
38 | Sub Structure | SOG | SOG/37
39 | Sub Structure | SOG | SOG/38
40 | Sub Structure | SOG | SOG/39
41 | Sub Structure | SOG | SOG/40
42 | Sub Structure | SOG | SOG/41
43 | Sub Structure | SOG | SOG/42
44 | Sub Structure | SOG | SOG/43
45 | Sub Structure | SOG | SOG/44
46 | Sub Structure | SOG | SOG/45
47 | Sub Structure | SOG | SOG/46
48 | Sub Structure | SOG | SOG/47
49 | Sub Structure | SOG | SOG/48
50 | Sub Structure | SOG
51 | Sub Structure | SOG
52 | Sub Structure | SOG
53 | Sub Structure | SOG
54 | Sub Structure | SOG
55 | Sub Structure | SOG
56 | Sub Structure | SOG
57 | Sub Structure | SOG
58 | Sub Structure | SOG
59 | Sub Structure | SOG
60 | Sub Structure | SOG
61 | Sub Structure | SOG
62 | Sub Structure | SOG
63 | Sub Structure | SOG
64 | Sub Structure | SOG
65 | Sub Structure | SOG
66 | Sub Structure | SOG
67 | Sub Structure | SOG
68 | Sub Structure | SOG
69 | Sub Structure | SOG
70 | Sub Structure | SOG
71 | Sub Structure | SOG
72 | Sub Structure | SOG
73 | Sub Structure | SOG
74 | Sub Structure | SOG
75 | Sub Structure | SOG
76 | Sub Structure | SOG
77 | Sub Structure | SOG
78 | Sub Structure | SOG
79 | Sub Structure | SOG
80 | Sub Structure | SOG
81 | Sub Structure | SOG
82 | Sub Structure | SOG
83 | Sub Structure | SOG
84 | Sub Structure | SOG
85 | Sub Structure | SOG
86 | Sub Structure | SOG
87 | Sub Structure | SOG
88 | Sub Structure | SOG
89 | Sub Structure | SOG
90 | Sub Structure | SOG
91 | Sub Structure | SOG
92 | Sub Structure | SOG
93 | Sub Structure | SOG
94 | Sub Structure | SOG
95 | Sub Structure | SOG
96 | Sub Structure | SOG
97 | Sub Structure | SOG
98 | Sub Structure | SOG
99 | Sub Structure | SOG
100 | Sub Structure | SOG
101 | Sub Structure | SOG
102 | Sub Structure | SOG
103 | Sub Structure | SOG
104 | Sub Structure | SOG
105 | Sub Structure | SOG
106 | Sub Structure | SOG
107 | Sub Structure | SOG
108 | Sub Structure | SOG
109 | Sub Structure | SOG
110 | Sub Structure | SOG
111 | Sub Structure | SOG
112 | Sub Structure | SOG
113 | Sub Structure | SOG
114 | Sub Structure | SOG
115 | Sub Structure | SOG
116 | Sub Structure | SOG
117 | Sub Structure | SOG
118 | Sub Structure | SOG
119 | Sub Structure | SOG
120 | Sub Structure | SOG
121 | Sub Structure | SOG
122 | Sub Structure | SOG
123 | Sub Structure | SOG
124 | Sub Structure | SOG
125 | Sub Structure | SOG
126 | Sub Structure | SOG
127 | Sub Structure | SOG
128 | Sub Structure | SOG
129 | Sub Structure | SOG
130 | Sub Structure | SOG
131 | Sub Structure | SOG
132 | Sub Structure | SOG
133 | Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
| Sub Structure | SOG
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
| Sub Structure | [10 empty] | Hassan
Sub Structure
| Sub Structure | [10 empty] | Hassan
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
Sub Structure
| Sub Structure | Basement | IT/277
| Sub Structure | Basement | IT/278
| Sub Structure | Basement | IT/279
| Sub Structure | Basement | IT/280
| Sub Structure | Basement | IT/281
| Sub Structure | Basement | IT/282
| Sub Structure | Basement | IT/283
| Sub Structure | Basement | IT/284
| Sub Structure | Basement | IT/285
| Sub Structure | Basement | IT/286
| Sub Structure | Basement | IT/287
| Sub Structure | Basement | IT/288
| Sub Structure | Basement | IT/289
| Sub Structure | Basement | IT/290
| Sub Structure | Basement | IT/291
| Sub Structure | Basement | IT/292
| Sub Structure | Basement | IT/293
| Sub Structure | Basement | IT/294
| Sub Structure | Basement | IT/295
| Sub Structure | Basement | IT/296
| Sub Structure | Basement | IT/297
| Sub Structure | Basement | IT/298
IT/299

## GE BW
PROJECT: CONSTRUCTION OF LAKE CITY ROOF GARDEN APARTMENTS
IR STATUS
|  |  | INSPECTION REQUEST LOG (I Tower) | [5 empty] | Fully Approved (A) |  | 1
[9 empty] | Approved with comments (B) |  | 0
[9 empty] | Rejected ( R) |  | 0
[9 empty] | Open/Pending (OP) |  | 0
[9 empty] | Total |  | 1
Sr. | Work Package | Floor | IR No. | Submission date | Inspection Date | Element | Activity Description | Level | Location/ Grid Ref | IR Status | IR Closing date | Pour Card No. | Concrete Qty (m3) | Remarks
I TOWER
1 | Sub Structure | B.W | B/W-216 | 2025-12-15 | 2025-12-15 | BOUNDRY WALL | CHECK THE PLASTER WORK AND BOUNDRY WALL | UMT SIDE | UMT SIDE | A | 2025-12-18
2 | Sub Structure | B.W
3 | Sub Structure | B.W
4 | Sub Structure | B.W
| Sub Structure | B.W
5 | Sub Structure | B.W
6 | Sub Structure | B.W
7 | Sub Structure | B.W
8 | Sub Structure | B.W
9 | Sub Structure | B.W
10 | Sub Structure | B.W
11 | Sub Structure | B.W
12 | Sub Structure | B.W
13 | Sub Structure | B.W
14 | Sub Structure | B.W
15 | Sub Structure | B.W
16 | Sub Structure | B.W
17 | Sub Structure | B.W
18 | Sub Structure | B.W
19 | Sub Structure | B.W
20 | Sub Structure | B.W
21 | Sub Structure | B.W
22 | Sub Structure | B.W
23 | Sub Structure | B.W
24 | Sub Structure | B.W
25 | Sub Structure | B.W
26 | Sub Structure | B.W
27 | Sub Structure | B.W